## Steel bar chart
NAME OF WORK: ESTIMATE FOR CONSTRUCTION OF VILLAGE ROAD CULVERT ALONG 2R, 3R, 4R, 5R & QUBO SUB DRAIN OF SKT SYSTEM (13NOS:).
1 | R.C.C Raft
|  | Two way | Main bar | 5/8" dia | at 6" c/c | 2 | x | 31 | x | 26 | x | 1.042 | = | 1679.704 | lbs:
|  |  | Distt: bar | 5/8" dia | at 6" c/c | 2 | x | 53 | x | 23 | x | 1.042 | = | 2540.396 | lbs:
2 | Abutment bearing plate
|  | Two way | Main bar | 5/8" dia |  | 2 | x | 8 | x | 16 | x | 1.042 | = | 266.752 | lbs:
|  |  | Ring | 1/4" dia |  | 2 | x | 15 | x | 4.5 | x | 0.167 | = | 22.545 | lbs:
3 | Top Slab
|  | Two way | Main bar | 3/4" dia | at 5" c/c | 1 | x | 45 | x | 14.75 | x | 1.5 | = | 995.625 | lbs:
|  |  | Distt: bar | 1/2" dia | at 6" c/c | 1 | x | 28 | x | 16 | x | 0.668 | = | 299.264 | lbs:
| For PPT Walls |  | Distt: bar | 1/2" dia | at 6" c/c | 1 | x | 16 | x | 5.5 | x | 0.668 | = | 58.784 | lbs:
|  |  | Distt: bar | 1/2" dia | at 6" c/c | 2 | x | 6 | x | 12.25 | x | 0.668 | = | 98.196 | lbs:
[12 empty] | 6.797 |  | 5961.266 | lbs:
|  |  |  | 5961.266 |  | ÷ |  | 112 |  |  |  | 53.2256 |  | 53.2256 | Cwt
Assistant Executive Engineer
Naudero Drainage Sub Division
Larkana

## ABSTRACT LDD
BD-5
Appendix-D to Bid
BILL OF QUANTITIES (BOQs)
Bill No: 3
NAME OF WORK: ESTIMATE FOR CONSTRUCTION OF VILLAGE ROAD CULVERT ALONG 2R, 3R, 4R, 5R & QUBO SUB DRAIN OF SKT SYSTEM (13NOS:).
S. No | Description | Quantity |  | Rate | Unit | Amount
1 | Dismantling Cement concrete reinforced separting reinformcement from concrete cleaning & strenghtening the same (Page No:10, Item No: 20) | 2145 | Cft: | 5445 | %Cft | 116795.25
2 | Dismantling brick work in lime or Cement mortar (Page No:10, Item No:13) | 7605 | Cft: | 1285.63 | %Cft | 97772.1615
3 | Dismantling Cement Concretr Plain 1:3:6 (Page No:10, Item No:19(b) | 3978 | Cft: | 1306.8 | %Cft | 51984.504
4 | Borrowpit Excavation undressed lead up to 100 ft: (a) ordinary soil (Page No: 1, Item No: 3 (a) | 657358 | Cft: | 2117.5 | %oCft | 1391955.565
5 | Supplying of clean screened (River or Pit) sand within 5 chain including removal of top crust of earth or over burden and royalty to the Government or cost to the private owner (P-6 Item No: 36) | 93600 | Cft: | 420 | %oCft | 39312
6 | Dressing and leveling of Earth work to designed section etc complete. b) in ordinary or hard soil (Page-3, Item No.11b) | 750958 | Cft: | 187.55 | %o Cft: | 140842.1729
7 | Carriage of 100 Cft:/ 5 tones of all material like stone aggregate, spwal, coal, lime, surkhi etc B G. rail fastening points and crossing bridges, girders, pipes, 10” x 5”or 1000 mounds of fuel wood by trucks or any other means owned by the contractors. (Average 03 miles. Rate analysis attached) | 750958 | Cft: | 579.41 | %Cft | 4351125.7478
8 | Excavation in foundation of buildings, bridges & other structure i/c dag bellings, dressing refilling around the structures with excavated earth watering & remaining lead up to 5 ft: in ordinary soil (P-4 Item No.18 (b) | 68250 | Cft: | 3176.25 | %o Cft: | 216779.0625
9 | Extra for wet earth work (P-3 Item No:15) | 34125 | Cft: | 1058.75 | %o Cft: | 36129.8438
10 | Full hire charges of the Pumping set per day inclusive of wages of driver and Assistant fuel or electric energy, plat forms required for placing Pumps etc. @ lower depths with suction and delivery pipes for pumping out water found at various depths from trenches i/c the cost of erection & dismantling after completion of the job. (iv) Hire charges of pumping set of up to 10 HP Pumping out water from 15' deep trench (P-76 Item-23 (PHED) 2012 | 195 | days | 1500 | P.day | 292500
11 | For working the pump beyond 8 Hours the following payment Shall be made. The hire of the Pumping set it self being for 24 Hours (ii) for a pumping set of Upto 10 HP (but not less than 5 HP). (P-77, Item-23 Note (ii) (PHED) 2012 | 3120 | Hrs: | 188 | P.Hrs | 586560
12 | Cement concrete plain i/c placing compacting finishing and curing complete i/c screening and washing of stone aggregate With out shuttering ratio 1:4:8 (P-15 Item No: 5 (i) | 11700 | Cft: | 11288.75 | % Cft: | 1320783.75
13 | Erection and removal of centering for RCC or plain cement concrete work of Deodar wood 2nd class Horizontal (P-17,Item-19 a (ii) | 3588 | Sft: | 7000 | % Sft | 251160
14 | (a) R.C.C. work in roof slab beams, columns rafts, lintels and other structural members laid in situ or pre cast laid in position complete in all respects. (i) Ratio 1:2:4 90 lbs cement 2 cft: sand 4 cft: shingle 1/8” to 1/4” gauge. (P-15&16 Item-6 (i) | 22832.16 | Cft: | 337 | P. Cft: | 7694437.92
15 | Fabrication of mild steel reinforcement for cement, concrete including cutting bending lying in position making joints and fastenings including cost of binding wire also includes removal of rust from bars. (Page No: 16 Item No: 08 (a) | 1019.2929 | Cwt: | 4820.2 | P.Cwt: | 377951.88
16 | Rehandling of earthwork. (b) Up to a lead of 50 ft: (P-2 Item No: 09 | 426608 | Cft: | 1058.75 | %o Cft: | 451671.22
|  |  | Total Rs: |  |  | 17417761.0774
Executive Engineer
Larkana Drainage Division
Larkana

## Cartage LDD
CARTAGE & MATERIAL STATEMENT
NAME OF WORK: ESTIMATE FOR CONSTRUCTION OF VILLAGE ROAD CULVERT ALONG SUB DRAINS
S.No | I t e m | Material for % Cft:/Sft: |  |  |  | Quantity | Cement Bags | Hill Sand Cft: | Bajri Shingle Cft: | Bricks Nos: | Steel Ton | Stone Cft:
|  | C bag | Sand | B/S | Bricks
1 | Cement Concrete plain Ratio 1:4:8 | 13 | 46 | 92 | 0 | 900 | 117 | 414 | 828 | 0 | 0 | 0
2 | R.C.C work Ratio 1:2:4 | 17.6 | 44 | 88 | 0 | 1756.32 | 309.1123 | 772.7808 | 1545.5616 | 0 | 0 | 0
3 | Fabrication of Mild steel | 53.23x 1.1/20= Ton |  | 0 | 0 | 78.4071 | 0 | 0 | 0 | 0 | 4.3124 | 0
|  | R A T E S |  |  |  | Total | 426.1123 | 1186.7808 | 2373.5616 | 0 | 4.3124 | 0
|  | Mile | Cement | Bricks | Others | Say | 426.1123 | 1186.7808 | 2373.5616 | 0 | 4.3124 | 0
|  | 1st | 6.1 | 325.6 | 407 | Station | Rohri | Sui | Arrore | Larkana | Karachi | Arrore
|  | 2nd | 1.43 | 76.4 | 95.52 | Total M | 85 | 155 | 91 | 25 | 318 | 91
|  | 3rd | 0 | 61.51 | 76.89 | Rate | 54.93 | 5623.4 | 3539.56 | 1112.49 | 10930.68 | 3539.56
|  | 4th | 0 | 56.36 | 70.45 | Unit | P.Bag | P. % Cft: | P. % Cft: | %o Nos: | P-5 Ton | P. % Cft:
|  | 5th | 0 | 51.54 | 64.43 | Amount | 23406.3497 | 66737.4315 | 84013.637 | 0 | 9427.4773 | 0
|  | 6th | 0 | 46.13 | 57.67
|  | Total | 7.53 | 617.54 | 771.96 | Total Rs: | 183584.8955
|  | 7th | 0.6 | 26.05 | 32.56 | Say Rs: | 183584.8955
Assistant Executive Engineer
Shahdadkot Drainage Sub Division
Larkana

## M Ment
MEASUREMENT SHEET
NAME OF WORK: ESTIMATE FOR CONSTRUCTION OF VILLAGE ROAD CULVERT ALONG SUB DRAINS
S.# | Description of Item | No | x | L | x | B | x | D | = | Quantity
1 | Dismantling of R.C.C
| RCC Slab | 1 | × | 15 | × | 8 | × | 1 | = | 120 | Cft:
| Bearing Plate | 2 | × | 15 | × | 1.5 | × | 1 | = | 45 | Cft:
[7 empty] | Total |  | = | 165 | Cft:
2 | Dismantling Pacca brick work
| Abutment | 2 | x | 15 | x | 5+1.5 | x | 6 | = | 585 | Cft:
2
[7 empty] | Total |  | = | 585 | Cft:
3 | Dismantling Cement Concrete 1:3:6
| Abutment Bed | 1 | × | 18 | × | 17 | × | 1 | = | 306 | Cft:
[7 empty] | Total |  | = | 306 | Cft:
4 | Borrowpit Excavation undressed
| a)Bundhas | 1 | × | 24 + 8 | × | 16 + 28 | × | 8 | = | 2816 | Cft:
|  |  |  | 2 |  | 2
| b)Diversion | 1 | x | 150 | × | 30 + 10 | × | 10 | = | 30000 | Cft:
2
| c)Approches | 2 | × | 50 | × | 16 + 28 | × | 8 | = | 17600 | Cft:
2
| d)Cushion over Slab | 1 | x | 15 | × | 10 | × | 1 | = | 150 | Cft:
[7 empty] | Total |  | = | 50566 | Cft:
5 | Supply of Clean Screened (River or pit)
| Filling under brick pitching behind R/Wall | 2 | x | 15 | x | 20 | x | 12 | = | 7200 | Cft:
[7 empty] | Total |  | = | 7200 | Cft:
6 | Dressing & Levelling
|  | Qty: same as item No: (4+5) | [6 empty] | = | 57766 | Cft:
[7 empty] | Total |  | = | 57766 | Cft:
7 | Carriage of 100 cft: 5 tone of all material
|  | Qty: same as item No: (4+5) | [6 empty] | = | 57766 | Cft:
[7 empty] | Total |  | = | 57766 | Cft:
8 | Excavation in foundation
| Bed | 1 | x | 40+30 | × | 30+20 | × | 6 | = | 5250 | Cft:
|  |  |  | 2 |  | 2
[7 empty] | Total |  | = | 5250 | Cft:
9 | Extra For Wet Earth Work
|  | Qty: 50% of Item No:8 | [6 empty] | = | 2625
[7 empty] | Total |  | = | 2625 | Cft:
10 | Full hire charges of the Pumping set
|  |  |  | 1 | x | 3 | x | 5 | = | 15 | Days
[7 empty] | Total |  | = | 15 | Days
11 | For working the pump beyond 8 Hours
|  |  |  | 3 | x | 5 | x | 16 | = | 240 | Hour
[7 empty] | Total |  | = | 240 | Hour
12 | C.C.Plain i/c placing 1:4:8
| Bed | 1 | x | 30 | x | 20 | x | 1.5 | = | 900 | Cft:
[7 empty] | Total |  | = | 900 | Cft:
13 | Errection & Removal of RCC
| For C C 1:4:8 Abbuttment | 1 | × | 2 | x | 30 | × | 1.5 |  | 180 | Sft:
| For C C 1:4:8 Abbuttment | 1 | × | 2 | x | 16 | × | 1.5 |  | 96 | Sft:
[7 empty] | Total |  | = | 276 | Sft:
14 | R.C.C work 1:2:4
| Base plate | 1 | × | 30 | × | 15 | x | 1.5 | = | 675 | Cft:
| Side Wall | 2 | × | 15 | × | 1.5 | x | 7 | = | 315 | Cft:
| Wing Wall | 4 | × | 10 | × | 1.5 | x | 7 | = | 420 | Cft:
| Slab | 1 | x | 15 | x | 13 | x | 1.25 | = | 243.75 | Cft:
| P/Wall | 2 | x | 13 | x | 1 | x | 3 | = | 102.57 | Cft:
[7 empty] | Total |  | = | 1756.32 | Cft:
15 | Fabrication of Mild Steel
|  | 1756.32 |  |  | x | 5 | / | 112 | = | 78.4071 | Cwt:
[7 empty] | Total |  | = | 78.4071 | Cwt:
16 | Rehandling of Earth Work
| Qty: Same as Item 4 (a) +(b) |  |  | 2816 | + | 30000 |  |  | = | 32816 | Cft:
[7 empty] | Total |  | = | 32816 | Cft:
Assistant Executive Engineer
Shahdadkot Drainage Sub Division
Larkana