## Cartage
CARTAGE & MATERIAL STATEMENT
NAME OF WORK: ESTIMATE FOR RE-CONSTRUCTION OF WATER COURSE ALONG SUB DRAIN
S.No | I t e m | Material for % Cft:/Sft: |  |  |  | Quantity | Cement Bags | Hill Sand Cft: | Bajri Shingle Cft: | Bricks Nos: | Steel Ton | Stone Cft:
|  | C bag | Sand | B/S | Bricks
1 | Cement Concrete plain Ratio 1:3:6 | 13 | 46 | 92 | 0 | 3096 | 402.48 | 1424.16 | 2848.32 | 0 | 0 | 0
2 | R.C.C work Ratio 1:2:4 | 17.6 | 44 | 88 | 0 | 1188.89 | 209.2446 | 523.1116 | 1046.2232 | 0 | 0 | 0
3 | Fabrication of Mild steel | 97x 1.1/20= Ton |  | 0 | 0 | 53.0754 | 0 | 0 | 0 | 0 | 2.9191 | 0
|  | R A T E S |  |  |  | Total | 611.7246 | 1947.2716 | 3894.5432 | 0 | 2.9191 | 0
|  | Mile | Cement | Bricks | Others | Say | 611.7246 | 1947.2716 | 3894.5432 | 0 | 2.9191 | 0
|  | 1st | 6.1 | 325.6 | 407 | Station | Rohri | Sui | Arrore | Larkana | Karachi | Arrore
|  | 2nd | 1.43 | 76.4 | 95.52 | Total M | 85 | 155 | 91 | 25 | 318 | 91
|  | 3rd | 0 | 61.51 | 76.89 | Rate | 54.93 | 5623.4 | 3539.56 | 1112.49 | 10930.68 | 3539.56
|  | 4th | 0 | 56.36 | 70.45 | Unit | P.Bag | P. % Cft: | P. % Cft: | %o Nos: | P-5 Ton | P. % Cft:
|  | 5th | 0 | 51.54 | 64.43 | Amount | 33602.0345 | 109502.8712 | 137849.6933 | 0 | 6381.6579 | 0
|  | 6th | 0 | 46.13 | 57.67
|  | Total | 7.53 | 617.54 | 771.96 | Total Rs: | 287336.2568
|  | 7th | 0.6 | 26.05 | 32.56 | Say Rs: | 287336.2568
Assistant Executive Engineer
Shahdadkot Drainage Sub Division
Larkana

## Abstract
BD-6
Appendix-D to Bid
BILL OF QUANTITIES (BOQs)
Bill No: 4
NAME OF WORK: ESTIMATE FOR RE-CONSTRUCTION OF WATER COURSE ALONG 4L, 4LA, 5L, 5LA, 5LB, 6L, SUB DRAIN OF MMD SYSTEM (12NOS:).
S. No | Description | Quantity |  | Rate | Unit | Amount
1 | Dismantling R.C.C 1:2:4 | 1567.2 | Cft: | 5445 | %Cft | 85334.04
Dismantling Cement concrete reinforced separting reinformcement from concrete cleaning & strenghtening the same (Page No:10, Item No: 20)
2 | Dismantling Pacca Work | 6366.6 | Cft: | 1285.63 | %Cft | 81850.9196
Dismantling brick work in lime or Cement mortar (Page No:10, Item No:13)
3 | Dismantling Cement Concrete 1:3:6 | 864 | Cft: | 1306.8 | %Cft | 11290.752
Dismantling Cement Concretr Plain 1:3:6 (Page No:10, Item No:19(b)
4 | Borrowpit Excavation | 231912 | Cft: | 2117.5 | %oCft | 491073.66
Borrowpit Excavation undressed lead up to 100 ft: (a) ordinary soil (Page No: 1, Item No: 3 (a)
5 | Rehandling of Earth work | 185856 | Cft: | 1058.75 | %oCft | 196775.04
Rehandling of Earth work (b) up to lead of 50 ft: (Page-2, Item No.9
6 | Dressing and leveling of Earth work | 231912 | Cft: | 187.55 | %o Cft: | 43495.0956
Dressing and leveling of Earth work to designed section etc complete. b) in ordinary or hard soil (Page-3, Item No.11(b)
7 | Excavation in Foundation | 16920 | Cft: | 3176.25 | %o Cft: | 53742.15
Excavation in foundation of buildings, bridges & other structure i/c dag bellings, dressing refilling around the structures with excavated earth watering & remaining lead up to 5 ft: in ordinary soil (P-4 Item No:18(b)
8 | Extra for Wet Earth | 8460 | Cft: | 1058.75 | %o Cft: | 8957.025
Extra for wet earth work (P-3 Item No:15)
9 | C.C. Plain Ratio 1:3:6 | 3096 | Cft: | 12595 | % Cft: | 389941.2
Cement concrete plain i/c placing compacting finishing and curing complete i/c screening and washing of stone aggregate With out shuttering ratio 1:3:6 (P-18 Item No: 5 (h)
10 | R.C.C. Plain 1:2:4 | 14266.68 | Cft: | 337 | P. Cft: | 4807871.16
Cement concrete plain i/c placing compacting finishing and curing complete i/c screening and washing of stone aggregate With out shuttering ratio 1:2:4 (P-15 & 16 Item No:6 (i)
11 | Fabrication of mild steel | 636.9054 | Cwt: | 4820.2 | P.Cwt: | 255856
Fabrication of mild steel reinforcement for cement, concrete including cutting bending lying in position making joints and fastenings including cost of binding wire also includes removal of rust from bars. (Page No: 16 Item No:08 (a)
12 | Full hire charges of the Pumping set | 120 | days | 1500 | P.day | 180000
Full hire charges of the Pumping set per day inclusive of wages of driver and Assistant fuel or electric energy, plat forms required for placing Pumps etc. @ lower depths with suction and delivery pipes for pumping out water found at various depths from trenches i/c the cost of erection & dismantling after completion of the job. (iv) Hire charges of pumping set of up to 10 HP Pumping out water from 15' deep trench (P-76 Item-23 (PHED) 2012
13 | For working the pump beyond 8 Hours | 1920 | Hrs: | 188 | P.Hrs | 360960
For working the pump beyond 8 Hours the following payment Shall be made. The hire of the Pumping set it self being for 24 Hours (ii) for a pumping set of Upto 10 HP (but not less than 5 HP). (P-77, Item No-23 Note (ii)) (PHED) 2012
|  |  | Total Rs: |  |  | 6967147.0422
Executive Engineer
Larkana Drainage Division
Larkana

## M Ment
MEASUREMENT SHEET
NAME OF WORK: ESTIMATE FOR RE-CONSTRUCTION OF WATER COURSE ALONG SUB DRAIN
S.# | Description of Item | No | x | L | x | B | x | D | = | Quantity
1 | Dismantling of R.C.C
| i) Slab IP & NIP | 1 | × | 16 | × | 5 | × | 0.5 | = | 40 | Cft:
| i) Side Wall | 2 | × | 20 | × | 0.38 | × | 3 | = | 45.6 | Cft:
| iii) Bed | 1 | × | 20 | × | 4.5 | × | 0.5 | = | 45 | Cft:
[7 empty] | Total |  | = | 130.6 | Cft:
2 | Dismantling Pacca brick work
| Abutment | 2 | x | 4.5 | x | 4+1.5 | x | 5 | = | 123.75 | Cft:
2
| Mas: Walls | 2 | × | 60 | × | 1.13 | × | 3 | = | 406.8 | Cft:
[7 empty] | Total |  | = | 530.55 | Cft:
3 | Dismantling Cement Concrete 1:3:6
| Abutment Bed | 2 | × | 6 | × | 6 | × | 1 | = | 72 | Cft:
[7 empty] | Total |  | = | 72 | Cft:
4 | Borrowpit Excavation undressed
| a) Diversion IP Side | 1 | × | 100 | × | 12+28 | × | 4 | = | 8000 | Cft:
2
| b) Approaches IP Side | 2 | × | 25 | × | 17+ 25 | × | 4.0+0 | = | 2100 | Cft:
[6 empty] | 2 |  | 2
| c) Approaches NIP Side | 2 | x | 25 | × | 12+20 | × | 4.0+0 | = | 1600 | Cft:
[6 empty] | 2 |  | 2
| d) Over Slab IP Side | 1 | x | 13 | × | 6 | × | 1 | = | 78 | Cft:
| e) Over Slab NIP Side | 1 | x | 10 | × | 6 | × | 1 | = | 60 | Cft:
| f) Bundas | 2 | x | 26 | x | 10+26 | x | 8 |  | 7488 | Cft:
[6 empty] | 2 | Total |  | = | 19326 | Cft:
5 | Rehandling of Earth Work
| Qty: Same as Item 4 (a+f) |  |  | 8000 | + | 7488 |  |  | = | 15488 | Cft:
[7 empty] | Total |  | = | 15488 | Cft:
6 | Dressing & Levelling
| Qty: Same as Item 4 | [7 empty] | = | 19326
[7 empty] | Total |  | = | 19326 | Cft:
7 | Excavation in foundation
| Cutting of bank NIP side | 1 | x | 17 | × | 6 | × | 4 | = | 408 | Cft:
| Cutting of bank IP side | 1 | x | 22 | x | 6 | x | 4 | = | 528 | Cft:
| berm side | 2 | x | 15 | × | 4.5 | × | 1 | = | 135 | Cft:
| wing walls | 4 | x | 2 | x | 1.5 | x | 2 | = | 24 | Cft:
| Abutment | 3 | x | 7 | x | 5 | x | 3 | = | 315 | Cft:
[7 empty] | Total |  |  | 1410 | Cft:
8 | Extra For Wet Earth Work
| Qty: 50% of Item No: 7 |  |  | 1410 | x | 50 | % |  | = | 705 | Cft:
[7 empty] | Total |  |  | 705 | Cft:
9 | C.C.Plain 1:3:6
| RCC Nali IP & NIP Side Bed | 1 | × | 28 | × | 6 | x | 0.5 | = | 84 | Cft:
| IP & NIP Side Berm | 2 | × | 14 | × | 4.5 | x | 0.5 | = | 63 | Cft:
| Wing walls | 4 | × | 2 | × | 1.5 | x | 0.5 | = | 6 | Cft:
| Abutment | 3 | × | 7 | × | 5 | x | 1 | = | 105 | Cft:
[7 empty] | Total |  | = | 258 | Cft:
10 | R.C.C work 1:2:4
| Abtment & Pier 1st Step | 3 | × | 6 | × | 4 | × | 1 | = | 72 | Cft:
| Abtment & Pier 2nd Step | 3 | × | 5 | × | 3 | × | 1 | = | 45 | Cft:
| Abtment & Pier 3rd Step | 3 | × | 4.75 | × | 3 | × | 1 | = | 42.75 | Cft:
| Abtment & Pier 4th Step | 3 | × | 4.5 | × | 1.5 | × | 5 | = | 101.25 | Cft:
| IP & NIP Bed Slab Side | 1 | × | 28 | × | 6 | × | 0.5 | = | 84 | Cft:
| IP & NIP Side Walls | 2 | × | 28 | × | 1.5 | × | 3.5 | = | 294 | Cft:
| IP & NIP Berm Bed | 2 | × | 14 | × | 4.5 | × | 0.5 | = | 63 | Cft:
| IP & NIP Berm Side Wall | 2 | × | 14 | × | 0.75 | × | 3.5 | = | 73.5 | Cft:
| Bed of Trough | 1 | × | 24.5 | × | 4.5 | × | 0.5 | = | 55.125 | Cft:
| Side Wall | 2 | × | 24.5 | × | 0.75 | × | 3.5 | = | 128.625 | Cft:
| Wing walls | 4 | × | 2 | × | 1.13 | × | 3.5 | = | 31.64 | Cft:
| IP & NIP Slab | 1 | × | 28 | × | 6 | × | 0.75 | = | 126 | Cft:
| P/wall | 4 | × | 6 | × | 1 | × | 3 | = | 72 | Cft:
[7 empty] | Total |  | = | 1188.89 | Cft:
11 | Fabrication of Mild Steel
| Quantity same as item No:11 |  |  |  |  | 1188.89 | x | 5 | = | 53.0754 | Cwt:
[6 empty] | 112 | Total |  | = | 53.0754 | Cwt:
12 | Full hire charges of the Pumping set
|  |  |  | 1 | x | 2 | x | 5 | = | 10 | Days
[7 empty] | Total |  | = | 10 | Days
13 | For working the pump beyond 8 Hours
|  |  |  | 2 | x | 5 | x | 16 | = | 160 | Hour
[7 empty] | Total |  | = | 160 | Hour
Assistant Executive Engineer
Shahdadkot Drainage Sub Division
Larkana