## ABSTRACT LDD
BD-4
Appendix-D to Bid
BILL OF QUANTITIES (BOQs)
Bill No: 2
Name of Work: Construction of Retaining Wall @ Larkana North (Shahmir) Pumping Station.
S. No | Description | Quantity |  | Rate | Unit | Amount
1 | Excavation in foundation of buildings, bridges & other structure i/c dag bellings, dressing refilling around the structures with excavated earth watering & remaining lead up to 5 ft: in ordinary soil (P-4 Item No.18 (b) | 3000 | Cft: | 3176.25 | %0Cft | 9528.75
2 | Cement concrete plain i/c placing compacting finishing and curing complete i/c screening and washing of stone aggregate With out shuttering ratio 1:4:8 (P-15 Item No: 5 (i) | 800 | Cft: | 11288.75 | % Cft: | 90310
3 | Cement concrete plain i/c placing compacting finishing and curing complete i/c screening and washing of stone aggregate With out shuttering ratio 1:3:6 (P-15 Item No: 5 (h) | 800 | Cft: | 12595 | % Cft: | 100760
4 | Pacca brick work in foundation & plinth in cement sand morter ratio 1:4 (Page No: 19 item No:4(i) | 1100 | Cft: | 12501.41 | % Cft: | 137515.51
5 | Pacca brick work other than buildings i/c stricking of joints up to 20 ft: height in cement sand mortar 1:3 (Page No: 21 item No:7(i) (b) | 2400 | Cft: | 13387.69 | % Cft: | 321304.56
6 | (a) R.C.C. work in roof slab beams, columns rafts, lintels and other structural members laid in situ or pre cast laid in position complete in all respects. (i) Ratio 1:2:4 90 lbs cement 2 cft: sand 4 cft: shingle 1/8” to 1/4” gauge. (P-15&16 Item-6 (i) | 150 | Sft: | 337 | % Sft | 50550
7 | Fabrication of mild steel reinforcement for cement, concrete including cutting bending lying in position making joints and fastenings including cost of binding wire also includes removal of rust from bars. (Page No: 16 Item No: 08 (a) | 6.6964 | Cft: | 4820.2 | % Cft: | 32278.125
8 | Cement Pointing struck joints 1:2 (P-52 item No:19 (a) | 200 | Sft: | 1287.44 | % Sft: | 2574.88
9 | Cement Plaster 3/4" thick up to 20' height 1:3 (P-51 item No:10 (c) | 800 | Sft: | 2795.3 | % Sft: | 22362.4
10 | Extra for wet earth work (P-3 Item No:15) | 1500 | Cft: | 1058.75 | %o Cft: | 1588.125
11 | Borrowpit Excavation undressed lead up to 100 ft: (a) ordinary soil (Page No: 1, Item No: 3 (a) | 7175 | Cft: | 2117.5 | %oCft | 15193.0625
12 | Carriage of 100 Cft:/ 5 tones of all material like stone aggregate, spwal, coal, lime, surkhi etc B G. rail fastening points and crossing bridges, girders, pipes, 10” x 5”or 1000 mounds of fuel wood by trucks or any other means owned by the contractors. (Average 03 miles. Rate analysis attached) | 7175 | Cft: | 579.41 | %Cft | 41572.6675
13 | Dressing and leveling of Earth work to designed section etc complete. b) in ordinary or hard soil (Page-3, Item No.11b) | 7175 | Cft: | 187.55 | %o Cft: | 1345.6713
14 | Full hire charges of the Pumping set per day inclusive of wages of driver and Assistant fuel or electric energy, plat forms required for placing Pumps etc. @ lower depths with suction and delivery pipes for pumping out water found at various depths from trenches i/c the cost of erection & dismantling after completion of the job. (iv) Hire charges of pumping set of up to 10 HP Pumping out water from 15' deep trench (P-76 Item-23 (PHED) 2012 | 5 | Day | 1500 | P.D | 7500
15 | For working the pump beyond 8 Hours the following payment Shall be made. The hire of the Pumping set it self being for 24 Hours (ii) for a pumping set of Upto 10 HP (but not less than 5 HP). (P-77, Item No-23 Note (ii)) (PHED) 2012 | 80 | Hrs | 188 | P.Hrs | 15040
16 | Rehandling of earthwork. (b) Up to a lead of 50 ft: (P-2 Item No:-9 | 2975 | Cft: | 1058.75 | %oCft | 3149.7812
|  |  | Total Rs: |  |  | 852573.5325
Executive Engineer
Larkana Drainage Division
Larkana

## Cartage LDD
CARTAGE & MATERIAL STATEMENT
Name of Work: Construction of Retaining Wall @ Larkana North (Shahmir) Pumping Station.
S.# | I t e m | Material for % Cft:/Sft: |  |  |  | Quantity | Cement Bags | Hill Sand Cft: | Bajri Shingle Cft: | Bricks Nos: | Steel Ton | R.CC Pipe
|  | C bag | Sand | B/S | Bricks
1 | Cement Concrete plain Ratio 1:4:8 | 9 | 48 | 96 | 0 | 800 | 72 | 384 | 768 | 0 | 0 | 0
2 | Cement Concrete plain Ratio 1:3:6 | 13 | 46 | 92 | 0 | 800 | 104 | 368 | 736 | 0 | 0 | 0
3 | Pacca Brick work Ratio 1:3 | 6 | 22.5 | -- | 1350 | 2400 | 144 | 540 | 0 | 32400 | 0 | 0
4 | Pacca Brick work Ratio 1:4 | 4.77 | 24 | 0 | 1350 | 1100 | 52.47 | 264 | 0 | 14850 | 0 | 0
5 | Cement Concrete plain Ratio 1:2:4 | 17.6 | 44 | 88 | 0 | 6.6964 | 1.1786 | 2.9464 | 5.8929 | 0 | 0 | 0
6 | Cement Pointing Ratio 1:3 | 0.54 | 2 | 0 | 0 | 200 | 1.08 | 4 | 0 | 0 | 0 | 0
7 | Cement Plaster 1:3 1/2 thick | 1.31 | 5.1 | 0 | 0 | 800 | 10.48 | 40.8 | 0 | 0 | 0 | 0
8 | R.C.C work Ratio 1:2:4 | 17.6 | 44 | 88 | 0 | 150 | 26.4 | 66 | 132 | 0 | 0 | 0
9 | Fabrication of Mild steel | 438.88x 1.1/20= Ton |  | 0 | 0 | 6.6964 | 0 | 0 | 0 | 0 | 0.3683 | 0
|  | R A T E S |  |  |  | Total | 411.6086 | 1669.7464 | 1509.8929 | 47250 | 0.3683 | 0
|  | Mile | Cement | Bricks | Others | Say | 411.6086 | 1669.7464 | 1509.8929 | 47250 | 0.3683 | 0
|  | 1st | 6.1 | 325.6 | 407 | Station | Rohri | Sui | Arrore | Larkana | Karachi | Larkana
|  | 2nd | 1.43 | 76.4 | 95.52 | Total M | 72 | 142 | 78 | 8 | 305 | 8
|  | 3rd | 0 | 61.51 | 76.89 | Rate | 47.13 | 4160.34 | 3116.28 | 669.64 | 10507.4 | 1711.64
|  | 4th | 0 | 56.36 | 70.45 | Unit | P.Bag | P. % Cft: | P. % Cft: | %o Nos: | P-5 Ton | P. % Cft:
|  | 5th | 0 | 51.54 | 64.43 | Amount | 19399.112 | 69467.1286 | 47052.4891 | 31640.49 | 773.9826 | 0
|  | 6th | 0 | 46.13 | 57.67
|  | Total | 7.53 | 617.54 | 771.96 | Total Rs: | 168333.2023
|  | 7th | 0.6 | 26.05 | 32.56 | Say Rs: | 168333.2023
Assistant Executive Engineer
Naudero Drainage Sub Division
Larkana

## M Ment
MEASUREMENT SHEET
Name of Work: Construction of Retaining Wall @ Larkana North (Shahmir) Pumping Station.
S.# | Description of Item | No | L B D | [9 empty] | = | Quantity
1 | Excavation in foundation
| Retaining Wall | 1 | x | 100 | x | 8 | + | 12 | / | 2 | x | 6 | = | 3000 | Cft:
[11 empty] | Total |  | = | 3000 | Cft:
2 | C.C.Plain i/c placing 1:4:8
| Retaining Wall | 1 | x | 100 | x | 8 | x | 1 |  |  |  |  | = | 800 | Cft:
[11 empty] | Total |  | = | 800 | Cft:
3 | C.C.Plain i/c placing 1:3:6
| Retaining Wall | 1 | x | 100 | x | 8 | x | 1 |  |  |  |  | = | 800 | Cft:
[11 empty] | Total |  | = | 800 | Cft:
4 | Pacca Brick work in Foundation Ratio 1:4.
| 1st Step R/Wall | 1 | x | 100 | x | 6 | x | 1 |  |  |  |  | = | 600 | Cft:
| 2nd Step R/Wall | 1 | x | 100 | x | 5 | x | 1 |  |  |  |  | = | 500 | Cft:
[11 empty] | Total |  | = | 1100 | Cft:
5 | Pacca Brick work other then Ratio 1:3.
| Retaining Wall | 1 | x | 100 | x | 4.5 | + | 1.5 | / | 2 | x | 8 | = | 2400 | Cft:
[11 empty] | Total |  | = | 2400 | Cft:
6 | R.C.C work 1:2:4
| Coping over Retaining Wall | 1 | x | 1 | x | 100 | x | 1.5 | x | 1 |  |  | = | 150 | Cft:
[11 empty] | Total |  | = | 150 | Sft:
7 | Fabrication of Mild Steel
| Retaining Wall | 1 | x | 150 | x | 5 | / | 112 |  |  |  |  | = | 6.6964 | Cft:
[11 empty] | Total |  | = | 6.6964 | Cft:
8 | Cement Pointing Struck Joints 1:3
| Retaining Wall out side | 1 | x | 100 | x | 2 | [6 empty] | = | 200 | Sft:
[11 empty] | Total |  | = | 200 | Sft:
9 | Cement Plaster 3/4" thick
| Retaining Wall in side | 1 | x | 100 | x | 8 | [6 empty] | = | 800 | Sft:
[11 empty] | Total |  | = | 800 | Sft:
10 | Extra for wet earth work
| Retaining Wall | 50% Qty of Item No: 1 |  |  |  |  | = | 3000 |  |  | / | 2 | = | 1500 | Cft:
[11 empty] | Total |  | = | 1500 | Cft:
11 | Borrowpit Excavation
| A) Bundhas | 1 | x | 50 | x | 8 | + | 26 | / | 2 | x | 7 | = | 2975 | Cft:
| B) Earth Filling behind R/W | 1 | x | 100 | x | 12 | + | 16 | / | 2 | x | 3 | = | 4200 | Cft:
[11 empty] | Total |  | = | 7175 | Cft:
12 | Carriage of 100 cft: 5 tone of all material
| Retaining Wall |  | Qty of Item No: 11 | [9 empty] | = | 7175 | Cft:
[11 empty] | Total |  | = | 7175 | Cft:
13 | Dressing and leveling
| Retaining Wall |  | Qty of Item No: 11 | [9 empty] | = | 7175 | Cft:
[11 empty] | Total |  | = | 7175 | Cft:
14 | Full hire charges
| Retaining Wall | 1 | x | 1 | x | 5 | [6 empty] | = | 5 | Days
[11 empty] | Total |  | = | 5 | Days
15 | For working the pump
| Retaining Wall | 1 | x | 5 | x | 16 | [6 empty] | = | 80 | H
[11 empty] | Total |  | = | 80 | H
16 | Rehandling of earthwork.
|  |  | Qty of Item No: 11 (A) | [9 empty] | = | 2975 | Cft:
[11 empty] | Total |  | = | 2975 | Cft:
Assistant Executive Engineer
Naudero Drainage Sub Division
Larkana