## Sheet1
Serial No.1-ii
SPPRA BIDDING DOCUMENT
STANDARD FORM OF BIDDING DOCUMENT
FOR
PROCURMENT OF WORKS
(For Contracts (Small) amounting between Rs.2.500 million to Rs.50.000 million)
NOTICE INVITING TENDERS VIDE NO.PD/P&PW/ , DATED 20.04.2015
| DATE & TIME OF ISSUE UPT0 | : | 08.05.2015 (2.00PM)
| DATE & TIME OF RETURN UPTO | : | 11.05.2015 (2.30PM)
| DATE & TIME OF OPENING | : | 11.05.2015 (3.00PM)
| Name of Work: | ADP No.837 of 2014-15 Raising / Construction of Watch Tower and Boundary Wall at (i) RRF Base Al-Falah Karachi (ii) Naval Colony Base Karachi (iii) Police Head Quarter District South Garden Road Karachi
ii. Naval Colony Base Karachi (Back Side)
| ISSUED TO | :
| DR No. | :
| DATE | :
Project Director
Police & Prison Works
Hyderabad
BIDDING DATA
(This section should be filled in by the Engineer / Procuring Agency before issuance of the Bidding Documents. The following specific data for the works to be tendered shall complement, amend, or supplement the provisions in the Instructions to Bidders. Wherever there is a conflict, the provisions herein shall prevail over those in the Instructions to Bidders).
Instructions to Bidders
Clause Reference
1.1 | Name of Procuring Agency | Project Director, Police & Prison Works, Hyderabad
| Brief Description of Works | ADP No.837 of 2014-15 Raising / Construction of Watch Tower and Boundary Wall at (i) RRF Base Al-Falah Karachi (ii) Naval Colony Base Karachi (iii) Police Head Quarter District South Garden Road Karachi
ii. Naval Colony Base Karachi (Back Side)
5.1a | Procuring Agency's Address | Shahbaz Building Block-A (2nd Floor), Hyderabad
b | Engineer's Address | Shahbaz Building Block-A (2nd Floor), Hyderabad
10.3 | Bid shall be quoted entirely in Pak. Rupees. The payment shall be made in Pak. Rupees.
11.2 | The bidder has the financial, technical and constructional capability necessary to perform the Contract as follows:
| i. Financial capability. | As per SPP Rules, 2010 (amended to date)
| ii. Technical capability. | As per SPP Rules, 2010 (amended to date)
| iii. Construction capacity. | As per SPP Rules, 2010 (amended to date)
12.1 | a. A detailed description of the works, essential technical and performance characteristics.
b. Complete set of technical information, description data, literature and drawings as required in accordance with schedule-B to Bid, Specific Works Data. This will include but not be limited to a sufficient number of drawings, photographs, catalogues, illustrations and such other information as is necessary to illustrate clearly the significant characteristics such as general construction dimensions and other relevant information about the works to be performed.
13.1 | Amount of Bid Security | 2% of the Bidding Amount
(fill in lump sum amount or in %age of bid amount / estimated cost, but not below 1% and not exceeding 5%)
14.1 | Period of Bid Validity | : | 90 | Days
(fill in "number of days" not exceeding 90)
14.4 | Number of copies of the Bid to be submitted: |  | One original plus one photo stat copies)
14.6 | a. Procuring Agency's Address for the Purpose of Bid Submission | Office of the Project Director, Police & Prison Works,
Shahbaz Building Block-A (2nd Floor), Hyderabad
15.1 | Deadline for submission of bids | : | 11.05.2015 (2.30PM)
16.1 | Venue, time and date of Bid Opening | : | 11.05.2015 (3.00PM)
Office of the Project Director, Police & Prison Works,
Shahbaz Building Block-A (2nd Floor), Hyderabad
16.4 | Responsiveness of Bids
i | Bid is valid till required period;
ii | Bid prices are firm during currency of contract / price adjustment;
iii | Completion period offered is within specified limits,
iv | Bidder is eligible to bid and possesses the requisite experience, capability and qualficiation.
v | Bid does not deviate from basic technical requirements and
vi | Bids are generally in order etc.
* | Procuring agency can adopt either of two options (select either of them)
a. Fixed price contract: In these contracts no escalation will be provided during currency of the contract and normally period of completion of these works is upto 12 months.
b. Price adjustment contract: In these contracts escalation will be paid only on those items and in the manner as notified by Finance Department, Government of Sindh, after bid opening during currency of the contract.
| Signature of Contractor / Bidder |  |  |  | Project Director
Police & Prison Works
Hyderabad
General Abstract
Composite Schedule Items.
| Construction of Boundary Wall (1,000 Rft) | [5 empty] | Rs. | 32047360
| Construction of Watch Towers (02 Nos) | [5 empty] | Rs. | 5509668
[6 empty] | Total | Rs. | 37557028
| Add: / Deducted ……………………………...… % Above / Below Premium | [5 empty] | Rs. | …………….
| Cost of Non Schedule Items | [5 empty] | Rs. | ……………..
|  | Total Bid Amount |  |  |  |  | Rs.
| Signature of Contractor / Bidder |  | Project Director
Police & Prison Works
Hyderabad

## Abstract (hidden)
Construction of Compound Wall including Steel Gate for Category-II Bungalow (1 No) @ District Jail Shaheed Benazirabad (Nawabshah).
General Abstract.
S. No:- | Description. | Quantity. |  | Rate. |  | Unit. | Amount.
1- | Excavation in foundation of Buildings Bridges & other structure i/c dagbelling dressing refilling around structure with excavated earth watering & ramming lead up to 5’ Feet (c) in Hard Soil or Soft murum (S.I. No:- 18 (c) / P-4). | 1193 | Cft. | Rs. | 1306.8 | %0 Cft. | Rs. | 1559.0124
2- | Cement concrete brick or stone ballast 1-1/2" thick to 2" gauge (b) Ratio 1:4:8 (S.I. No:- 4 (b) / P-17). | 445 | Cft. | Rs. | 3584.1 | % Cft. | Rs. | 15949.245
3- | Pacca Brick Work in Foundation & Plinth in (i) (e) Cement Sand Mortar Ratio 1:6 (R.A. Attached). | 1161 | Cft. | Rs. | 13280.17 | % Cft. | Rs. | 154182.7737
4- | Fabrication of mild steel reinforcement for cement concrete including cutting bending, laying in position, making joints & fasteningS including cost of binding wire (also includes removal of rust from bars) (b) Using TOR Bars (S.I.No:- 7 (ii) (a) / P-20). | 21.06 | Cwt. | Rs. | 2772.55 | P. Cwt. | Rs. | 58389.903
5- | Reinforcement cement concrete work including all labour & material except the cost of steel reinforcement & its labour for bending & binding which will be paid separately. This rates also includes all kinds of forms moulds: lifting shuttering curing rendering & finishing the exposed surface (including screening & washing of shingle) (a) R.C. work in roof slab, beams columns rafts, lintels & other structural members laid in situ or precast laid in position completed in all respects (I) Ratio (1:2:4) 90 Lbs Cement 2 Cft. Sand 4 Cft. Shingle 1/8" to 1/4" gauge (S.I. No:- 6 (I) / P-19). | 238 | Cft. | Rs. | 114 | P. Cft. | Rs. | 27132
6- | Pacca Brick Work in Ground Floor including Stricking in Joints in Cement Sand Mortar Ratio 1:6 (R.A. Attached). | 1595 | Cft. | Rs. | 13761.88 | % Cft. | Rs. | 219501.986
7- | Cement Plaster 1:6 upto 20" Height (b) 1/2" Thick (R.A. Attached). | 5166 | Sft. | Rs. | 1386.95 | % Sft. | Rs. | 71649.837
8- | Cement Plaster 1:4 Upto 20" Height (a) 3/8" Thick (R.A. Attached). | 5166 | Sft. | Rs. | 1367.24 | % Sft. | Rs. | 70631.6184
9- | Cement Concrete Plain including Placing, Compacting, Finished & Curing Complete (including Screening & Washing of Stone Aggregate without Shuttering) (h) Ratio 1:3:6 (S.I. No:- 5 (h) / P-18). | 81 | Sft. | Rs. | 5001.7 | % Sft. | Rs. | 4051.377
10- | Erection & Removal of Centering for R.C.C. or Plain Cement Concrete Works of Deodar Wood (2nd Class) (b) For Partal Wood (ii) Vertical (S.I.No:- 18 (b) (ii) / P-21). | 144 | Sft. | Rs. | 1405.75 | % Sft. | Rs. | 2024.28
11- | Making & fixing steel grated doors with 1/16" thick sheeting including angle iron frame 2"x 2"x 3/8" & 3/4" square bars 4" centre to centre (S.I.No:- 24 / P-97). | 60 | Sft. | Rs. | 385.76 | P. Sft. | Rs. | 23145.6
12- | Distempering (c) Three Coats (S.I.No:- 24 (c) / P-60). | 5166 | Sft. | Rs. | 263.51 | % Sft. | Rs. | 13612.9266
13- | Painting Guard Bars, gates iron bars gratings, railings including standard braces etc: & similar open work (i) First Coat (ii) Each Subsequent Coat (S.I.No:- 5 (i + ii) / P-76). | 120 | Sft. | Rs. | 584.54 | % Sft. | Rs. | 701.448
|  | Total:- |  |  |  |  | Rs. | 662532.0071
|  | Cartage. |  |  |  |  | Rs. | 27311
|  | Total:- |  |  |  |  | Rs. | 689843.0071
|  | Add 20% Above Except Non Schedule Items (Rs. 689843 Rs. 515967 = Rs. 173876). |  |  |  |  | Rs. | 34775
|  | Total:- |  |  |  |  | Rs. | 724618.0071
|  | Add Difference Cost of Cement 96 Bags @ Rs. 105/- Per Bag. |  |  |  |  | Rs. | 10080
|  | Add Difference Cost of Steel 1.05 Tons @ Rs. 23000/- Per Cwt. |  |  |  |  | Rs. | 24150
|  | Grand Total:- |  |  |  |  | Rs. | 758848.0071
|  | Say:- |  |  |  |  | Rs. | 0.759 (M)
| Sub-Engineer |  | Deputy District Officer (Buildings)
Woks & Services Department
Sakrand.
Project Director
Police & Prison Works Sindh
Hyderabad.
D/Estimate/Estimate of Category II B'low N'Shah Jail/Abstract C/Wall.