## Escalation (hidden)
Escalation Sheet.
S. No:- | Year. | Allocation. | Escalation Factor. | Escalated Amount. | Total.
1 | 2 | 3 | 4 | 5 | 6
01- | 2013-2014. | 10 | 0 | 0 | 10
02- | 2014-2015. | 15.2678 | 0.065 | 1.3159 | 16.5837
| Total:- | 25.2678 | 0 | 1.3159 | 26.5837
| Add Cost of Demand Notices:- |  |  | Rs. | 2.5267
|  |  | G. Total:- | Rs. | 29.1104
| Assistant Engineer |  |  | Executive Engineer
| Police & Prison Works Sub-Division |  |  | Police & Prison Works Division
| Sukkur. |  |  | Sukkur.
Project Director
Police & Prison Works Sindh
Hyderabad.
D/Escalation for Police Station Jacobabad/Abstract.

## Sheet1
Serial # 2-i
SPPRA BIDDING DOCUMENT
STANDARD FORM OF BIDDING DOCUMENT
FOR
PROCURMENT OF WORKS
(For Contracts (Small) amounting between Rs.2.500 million to Rs.50.000 million)
NOTICE INVITING TENDERS NO.PD/P&PW/ DATED 20.04.2015
Name of Work:
ADP No.881 of 2014-15 Extension of District Jail Malir for 1,000 Prisoners including Raising and Strengthening of existing main Compound Wall
i. External Drainage, Septic Tank and External Development
| TENDER COST | : | Rs.17.010 million
| COMPLETION PERIOD | : | 12 (twelive) months
| Earnest Money | : | 2% of Bid Price
| Call Deposit / Pay Order No & Date | : | ……………………………..
| Name of Bank | : | ……………………………..
| Amount of Call Deposit / Pay Order | : | Rs…………………………..
| DATE & TIME OF ISSUE UPT0 | : | 08.05.2015 (2.00PM)
| DATE & TIME OF RETURN UPTO | : | 11.05.2015 (2.30PM)
| DATE & TIME OF OPENING | : | 11.05.2015 (3.00PM)
| ISSUED TO (Name of Bidder) | :
| DR No. | :
| DATE | :
| BIDDING DOCUMENTS FEE : |  |  |  |  | Rs.3,000/- (Rupees three thousand only)
| Name of Bidder |  |  | Project Director
Police & Prison Works
Hyderabad
BIDDING DATA
(This section should be filled in by the Engineer / Procuring Agency before issuance of the Bidding Documents. The following specific data for the works to be tendered shall complement, amend, or supplement the provisions in the Instructions to Bidders. Wherever there is a conflict, the provisions herein shall prevail over those in the Instructions to Bidders).
Instructions to Bidders
Clause Reference
1.1 | Name of Procuring Agency | Project Director, Police & Prison Works, Hyderabad
| Brief Description of Works | ADP No.881 of 2014-15 Extension of District Jail Malir for 1,000 Prisoners including Raising and Strengthening of existing main Compound Wall
i. External Drainage, Septic Tank and External Development
5.1a | Procuring Agency's Address | Shahbaz Building Block-A (2nd Floor), Hyderabad
b | Engineer's Address | Shahbaz Building Block-A (2nd Floor), Hyderabad
10.3 | Bid shall be quoted entirely in Pak. Rupees. | The payment shall be made in Pak. Rupees.
11.2 | The bidder has the financial, technical and constructional capability necessary to perform the Contract as follows:
| i. Financial capability. | As per SPP Rules, 2010 (amended to date)
| ii. Technical capability. | As per SPP Rules, 2010 (amended to date)
| iii. Construction capacity. | As per SPP Rules, 2010 (amended to date)
12.1 | a. A detailed description of the works, essential technical and performance characteristics.
b. Complete set of technical information, description data, literature and drawings as required in accordance with schedule-B to Bid, Specific Works Data. This will include but not be limited to a sufficient number of drawings, photographs, catalogues, illustrations and such other information as is necessary to illustrate clearly the significant characteristics such as general construction dimensions and other relevant information about the works to be performed.
13.1 | Amount of Bid Security | 2% of the Bidding Amount
(fill in lump sum amount or in %age of bid amount / estimated cost, but not below 1% and not exceeding 5%)
14.1 | Period of Bid Validity | : | 90 | Days
(fill in "number of days" not exceeding 90)
14.4 | Number of copies of the Bid to be submitted: |  |  |  |  | One original plus one photo stat copies)
14.6 | a. Procuring Agency's Address for the Purpose of Bid Submission | Office of the Project Director, Police & Prison Works, Shahbaz Building Block-A (2nd floor) Hyderabad
15.1 | Deadline for submission of bids | : | 11.05.2015 (2.30PM)
16.1 | Venue, time and date of Bid Opening | : | 11.05.2015 (3.00PM)
Office of the Project Director, Police & Prison Works, Shahbaz Building Block-A (2nd floor) Hyderabad
16.4 | Responsiveness of Bids
i | Bid is valid till required period;
ii | Bid prices are firm during currency of contract / price adjustment;
iii | Completion period offered is within specified limits,
iv | Bidder is eligible to bid and possesses the requisite experience, capability and qualficiation.
v | Bid does not deviate from basic technical requirements and
vi | Bids are generally in order etc.
* | Procuring agency can adopt either of two options (select either of them)
a. Fixed price contract: In these contracts no escalation will be provided during currency of the contract and normally period of completion of these works is upto 12 months.
b. Price adjustment contract: In these contracts escalation will be paid only on those items and in the manner as notified by Finance Department, Government of Sindh, after bid opening during currency of the contract.
| Signature of Bidder |  |  | Project Director
Police & Prison Works
Hyderabad
General Abstract
A | Septic Tank
i | Cost of Composite Schedule Items |  |  | Rs. | 759055
ii | Add: / Deduct ………... % Above / Below Premium Rs………………….
iii | Cost of Non Schedule Items / Offer Rates |  |  | Rs. | ……………….
B | External Drainage
i | Cost of Composite Schedule Items |  |  | Rs. | 1444708
ii | Add: / Deduct ………... % Above / Below Premium Rs………………….
iii | Cost of Non Schedule Items / Offer Rates |  |  | Rs. | ……………….
C | External Development
i | Cost of Composite Schedule Items |  |  | Rs. | 11947116
ii | Add: / Deduct ………... % Above / Below Premium Rs………………….
iii | Cost of Non Schedule Items / Offer Rates |  |  | Rs. | ……………….
|  |  | Total Bid Amount | Rs. | ……………….
| Signature of Bidder |  |  | Project Director
Police & Prison Works
Hyderabad

## Measurement (hidden)
Construction of Women Police Hostels 3 Nos. in Sindh @ Sukkur, Hyderabad & Karachi.
Measurement Sheet.
S. No:- | Description of Items. | No. |  |  |  | Length. |  |  | Width. |  | Depth / Height. |  | Quantity.
Main Building (Ground Floor).
Marble Flooring.
| Room. |  |  | 12 | x | 14 | x | 16 |  |  |  | = | 2688 | Sft.
| Office, Staircase, Hall. |  |  | 2 | x | 18 | x | 16 |  |  |  | = | 576 | Sft.
| Plate From. |  |  | 1 | x | 32 | x | 12 |  |  |  | = | 384 | Sft.
| Entrance Lobby. |  |  | 1 | x | 36 | x | 32 |  |  |  | = | 1152 | Sft.
| Dining. |  |  | 1 | x | 30 | x | 28 |  |  |  | = | 840 | Sft.
| Wash up Room. |  |  | 2 | x | 12 | x | 14 |  |  |  | = | 336 | Sft.
| Corridor. |  |  | 2 | x | 56 | x | 8 |  |  |  | = | 896 | Sft.
[11 empty] | Total:- | = | 6872 | Sft.
Marble Dado.
| Room. | 12 | x | 2 | x ( | 14 | + | 16 | ) x | 1 |  | = | 720 | Sft.
| Office, Staircase. | 2 | x | 2 | x ( | 18 | + | 16 | ) x | 1 |  | = | 136 | Sft.
| Entrance Lobby. | 1 | x | 2 | x ( | 36 | + | 32 | ) x | 1 |  | = | 136 | Sft.
| Dining. | 1 | x | 2 | x ( | 30 | + | 28.75 | ) x | 1 |  | = | 117.5 | Sft.
| Corridor. | 2 | x | 2 | x ( | 56 | + | 8 | ) x | 1 |  | = | 256 | Sft.
[11 empty] | Total:- | = | 1365.5 | Sft.
Deduction.
| D-. | 30 | x | 1 | x | 3 | x | 1 |  |  |  | = | 90 | Sft.
| D-1. |  |  | 12 | x | 2.5 | x | 1 |  |  |  | = | 30 | Sft.
[11 empty] | Total:- | = | 120 | Sft.
| Net Quantity (1366 - 120):- |  |  |  |  | 1366 | - | 120 |  |  | G. Total | = | 1245.5 | Sft.
Tiles Flooring.
| Bath. |  |  | 12 | x | 6 | x | 8 |  |  |  | = | 576 | Sft.
| Kitchen. |  |  | 1 | x | 20 | x | 14 |  |  |  | = | 280 | Sft.
| Wash up Room. |  |  | 1 | x | 12 | x | 14 |  |  |  | = | 168 | Sft.
[11 empty] | Total:- | = | 1024 | Sft.
Marble Dado.
| Bath. | 12 | x | 2 | x ( | 6 | + | 8 | ) x | 5 |  | = | 1680 | Sft.
| Kitchen. | 1 | x | 2 | x ( | 20 | + | 14 | ) x | 5 |  | = | 340 | Sft.
| Wash up Room. | 1 | x | 2 | x ( | 12 | + | 14 | ) x | 5 |  | = | 260 | Sft.
[11 empty] | Total:- | = | 2280 | Sft.
Deduction.
|  | 16 | x | 1 | x | 2.5 | x | 5 |  |  |  | = | 200 | Sft.
[11 empty] | Total:- | = | 200 | Sft.
| Net Quantity (2280 - 200):- |  |  |  |  | 2280 | - | 200 |  |  | G. Total | = | 2080 | Sft.
Main Building (First Floor).
Marble Flooring.
| Room. |  |  | 12 | x | 14 | x | 16 |  |  |  | = | 2688 | Sft.
| Room. |  |  | 1 | x | 12 | x | 16 |  |  |  | = | 192 | Sft.
| Entrance Lobby. |  |  | 1 | x | 36 | x | 32 |  |  |  | = | 1152 | Sft.
| Lounge. |  |  | 1 | x | 30 | x | 20 |  |  |  | = | 600 | Sft.
| Corridor. |  |  | 2 | x | 56 | x | 8 |  |  |  | = | 896 | Sft.
[11 empty] | Total:- | = | 5528 | Sft.
Marble Dado.
| Room. | 12 | x | 2 | x ( | 14 | + | 16 | ) x | 1 |  | = | 720 | Sft.
| Room. | 1 | x | 2 | x ( | 12 | + | 16 | ) x | 1 |  | = | 56 | Sft.
| Entrance Lobby. | 1 | x | 2 | x ( | 36 | + | 32 | ) x | 1 |  | = | 136 | Sft.
| Lounge. | 1 | x | 2 | x ( | 30 | + | 20 | ) x | 1 |  | = | 100 | Sft.
| Corridor. | 2 | x | 2 | x ( | 56 | + | 8 | ) x | 1 |  | = | 256 | Sft.
[11 empty] | Total:- | = | 1268 | Sft.
Deduction.
| D-. | 30 | x | 1 | x | 3 | x | 1 |  |  |  | = | 90 | Sft.
| D-1. | 14 | x | 1 | x | 2.5 | x | 1 |  |  |  | = | 35 | Sft.
[11 empty] | Total:- | = | 125 | Sft.
| Net Quantity (1268 - 125):- |  |  |  |  | 1268 | - | 125 |  |  | G. Total | = | 1143 | Sft.
Tiles Flooring.
| Bath. |  |  | 14 | x | 6 | x | 8 |  |  |  | = | 672 | Sft.
[11 empty] | Total:- | = | 672 | Sft.
Tiles Dado.
| Bath. | 14 | x | 2 | x ( | 6 | + | 8 | ) x | 5 |  | = | 1960 | Sft.
[11 empty] | Total:- | = | 1960 | Sft.
Deduction.
|  | 14 | x | 1 | x | 2.5 | x | 5 |  |  |  | = | 175 | Sft.
[11 empty] | Total:- | = | 175 | Sft.
| Net Quantity (1960 - 175):- |  |  |  |  | 1960 | - | 175 |  |  | G. Total | = | 1785 | Sft.
(Aftab Ahmed Soomro)
Project Director
Police & Prison Works Sindh
Hyderabad.
D/Escalation for Women Police Hostels/Measurement.

## Sheet2 (hidden)
S. No:- | Item of Work. | Quantity. |  | Rate. |  | Unit. | Amount.
7 | Painting Old Surfaces (d) Painting Guard Bars Gates Iron Bars Gratings, Railing including Standard Braces etc & Similar Open Work Any Type 02 Coats (S.I. No:- 4 (d) / P-69). | 408 | Sft. | Rs. | 1269.83 | % Sft. | Rs. | 5180.9064
|  | Total:- |  |  |  |  | Rs. | 612909
|  | Add 20% Below Except Item Nos:- 3 & 4. |  |  |  |  | Rs. | 78210
|  | Total:- |  |  |  |  | Rs. | 534699
|  | Add 5% Above Item No:- |  |  |  |  | Rs. | 2398
|  | Add:- |  |  |  |  | Rs. | 36543
|  | Grand Total:- |  |  |  |  | Rs. | 573640
| Rate for 01- Rft:- | Rs. | 573640 |  |  | 2 | Rs. | 286820

## Sheet3 (hidden)
CENTRAL PRISON HYDERABAD.
G E N E R A L A B S T R A C T.
Type-A Flats (G + 3).
For Grade (15 to 17).
One Block of 6 Flats.
Two Flats on Each Block.
| Total Nos. of Flats (6 x 2). |  |  | 12 | Flats.
Type-B Flats (G + 3).
For Grade (11 to 14).
i) | One Block of 6 Flats.
Two Flats on Each Block.
| Total Nos. of Flats (6 x 1). |  |  | 6 | Flats.
For Grade (11 to 14).
ii) | One Block of 4 Flats.
Two Flats on Each Block.
| Total Nos. of Flats (4 x 1). |  |  | 4 | Flats.
Type-C Flats (G + 3).
For Grade (1 to 10).
One Block of 6 Flats.
Two Flats on Each Block.
| Total Nos. of Flats (13 x 6). |  |  | 78 | Flats.
|  | Total:- |  | 100 | Flats.
| Assistant Engineer |  | Executive Engineer
| Police & Prison Works Sub-Divison |  | Police & Prison Works Divison
| Hyderabad. |  | Hyderabad.
Project Director
Police & Prison Works Sindh
Hyderabad.