## Culv
S.No | 11 |  | SCHEDULE "B"
PART "B"
PACKAGE-11 Construction of Open Drain Various street of Mirpurkhas City Length 2000 Rft
MEASUREMENT CUM ABSTRACT SHEET
S.NO |  | I T E M O F W O R K S | [15 empty] | RATE |  | UNIT |  |  | AMOUNT
1 | EXCAVATION
Excavation in foundation of Building, Bridges and other structures including dagbelling dressing, refilling around structure with excavated earth, watering and ramming.lead upto 5.00 ft. (In Ordinary soil)
| Qty. |  | 500 |  |  |  |  | Cft. | @ Rs |  |  | 3176.25 |  |  |  | Per %0 Cft. | [5 empty] | Rs. | 1588 | /=
2 | CEMENT CONCRETE RATIO 1:4:8
Cement Concrete brick or stone ballast 1 1/2" to 2" gauge. Ratio 1:4:8
| Qty. |  | 250 |  |  |  |  | Cft. | @ Rs |  |  | 9416.28 |  |  |  | Per % Cft. | [5 empty] | Rs. | 23541 | /=
3 | PUCCA BRICK WORK RATIO 1:4
Pucca brick work in foundation and plinth in cement sand mortar Ratio 1:4
| Qty. |  | 375 |  |  |  |  | Cft. | @ Rs |  |  | 12501.41 |  |  |  | Per % Cft. | [5 empty] | Rs. | 46880 | /=
4 | CANUTE BLOCK
Construction of Standard open surface drain canute block 1:2:4 etc completed
| Qty. |  | 100 |  |  |  |  | Rft | @ Rs |  |  | 72.2 |  |  |  | Per Rft | [5 empty] | Rs. | 7220 | /=
5 | BRICK ON EDGE FLOORING
Brick on edge flooring laid in 1:6 cement mortar over a bed, 3/4" thick cement mortar Ratio 1:6
| Qty. |  | 200 |  |  |  | Sft. |  | @ Rs |  |  | 5256.63 |  |  |  | Per % Sft. | [5 empty] | Rs. | 10513 | /=
6 | CEMENT PLASTER RATIO 1:3
Cement Plaster 1:3 upto 20.0' height. 1/2" thick.
| Qty. |  | 1350 |  |  |  | Sft. |  | @ Rs |  |  | 2344.59 |  |  |  | Per % Sft. | [5 empty] | Rs. | 31652 | /=
[15 empty] | Total 100 Rft | [6 empty] | Rs. | 121394 | /=
[5 empty] | 121394 |  |  |  | / | 100 |  |  | + | 1213.94 |  |  | Rate for 1 Rft
|  | 1960 |  |  | Rft |  | X | 1213.94 | [13 empty] | Rs. | 2379322.4 | /=
5 | Supplying and Fixing Inuaguration
Supplying and fixing inauguration Stone at Site of work including Masonry work cartage of material etc complete.
|  | Say Qty. |  |  |  | 2 |  |  | Job |  | @ | Rs. |  | 5000 |  |  | Each |  |  |  |  | Rs. | 10000 |  | / =
[21 empty] | G-Total:- | Rs. | 2389322.4 |  | /=
NOTE:- |  |  | 1 | Difference in cost of construction material is to be allowed as per notificaiton / circulars issued by standing Rates committee (S.R.C) from time to time.
|  |  | 2 | No Cartage of material what-ever so is will be paid to contractor separately.
CONTRACTOR | [18 empty] | EXECUTIVE ENGINEER
HIGHWAYS DIVISION
MIRPURKHAS