## Sch-B
S.# 67
BILL OF QUANTITY
NIT No. MC/736, DATED: 18.05.2015
NAME OF WORK;-
CONSTRUCTION OF SURFACE DRAINS IN DHORONARO TOWN
NAME OF AGENCY: -
S.# | Item of work. | [5 empty] | Quantity |  |  | Rate |  | Unit. |  | Amount.
1 | Excavation in foundation of building bridges and other structures i/c dag belling dressing refilling earth around structure with excavated earth watering and ramming lead upto 5’ ft ( in ordinary soil) (G.S.I No. 18 P-4)
| Say |  | 5319.16 | Sft. | @ | Rs. | 3176.25 |  | Per %0Cft. |  | Rs. |  | 16895 |  | / =
2 | Cement concrete plain i/c placing compacting, finishing and curing complete i/c screening & washing of stone aggregate, without shuttering Ratio (1:4:8) (GSI No. 5/i P-16)
| Say | 1329.79 |  | Cft. | @ | Rs. | 11288.75 |  | Per % Cft. |  | Rs. |  | 150117 |  | / =
3 | Pacca brick work in foundation and plinth in cement sand mortar Ratio (1:6) (C S I No. 4/e P-20).
| Say | 3297 |  | Cft. | @ | Rs. | 11948.36 |  | Per % Cft. |  | Rs. |  | 393937 |  | / =
4 | Construction of standard open drains cunette block of cement concrete (1:2:4) in situ to the design profile i/c cost of mould as per drawing i/c applying floating coat of cement 1/32” to the exposed face finished smooth curing etc complete as per det ailed drawing (PHSI NO;D PAGE-58)
TYPE A
| Say | 2198 |  | Rft. | @ | Rs. | 94 |  | Per Rft. |  | Rs. |  | 206612 |  | / =
5 | Cement Plaster (1:4) up top 12’ ft height ½ thick (GSI No. 11/B P-16).
| Say | 6594 |  | Sft. | @ | Rs. | 2283.93 |  | Per%Sft. |  | Rs. |  | 150602 |  | / =
6 | R.CC work i/c all labour and material except the cost of steel reinforcement and its labour for bending & binding which will be paid separately. This rate also includes all kind of forms moulds: lifting shuttering curing rendering and finishing the exposed surface (including screening and washing of single. (a) R.C work in roof slab, beams columns raft. Lintels and other structural members laid in situ or precast laid in position compete in all respect. ( GSI No.6 P-16)
| Say | 453.75 |  | Cft. | @ | Rs. | 337 |  | Per Cft. |  | Rs. |  | 152914 |  | / =
7 | Fabrication of Mild Steel reinforcement for cement concrete i/c cutting bending laying in position making joints and fastening i/c cost of binding wire also i/c removal of rust from bars (GSI No.8(a) P-17).
| Say | 18.23 |  | Cwt | @ | Rs. | 5001.7 |  | Per Cft. |  | Rs. |  | 91186 |  | / =
[11 empty] | Total Rs. | 1162263 |  |  | / =
Note: |  | Item/Quantities/Rates and amount are estimated provisional and will be corrected to the Detail Working Estimate sanctioned by competent authority.
ENGINEER MUNICIPAL COMMITTEE UMERKOT DISTRICT UMERKOT
I am agree for execution of above said work/job at the ______________ %
| CONTRACTOR | [6 empty] | ENGINEER MUNICIPAL COMMITTEE UMERKOT DISTRICT UMERKOT