## Sheet1
Guidelines. Regulations For Procurement of Works | [10 empty] | (Annesure A-I)
(Annesure A-I)
PROCUREMENT PLAN (Development / Capital)
Serial No. | ADP No* | Name of Scheme & Estimated Cost | Allocated Funds | Cost of ongoing works (Expenditure already incurred) | Funds earmarked for ongoing works | Cost of New Works (components) | Funds for Works (c-e) | Nature of Procurement | Mothod of Procurement | Anticipated/Actual Date of Advertisement | Anticipated/Actual Date of Start | Anticipated/Actual Date of Completion.
| a | b | c | d | e | f | g | h | i | j | k | l
01 | 752 | Constructing Relief Escape for Nasrat Branch at RD-207 N.I.P. side | 12.00 million | -NIL- | -NIL- | 39458869 | 12.00 million | National competitive bidding procedure | Single stage one onvelope procedure | 21/10/2015 | 21/11/2015 | 30/06/2016
SINDH PUBLIC PROCUREMENT REGULATORY AUTHORITY
Guidelines. Regulations For Procurement of Works | k: (Annesure A-I)
Guidelines. Regulations For Procurement of Works | k: (Annesure A-I)
(Annesure A-I)
PROCUREMENT PLAN (Development / Capital)
Serial No. | ADP No* | Name of Scheme & Estimated Cost | Allocated Funds | Cost of ongoing works (Expenditure already incurred) | Funds earmarked for ongoing works | Cost of New Works (components) | Funds for Works (c-e) | Nature of Procurement | Mothod of Procurement | Anticipated/Actual Date of Advertisement | Anticipated/Actual Date of Start | Anticipated/Actual Date of Completion.
| a | b | c | d | e | f | g | h | i | j | k | l
01 | 752 | Constructing Relief Escape for Gajrah Branch at RD-43+800 N.I.P. side | 12.00 million | -NIL- | -NIL- | 11806048 | 12.00 million | National competitive bidding procedure | Single stage one onvelope procedure | 21/10/2015 | 21/11/2015 | 30/06/2016
SINDH PUBLIC PROCUREMENT REGULATORY AUTHORITY
Guidelines. Regulations For Procurement of Works | k: (Annesure A-I)
Guidelines. Regulations For Procurement of Works | k: (Annesure A-I)
(Annesure A-I)
PROCUREMENT PLAN (Development / Capital)
Serial No. | ADP No* | Name of Scheme & Estimated Cost | Allocated Funds | Cost of ongoing works (Expenditure already incurred) | Funds earmarked for ongoing works | Cost of New Works (components) | Funds for Works (c-e) | Nature of Procurement | Mothod of Procurement | Anticipated/Actual Date of Advertisement | Anticipated/Actual Date of Start | Anticipated/Actual Date of Completion.
| a | b | c | d | e | f | g | h | i | j | k | l
01 | 752 | Constructing Relief Escape for tail of Nasrat Branch system along Chan Bandhni Distry at RD-22 I.P. side | 12.00 million | -NIL- | -NIL- | 13073817 | 12.00 million | National competitive bidding procedure | Single stage one onvelope procedure | 21/10/2015 | 21/11/2015 | 30/06/2016
SINDH PUBLIC PROCUREMENT REGULATORY AUTHORITY
Guidelines. Regulations For Procurement of Works | k: (Annesure A-I)