## 02 Comparative
COMPARATIVE STATEMENT
6
NAME OF WORK:- |  |  | PACKAGE NO. 06
M&R road to Village Nizamuddin Malik Mile;- 0/0-0/5 (in portion) M&R road to Village Badal Shah Mile 0/0-1/2 (in Portion) Taluka Shujabad
# | Item of Work |  | Rate quoted by |  |  |  |  | Rate quoted by |  |  |  |  | Rate quoted by
|  |  | M/s M.S & Co: |  |  |  |  | M/s Bilal & Co: |  |  |  |  | M/s Civil Link Associates
1 | Part "A" |  | Schedule "B" |  | Rs= | 3664002 | /= | Schedule "B" |  | Rs= | 3664002 | /= | Schedule "B" |  | Rs= | 3664002 | /=
| Road Work |  | 5.4 | %Above | Rs= | 197856 | /= | 7.8 | %Above | Rs= | 285792 | /= | 12 | %Above | Rs= | 439680 | /=
|  | (-) | Diff cost of Bitumen |  | Rs= | 384720.96 | /= | Diff cost of Bitumen |  | Rs= | 384720.96 | /= | Diff cost of Bitumen |  | Rs= | 384720.96 | /=
|  |  |  | Total | Rs= | 3477137.04 | /= |  | Total | Rs= | 3565073.04 | /= |  | Total | Rs= | 3718961.04 | /=
2 | Part "B" |  | Schedule "B" |  | Rs= | 2275036 | /= | Schedule "B" |  | Rs= | 2275036 | /= | Schedule "B" |  | Rs= | 2275036 | /=
| Road Work |  | 5.8 | %Above | Rs= | 131952 | /= | 9 | %Above | Rs= | 204753 | /= | 16 | %Above | Rs= | 364006 | /=
|  | (-) | Diff cost of Bitumen |  | Rs= | 231606.44 | /= | Diff cost of Bitumen |  | Rs= | 231606.44 | /= | Diff cost of Bitumen |  | Rs= | 231606.44 | /=
|  |  |  | Total | Rs= | 2175381.56 | /= |  | Total | Rs= | 2248182.56 | /= |  | Total | Rs= | 2407435.56 | /=
|  |  | Grand Total |  | Rs= | 5652518.6 | /= | Grand Total |  | Rs= | 5813255.6 | /= | Grand Total |  | Rs= | 6126396.6 | /=
5679052.88
|  | MUHAMMAD YOUNUS PANHWAR |  |  |  |  | INAYATULLAH MEMON | [6 empty] | AMIR AZAM WASSAN
|  | ASSISTANT ENGINEER |  |  |  |  | ASSISTANT ENGINEER | [6 empty] | EXECUTIVE ENGINEER
|  | HIGHWAY SUB DIVISION |  |  |  |  | PUBLIC HEALTH ENGINEERING | [6 empty] | HIGHWAYS DIVISION
|  | KOT GHULAM MUHAMMAD |  |  |  |  | SUB DIVISION MIRPURKHAS | [6 empty] | MIRPURKHAS

## 02 Financial Rew
FINANCIAL REVIEW
NAME OF WORK:- |  |  |  | PACKAGE NO. 06
M&R road to Village Nizamuddin Malik Mile;- 0/0-0/5 (in portion) M&R road to Village Badal Shah Mile 0/0-1/2 (in Portion) Taluka Shujabad
PART "A" ( Road Work)
(A) | AS PER ESTIMATES
| 1 | Amount of Schedule "B" | [9 empty] | Rs= | 3664002 | /=
| 2 | 6 |  | %above Fixed by the CH: Engineer | [5 empty] | Rs= (+) | 219840.12
[11 empty] | 219840.12 | Rs (+) | 219840.12 | /=
219840.12 |  | (-) |  | = | 219840.12 | x | 100 | = | 6 | %Above
3664002
| 3 | Add: Diff: Cost of Bricks |  |  | 0 | Nos @ Rs: |  |  | 3800 | P.%0 | 0 | Rs= | 0 | /=
| 3 | Deduct Diffence Cost of (-) |  |  | 13.92 | Ton Bitumen @ Rs. |  |  |  | 27638 |  | Rs= | 384720.96 | /=
|  | Total | [9 empty] | Rs= | 3499121.16 | /=
(B) | AS PER RATE QOUTED BY THE CONTRACTOR
| 1 | Amount of Schedule "B" | [9 empty] | Rs= | 3664002 | /=
| 3 | Add: Diff: Cost of Bricks |  |  | 0 | Nos @ Rs: |  |  | 3800 | P.%0 |  | Rs= | 0 | /=
| 2 | Add: | 5.4 | %Above Rate qouted by the Contractor | [7 empty] | Rs= | 197856 | /=
| 3 | Deduct Diffence Cost of (-) |  |  | 13.92 | Ton Bitumen @ Rs. |  |  |  | 27638 |  | Rs= | 384720.96 | /=
|  | Total | [9 empty] | Rs= | 3477137.04 | /=
| DIFFERENCE (A-B) | [10 empty] | Rs= | 21984.12 | /Saving
PART "B" ( Road Work)
(A) | AS PER ESTIMATES
| 1 | Amount of Schedule "B" | [9 empty] | Rs= | 2275036 | /=
| 2 | 6 |  | %above Fixed by the CH: Engineer | [5 empty] | Rs= (+) | 136502.16
[11 empty] | 136502.16 | Rs (+) | 136502.16 | /=
136502.16 |  | (-) |  | = | 136502.16 | x | 100 | = | 6 | %Above
2275036
| 3 | Add: Diff: Cost of Bricks |  |  | 0 | Nos @ Rs: |  |  | 3800 | P.%0 | 0 | Rs= | 0 | /=
| 3 | Deduct Diffence Cost of (-) |  |  | 8.38 | Ton Bitumen @ Rs. |  |  |  | 27638 |  | Rs= | 231606.44 | /=
|  | Total | [9 empty] | Rs= | 2179931.72 | /=
(B) | AS PER RATE QOUTED BY THE CONTRACTOR
| 1 | Amount of Schedule "B" | [9 empty] | Rs= | 2275036 | /=
| 3 | Add: Diff: Cost of Bricks |  |  | 0 | Nos @ Rs: |  |  | 3800 | P.%0 |  | Rs= | 0 | /=
| 2 | Add: | 5.8 | %Above Rate qouted by the Contractor | [7 empty] | Rs= | 131952 | /=
| 3 | Deduct Diffence Cost of (-) |  |  | 8.38 | Ton Bitumen @ Rs. |  |  |  | 27638 |  | Rs= | 231606.44 | /=
|  | Total | [9 empty] | Rs= | 2175381.56 | /=
| DIFFERENCE (A-B) | [10 empty] | Rs= | 4550.16 | /Saving
PART "B" (15.0 rft Slab Bridge)
(B) | AS PER ESTIMATES |  |  | FOR MASONRY WORK
| 1 | Amount of Schedule "B" | [9 empty] | Rs= | 1386814 | /=
| 2 | Add Cartage of Material | [5 empty] | Rs= | 204271
[8 empty] | Rs= | 204271 |  | (+) | Rs= | 204271
| 4 | Amount of Sch: "B" |  |  | Rs: | 1386814 |  |  | /=
|  | + | 0 | 204271 | x100 | 14.7295 |  | %Above
1386814
|  | Total | [9 empty] | Rs= | 1591085 | /=
[10 empty] | 1 | Bridge | Rs= | 1591085 |  | /=
(B) | AS PER RATE QOUTED BY THE CONTRACTOR
| 1 | Amount of Schedule "B" | [9 empty] | Rs= | 1386814 | /=
| 2 | Add | 13.9 | %Above rate qouted by the contractor | [7 empty] | Rs= | 192767.146 | /=
| 3 | Amount of Sch: "B" |  |  | Rs: | 1386814 |  |  | /=
|  | Total | [9 empty] | Rs= | 1579581.146 | /=
[10 empty] | 1 | Bridge | Rs= | 1579581.146
| DIFFERENCE (A-B) | [10 empty] | Rs= | 11503.854 | /=Saving
1591085 |  | (-) | 1579581.146 | = | 11503.854 |  | x 100 |  |  |  |  | 0.72302 | % Saving
PART "C" (3.00 ft Span Culverts)
(B) | AS PER ESTIMATES |  |  | FOR MASONRY WORK
| 1 | Amount of Schedule "B" | [9 empty] | Rs= | 157377 | /=
| 2 | Add Cartage of Material | [5 empty] | Rs= | 25739 | [5 empty] | #VALUE!
[8 empty] | Rs= | 25739 |  | (+) | Rs= | 25739
| 4 | Amount of Sch: "B" |  |  | Rs: | 157377 |  |  | /=
|  | + | 0 | 25739 | x100 | 16.355 |  | %Above
157377
|  | Total | [9 empty] | Rs= | 183116 | /=
[10 empty] | 5 | Culverts | Rs= | 915580 |  | /=
(B) | AS PER RATE QOUTED BY THE CONTRACTOR
| 1 | Amount of Schedule "B" | [9 empty] | Rs= | 157377 | /=
| 2 | Add | 14 | %Above rate qouted by the contractor | [7 empty] | Rs= | 22032.78 | /=
| 3 | Amount of Sch: "B" |  |  | Rs: | 157377 |  |  | /=
|  | Total | [9 empty] | Rs= | 179409.78 | /=
[10 empty] | 5 | Culverts | Rs= | 897048.9
| DIFFERENCE (A-B) | [10 empty] | Rs= | 18531.1 | /=Saving
915580 |  | (-) | 897048.9 | = | 18531.1 |  | x 100 |  |  |  |  | 2.024 | % Saving
EXECUTIVE ENGINEER
HIGHWAYS DIVISION
MIPRUKHAS