## NIT
LIST OF WORK.
Sr. No. | Name of Works. | Estimate Cost. |  | Bid Security. |  | Tenders Fee. |  | Completion Period.
1 | 2 | 3 |  | 4 |  | 5 |  | 6
1 | Construction of Office Complex at Taluka Shujabad District Mirpurkhas.
i. | Construction of Main Building / Porch. | 46 | (M) | 0.92 | (M) | 3000 | /- | 36-Months.
ii. | Construction of Mosque. | 2.4 | (M) | 0.048 | (M) | 3000 | /- | 36-Months.
iii | Construction of 6 Nos: Garrage and All-round Compound Wall i/c Steel Gate. | 6 | (M) | 0.12 | (M) | 3000 | /- | 36-Months.
iv. | Providing E.I. Work of Main Building. | 3.1 | (M) | 0.062 | (M) | 3000 | /- | 36-Months.
v. | Providing E.I. Work of Mosque. | 0.14 | (M) | 0.0028 | (M) | 750 | /- | 36-Months.
vi. | Providing E.I. Work of Garrage. (06-Nos:) | 0.25 | (M) | 0.005 | (M) | 1000 | /- | 36-Months.
2 | Up-Gradation R.H.C. to the level of T.H.Q. Hospital Mirwah District Mirpurkhas.
i. | Providing E.I. Work of Main Building. | 2.4 | (M) | 0.048 | (M) | 3000 | /- | 36-Months.
EXECUTIVE ENGINEER BUILDINGS DIVISION MIRPURKHAS

## 1-i
Name of Work :- |  |  |  |  | 1 | Construction of Office Complex at Taluka Shujabad District Mirpurkhas.
[5 empty] | i. | Construction of Main Building / Porch.
Issued to Mr. / M/s.
DR. No. | [7 empty] | Dated:
Tender Fee Amount. | [6 empty] | Rs.
INVITATION FOR BIDS
[9 empty] | Date : |  | 21-01-2016
[9 empty] | Bid Referrence No: | 65
1. | The Procuring Agency, Executrive Engineer, Buildings Division Mirpurkhas, invites sealed bids from interested firms or persons licensed by the Pakistan Engineering Council in the appropriate category (not required for works costing Rs 2.5 million or less) and / or duly pre-qualified (if pre-qualification is done for specific scheme / project) with the Procuring Agency for the Works, "Construction of Office Complex at Taluka Shujabad District Mirpurkhas (i) Construction of Main Building / Porch", which will be completed in 36-months.
2. | A complete set of Bidding Documents may be purchased by an interested eligible bidder on submission of a written application to the office given below and upon payment of a non-refundable fee of Rupees 3000/- (Three Thousand). Bidders may acquire the Bidding Documents from the Office of the Procuring Agency, at 22-02-2016, @ Near APWA Girls High School M.A. Jinnah Road Mirpurkhas.
3. | All bids must be accompanied by a Bid Security in the amount of Rs.0.9200 (M) (Zero Point Nine Hundred Twenty Thousand Million) only in the form of (pay order / demand draft / bank guarantee) and must be delivered to office of Executrive Engineer, Buildings Division Mirpurkhas at or before on 22-02-2016. Bids will be opened at 01.00 pm on the 22-02-2016 day in the presence of bidders‘ representatives who choose to attend, at the same address [indicate the address if it differs].
Note: | 1. | Procuring Agency to enter the requisite information in blank spaces.
| 2. | The bid shall be opened within one hour after the deadline for submission of bids.]
Sindh Public Procurement Regulatory Authority l www.spprasindh.gov.pk | [10 empty] | 3
Tell # 0233-9290047 Sr. No.01 (i) | [10 empty] | NIT No.TC/G-55/ 65
BIDDING DATA.
(This section should be filled in by the Engineer / Procuring Agency before issuance of the Bidding Documents. The following specific data for the works to be tendered shall complement, amend, or supplement the provisions in the Instructions to Bidders. Wherever there is a conflict, the provisions herein shall prevail over those in the Instructions to Bidders.)
Instructions to Bidders Clause Reference
1.1 | Name of Procuring Agency :-
Executive Engineer, Buildings Division Mirpurkhas.
(Insert name of the Procuring Agency)
Brief Description of Works :-
1 | Construction of Office Complex at Taluka Shujabad District Mirpurkhas.
i. | Construction of Main Building / Porch.
5.1 | (a) |  | Procuring Agency’s Address :-
Near APWA Girls High School M.A. Jinnah Road Mirpurkhas.
(Insert address of the Procuring Agency with Telex / Fax)
| (b) |  | Engineer's Address :-
Same as 5.1 (a)
(Insert name and address of the Engineer, if any, with Telex / Fax)
10.3 | Bid shall be qouted entirely in Pak: Rupees. The payment shall be made in Pak: Rupees.
11.2 | The Bidder has the financial, technical and constructional capability necessary to perform the Contract as follows. (Insert required capabilities and documents)
| i. |  | Financial Capacity :-
| ii. |  | Technical Capacity :- (mention the appropriate category of registration with PEC and qualification and experience of the staff)
| iii. |  | Construction Capacity :- (mention the names and number of equipments required for the work)
Sindh Public Procurement Regulatory Authority l www.spprasindh.gov.pk | [10 empty] | 17
12.1 | (a) |  | A detailed description of the Works, essential technical and performance characteristics.
| (b) |  | Complete set of technical information, description data, literature and drawings as required in accordance with Schedule "B" to Bid, Specitic Works Data. This will include but not be limited to a sufficient number of drawings, photographs, catalogues, illstrations and such other information as is necessary to illustrate clearly the significant characteristics such as general construction dimensions and other relevant information about the works to be performed.
13.1 | Amount of Bid Security :-
| Rs. |  | 0.92 |  | (M) | (Zero Point Nine Hundred Twenty Thousand Million) only.
(Fill in lump sum amount or in %age of Bid Amount / Estimated Cost, but not below 1% and not exceeding 5%)
14.1 | Period of Bid Validity.
60-Days.
(Fill in "number of days" not exceeding 90)
14.4 | Number of Copies of the Bid to be submitted :-
One original copy.
14.6 | (a) |  | Procuring Agency's Address for the Purpose of Bid submission.
Near APWA Girls High School M.A. Jinnah Road Mirpurkhas.
(insert postal address or location of Bid box for delivery by hand)
15.1 | Deadline for Submission of Bids :-
| Time : |  | 01:00 P.M. on 22-02-2016
16.1 | Venue, Time and Date of Bid Opening :-
| Venue: |  | Office of the |  |  | Executive Engineer, Buildings Division Mirpurkhas.
| Time : |  | 02:00 P.M. on 22-02-2016
16.4 | Responsiveness of Bids.
| (i) |  | Bid is valid till required period, |  |  |  |  | 60-Days.
Sindh Public Procurement Regulatory Authority l www.spprasindh.gov.pk | [10 empty] | 18
| (ii) |  | Bid prices are firm during currency of contract / Price adjustment.
| (iii) |  | Completion period offered is within specifed limits.
| (iv) |  | Bidder is eligible to Bid and possesses the requisite experience, capability and qualification.
| (v) |  | Bid does not deviate from basic technical requirements and
| (vi) |  | Bid are generally in order, etc.
Procuring agency can adopt either of two options. (Select either of them)
| (a) |  | Fixed Price Contract :-
In these contracts no escalation will be provided during currency of the contract and normally period of completion of these works is upto 36 months.
| (b) |  | Price Adjustment Contract :-
In these contracts escalation will be paid only on those items and in the manner as notified by Finance Department, Government of Sindh, after bid opening during currency of the contract.
Sindh Public Procurement Regulatory Authority l www.spprasindh.gov.pk | [10 empty] | 19
FORM OF BID
(LETTER OF OFFER)
Bid Reference No. |  |  |  | 65
Date | 21-01-2016
1 | Construction of Office Complex at Taluka Shujabad District Mirpurkhas.
i. | Construction of Main Building / Porch.
(Name of Works)
To:
_______________________________
_______________________________
_______________________________
Gentlemen,
|  | 1. |  | Having examined the Bidding Documents including Instructions to Bidders, Bidding Data, Conditions of Contract, Contract Data, Specifications, Drawings, if any, Schedule of Prices and Addenda Nos. _________________________ for the execution of the above-named works, we, the undersigned, being a company doing business under the name of and address ______________________________________________________________________________________________ and being duly incorporated under the laws of Pakistan hereby offer to execute and complete such works and remedy any defects therein in conformity with the said Documents including Addenda thereto for the Total Bid Price of Rs______________________ (Rupees______________________________________________________) or such other sum as may be ascertained in accordance with the said Documents.
|  | 2. |  | We understand that all the Schedules attached hereto form part of this Bid.
|  | 3. |  | As security for due performance of the undertakings and obligations of this Bid, we submit herewith a Bid Security in the amount of Rs.0.9200 (M) (Zero Point Nine Hundred Twenty Thousand Million) drawn in your favour or made payable to you and valid for a period of twenty eight (28) days beyond the period of validity of Bid.
|  | 4. |  | We undertake, if our Bid is accepted, to commence the Works and to deliver and complete the Works comprised in the Contract within the time(s) stated in Contract Data.
|  | 5. |  | We agree to abide by this Bid for the period of ______ days from the date fixed for receiving the same and it shall remain binding upon us and may be accepted at any time before the expiration of that period.
|  | 6. |  | Unless and until a formal Agreement is prepared and executed, this Bid, together with your written acceptance thereof, shall constitute a binding contract between us.
|  | 7. |  | We undertake, if our Bid is accepted, to execute the Performance Security
Sindh Public Procurement Regulatory Authority l www.spprasindh.gov.pk | [10 empty] | 20
CONTRACT DATA
(Note: Except where otherwise indicated, all Contract Data should be filled in by the Procuring Agency prior to issuance of the Bidding Documents.)
Sub-Clauses of
Conditions of Contract
1.1.3 |  | Procuring Agency‘s Drawings, if any
(To be listed by the Procuring Agency)
1.1.4 |  | The Procuring Agency means
Executive Engineer, Buildings Division Mirpurkhas.
__________________________________________
1.1.5 |  | The Contractor means
______________________________
______________________________
1.1.7 |  | Commencement Date means the date of issue of Engineer‘s Notice to Commence which shall be issued within fourteen (14) days of the signing of the Contract Agreement.
1.1.9 |  | Time for Completion |  |  |  | 36-Months.
(The time for completion of the whole of the Works should be assessed by the Procuring Agency)
1.1.20 |  | Engineer (mention the name along with the designation including whether he belongs to department or consultant) and other details.
______________________________
______________________________
1.3 |  | Documents forming the Contract listed in the order of priority:
(a) |  | The Contract Agreement
(b) |  | Letter of Acceptance
(c) |  | The completed Form of Bid
(d) |  | Contract Data
(e) |  | Conditions of Contract
(f) |  | The completed Schedules to Bid including Schedule of Prices
(g) |  | The Drawings, if any
(h) |  | The Specifications
(i) |  | ___________________
(j) |  | ___________________
(The Procuring Agency may add, in order of priority, such other documents as form part of the Contract. Delete the document, if not applicable)
Sindh Public Procurement Regulatory Authority l www.spprasindh.gov.pk | [10 empty] | 49
2.1 |  | Provision of Site: On the Commencement Date
3.1 |  | Authorized person: _________________
3.2 |  | Name and address of Engineer’s/Procuring Agency’s representative.
Executive Engineer, Buildings Division Mirpurkhas.
4.4 |  | Performance Security:
Amount_________________
Validity_________________
(Form: As provided under Standard Forms of these Documents)
5.1 |  | Requirements for Contractor’s design (if any):
Specification Clause No‘s__________________
7.2 |  | Programme:
Time for submission: Within fourteen (14) days* of the Commencement Date.
Form of programme: __________________ (Bar Chart/CPM/PERT or other)
7.4 |  | Amount payable due to failure to complete shall be __% per day up to a maximum of (10%) of sum stated in the Letter of Acceptance
(Usually the liquidated damages are set between 0.05 percent and 0.10 percent per day.)
7.5 |  | Early Completion
In case of earlier completion of the Work, the Contractor is entitled to be paid bonus up-to limit and at a rate equivalent to 50% of the relevant limit and rate of liquidated damages stated in the contract data.
9.1 |  | Period for remedying defects
____________________________________________
____________________________________________
10.2 | (e) |  | Variation procedures:
Day work rates______________
__________________________(details)
11.1 |  |  | Terms of Payments
| a) | Mobilization Advance
|  | (1) | Mobilization Advance up to 10 % of the Contract Price stated in the Letter of Acceptance shall be paid by the Procuring Agency to the Contractor on the works costing Rs.2.5 million or above on following conditions:
Sindh Public Procurement Regulatory Authority l www.spprasindh.gov.pk | [10 empty] | 50
(For Contracts (Small) Amounting Between Rs.4.00 Million to Rs.50.00 Million)
SPPRA BIDDING DOCUMENT
STANDARD BIDDING DOCUMENT
FOR
PROCUREMENT OF WORKS

## 1-ii
Name of Work :- |  | 1 | Construction of Office Complex at Taluka Shujabad District Mirpurkhas.
|  | ii. | Construction of Mosque.
Issued to Mr. / M/s.
DR. No. | [5 empty] | Dated:
Tender Fee Amount. |  |  |  | Rs.
Standard Bidding Document is intended as a model for admeasurements (Percentage Rate / Unit Price for unit rates in a Bill of Quantities) type of contract. The main text refers to admeasurements contract.
Tell # 0233-9290047 Sr. No.01 (ii) | [8 empty] | NIT No.TC/G-55/ 65
(This section should be filled in by the Engineer / Procuring Agency before issuance of the Bidding Documents)
(a). | Name of Procuring Agency :- |  |  |  | Executive Engineer, Buildings Division Mirpurkhas.
(b). | Brief Description of Works :- |  |  | 1 | Construction of Office Complex at Taluka Shujabad District Mirpurkhas.
|  |  |  | ii. | Construction of Mosque.
(c). | Procuring Agency’s Address :- |  |  |  | Near APWA Girls High School M.A. Jinnah Road Mirpurkhas.
(d). | Estimated Cost :- |  |  |  | Rs. | 2.4 | (M)
(e). | Amount of Bid Security :- |  |  |  | Rs. | 0.048 | (M) | (Fill in lump sum amount or in %age of Bid Amount / Estimated Cost, but not exceeding 5%)
(f). | Period of Bid Validity (Days) :- |  |  |  |  | 60-Days. |  | (Not more than sixty days).
(g). | Security Deposit :- (including Bid Security) |  |  |  | Rs. | 0.144 | (M) | (in %age of Bid Amount / Estimate Cost equal to 10%)
(h). | Percentage, if any, to be Deducted from Bills. |  |  |  |  | --
(i). | Deadline for Submission of Bids alongwith time :- |  |  |  |  | 22-02-2016 (Ist: Attempt) |  | (01:00 PM)
(j). | Venue, Time and Date of Bid Opening :- |  |  |  |  | 22-02-2016 (Ist: Attempt) |  | (02:00 PM)
(k). | Time for Completion form written order of commence :- |  |  |  |  | 36-Months.
(l). | Liquidity Damages :- |  |  |  |  | -- |  | (0.05 of Estimated Cost or Bid Cost per day of delay, but total not exceeding 10%)
(m). | Deposit Receipt No. |  |  | Date |  |  |  | Amount Rs.
(Executive Engineer / Authority issuing bidding documents).
Sindh Public Procurement Regulatory Authority l www.spprasindh.gov.pk | [8 empty] | 4
SPPRA BIDDING DOCUMENT
STANDARD BIDDING DOCUMENTS
(For Contract Costing Upto Rs.4.00 Million)
PRODUREMENT OF WORKS

## 1-iii
Name of Work :- |  |  |  |  | 1 | Construction of Office Complex at Taluka Shujabad District Mirpurkhas.
[5 empty] | iii | Construction of 6 Nos: Garrage and All-round Compound Wall i/c Steel Gate.
Issued to Mr. / M/s.
DR. No. | [7 empty] | Dated:
Tender Fee Amount. | [6 empty] | Rs.
INVITATION FOR BIDS
[9 empty] | Date : |  | 21-01-2016
[9 empty] | Bid Referrence No: | 65
1. | The Procuring Agency, Executrive Engineer, Buildings Division Mirpurkhas, invites sealed bids from interested firms or persons licensed by the Pakistan Engineering Council in the appropriate category (not required for works costing Rs 2.5 million or less) and / or duly pre-qualified (if pre-qualification is done for specific scheme / project) with the Procuring Agency for the Works, "Construction of Office Complex at Taluka Shujabad District Mirpurkhas (iii) Construction of 6 Nos: Garrage and All-round Compound Wall i/c Steel Gate", which will be completed in 36-months.
2. | A complete set of Bidding Documents may be purchased by an interested eligible bidder on submission of a written application to the office given below and upon payment of a non-refundable fee of Rupees 3000/- (Three Thousand). Bidders may acquire the Bidding Documents from the Office of the Procuring Agency, at 22-02-2016, @ Near APWA Girls High School M.A. Jinnah Road Mirpurkhas.
3. | All bids must be accompanied by a Bid Security in the amount of Rs.0.1200 (M) (Zero Point One Hundred Twenty Thousand Million) only in the form of (pay order / demand draft / bank guarantee) and must be delivered to office of Executrive Engineer, Buildings Division Mirpurkhas at or before on 22-02-2016. Bids will be opened at 01.00 pm on the 22-02-2016 day in the presence of bidders‘ representatives who choose to attend, at the same address [indicate the address if it differs].
Note: | 1. | Procuring Agency to enter the requisite information in blank spaces.
| 2. | The bid shall be opened within one hour after the deadline for submission of bids.]
Sindh Public Procurement Regulatory Authority l www.spprasindh.gov.pk | [10 empty] | 3
Tell # 0233-9290047 Sr. No.01 (iii) | [10 empty] | NIT No.TC/G-55/ 65
BIDDING DATA.
(This section should be filled in by the Engineer / Procuring Agency before issuance of the Bidding Documents. The following specific data for the works to be tendered shall complement, amend, or supplement the provisions in the Instructions to Bidders. Wherever there is a conflict, the provisions herein shall prevail over those in the Instructions to Bidders.)
Instructions to Bidders Clause Reference
1.1 | Name of Procuring Agency :-
Executive Engineer, Buildings Division Mirpurkhas.
(Insert name of the Procuring Agency)
Brief Description of Works :-
1 | Construction of Office Complex at Taluka Shujabad District Mirpurkhas.
iii | Construction of 6 Nos: Garrage and All-round Compound Wall i/c Steel Gate.
5.1 | (a) |  | Procuring Agency’s Address :-
Near APWA Girls High School M.A. Jinnah Road Mirpurkhas.
(Insert address of the Procuring Agency with Telex / Fax)
| (b) |  | Engineer's Address :-
Same as 5.1 (a)
(Insert name and address of the Engineer, if any, with Telex / Fax)
10.3 | Bid shall be qouted entirely in Pak: Rupees. The payment shall be made in Pak: Rupees.
11.2 | The Bidder has the financial, technical and constructional capability necessary to perform the Contract as follows. (Insert required capabilities and documents)
| i. |  | Financial Capacity :-
| ii. |  | Technical Capacity :- (mention the appropriate category of registration with PEC and qualification and experience of the staff)
| iii. |  | Construction Capacity :- (mention the names and number of equipments required for the work)
Sindh Public Procurement Regulatory Authority l www.spprasindh.gov.pk | [10 empty] | 17
12.1 | (a) |  | A detailed description of the Works, essential technical and performance characteristics.
| (b) |  | Complete set of technical information, description data, literature and drawings as required in accordance with Schedule "B" to Bid, Specitic Works Data. This will include but not be limited to a sufficient number of drawings, photographs, catalogues, illstrations and such other information as is necessary to illustrate clearly the significant characteristics such as general construction dimensions and other relevant information about the works to be performed.
13.1 | Amount of Bid Security :-
| Rs. |  | 0.12 |  | (M) | (Zero Point One Hundred Twenty Thousand Million) only.
(Fill in lump sum amount or in %age of Bid Amount / Estimated Cost, but not below 1% and not exceeding 5%)
14.1 | Period of Bid Validity.
60-Days.
(Fill in "number of days" not exceeding 90)
14.4 | Number of Copies of the Bid to be submitted :-
One original copy.
14.6 | (a) |  | Procuring Agency's Address for the Purpose of Bid submission.
Near APWA Girls High School M.A. Jinnah Road Mirpurkhas.
(insert postal address or location of Bid box for delivery by hand)
15.1 | Deadline for Submission of Bids :-
| Time : |  | 01:00 P.M. on 22-02-2016
16.1 | Venue, Time and Date of Bid Opening :-
| Venue: |  | Office of the |  |  | Executive Engineer, Buildings Division Mirpurkhas.
| Time : |  | 02:00 P.M. on 22-02-2016
16.4 | Responsiveness of Bids.
| (i) |  | Bid is valid till required period, |  |  |  |  | 60-Days.
Sindh Public Procurement Regulatory Authority l www.spprasindh.gov.pk | [10 empty] | 18
| (ii) |  | Bid prices are firm during currency of contract / Price adjustment.
| (iii) |  | Completion period offered is within specifed limits.
| (iv) |  | Bidder is eligible to Bid and possesses the requisite experience, capability and qualification.
| (v) |  | Bid does not deviate from basic technical requirements and
| (vi) |  | Bid are generally in order, etc.
Procuring agency can adopt either of two options. (Select either of them)
| (a) |  | Fixed Price Contract :-
In these contracts no escalation will be provided during currency of the contract and normally period of completion of these works is upto 36 months.
| (b) |  | Price Adjustment Contract :-
In these contracts escalation will be paid only on those items and in the manner as notified by Finance Department, Government of Sindh, after bid opening during currency of the contract.
Sindh Public Procurement Regulatory Authority l www.spprasindh.gov.pk | [10 empty] | 19
FORM OF BID
(LETTER OF OFFER)
Bid Reference No. |  |  |  | 65
Date | 21-01-2016
1 | Construction of Office Complex at Taluka Shujabad District Mirpurkhas.
iii | Construction of 6 Nos: Garrage and All-round Compound Wall i/c Steel Gate.
(Name of Works)
To:
_______________________________
_______________________________
_______________________________
Gentlemen,
|  | 1. |  | Having examined the Bidding Documents including Instructions to Bidders, Bidding Data, Conditions of Contract, Contract Data, Specifications, Drawings, if any, Schedule of Prices and Addenda Nos. _________________________ for the execution of the above-named works, we, the undersigned, being a company doing business under the name of and address ______________________________________________________________________________________________ and being duly incorporated under the laws of Pakistan hereby offer to execute and complete such works and remedy any defects therein in conformity with the said Documents including Addenda thereto for the Total Bid Price of Rs______________________ (Rupees______________________________________________________) or such other sum as may be ascertained in accordance with the said Documents.
|  | 2. |  | We understand that all the Schedules attached hereto form part of this Bid.
|  | 3. |  | As security for due performance of the undertakings and obligations of this Bid, we submit herewith a Bid Security in the amount of Rs.0.1200 (M) (Zero Point One Hundred Twenty Thousand Million) drawn in your favour or made payable to you and valid for a period of twenty eight (28) days beyond the period of validity of Bid.
|  | 4. |  | We undertake, if our Bid is accepted, to commence the Works and to deliver and complete the Works comprised in the Contract within the time(s) stated in Contract Data.
|  | 5. |  | We agree to abide by this Bid for the period of ______ days from the date fixed for receiving the same and it shall remain binding upon us and may be accepted at any time before the expiration of that period.
|  | 6. |  | Unless and until a formal Agreement is prepared and executed, this Bid, together with your written acceptance thereof, shall constitute a binding contract between us.
|  | 7. |  | We undertake, if our Bid is accepted, to execute the Performance Security
Sindh Public Procurement Regulatory Authority l www.spprasindh.gov.pk | [10 empty] | 20
CONTRACT DATA
(Note: Except where otherwise indicated, all Contract Data should be filled in by the Procuring Agency prior to issuance of the Bidding Documents.)
Sub-Clauses of
Conditions of Contract
1.1.3 |  | Procuring Agency‘s Drawings, if any
(To be listed by the Procuring Agency)
1.1.4 |  | The Procuring Agency means
Executive Engineer, Buildings Division Mirpurkhas.
__________________________________________
1.1.5 |  | The Contractor means
______________________________
______________________________
1.1.7 |  | Commencement Date means the date of issue of Engineer‘s Notice to Commence which shall be issued within fourteen (14) days of the signing of the Contract Agreement.
1.1.9 |  | Time for Completion |  |  |  | 36-Months.
(The time for completion of the whole of the Works should be assessed by the Procuring Agency)
1.1.20 |  | Engineer (mention the name along with the designation including whether he belongs to department or consultant) and other details.
______________________________
______________________________
1.3 |  | Documents forming the Contract listed in the order of priority:
(a) |  | The Contract Agreement
(b) |  | Letter of Acceptance
(c) |  | The completed Form of Bid
(d) |  | Contract Data
(e) |  | Conditions of Contract
(f) |  | The completed Schedules to Bid including Schedule of Prices
(g) |  | The Drawings, if any
(h) |  | The Specifications
(i) |  | ___________________
(j) |  | ___________________
(The Procuring Agency may add, in order of priority, such other documents as form part of the Contract. Delete the document, if not applicable)
Sindh Public Procurement Regulatory Authority l www.spprasindh.gov.pk | [10 empty] | 49
2.1 |  | Provision of Site: On the Commencement Date
3.1 |  | Authorized person: _________________
3.2 |  | Name and address of Engineer’s/Procuring Agency’s representative.
Executive Engineer, Buildings Division Mirpurkhas.
4.4 |  | Performance Security:
Amount_________________
Validity_________________
(Form: As provided under Standard Forms of these Documents)
5.1 |  | Requirements for Contractor’s design (if any):
Specification Clause No‘s__________________
7.2 |  | Programme:
Time for submission: Within fourteen (14) days* of the Commencement Date.
Form of programme: __________________ (Bar Chart/CPM/PERT or other)
7.4 |  | Amount payable due to failure to complete shall be __% per day up to a maximum of (10%) of sum stated in the Letter of Acceptance
(Usually the liquidated damages are set between 0.05 percent and 0.10 percent per day.)
7.5 |  | Early Completion
In case of earlier completion of the Work, the Contractor is entitled to be paid bonus up-to limit and at a rate equivalent to 50% of the relevant limit and rate of liquidated damages stated in the contract data.
9.1 |  | Period for remedying defects
____________________________________________
____________________________________________
10.2 | (e) |  | Variation procedures:
Day work rates______________
__________________________(details)
11.1 |  |  | Terms of Payments
| a) | Mobilization Advance
|  | (1) | Mobilization Advance up to 10 % of the Contract Price stated in the Letter of Acceptance shall be paid by the Procuring Agency to the Contractor on the works costing Rs.2.5 million or above on following conditions:
Sindh Public Procurement Regulatory Authority l www.spprasindh.gov.pk | [10 empty] | 50
(For Contracts (Small) Amounting Between Rs.4.00 Million to Rs.50.00 Million)
SPPRA BIDDING DOCUMENT
STANDARD BIDDING DOCUMENT
FOR
PROCUREMENT OF WORKS

## 1-iv
Name of Work :- |  | 1 | Construction of Office Complex at Taluka Shujabad District Mirpurkhas.
|  | iv. | Providing E.I. Work of Main Building.
Issued to Mr. / M/s.
DR. No. | [5 empty] | Dated:
Tender Fee Amount. |  |  |  | Rs.
Standard Bidding Document is intended as a model for admeasurements (Percentage Rate / Unit Price for unit rates in a Bill of Quantities) type of contract. The main text refers to admeasurements contract.
Tell # 0233-9290047 Sr. No.01 (iv) | [8 empty] | NIT No.TC/G-55/ 65
(This section should be filled in by the Engineer / Procuring Agency before issuance of the Bidding Documents)
(a). | Name of Procuring Agency :- |  |  |  | Executive Engineer, Buildings Division Mirpurkhas.
(b). | Brief Description of Works :- |  |  | 1 | Construction of Office Complex at Taluka Shujabad District Mirpurkhas.
|  |  |  | iv. | Providing E.I. Work of Main Building.
(c). | Procuring Agency’s Address :- |  |  |  | Near APWA Girls High School M.A. Jinnah Road Mirpurkhas.
(d). | Estimated Cost :- |  |  |  | Rs. | 3.1 | (M)
(e). | Amount of Bid Security :- |  |  |  | Rs. | 0.062 | (M) | (Fill in lump sum amount or in %age of Bid Amount / Estimated Cost, but not exceeding 5%)
(f). | Period of Bid Validity (Days) :- |  |  |  |  | 60-Days. |  | (Not more than sixty days).
(g). | Security Deposit :- (including Bid Security) |  |  |  | Rs. | 0.186 | (M) | (in %age of Bid Amount / Estimate Cost equal to 10%)
(h). | Percentage, if any, to be Deducted from Bills. |  |  |  |  | --
(i). | Deadline for Submission of Bids alongwith time :- |  |  |  |  | 22-02-2016 (Ist: Attempt) |  | (01:00 PM)
(j). | Venue, Time and Date of Bid Opening :- |  |  |  |  | 22-02-2016 (Ist: Attempt) |  | (02:00 PM)
(k). | Time for Completion form written order of commence :- |  |  |  |  | 36-Months.
(l). | Liquidity Damages :- |  |  |  |  | -- |  | (0.05 of Estimated Cost or Bid Cost per day of delay, but total not exceeding 10%)
(m). | Deposit Receipt No. |  |  | Date |  |  |  | Amount Rs.
(Executive Engineer / Authority issuing bidding documents).
Sindh Public Procurement Regulatory Authority l www.spprasindh.gov.pk | [8 empty] | 4
SPPRA BIDDING DOCUMENT
STANDARD BIDDING DOCUMENTS
(For Contract Costing Upto Rs.4.00 Million)
PRODUREMENT OF WORKS

## 1-v
Name of Work :- |  | 1 | Construction of Office Complex at Taluka Shujabad District Mirpurkhas.
|  | v. | Providing E.I. Work of Mosque.
Issued to Mr. / M/s.
DR. No. | [5 empty] | Dated:
Tender Fee Amount. |  |  |  | Rs.
Standard Bidding Document is intended as a model for admeasurements (Percentage Rate / Unit Price for unit rates in a Bill of Quantities) type of contract. The main text refers to admeasurements contract.
Tell # 0233-9290047 Sr. No.01 (v) | [8 empty] | NIT No.TC/G-55/ 65
(This section should be filled in by the Engineer / Procuring Agency before issuance of the Bidding Documents)
(a). | Name of Procuring Agency :- |  |  |  | Executive Engineer, Buildings Division Mirpurkhas.
(b). | Brief Description of Works :- |  |  | 1 | Construction of Office Complex at Taluka Shujabad District Mirpurkhas.
|  |  |  | v. | Providing E.I. Work of Mosque.
(c). | Procuring Agency’s Address :- |  |  |  | Near APWA Girls High School M.A. Jinnah Road Mirpurkhas.
(d). | Estimated Cost :- |  |  |  | Rs. | 0.14 | (M)
(e). | Amount of Bid Security :- |  |  |  | Rs. | 0.0028 | (M) | (Fill in lump sum amount or in %age of Bid Amount / Estimated Cost, but not exceeding 5%)
(f). | Period of Bid Validity (Days) :- |  |  |  |  | 60-Days. |  | (Not more than sixty days).
(g). | Security Deposit :- (including Bid Security) |  |  |  | Rs. | 0.0084 | (M) | (in %age of Bid Amount / Estimate Cost equal to 10%)
(h). | Percentage, if any, to be Deducted from Bills. |  |  |  |  | --
(i). | Deadline for Submission of Bids alongwith time :- |  |  |  |  | 22-02-2016 (Ist: Attempt) |  | (01:00 PM)
(j). | Venue, Time and Date of Bid Opening :- |  |  |  |  | 22-02-2016 (Ist: Attempt) |  | (02:00 PM)
(k). | Time for Completion form written order of commence :- |  |  |  |  | 36-Months.
(l). | Liquidity Damages :- |  |  |  |  | -- |  | (0.05 of Estimated Cost or Bid Cost per day of delay, but total not exceeding 10%)
(m). | Deposit Receipt No. |  |  | Date |  |  |  | Amount Rs.
(Executive Engineer / Authority issuing bidding documents).
Sindh Public Procurement Regulatory Authority l www.spprasindh.gov.pk | [8 empty] | 4
SPPRA BIDDING DOCUMENT
STANDARD BIDDING DOCUMENTS
(For Contract Costing Upto Rs.4.00 Million)
PRODUREMENT OF WORKS

## 1-vi
Name of Work :- |  | 1 | Construction of Office Complex at Taluka Shujabad District Mirpurkhas.
|  | vi. | Providing E.I. Work of Garrage. (06-Nos:)
Issued to Mr. / M/s.
DR. No. | [5 empty] | Dated:
Tender Fee Amount. |  |  |  | Rs.
Standard Bidding Document is intended as a model for admeasurements (Percentage Rate / Unit Price for unit rates in a Bill of Quantities) type of contract. The main text refers to admeasurements contract.
Tell # 0233-9290047 Sr. No.01 (vi) | [8 empty] | NIT No.TC/G-55/ 65
(This section should be filled in by the Engineer / Procuring Agency before issuance of the Bidding Documents)
(a). | Name of Procuring Agency :- |  |  |  | Executive Engineer, Buildings Division Mirpurkhas.
(b). | Brief Description of Works :- |  |  | 1 | Construction of Office Complex at Taluka Shujabad District Mirpurkhas.
|  |  |  | vi. | Providing E.I. Work of Garrage. (06-Nos:)
(c). | Procuring Agency’s Address :- |  |  |  | Near APWA Girls High School M.A. Jinnah Road Mirpurkhas.
(d). | Estimated Cost :- |  |  |  | Rs. | 0.25 | (M)
(e). | Amount of Bid Security :- |  |  |  | Rs. | 0.005 | (M) | (Fill in lump sum amount or in %age of Bid Amount / Estimated Cost, but not exceeding 5%)
(f). | Period of Bid Validity (Days) :- |  |  |  |  | 60-Days. |  | (Not more than sixty days).
(g). | Security Deposit :- (including Bid Security) |  |  |  | Rs. | 0.015 | (M) | (in %age of Bid Amount / Estimate Cost equal to 10%)
(h). | Percentage, if any, to be Deducted from Bills. |  |  |  |  | --
(i). | Deadline for Submission of Bids alongwith time :- |  |  |  |  | 22-02-2016 (Ist: Attempt) |  | (01:00 PM)
(j). | Venue, Time and Date of Bid Opening :- |  |  |  |  | 22-02-2016 (Ist: Attempt) |  | (02:00 PM)
(k). | Time for Completion form written order of commence :- |  |  |  |  | 36-Months.
(l). | Liquidity Damages :- |  |  |  |  | -- |  | (0.05 of Estimated Cost or Bid Cost per day of delay, but total not exceeding 10%)
(m). | Deposit Receipt No. |  |  | Date |  |  |  | Amount Rs.
(Executive Engineer / Authority issuing bidding documents).
Sindh Public Procurement Regulatory Authority l www.spprasindh.gov.pk | [8 empty] | 4
SPPRA BIDDING DOCUMENT
STANDARD BIDDING DOCUMENTS
(For Contract Costing Upto Rs.4.00 Million)
PRODUREMENT OF WORKS

## 2-i
Name of Work :- |  | 2 | Up-Gradation R.H.C. to the level of T.H.Q. Hospital Mirwah District Mirpurkhas.
|  | i. | Providing E.I. Work of Main Building.
Issued to Mr. / M/s.
DR. No. | [5 empty] | Dated:
Tender Fee Amount. |  |  |  | Rs.
Standard Bidding Document is intended as a model for admeasurements (Percentage Rate / Unit Price for unit rates in a Bill of Quantities) type of contract. The main text refers to admeasurements contract.
Tell # 0233-9290047 Sr. No.02 (i) | [8 empty] | NIT No.TC/G-55/ 65
(This section should be filled in by the Engineer / Procuring Agency before issuance of the Bidding Documents)
(a). | Name of Procuring Agency :- |  |  |  | Executive Engineer, Buildings Division Mirpurkhas.
(b). | Brief Description of Works :- |  |  | 2 | Up-Gradation R.H.C. to the level of T.H.Q. Hospital Mirwah District Mirpurkhas.
|  |  |  | i. | Providing E.I. Work of Main Building.
(c). | Procuring Agency’s Address :- |  |  |  | Near APWA Girls High School M.A. Jinnah Road Mirpurkhas.
(d). | Estimated Cost :- |  |  |  | Rs. | 2.4 | (M)
(e). | Amount of Bid Security :- |  |  |  | Rs. | 0.048 | (M) | (Fill in lump sum amount or in %age of Bid Amount / Estimated Cost, but not exceeding 5%)
(f). | Period of Bid Validity (Days) :- |  |  |  |  | 60-Days. |  | (Not more than sixty days).
(g). | Security Deposit :- (including Bid Security) |  |  |  | Rs. | 0.144 | (M) | (in %age of Bid Amount / Estimate Cost equal to 10%)
(h). | Percentage, if any, to be Deducted from Bills. |  |  |  |  | --
(i). | Deadline for Submission of Bids alongwith time :- |  |  |  |  | 22-02-2016 (Ist: Attempt) |  | (01:00 PM)
(j). | Venue, Time and Date of Bid Opening :- |  |  |  |  | 22-02-2016 (Ist: Attempt) |  | (02:00 PM)
(k). | Time for Completion form written order of commence :- |  |  |  |  | 36-Months.
(l). | Liquidity Damages :- |  |  |  |  | -- |  | (0.05 of Estimated Cost or Bid Cost per day of delay, but total not exceeding 10%)
(m). | Deposit Receipt No. |  |  | Date |  |  |  | Amount Rs.
(Executive Engineer / Authority issuing bidding documents).
Sindh Public Procurement Regulatory Authority l www.spprasindh.gov.pk | [8 empty] | 4
SPPRA BIDDING DOCUMENT
STANDARD BIDDING DOCUMENTS
(For Contract Costing Upto Rs.4.00 Million)
PRODUREMENT OF WORKS