## ProPlanSch
SINDH SMALL INDUSTRIES CORPORATION
PROCUMENT PLAN (DEVELOPMENT CAPITAL)
Sr. No. | ADP No. | Name of Scheme | Estimated Cost | Allocated Funds (2015-16) | Funds to be allocated for the year 2016-17 | Cost of on-going works (expdt already incurred) | Funds earmarked for ongoing works | Cost of new works (Component) | Funds earmarked for new works (c-e) | Nature of Procurement | Method of Procurement | Anticipated/ Actual date of advertisement | Anticipated/ Actual date of start | Anticipated/ actual date of completion
1. | 527 | Establishment of un-developed area of Small Industrial Estate, Nawabshah | 59.74 | 23.532 | 36.208
i) |  | Construction of Road | 30.268 |  |  | 0 | 30.268 | 0 | 0 | Open Competitive Bidding | National Competitive Bidding "Single Stage - One Evelope Procedure) | 3rd February 2016 | 15th March 2016 | 30th June 2017 | ok
ii) |  | Providing/ Laying Water Supply Line | 5.971 |  |  | 0 | 5.971 | 0 | 0 | do | do | do | do | 31st Dec 2016
iii) |  | Construction of underground Drainage | 10.381 |  |  | 0 | 10.381 | 0 | 0 | do | do | do | do | 30th June 2017
iv) |  | Providing & Laying A.C. Pressure Pipe | 6.16 |  |  | 0 | 6.16 | 0 | 0 | do | do | do | do | do
v) |  | Providing & Fixing HT/LT Line | 5.22 |  |  | 0 | 0 | 5.22 | 5.22 | do | do | 15th July 2016 | 1st September 2016 | do
2. | 528 | Establishment of un-developed area of Small Industrial Estate, Thatta | 45.32 | 19.784 | 25.536
i) |  | Construction of Road | 21.596 |  |  | 0 | 21.596 | 0 | 0 | Open Competitive Bidding | National Competitive Bidding "Single Stage - One Evelope Procedure) | 3rd February 2016 | 15th March 2016 | 30th June 2017
ii) |  | Construction of underground Drainage | 7.515 |  |  | 0 | 7.515 | 0 | 0 | Open Competitive Bidding | National Competitive Bidding "Single Stage - One Evelope Procedure) | do | do | do
iii) |  | Providing/ Laying Water Supply Line | 8.207 |  |  | 0 | 8.207 | 0 | 0 | do | do | do | do | 31st Dec 2016
iv) |  | Providing & Fixing HT/LT Line | 4.817 |  |  | 0 | 0 | 4.817 | 4.817 | do | do | 15th July 2016 | 1st September 2016 | 30th June 2017
3. | 529 | Establishment of un-developed area of Small Industrial Estate, Sanghar | 21.732 | 14.116 | 7.616
i) |  | Construction of Road | 7.3 |  |  | 0 | 7.3 | 0 | 0 | Open Competitive Bidding | National Competitive Bidding "Single Stage - One Evelope Procedure) | 3rd February 2016 | 15th March 2016 | 31st Dec 2016
ii) |  | Providing/ Laying Water Supply Line | 1.345 |  |  | 0 | 1.345 | 0 | 0 | do | do | do | do | do
iii) |  | Construction of underground Drainage | 8.604 |  |  | 0 | 8.604 | 0 | 0 | do | do | do | do | do
iv) |  | Providing & Fixing HT/LT Line | 3.85 |  |  | 0 | 0 | 3.85 | 3.85 | do | do | 15th July 2016 | 1st September 2016 | 30th June 2017