## M. Khan Shoro-I
Annexure A-1
(Annexure-A)
PROCUREMENT PLAN (Development)
Serial No/ ADP No: | Name of Scheme & Estimated Cost | Allocated Funds | Cost of ongoing works (Expenditure already incurred | Funds ongoing works | Cost of new works (components) | Funds for New works | Nature of Procurement | Method of Procurement | Anticipated / Actual Date of Advertisement | Anticipated/Actual Date of Start | Anticipated/Actual Date of Completion
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Provincial ADP 2015-2016
1 | Supplying Installing & Testing Pumping Machinery 20 BHP (2 Sets) i/c Inter Connection @ Water Works, Providing, Laying Jointing and Testing PVC Pipe 4” dia for Distribution System for Rural Water Supply Scheme Muhammad Khan Shoro (Dabhoo) Taluka Kotri District Jamshoro Rs:- 5.000 | 5 | 0 | 5 | Rs: - 5.000 01. Tube Well i/c Trial Bore (01 No) 02. Pump House (01 No) 03. P/Machinery 15 BHP 01 Set 04. Distribution System i. PVC Pipe 3" (2770 Rft:) ii. PVC Pipe 3" (1700 Rft:) 05. L.S.R / Storage Tank (01 No) | 5 | Execution of construction work | Single Stage Envelope | 11/2015 | After issue of Work Order | 06/2016
(RASHEED AHMED SOOMRO)
EXECUTIVE ENGINEER
PUBLIC HEALTH ENGG: DIVISION
JAMSHORO

## M. Khan Shoro-II
ANNEXURE A-II
ANNEXURE-II
PROCUREMENT PLAN (Non-Development)
S. No | Found Head & Sub head | Name of work and break up | Allocated Found and break up for different locations/sites | ltems to be executed | Method of Procurement | Anticipated/Actual of Advertisement | Anticipated/Actual Date of Start | Anticipated/Actual Date of Completion | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
--------------NIL--------------
(RASHEED AHMED SOOMRO)
EXECUTIVE ENGINEER
PUBLIC HEALTH ENGG: DIVISION
JAMSHORO

## Yameen Palari-I
Annexure A-1
(Annexure-A)
PROCUREMENT PLAN (Development)
Serial No/ ADP No: | Name of Scheme & Estimated Cost | Allocated Funds | Cost of ongoing works (Expenditure already incurred | Funds ongoing works | Cost of new works (components) | Funds for New works | Nature of Procurement | Method of Procurement | Anticipated / Actual Date of Advertisement | Anticipated/Actual Date of Start | Anticipated/Actual Date of Completion
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Provincial ADP 2015-2016
1 | Construction of Water Supply Scheme Yameen Palari, Taluka Thana Bula Khan District Jamshoro Rs:- 5.500 | 6.685 | 0 | 6.685 | Rs: - 5.500 01. Tube Well i/c Trial Bore (01 No) 02. Pump House (01 No) 03. P/Machinery 15 BHP 01 Set 04. Distribution System i. PVC Pipe 3" (2770 Rft:) ii. PVC Pipe 3" (1700 Rft:) 05. L.S.R / Storage Tank (01 No) | 6.685 | Execution of construction work | Single Stage Envelope | 11/2015 | After issue of Work Order | 06/2016
(RASHEED AHMED SOOMRO)
EXECUTIVE ENGINEER
PUBLIC HEALTH ENGG: DIVISION
JAMSHORO

## Yameen Palari-II
ANNEXURE A-II
ANNEXURE-II
PROCUREMENT PLAN (Non-Development)
S. No | Found Head & Sub head | Name of work and break up | Allocated Found and break up for different locations/sites | ltems to be executed | Method of Procurement | Anticipated/Actual of Advertisement | Anticipated/Actual Date of Start | Anticipated/Actual Date of Completion | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
--------------NIL--------------
(RASHEED AHMED SOOMRO)
EXECUTIVE ENGINEER
PUBLIC HEALTH ENGG: DIVISION
JAMSHORO

## P-Mach Subhanallah Colony-I
Annexure A-1
(Annexure-A)
PROCUREMENT PLAN (Development)
Serial No/ ADP No: | Name of Scheme & Estimated Cost | Allocated Funds | Cost of ongoing works (Expenditure already incurred | Funds ongoing works | Cost of new works (components) | Funds for New works | Nature of Procurement | Method of Procurement | Anticipated / Actual Date of Advertisement | Anticipated/Actual Date of Start | Anticipated/Actual Date of Completion
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Provincial ADP 2015-2016
1 | Supplying / Installing & Testing Pumping Machinery 30 BHP (4 Sets) i/c Diesel Engine 48 BHP @ Disposal work i/c P/L/J Testing A.C. Pipe 20" dia for Drainage Scheme Subhanallah Colony Taluka Kotri District Jamshoro Rs:- 6.570 | 6.57 | 0 | 6.57 | Rs: - 6.570 01. Tube Well i/c Trial Bore (01 No) 02. Pump House (01 No) 03. P/Machinery 15 BHP 01 Set 04. Distribution System i. PVC Pipe 3" (2770 Rft:) ii. PVC Pipe 3" (1700 Rft:) 05. L.S.R / Storage Tank (01 No) | 6.57 | Execution of construction work | Single Stage Envelope | 12/2015 | After issue of Work Order | 06/2016
(RASHEED AHMED SOOMRO)
EXECUTIVE ENGINEER
PUBLIC HEALTH ENGG: DIVISION
JAMSHORO

## M.K Shoro & Yameen Palari
Annexure A-1
(Annexure-A)
PROCUREMENT PLAN (Development)
Serial No/ ADP No: | Name of Scheme & Estimated Cost | Allocated Funds | Cost of ongoing works (Expenditure already incurred | Funds ongoing works | Cost of new works (components) | Funds for New works | Nature of Procurement | Method of Procurement | Anticipated / Actual Date of Advertisement | Anticipated/Actual Date of Start | Anticipated/Actual Date of Completion
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Provincial ADP 2015-2016
1 | Supplying Installing & Testing Pumping Machinery 30 BHP (2 Sets) @ Siource & 20 BHP (2 Sets) @ Water works for Rural Water Supply Scheme Muhammad Khan Shoro (Daboo) Taluka Kotri District Jamshoro (2.100) | 12.95 | 0 | 12.95 | Rs:2.100 1. Pumping Machinery 30 BHP (02 Sets) @ Source 2. Pumping Machinery 20 BHP (02 Sets) @ Water Works | 12.95 | Execution of construction work | Single Stage Envelope | 02/2016 | After issue of Work Order | 06/2016
2 | Water Supply Scheme Yameen Palari Taluka Thana Bula Khan District Jamshoro (5.000) | 6.685 | 0 | 6.685 | Rs:5.000 1. Tube Well 01 No. 2. Submercible Pump 15 BHP 01 Set 3. Constt: of Pump House 01 No. 4. Constt: of L.S.R 03 Nos. 5. P/L/J & Testing PVC Pipe Delivery main 3" dia | 6.685 | Execution of construction work | Single Stage Envelope | 02/2016 | After issue of Work Order | 06/2016
(RASHEED AHMED SOOMRO)
EXECUTIVE ENGINEER
PUBLIC HEALTH ENGG: DIVISION
JAMSHORO

## M.K. Shoro & Yameen Palari-I
ANNEXURE A-II
ANNEXURE-II
PROCUREMENT PLAN (Non-Development)
S. No | Found Head & Sub head | Name of work and break up | Allocated Found and break up for different locations/sites | ltems to be executed | Method of Procurement | Anticipated/Actual of Advertisement | Anticipated/Actual Date of Start | Anticipated/Actual Date of Completion | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
--------------NIL--------------
(RASHEED AHMED SOOMRO)
EXECUTIVE ENGINEER
PUBLIC HEALTH ENGG: DIVISION
JAMSHORO