## Sheet3
|  | Guidelines / Regulations for Procurement of Works | [8 empty] | (Annexure A-I)
(Annexure- A)
PROCUREMENT PLAN (Development/Capital)
| Serial No/ADP* | Name of Scheme & Estimated Cost | Allocated Funds | Cost of ongoing works (Expenditure already incurred) | Funds earmarked for ongoing works | Cost of New Works (Components) | Funds for New Works (e-e) | Nature of Procurement | Method of Procurement | Anticipated / Actual Date of Advertisement | Anticipated / Actual Date of Start | Anticipated / Actual Date of Completion
| a | b | c | d | e | f | g | h | i | j | k | l
ELECTRIC WORKS
Nawabshah package for Education 2008-09 Programme ADP.No.1232 Rehabilitaion of existing Primary/Midlle Schools in Distt:SBA.
| 1 | GBPS Mitho Zardari ,GBPS Lal Bux Shahani,GBPS Mubark Brohi | 0.18 | Nil | Nil | 0.18 | 0.18 | National Compitative Bidding | Single Stage one Envelope Procedure | 19.02.2016 | 3.2016 | 30.6.2016
| 2 | GGPS Gupchani,GBPS Ali Jan Brohi,GBPS Hayat Korai | 0.15 | Nil | Nil | 0.15 | 0.15 | Do | Do | 19.02.2016 | 3.2016 | 30.6.2016
| 3 | Constt:/Reconstt: of Existing Primary School GBPS Doulat Calony Nawabshah District SBA 2010-11 programme ADP-152 | 0.385 | Nil | Nil | 0.385 | 0.385 | Do | Do | 19.02.2016 | 3.2016 | 31.082
| 4 | Construction of Digital Library at H.M Khoja Library Nawabshah District SBA2010-11 progr: ADP.159 | 0.775 | Nil | Nil | 0.775 | 0.775 | Do | Do | 19.02.2016 | 3.2016 | 31.08.2016
| 5 | Constt:/Reconstt: of Existing Primary School GGPS police line Nawabshah (Old Wing) District SBA 2010-11 programme ADP-160 | 0.166 | Nil | Nil | 0.166 | 0.166 | Do | Do | 19.02.2016 | 3.2016 | 31.06.2016
Rehablitaion of Elementry Secondry Schools of Tal:Nawabshah & Daur Distt:SBA.2013-14 Prog:ADP.No.161
| 6 | GBPS Sajjan Khan Zardari,GBPS Qaimdin Khatti,GBPS Mola Bux Brohi | 0.16 | Nil | Nil | 0.16 | 0.16 | Do | Do | 19.02.2016 | 3.2016 | 30.6.2016
Rehablitaion of Elementry Secondry Schools of Tal:Sakrand & Q.Ahmed Distt:SBA.2013-14 Prog:ADP.No.162
| 7 | GBPS Hamal Kaloi | 0.054 | Nil | Nil | 0.054 | 0.054 | Do | Do | 19.02.2016 | 3.2016 | 30.6.2016
Construction/Addition of C/Room in Existing Elementry/Secondry School of Tal:Nawabshah & Daur 2013-14 Progr: ADP.No.163
| 8 | GBPS Misri Chandio | 0.056 | Nil | Nil | 0.056 | 0.056 | Do | Do | 19.02.2016 | 3.2016 | 30.6.2016
Addition of C/Room in Existing Elementry/Secondry School of Tal:Nawabshah & Daur 2013-14 Progr: ADP.No.165
| 9 | GBPS Lal Chand,GBPS Khan Muhammad Chandio | 0.16 | Nil | Nil | 0.16 | 0.16 | Do | Do | 19.02.2016 | 3.2016 | 30.6.2016
| 10 | GBPS Hashim Khaskhali,GBPS Niaz Fakir | 0.16 | Nil | Nil | 0.16 | 0.16 | Do | Do | 19.02.2016 | 3.2016 | 30.6.2016
| 11 | GBPS Raza Muhammad,GBPS Behram Khan | 0.16 | Nil | Nil | 0.16 | 0.16 | Do | Do | 19.02.2016 | 3.2016 | 30.6.2016
| 12 | GBPS Ali Gul Chandio,GBPS Illahi Bux Soomro | 0.16 | Nil | Nil | 0.16 | 0.16 | Do | Do | 19.02.2016 | 3.2016 | 30.6.2016
| 13 | GBPS Muhammad Yaqoob Brohi,GBPS Muhammad Ramzan Arain | 0.16 | Nil | Nil | 0.16 | 0.16 | Do | Do | 19.02.2016 | 3.2016 | 30.6.2016
| 14 | GBPS Village Meenho Khan Zardari,GBPS Gul Jan Mari | 0.11 | Nil | Nil | 0.11 | 0.11 | Do | Do | 19.02.2016 | 3.2016 | 30.6.2016
Addition of C/Room in Existing Elementry/Secondry Schools of Tal:Sakrand & Q.Ahmed Distt:SBA 2013-14 Progr: ADP.No.166
| 15 | GBPS Mir Khan Mugheri,GBPS Malik Rahu,GBPS Photo khan Zardari | 0.245 | Nil | Nil | 0.245 | 0.245 | Do | Do | 19.02.2016 | 0 | 30.6.2016
Rehablitaion of Elementry Secondry Schools of Tal:Nawabshah & Daur Distt:SBA.2013-14 Prog:ADP.No.167
| 16 | GBPS Mir Muhammad Keerio,GBPS Muhammad Hassan Shahani,GBPS Lal Khan Jiskani. | 0.204 | Nil | Nil | 0.204 | 0.204 | Do | Do | 19.02.2016 | 3.2016 | 30.6.2016
| 17 | GBPS Muhammad Ramzan Khatian,GBPS Peero Lakhmir,GBPS Suleman Brohi | 0.21 | Nil | Nil | 0.21 | 0.21 | Do | Do | 19.02.2016 | 3.2016 | 30.6.2016
| 18 | GBPS Fakir Khair Muhammad khoso,GBPS Haji Ramzan Magsi | 0.195 | Nil | Nil | 0.195 | 0.195 | Do | Do | 19.02.2016 | 3.2016 | 30.6.2016
Rehablitaion of Elementry Secondry Schools of Tal:Sakrand & Q.Ahmed Distt:SBA.2013-14 Prog:ADP.No.168
| 19 | GBMS Rahib Shah,GBPS Ramzan Dahri | 0.181 | Nil | Nil | 0.181 | 0.181 | Do | Do | 19.02.2016 | 3.2016 | 30.6.2016
| 20 | GBPS Long Khan Soomro,GBPS Ghandia | 0.212 | Nil | Nil | 0.212 | 0.212 | Do | Do | 19.02.2016 | 3.2016 | 30.6.2016
| 21 | Missing Facilites in Elementry Secondry Schools in Distt:SBA.2013-14 Prog:(12 Nos Lavatory Blocks),ADP.No.169 | 0.19 | Nil | Nil | 0.19 | 0.19 | Do | Do | 19.02.2016 | 3.2016 | 30.6.2016
| 22 | Improvement of H.M Khoja Garden (Willis Branch) phase-II 2012-13 programme ADP.170. | 2.7 | Nil | Nil | 2.7 | 2.7 | Do | Do | 19.02.2016 | 3.2016 | 31.12.2016
|  | SINDH PUBLIC PROCUREMENT REGULATORY AUTHORITY | [8 empty] | Page 62