## Summary
Project Management Implementation Unit (SERP-II) Education and Literacy Deptarment Govt. of Sindh |  | District : Jamshoro Talka : Manjhand GBHS Lakhi Shah Sadar
Government of Sindh,
Education and Litracy Department,
Project Management & Implementation Unit
Region II Hyderabad
Summary Cost of Project
School Name :GBHS Lakhi Shah Sadar |  | District : Jamshoro
School ID : 422040184 |  | Taulka : Manjhand
Sub Head :New Construction
S.No | Description of Works | COST (Rs.)
1 | New Construction
i | Civil Work Part-A Sindh Schedule Rate 2012-(A) | 2576215.0326
ii | Civil Work Part -B Non Schedule Rate -(B) | 206401.5
iii | Carrage of Material (C ) | 0
2 | Electrical Work
i | Part-A Sindh Schedule Rate 2012-( D ) | 96126
ii | Part -B Non Schedule Rate -(E ) | 92151.2
| Sum of Scheduled Item (A+C+D) | 2672341.0326
| Sum of Non Scheduled Items (B+E) | 298552.7

## Civil_New_Class Roo_Schedul
Project Management Implementation Unit (SERP-II) Education and Literacy Deptarment Govt. of Sindh |  |  |  |  | District : Jamshoro Talka : Manjhand GBHS Lakhi Shah Sadar
Engineer Estimate
School Name : GBHS Lakhi Shah Sadar |  |  |  |  | District : Jamshoro
School ID : 422040184 |  |  |  |  | Talka Manjhand
Bill No. 2(ii)- Civil Works New Construction_Class Room
Part-A-Composite Scheduled Rate 2012
Item No. | Description | Unit | T.Quantity | Rate |  | Amount ( Rs.)
|  |  |  | Rs// Unit (In Figure) | Rs// Unit (In Words) | Rs.
1.1 | EARTH WORK IN EXCAVATION
Excavation in foundation of building, bridges and other structures including dagbelling, dressing, refilling around structure with earth watering and ramming lead upto 5ft. (Page # 4, Item # 18)
| a) In ordinary soil. | Cft | 4680 | 3.18 |  | 14882.4
1.2 | BACK FILLING
1.2.1 | Filling, watering and ramming earth in floors with surplus earth from foundation lead upto one chain and lift upto 5 feet. (Page # 4, Item # 21) | Cft | 2826.81 | 1.51 |  | 4268.4831
1.2.2 | BORROW PIT
Borrowpit excavation undressed lead upto 100ft. (Ch # 1,Page # 1, Item # 3)
| (a) Ordinary soil | Cft | 3840 | 2.11 |  | 8102.4
Extra for every 50 ft additional lead or part thereof. This rate shall apply to lead upto 0.50 mile. When the lead is more than 0.50 mile the lead shall be paid under item ( Ch # 1,Page # 2, Item # 8)
| (a) For earth work (soft, ordinary, hard and very hard) | Cft | 3840 | 0.1 |  | 384
Earth work compaction (soft, ordinary or hard soil). (Ch # 1,Page # 3, Item # 13)
| (b) Laying earth in 6" layers levelling, dressing and watering for compaction etc. complete. | Cft | 3840 | 0.35 |  | 1344
1.3 | TERMITE PROOFING
| Providing Anti-termmite treatment by spraying /sprinkling /spreading Neptachler 0.5% Emulsion as an overall pre construction treatment in slab type construction along external foundation, trenches of the building over complete parimeter of the foundation trench etc, as per directions of Engineer Incharge. (Page # 109, Item # 91) | P.Rft | 396 | 40.1 |  | 15879.6
1.4 | CONCRETE WORKS
1.4.1 | Providing and laying lean concrete having 1450 PSI cylindrical strength ( ready mixed concrete) including placing compactng finishing curing compelete and screening and washing of crushed stone aggregate excluding the cost of shuttering.
| (Page # 111,Item # 98) | Cft | 451.44 | 171.97 |  | 77634.1368
1.4.2 | Reinforcement cement concrete work including all labour and material except the cost of steel reinforcement and its labour for bending and binding which will be paid seperately. This rates also includes all kinds of forms moulds, lifting shuttering, curing, rendering and finishing the exposed surface (including screening and washing of shingle). (Page # 16, Item # 6)
R.C. work in roof slab, beams, columns, rafts, lintels and other structural members laid in situ or precast laid in position complete in all recpects.
a)Super Structure (OPC Cement)
| Ratio (1:2:4) | Cft | 2136.75 | 337 |  | 720084.75
1.6 | BRICK MASONRY
1.6.1 | Pacca brick work in foundation and plinth in: (Page # 20, Item # 4-I)
| (a) Cement sand mortor 1:5 | Cft |  | 121.76 |  | 0
1.6.2 | Pacca brick work in ground floor in: (Page # 21, Item # 5-I)
| (a) Cement sand mortor 1:5 | Cft | 3384 | 129.0208 |  | 436606.3872
1.7 | PLASTER WORK
Cement plaster 1:4 upto 12' height plaster. (Page # 51, Item # 11b)
| (i) 1/2" thick | Sft | 10953 | 22.84 |  | 250166.52
1.8 | PAINTING WORK
1.8.1 | INTERNAL PAINTING
| (A)Preparing the surface and painting with plastic emulsion paint of approved make I/c rubbing the surface with sand paper , filling the voids with chalk / plaster of paris and then painting etc, complete. (Page # 55, Item # 40.A) | Sft | 4098 | 10.81 |  | 44299.38
| (B) 2nd & subsequent coat. (Page # 55) | Sft | 4098 | 5.79 |  | 23727.42
1.8.2 | CEILING PAINTING
Distempering. (Page # 53, Item # 24)
| (a) One coat (Ist coat over priming coat) | Sft | 1609.5 | 6.02 |  | 9689.19
| (b) Two coats. | Sft | 1609.5 | 10.44 |  | 16803.18
1.8.3 | EXTERNAL PAINTING
| (A)Preparing the serface and painting with weather coat I/c rubbing the surface with rubbing brick / sand paper, filling the voids with chalk / plaster of paris and then painting with weather coat of approved make. (Page # 55, Item # 38.A) | Sft | 4728 | 13.28 |  | 62787.84
| (B) 2nd & subsequent coat. (Page # 55) | Sft | 4728 | 6.2 |  | 29313.6
1.9 | FLOORING
1.9.1 | TERRAZZO FLOORING
| Mosaic tiles of grey cement 12" x 12" x 1" of approved shade laid flat in 1:2 white cement mortar over a bed of 3/4" thick lime mortar 1:2. (Page # 45, Item # 47) | Sft | 1609.5 | 64.85 |  | 104376.075
1.9.2 | Cement concrete plain including placing, compacting, finishing and curing complete (including screening and washing at stone aggregate without shuttering). (Page # 16, Item # 5)
| Ratio 1:2:4 | Cft | 531.135 | 144.3 |  | 76642.7805
1.9.3 | STONE SOLLING
| Providing & laying Stone Soling 4" thick. TO 6" thick.including using granular materal for filling stone wides levelling and compacting to required density etc.complete as per drawing and instruction approval of the Engineer Incharge / Consultant. | Cft | 804.75 | 35 |  | 28166.25
1.1 | DOORS AND WINDOWS
1.10.1 | Supplying and fixing in position doors, windows and ventilators, of 1st. Class deodar wood frame and 1-1/2" thick Teak wood ply shutter of 2nd class deodar wood skeleton (Solid) style and rails core of partal wood and Teak ply wood (2-ply) on both side i/c hold fasts,hinges, iron tower bolts, handles and cleans with cord etc complete. | Sft | 456 | 1182.56 |  | 539247.36
1.10.2 | Painting doors and windows any type
Preparing surface and painting of doors and windows any type (including edges)
| (i) Priming coat | Sft | 456 | 8.62 |  | 3930.72
| (ii) each subsequent coat o fpaint | Sft | 456 | 6.26 |  | 2854.56
Scheduled Item (Page # 67,item # 5c)
1.1 | ROOF TREATMENT
| Providing and fixing bitumen felt paper of 60 Lbs over roof I/c cleaning of roof with wire brush an removing dust, applying bitumen coat at the rate of 34 Lbs per % sft as premix inter coats and then laying felt paper with 10% over laps, then applying and spreading hill sand at the rate of 1 cft for 100 sft. The cost also i/c necessary fire material,kerosene oil, wood etc. (Page # 37, Item # 41) | Sft | 1920 | 54.7 |  | 105024
[5 empty] | Total Amount Bill No.2(ii) Part-A_Class Room Rs. | 2576215.0326
Carried Farward to Summary

## Civil_New_Clas Room_Non Schedul
Project Management Implementation Unit (SERP-II) Education and Literacy Deptarment Govt. of Sindh |  |  |  |  | District : Jamshoro Talka : Manjhand GBHS Lakhi Shah Sadar
Engineer Estimate
School Name : GBHS Lakhi Shah Sadar |  |  |  |  | District : Jamshoro
School ID : 422040184 |  |  |  |  | Talka Manjhand
Bill No. 2(ii)- Civil Works New Construction_Class Room
Part-B-Non Scheduled Rates
Item No. | Description | Unit | T.Quantity | Rate |  | Amount ( Rs.)
|  |  |  | Rs// Unit (In Figure) | Rs// Unit (In Words) | Rs.
1.1 | CONCRETE WORKS
Reinforcement cement concrete work including all labour and material except the cost of steel reinforcement and its labour for bending and binding which will be paid seperately. This rates also includes all kinds of forms moulds, lifting shuttering, curing, rendering and finishing the exposed surface (including screening and washing of shingle). (Page # 16, Item # 6)
R.C. work in roof slab, beams, columns, rafts, lintels and other structural members laid in situ or precast laid in position complete in all recpects.
Sub Structure (SR Cement Ratio 1:2:4)
| a) Foundation | Cft | 165.375 | 252 |  | 41674.5
| b)Columns up to Plinth | Cft | 40.5 | 364 |  | 14742
| c)Plinth Beam | Cft | 495 | 303 |  | 149985
700.875
1.2 | STEEL REINFORCEMENT
| (a) Fabrication of Tor bars reinforcement for cement concrete including cutting, bending, laying in position, making joints and fastenings including cost of binding wire (also includes removal of rust from bars (Page # 16, Item # 8) | Ton | 10.448 | 114973.3 |  | 1201241.0384
[5 empty] | Total Amount Bill No.2(ii) Part-B_Class Room Rs. | 206401.5
Carried Farward to Summary

## Bill 4 Elect sched
Project Management Implementation Unit (SERP-II) Education and Literacy Deptarment Govt. of Sindh |  |  |  |  | District : Jamshoro Talka : Manjhand GBHS Lakhi Shah Sadar
Engineer Estimate
School Name : GBHS Lakhi Shah Sadar |  |  |  |  | District : Jamshoro
School ID : 422040184 |  |  |  |  | Talka Manjhand
Bill No. 4 Electrical Work _New Class Rooms | [6 empty] | Room | 6
Part-A Composite Scheduled Rate 2012
Item No. | Description | Unit | T.Quantity | Rate |  | Amount ( Rs.)
|  |  |  | Rs// Unit (In Figure) | Rs// Unit (In Words) | Rs.
1 | WIRING FOR LIGHT OR FAN POINT
| Wiring for light or fan point with 1/1.13 (3/0.029") PVC insulated wire in 20mm(3/4") channel patti on surface as required. (Page # 15, Item # 129) | Point | 36 | 910 |  | 32760
2 | WIRING FOR PLUG POINT
| Wiring for plug point with 1/1.13 (3/0.029") PVC insulated wire in 20mm(3/4") channel patti as required. (Page # 15, Item # 130) | Point | 12 | 742 |  | 8904
3 | POWER CABLE
| Providing and laying (Main or Sub Main) PVC insulated with size 2-7/.064 (16mm2) copper conductor in 1" dia PVC conduit on surface. (Page # 1, Item # 7) | Rft | 70 | 184.4 |  | 12908
4 | FLUSH TYPE SWITCHES
| Providing and fixing one way SP 5amp switch surface type. (Page # 33, Item # 216) | No | 12 | 34 |  | 408
5 | 2 PIN, 5 AMPS PLUG- SOCKET
| Providing and fixing two pin 5amp plug & socket. (Page # 33, Item # 222) | No | 12 | 80 |  | 960
6 | 3 PIN, 15 AMPS PLUG- SOCKET
| Providing and fixing f3 pin 10/15amp plug & socket. (Page # 33, Item # 224) | No | 2 | 151 |  | 302
7 | CEILING FANS
| Providing and fixing brass ceiling fan 56" (good quality). (Page # 34, Item # 235) | No | 12 | 3185 |  | 38220
8 | JUNCTION BOX
Providing and fixing junction box as per following specification following:
| Size of box 8" x 6" x 4", MS plate size 16 SWG thick, clamp with nuts & bolts, cover plate with screw, painting two coats of rust preventive red oxide & two coats of ICI oil paint as per site requirement & instruction of EI. (Page # 24, Item # 158) | No | 1 | 800 |  | 800
9 | SUB HEAD CIRCUIT BREAKERS
| Providing and fixing circuit breakers 10,20SP (TB-5S) on prepared board as required. (Page # 31, Item # 203) | No |  | 916 |  | 0
| Providing and fixing circuit breakers 10,20,30,40,50 & 60 amp TP (XE-100CS) on prepared board as required. (Page # 31, Item # 206) | No |  | 5521 |  | 0
10 | CEILING ROSE
| Providing and fixing ceiling rose with two terminals . (Page # 33, Item # 228) | No | 12 | 72 |  | 864
[5 empty] | Total Amount Bill No.4 Part-A Rs. | 96126
Carried Farward to Summary

## Bill 4 Elect Non Sched
Project Management Implementation Unit (SERP-II) Education and Literacy Deptarment Govt. of Sindh |  |  |  |  | District : Jamshoro Talka : Manjhand GBHS Lakhi Shah Sadar
Engineer Estimate
School Name : GBHS Lakhi Shah Sadar |  |  |  |  | District : Jamshoro
School ID : 422040184 |  |  |  |  | Talka Manjhand
Bill No. 4 Electrical Work _New Class Rooms
Part-B-Non Scheduled Rates
Item No. | Description | Unit | T.Quantity | Rate |  | Amount ( Rs.)
|  |  |  | Rs// Unit (In Figure) | Rs// Unit (In Words) | Rs.
1.1 | FAN CLAMPS
| Providing and fixing mild steel bar fan clamps 15.8 mm (5/8") dia suitable for R.C.C. roof | No. | 12 | 280 |  | 3360
1.2 | DIMMER
| P/F Fan dimmer fancy type pak/ royal/ millat/ Imported make with necessary connection. On sheet complete as required. | No. | 12 | 400 |  | 4800
1.3 | EARTHING SET
| P/F earthing set with 2"x 2"x 1/2" copper plate burried in ground at a depth of 12 or less f water comes out fronm the ground level with salt and chorcoal, etc ,in/c. making the pit 12" deep by excavation of all type of soil. Earth plate to be connected with No. 8 S.W.G. bare copper wire run in 1/2" G.L. pipe straght from the earth plate upto the metallic Electrical assesary i/e providing necessary Tee. | Job | 1 | 7220 |  | 7220
1.4 | EARTH CONDUCTOR
| providing & fixing hard drawn bare copper wire no.10 S.w.g. as earth continuity with any given mains or sub-mains in all system of wiring including metallic Electrical assesary. | Rft | 80 | 14.64 |  | 1171.2
1.5 | LIGHT FIXTURE
| Providing and fixing bulb holder complete with 23 watts philips CFL i/c necessary electric connection and fixing on wall or ceiling etc. | No | 24 | 400 |  | 9600
1.6 | DISTRIBUTION BOARD
| Distribution board-1 (for RO/Washroom). same as item no 22 but with following specification and requirements: a) MCB (15amp) 01no b) MCB (10amp) 01no c) MCB (2-6amp) 06 no (1 spare) | No | 1 | 38000 |  | 38000
1.7 | DISTRIBUTION BOARD
Supply, installation, connection of wires/cables, testing and commissioning of 500 volts, 50 Hz, 3-Phase and neutral distribution boards (DBs) concealed type, wall mounted to be installed as and where shown on drawings,made of M.S. sheet 16 SWG with hinged door, handle, catcher, earthing bar, neutral strip, internal wiring from MCCBs terminating on cable terminal blocks. One coat of antirust and anti-corrosive paint with further two coats of enamelled paint of approved colour, all necessary materials complete in all respects and manufactured by any one of the approved manufacturers: conforming to single line diagram. D.B
| 4-Ways, 3-Phase | Job | 1 | 28000 |  | 28000
[5 empty] | Total Amount Bill No.4 Part-B Rs. | 92151.2
Carried Farward to Summary

## Material Statement
Material Statement
Material Detail
S.# | Item Description | Material carriage statement |  | Cement Bags | Sand Cft | Coarse Aggreagate Cft | Steel ton | Bricks Nos | Tiles Nos | Bitumans
1 | Lean Conc. 1450 psi
1..i | Building | 451.44 | Cft | 42.8868 | 209.2876 | 418.5752
1.ii | Rest Room | 0 | Cft | 100 | 4 | 104
1.iii | Boundary Wall |  | Cft
1.iv | Overhead Tank | 0 | Cft | 10 | 4 | 14
1.v | UG Tank |  | Cft
|  |  |  | 15 | 4
2 | 1:2:4 Concrete
| Ordinary Port Land Cement |  | Cft | 15 | 4
2.i | Building (Flooring) | 2136.75 | Cft | 363.2475 | 908.1187 | 1816.2375
2.ii | Rest Room | 0 | Cft | 0 | 4 | 8
2.iii | Boundary wall | 0 | Cft | 0 | 0 | 0
2.iv | Overhead Tank | 0 | Cft | 0 | 4 | 8
2.v | UG Tank |  | Cft | 0 | 0 | 0
4
SR Cement NS
2.vi | Building | 700.875 | Cft | 122.6531 | 306.6328 | 613.2656
2.vii | Boundary wall | 0 | Cft | 0 | 0 | 0
2.viii | Overhead Tank | 0 | Cft | 0 | 0 | 0
2.ix | UG Tank | 0 | Cft | 0 | 0 | 0
3 | Steel Rainformcement
3.i | Building | 10.448 | Ton |  |  |  | 10.448
3.ii | Rest Room | 0 | Ton |  |  |  | 0
3.iii | Boundary wall | 0 | Ton |  |  |  | 0
3.iv | Overhead Tank | 0 | Ton |  |  |  | 0
3.v | UG Tank | 0 | Ton |  |  |  | 0
4 | Brick Work
4.i | Building | 3384 | Cft | 135.36 | 1015.2 |  |  | 45684
4.ii | Rest Room | 0 | Cft | 0 | 0 |  |  | 0
4.iii | Boundary wall | 0 | Cft | 0 | 0 |  |  | 0
5 | Tiles /Morbal Work
5.i | Building | 1609.5 | sft | [5 empty] | 5722.6667
5.ii | Rest Room | 0 | sft | [5 empty] | 0
6 | Plaster Work
6.i | Building | 10953 | Sft | 182.55 | 912.75
6.ii | Rest Room | 0 | Sft | 0 | 0
6.iii | Boundary Wall | 0 | Sft | 0 | 0
6.iv | Overhead water tank | 0 | Sft | 0 | 0
6.v | UG Water Tank | 0 | Sft | 0 | 0
7 | Stone Souling
7.i | Building | 804.75 | Cft |  |  | 885.225
8 | Bitumans | [8 empty] | 0
8.i | Building | 1920 | [7 empty] | 288
8.ii | Rest Room | 0 | [7 empty] | 0
8.iii | UG Tank | 0 | Sft | [6 empty] | 0
| Total |  |  | 986.6974 | 3379.9891 | 3867.3033 | 10.448 | 45684 | 5722.6667 | 288
Note on D5: Microsoft:

## Material Carriage
Material Statement for Hyderabad( City )
Material carriage statement
Mile Rate
| S.No | 0 | Source City | 0 | 0 | 0 | Qty | Unit | 1st Mile | 2nd Mile | 3rd | 4th | 5th | 6th | carriage upto 6 Mile | 7th | Kacha track Allowance 25% | Carriage for 7mile & Beyond | Total Amount
| 1 | Steel | Karachi | 100 | 4 | 104 | 10.448 | Ton | 407 | 95.52 | 76.89 | 70.45 | 64.43 | 57.67 | 8065.4381 | 32.56 |  | 33338.3142 | 86517.2808
| 2 | Brick | Tando Qaisr | 10 | 4 | 14 | 45684 | Nos | 325.6 | 76.4 | 61.51 | 56.36 | 51.54 | 46.13 | 28211697.36 | 26.05 |  | 9520545.6 | 37732.243
| 3 | Sand | Bolari | 15 | 4 | 19 | 3379.9891 | CFt | 407 | 95.52 | 76.89 | 70.45 | 64.43 | 57.67 | 2609216.4215 | 32.56 | 43.1025 | 6174217.3859 | 87834.3381
| 4 | Aggreagtes | Jamshoro | 15 | 4 | 19 | 3867.3033 | CFt | 407 | 95.52 | 76.89 | 70.45 | 64.43 | 57.67 | 2985403.4501 | 32.56 |  | 1636952.1379 | 46223.5559
| 5 | Cement | Dada Bhai | 40 | 4 | 44 | 986.6974 | bags | 6.1 | 1.43 | 0.6 | 0.6 | 0.6 | 0.6 | 9797.9054 | 0.6 |  | 22496.7013 | 32294.6067
| 6 | Tiles | Hyderabad | 0 | 4 | 4 | 5722.6667 | NoS | 195.36 | 45.84 | 36.9 | 33.82 | 30.93 | 27.68 | 2120419.68 | 15.63 |  | 357781.12 | 2478.2008
| 7 | Bitumanns | Karachi | 100 | 4 | 104 | 288 | KG | 122.1 | 28.65 | 9.77 | 9.77 | 9.77 | 9.77 | 54671.04 | 9.77 |  | 275748.48 | 330.4195
293410.6448
0

## Measuremnt
Project Management Implementation Unit (SERP-II) Education and Literacy Deptarment Govt. of Sindh |  |  |  | District : Jamshoro Talka : Manjhand GBHS Lakhi Shah Sadar
Measurement Sheet
School Name : GBHS Lakhi Shah Sadar |  |  |  |  | District : Jamshoro
School ID : 422040184 |  |  |  |  | Talka Manjhand
Sr# | Description | Units | Qty | L (ft) | B (ft) | H (ft) | Total Qty | Remarks
1 | Renovation Work
Excavation
| Foundation | Cft | 6 | 4 | 4 | 4 | 384
| Plinth Beam | Cft | 2 | 20 | 1.5 | 3 | 180
|  | Cft | 3 | 16 | 1.5 | 3 | 216
[5 empty] | Total |  | 780
| For Six Class Rooms | Cft | 6 | Total Qty |  |  | 4680
2 | Lean Concrete
|  | Cft | 6 | 4 | 4 | 0.33 | 31.68
|  | Cft | 2 | 20 | 1.5 | 0.33 | 19.8
|  | Cft | 3 | 16 | 1.5 | 0.33 | 23.76
[5 empty] | Total |  | 75.24
| For Six Class Rooms | Cft | 6 | Total Qty |  |  | 451.44
3 | RCC
SRC | Foundation | Cft | 6 | 3.5 | 3.5 | 0.75 | 55.125 | 165.375
| Columns | Cft | 6 | 1.5 | 0.75 | 2 | 13.5 | 40.5
| Plinth Beam | Cft | 2 | 20 | 2.5 | 0.75 | 75 | 225
|  | Cft | 3 | 16 | 2.5 | 0.75 | 90 | 270
[7 empty] | 233.625 | 700.875
OPC | Columns | Cft | 6 | 1.5 | 0.75 | 9.5 | 64.125
| Roof Beam | Cft | 2 | 20 | 2 | 0.75 | 60
|  | Cft | 3 | 16 | 2 | 0.75 | 72
| Roof Slab | Cft | 1 | 20 | 16 | 0.5 | 160
[5 empty] | Total |  | 356.125
| For Six Class Rooms | Cft | 6 | Total Qty |  |  | 2136.75
| Steel @ 3 Kg per cft | [5 empty] | 1769.25
34.8278
| For Six Class Rooms | Cwt | 6 | Total Qty |  |  | 208.9665
4 | Back Filling of Excavated Earth |  |  |  | Total |  | 471.135
| For Six Class Rooms | Cft | 6 | Total Qty |  |  | 2826.81
| Borrow Earth |  |  |  | Total |  | 640
| For Six Class Rooms | Cft | 6 | Total Qty |  |  | 3840
5 | Stone Solling 6" Thick | Cft | 1 | 18.5 | 14.5 | 0.5 | 134.125
[5 empty] | Total |  | 134.125
| For Six Class Rooms | Cft | 6 | Total Qty |  |  | 804.75
| Antitermite Treatment | Rft | 1 | 66 |  |  | 66
[5 empty] | Total |  | 66
| For Six Class Rooms | Rft | 6 | Total Qty |  |  | 396
| PCC For Flooring | Cft | 1 | 18.5 | 14.5 | 0.33 | 88.5225
[5 empty] | Total |  | 88.5225
| For Six Class Rooms | cft | 6 | Total Qty |  |  | 531.135
Terrazzo Flooring
| a) Rooms | sft | 1 | 18.5 |  | 14.5 | 268.25
[5 empty] | Total |  | 268.25
| For Six Class Rooms | sft | 6 | Total Qty |  |  | 1609.5
Brick Masonary
a) Room # 01
| Long Wall | Cft | 2 | 20 | 0.75 | 11.5 | 345
| Short Wall | Cft | 2 | 16 | 0.75 | 11.5 | 276
Deduction
| Door | Cft | 1 | -4 | 0.75 | 7 | -21
| Window | Cft | 3 | -4 | 0.75 | 4 | -36
[5 empty] | Total |  | 564
| For Six Class Rooms | cft | 6 | Total Qty |  |  | 3384
1.2 | Plaster Work
| a) Internal Rooms Walls | sft | 1 | 69 |  | 11.5 | 793.5
| b) External Walls | sft | 1 | 72 |  | 12 | 864
| c) Ceiling Plaster | sft | 1 | 20 |  | 16 | 320
Deduction
| Doors (Both Sides) | sft | 2 | -4 |  | 7 | -56
| Windows (Both Sides) | sft | 6 | -4 |  | 4 | -96
[5 empty] | Total |  | 1825.5
| For Six Class Rooms | sft | 6 | Total Qty |  |  | 10953
1.3 | Interior Painting Work
Painting Plastic Emulsion paint (Internal Wall)
a) Room # 01
| Long Wall | sft | 2 | 18.5 |  | 11.5 | 425.5
| Short Wall | sft | 2 | 14.5 |  | 11.5 | 333.5
Deduction
| Doors (One Sides) | sft | 1 | -4 |  | 7 | -28
| Windows (One Sides) | sft | 3 | -4 |  | 4 | -48
[5 empty] | Total |  | 683
| For Six Class Rooms | Rft | 6 | Total Qty |  |  | 4098
1.4 | Ceiling Paint
Distempering with vinyle distemper (ICI) Dulux / removal of old paint if any
| a) Ceiling | sft | 1 | 18.5 |  | 14.5 | 268.25
[5 empty] | Total |  | 268.25
| For Six Class Rooms | Sft | 6 | Total Qty |  |  | 1609.5
Exterior Paint Work
1.5 | Painting three coats with weather shield paint deluxe (ICI) out side of building
| a) Long Wall | sft | 2 | 20 |  | 12 | 480
| b) Short Wall | sft | 2 | 16 |  | 12 | 384
Deduction
| Doors (One Sides) | sft | 1 | -4 |  | 7 | -28
| Windows (One Sides) | sft | 3 | -4 |  | 4 | -48
[5 empty] | Total |  | 788
| For Six Class Rooms | Sft | 6 | Total Qty |  |  | 4728
1.7 | New Wooden Door provide
| Door (Single Leaf) | sft | 1 | 4 |  | 7 | 28
| Windows | sft | 3 | 4 |  | 4 | 48
[5 empty] | Total |  | 76
| For Six Class Rooms | Sft | 6 | Total Qty |  |  | 456
Frames
| Door (Single Leaf) | sft | 1 | 18 |  | 0.75 | 13.5
| Windows | sft | 3 | 16 |  | 0.75 | 36
[5 empty] | Total |  | 49.5
| For Six Class Rooms | Sft | 6 | Total Qty |  |  | 297
Enamel Paint On door
| Door (Single Leaf) | sft | 1 | 4 |  | 7 | 28
| Windows | sft | 3 | 4 |  | 4 | 48
[5 empty] | Total |  | 76
| For Six Class Rooms | Sft | 6 | Total Qty |  |  | 456
1.8 | Roof screeding
| Roof | sft | 1 | 20 | 16 |  | 320
[5 empty] | Total |  | 320
| For Six Class Rooms | Sft | 6 | Total Qty |  |  | 1920

## Steel schedule
Project Management Implementation Unit (SERP-II) Education and Literacy Deptarment Govt. of Sindh | [9 empty] | District : Jamshoro Talka : Manjhand GBHS Lakhi Shah Sadar
Measurement Sheet
School Name : GBHS Lakhi Shah Sadar | [11 empty] | District : Jamshoro
School ID : 422040184 | [11 empty] | Talka Manjhand
S.no | Description | Mark |  |  |  | Unit | Dia | C/C | No.Site | No. Bar | Cut Length | Total Length | 3/8" | 4/8"
1 | Footing
| Main Bar |  |  |  |  | ft | 4/8" | 6" | 4 | 7 | 3.5 | 98 |  | 98
|  | 0.25 |  |  | 0.25
3
| Distribution bar |  |  |  |  | ft | 4/8" | 6" | 4 | 7 | 3.5 | 98 |  | 98
|  | 0.25 |  |  | 0.25
3
[11 empty] | (ft) | (ft)
2 | Columns
| Vertical Bar |  |  | 0.75 |  | ft | 4/8" | - | 4 | 6 | 17 | 408 |  | 408
15.5
0.75
| Stirrups |  | 1.25 |  |  | ft | 3/8" | 8" | 4 | 23.2733 | 4 | 372.3724 | 372.3724
|  | 0.5 |  | 0.25 | 0.5
1.25
3 | Plinth Beams
Long Span
| Top Bars |  |  |  |  | ft | 4/8" | - | 2 | 2 | 20.75 | 83 |  | 83 | 18.5
|  |  | 19.75 | [11 empty] | 4.625
|  | 0.5 |  |  | 0.5
| Bottom Bars |  |  |  |  | ft | 4/8" | - | 2 | 3 | 20.75 | 124.5 |  | 124.5
|  | 0.5 |  |  | 0.5
19.75
| Stirrups |  | 2.25 |  |  | ft | 3/8" | 6" | 2 | 39.5 | 6 | 474 | 474
|  | 0.5 |  | 0.25 | 0.5
2.25
Short Span
| Top Bars |  |  |  |  | ft | 4/8" | - | 2 | 2 | 16.75 | 67 |  | 67
15.75
|  | 0.5 |  |  | 0.5
| Bottom Bars |  |  |  |  | ft | 4/8" | - | 2 | 3 | 16.75 | 100.5 |  | 100.5
|  | 0.5 |  |  | 0.5
15.75
| Stirrups |  | 2.25 |  |  | ft | 3/8" | 6" | 2 | 31.5 | 6 | 378 | 378
|  | 0.5 |  | 0.25 | 0.5
2.25
4 | Floor Beams
Long Span
| Top Bars |  |  |  |  | ft | 4/8" | - | 2 | 2 | 20.75 | 83 |  | 83
19.75
|  | 0.5 |  |  | 0.5
| Bottom Bars |  |  |  |  | ft | 4/8" | - | 2 | 4 | 20.75 | 166 |  | 166
|  | 0.5 |  |  | 0.5
19.75
| Stirrups |  | 2.25 |  |  | ft | 3/8" | 6" | 2 | 39.5 | 6 | 474 | 474
|  | 0.5 |  | 0.25 | 0.5
2.25
Short Span
| Top Bars |  |  |  |  | ft | 4/8" | - | 2 | 2 | 16.75 | 67 |  | 67
15.75
|  | 0.5 |  |  | 0.5
| Bottom Bars |  |  |  |  | ft | 4/8" | - | 2 | 4 | 16.75 | 134 |  | 134
|  | 0.5 |  |  | 0.5
15.75
| Stirrups |  | 2.25 |  |  | ft | 3/8" | 6" | 2 | 31.5 | 6 | 378 | 378
|  | 0.5 |  | 0.25 | 0.5
2.25
5 | Slab
Rooms
| Main Bar |  |  |  |  | ft | 3/8" | 10" | 2 | 22.2089 | 16.25 | 721.7887 | 721.7887
|  | 0.25 |  |  | 0.25
15.75
| Distribution bar |  |  |  |  | ft | 3/8" | 10" | 2 | 17.407 | 20.25 | 704.982 | 704.982
|  | 0.25 |  |  | 0.25
19.75
| Negative Bar (Short Span) |  |  |  |  | ft | 3/8" | 10" | 2 | 17.407 | 4.875 | 169.7179 | 169.7179
4.625
0.25
| Negative.Dist Bar (Short Span) |  |  |  |  | ft | 3/8" | 10" | 2 | 5.5522 | 7.25 | 80.5072 | 80.5072
7.25
| Negative Bar (Long Span) |  |  |  |  | ft | 3/8" | 10" | 2 | 22.2089 | 3.875 | 172.1188 | 172.1188
3.625
0.25
| Negative Dist. Bar (Long Span) |  |  |  |  | ft | 3/8" | 10" | 2 | 4.3517 | 9.25 | 80.5072 | 80.5072
9.25
Total Length In (Ft) | [12 empty] | 4005.9942 | 1429
Unit Weight (kg/Ft) | [12 empty] | 0.17 | 0.302
Total Weight In Kg | [12 empty] | 681.019 | 431.558