## Civil Summary
Project Management Implementation Unit (SERP-II) Education and Literacy Deptarment Govt. of Sindh |  | District : Jamshoro Talka : Sehwan GBPS Kot Mandi Saeedabad
Government of Sindh,
Education and Litracy Department,
Project Management & Implementation Unit
Region II Hyderabad
Summary Cost of Project Optional
School Name :GBPS Kot Mandi Saeedabad |  | District : Jamshoro
School Id :422020214 |  | Taulka : Sehwan
Sub Head :Civil Work
S.No | Description of Works | COST (Rs.)
1 | Civil Work
i | Civil Work Part-A Sindh Schedule Rate 2012-(A) | 1239007.0445
ii | Civil Work Part -B Non Schedule Rate -(B) | 0
2 | Under Ground Tank
i | Civil Work Part-A Sindh Schedule Rate 2012 -(C) | 4422.5
ii | Civil Work Part -B Non Schedule Rate -(D) | 0
3 | Over Head Tank
i | Civil Work Part-A Sindh Schedule Rate 2012 -(E) | 12048.0533
ii | Civil Work Part -B Non Schedule Rate -(F) | 0
| Sum of Scheduled Item (A+C+E) | 1255477.5978
| Sum of Non Scheduled Items (B+D+F) | 0

## Bill 2 Civil Schedule
Project Management Implementation Unit (SERP-II) Education and Literacy Deptarment Govt. of Sindh |  |  |  |  | District : Jamshoro Talka : Sehwan GBPS Kot Mandi Saeedabad
Bill Of Quantities
School Name :GBPS Kot Mandi Saeedabad |  |  |  |  | District : Jamshoro
School Id :422020214 |  |  |  |  | Talka Sehwan
Bill No. 2(ii)- Civil Works New Construction_School 01
Part-A-Composite Scheduled Rate 2012
Item No. | Description | Unit | T.Quantity | Rate |  | Amount ( Rs.)
|  |  |  | Rs// Unit (In Figure) | Rs// Unit (In Words) | Rs.
1.1 | EARTH WORK IN EXCAVATION
Excavation in foundation of building, bridges and other structures including dagbelling, dressing, refilling around structure with earth watering and ramming lead upto 5ft. (Ch # 01, Page # 4, Item # 18)
| a) In ordinary soil. | Cft | 2970.4981 | 3.18 |  | 9446.184
1.2 | BACK FILLING
1.2.1 | Filling, watering and ramming earth in floors with surplus earth from foundation lead upto one chain and lift upto 5 feet. (Ch # 01, Page # 4, Item # 21) | Cft | 772.5817 | 1.51 |  | 1166.5984
1.2.2 | BORROW PIT
Borrowpit excavation undressed lead upto 100ft. (Ch # 1,Page # 1, Item # 3)
| (a) Ordinary soil | Cft | 1197.9875 | 2.11 |  | 2527.7536
Extra for every 50 ft additional lead or part thereof. This rate shall apply to lead upto 0.50 mile. When the lead is more than 0.50 mile the lead shall be paid under item ( Ch # 1,Page # 2, Item # 8)
| (a) For earth work (soft, ordinary, hard and very hard) | Cft | 1197.9875 | 0.1 |  | 119.7988
Earth work compaction (soft, ordinary or hard soil). (Ch # 1,Page # 3, Item # 13)
| (b) Laying earth in 6" layers levelling, dressing and watering for compaction etc. complete. | Cft | 1197.9875 | 0.35 |  | 419.2956
1.3 | TERMITE PROOFING
| Providing Anti-termmite treatment by spraying /sprinkling /spreading Neptachler 0.5% Emulsion as an overall pre construction treatment in slab type construction along external foundation, trenches of the building over complete parimeter of the foundation trench etc, as per directions of Engineer Incharge. (Ch # 18, Page # 109, Item # 91) | Rft | 270.5 | 40.1 |  | 10847.05
1.4 | CONCRETE WORKS
1.4.1 | Providing and laying lean concrete having 1450 PSI cylindrical strength ( ready mixed concrete) including placing compactng finishing curing compelete and screening and washing of crushed stone aggregate excluding the cost of shuttering.
| (Ch # 18, Page # 111,Item # 98) | Cft | 1836.6724 | 171.97 |  | 315852.5468
1.4.2 | Reinforcement cement concrete work including all labour and material except the cost of steel reinforcement and its labour for bending and binding which will be paid seperately. This rates also includes all kinds of forms moulds, lifting shuttering, curing, rendering and finishing the exposed surface (including screening and washing of shingle). (Ch # 04, Page # 16, Item # 6)
R.C. work in roof slab, beams, columns, rafts, lintels and other structural members laid in situ or precast laid in position complete in all recpects.
a)Super Structure (OPC Cement)
| Ratio (1:2:4) | Cft | 2301.0535 | 337 |  | 775455.0312
1.5 | BLOCK MASONARY
1.5.1 | Precast cement Concrete solid or face blocks (1:2:4) including cost of templates. (Ch # 04, Page # 16, item # 09) | Cft | 564.7215 | 146.06 |  | 82483.2223
1.5.2 | Precast cement Concrete hollow blocks (1:2:4) including cost of templates and constructing walls there of. (Ch # 04, Page # 16, item # 10) | Cft | 2043.0844 | 126.81 |  | 259083.529
1.6 | P.C.C Grill
Proiding and Fixing ornamental Cement Jali 2" thick (1:2:4) without Steel. (Ch # 04, Page # 17, Item # 11)
|  | Sft | 1000 | 226.02 |  | 226020
1.7 | PLASTER WORK
Cement plaster 1:4 upto 12' height plaster. (Ch # 09, Page # 51, Item # 11b)
| (i) 1/2" thick | Sft | 12165.2425 | 22.84 |  | 277854.1387
1.8 | PAINTING WORK
1.8.1 | INTERNAL PAINTING
| (A)Preparing the surface and painting with plastic emulsion paint of approved make I/c rubbing the surface with sand paper , filling the voids with chalk / plaster of paris and then painting etc, complete. (Ch # 09, Page # 55, Item # 40.A) | Sft | 5616.9275 | 10.81 |  | 60718.9863
| (B) 2nd & subsequent coat. (Page # 55) | Sft | 5616.9275 | 5.79 |  | 32522.0102
1.8.2 | CEILING PAINTING
Distempering. (Ch # 09, Page # 53, Item # 24)
| (a) One coat (Ist coat over priming coat) | Sft | 2343.99 | 6.02 |  | 14110.8198
| (b) Two coats. | Sft | 2343.99 | 10.44 |  | 24471.2556
1.8.3 | EXTERNAL PAINTING
| (A)Preparing the serface and painting with weather coat I/c rubbing the surface with rubbing brick / sand paper, filling the voids with chalk / plaster of paris and then painting with weather coat of approved make. (Ch # 09, Page # 55, Item # 38.A) | Sft | 6300.475 | 13.28 |  | 83670.308
| (B) 2nd & subsequent coat. (Page # 55) | Sft | 6300.475 | 6.2 |  | 39062.945
1.9 | FLOORING
1.9.1 | TERRAZZO FLOORING
| Mosaic tiles of grey cement 12" x 12" x 1" of approved shade laid flat in 1:2 white cement mortar over a bed of 3/4" thick lime mortar 1:2. (Ch # 08, Page # 45, Item # 47) | Sft | 2033.5 | 64.85 |  | 131872.475
1.9.2 | TILE FLLOORING
| Laying floors/walls of approved coloured glazed tiles 1/4"thick laid in white cement and pigment on a bed 3/4" thick cement mortar 1:2. (Ch # 08, Page # 42, item # 25) | Sft. | 611.185 | 277.47 |  | 169585.502
1.9.3 | Cement concrete plain including placing, compacting, finishing and curing complete (including screening and washing at stone aggregate without shuttering). (Ch # 04, Page # 16, Item # 5)
| Ratio 1:2:4 | Cft | 1058.0575 | 144.3 |  | 152677.6972
1.1 | DOORS AND WINDOWS
1.10.1 | Supplying and fixing in position doors, windows and ventilators, of 1st. Class deodar wood frame and 1-1/2" thick Teak wood ply shutter of 2nd class deodar wood skeleton (Solid) style and rails core of partal wood and Teak ply wood (2-ply) on both side i/c hold fasts,hinges, iron tower bolts, handles and cleans with cord etc complete. | Sft | 583 | 1182.56 |  | 689432.48
1.10.2 | Painting doors and windows any type
Preparing surface and painting of doors and windows any type (including edges)
| (i) Priming coat | Sft | 1166 | 8.62 |  | 10050.92
| (ii) each subsequent coat o fpaint | Sft | 1166 | 6.26 |  | 7299.16
Scheduled Item (Page # 67,item # 5c)
1.11 | STONE SOLLING
| Stone masonary dry hand packed as filling behind retaining wall or in pitching and approns.(Ch # 06, Page # 30, Item # 16). | Cft | 1197.9875 | 26.84 |  | 32153.9845
1.12 | ROOF TREATMENT
| Providing and fixing bitumen felt paper of 60 Lbs over roof I/c cleaning of roof with wire brush an removing dust, applying bitumen coat at the rate of 34 Lbs per % sft as premix inter coats and then laying felt paper with 10% over laps, then applying and spreading hill sand at the rate of 1 cft for 100 sft. The cost also i/c necessary fire material,kerosene oil, wood etc. (Ch # 07, Page # 37, Item # 41) | Sft | 2390.875 | 54.7 |  | 130780.8625
1.13 | PLINTH PROTECTION
1.13.1 | Cement concrete plain including placing, compacting, finishing and curing complete (including screening and washing at stone aggregate without shuttering). (Ch # 4,Page # 15, Item # 5) | Cft | 171.765 | 112.89 |  | 19390.5509
(i) Ratio 1:4:8
1.13.2 | Providing and laying 1" thick topping cement concrete (1:2:4) including surface finishing and dividing into panels. (Ch # 08, Page # 41, Item # 16c) | Sft | 520.5 | 32.76 |  | 17051.58
(c) 2" thick
1.14 | PAVERS ON WALKWAY
| Providing & fixing cement paving blocks flooring having size of 197 x 97 x 60 (mm) of city / quddra / cobble shape with natural colour, having strength between 5000 psi to 8500 psi I/c filling the joints with hill sand and laying in specified manner / pattern and design etc. (ch # 08, page # 48, item # 71). | Sft | 600 | 199.77 |  | 119862
1.15 | SUB BASE
| Preparing sub base coarse by suppying and spreading stone metal 1-1/2"-2"guage of approved quality from approved quarry in required thickness to proper camber and grade including hand packing filling voids 20 cft of pit canal sand having plasticity index more than 6% of suitable quality, watering and compacting to achieve 98-100% density as per modify AASHO specification (rate includes all cost of material T & P and carriage upto 3 chains).(Highways Work, Finished Item, Page # 03, Item # 11). | Cft | 480 | 43.8176 |  | 21032.448
[5 empty] | Total Amount Bill No.2(ii) Part-A_Class Room Rs. | 3717021.1334
Carried Farward to Summary

## Bill 2 Civil Non Schedule
Project Management Implementation Unit (SERP-II) Education and Literacy Deptarment Govt. of Sindh |  |  |  |  | District : Jamshoro Talka : Sehwan GBPS Kot Mandi Saeedabad
Bill Of Quantities
School Name :GBPS Kot Mandi Saeedabad |  |  |  |  | District : Jamshoro
School Id :422020214 |  |  |  |  | Talka Sehwan
Bill No. 2(ii)- Civil Works New Construction_School 01
Part-B-Non Scheduled Rates
Item No. | Description | Unit | T.Quantity | Rate |  | Amount ( Rs.)
|  |  |  | Rs// Unit (In Figure) | Rs// Unit (In Words) | Rs.
1.1 | CONCRETE WORKS
Reinforcement cement concrete work including all labour and material except the cost of steel reinforcement and its labour for bending and binding which will be paid seperately. This rates also includes all kinds of forms moulds, lifting shuttering, curing, rendering and finishing the exposed surface (including screening and washing of shingle). (Page # 16, Item # 6)
| R.C. work in roof slab, beams, columns, rafts, lintels and other structural members laid in situ or precast laid in position complete in all recpects. | [5 empty] | 12.9021
| Sub Structure (SR Cement Ratio 1:2:4) | [5 empty] | 141.9229
| a) Foundation | Cft | 264 |  |  | 0
| b)Columns up to Plinth | Cft | 60.049 |  |  | 0
| c)Plinth Beam | Cft | 653.3525 |  |  | 0
| d)Wall upto Plinth | Cft | 713.28 |  |  | 0
1.2 | STEEL REINFORCEMENT
| (a) Fabrication of Deformed bars reinforcement for cement concrete including cutting, bending, laying in position, making joints and fastenings including cost of binding wire (also includes removal of rust from bars | Tons | 9.76 |  |  | 0
1.3 | RAMP
| Construction of concrete 4 feet wide ramp with required slope for disabled children for access in school building, complete in all aspect , work include backfilling of material and placing 4 inch 1:2:4 concrete in alternate panel of 20 N/M concrete finishing job also include fixing of steel railing with one coat of red oxide paint and two coat of approved enamel paint as per drawing and specification | Job | 1 |  |  | 0
1690.6815
[5 empty] | Total Amount Bill No.2(ii) Part-B_School 1 Rs. | 0
Carried Farward to Summary

## OHT_New_ Sched
Project Management Implementation Unit (SERP-II) Education and Literacy Deptarment Govt. of Sindh |  |  |  |  | District : Jamshoro Talka : Sehwan GBPS Kot Mandi Saeedabad
Bill Of Quantities
School Name :GBPS Kot Mandi Saeedabad |  |  |  |  | District : Jamshoro
School Id :422020214 |  |  |  |  | Talka Sehwan
Bill No. 2(ii)- Civil Works New Construction_Over Head water Tank
Part-A-Composite Scheduled Rate 2012
Item No. | Description | Unit | T.Quantity | Rate |  | Amount ( Rs.)
|  |  |  | Rs// Unit (In Figure) | Rs// Unit (In Words) | Rs.
1.1 | R.C.C. CONCRETE
Reinforcement cement concrete work including all labour and material except the cost of steel reinforcement and its labour for bending and binding which will be paid seperately. This rates also includes all kinds of forms moulds, lifting shuttering, curing, rendering and finishing the exposed surface (including screening and washing of shingle). (Ch # 04,Page # 16, Item # 6)
R.C. work in roof slab, beams, columns, rafts, lintels and other structural members laid in situ or precast laid in position complete in all recpects.
Super Structure (OPC Cement)
| (i) Ratio (1:2:4) | Cft | 92 | 337 |  | 31004
[7 empty] | #REF! | Steel
1.2 | EXTERNAL PAINTING
| (A)Preparing the serface and painting with weather coat I/c rubbing the surface with rubbing brick / sand paper, filling the voids with chalk / plaster of paris and then painting with weather coat of approved make. (Ch # 09,Page # 55, Item # 38.A) | Sft | 192 | 13.28 |  | 2549.76
| (B) 2nd & subsequent coat. (Ch # 09,Page # 55) | Sft | 192 | 6.2 |  | 1190.4
1.3 | Providing C.I Manhole Cover & Frame i/c cost of material (Ch: P.Health Page#35,Item # J-1 | Kg | 10 | 140 |  | 1400
[5 empty] | Total Amount Bill No.2(ii) Part-A_OHT Rs. | 36144.16
Carried Farward to Summary

## OHT_New_ Non Scheduled
Project Management Implementation Unit (SERP-II) Education and Literacy Deptarment Govt. of Sindh |  |  |  |  | District : Jamshoro Talka : Sehwan GBPS Kot Mandi Saeedabad
Bill Of Quantities
School Name :GBPS Kot Mandi Saeedabad |  |  |  |  | District : Jamshoro
School Id :422020214 |  |  |  |  | Talka Sehwan
Bill No. 2(ii)- Civil Works New Construction_Over Head water Tank
Part-B-Non Scheduled Items
Item No. | Description | Unit | T.Quantity | Rate |  | Amount ( Rs.)
|  |  |  | Rs// Unit (In Figure) | Rs// Unit (In Words) | Rs.
1.1 | PLASTER WORK
| Providing and applying cement plaster 1/2" thick in 1:4 cement sand mortar with Pudlo 5 lbs of pudlo per bag of cement for Over Head Water Tank & Under Ground Water Tank include all corners, recesses, jams and racking mortar to walls, and base etc. and making of chamfer on all corner of UGWT, OHWT .and water curing as per engineering Specification | Sft | 302 |  |  | 0
1.2 | STEEL REINFORCEMENT
| (a) Fabrication of Deformed bars reinforcement for cement concrete including cutting, bending, laying in position, making joints and fastenings including cost of binding wire (also includes removal of rust from bars | Tons | 0.276 |  |  | 0
1.3 | Supply and fixing of Pvc 6" wide water stopper | Rft | 22 |  |  | 0
[5 empty] | Total Amount Bill No.2(ii) Part-B_OHT Rs. | 0
Carried Farward to Summary

## Civil_New_UGT_ Sched
Project Management Implementation Unit (SERP-II) Education and Literacy Deptarment Govt. of Sindh |  |  |  |  | District : Jamshoro Talka : Sehwan GBPS Kot Mandi Saeedabad
Bill Of Quantities
School Name :GBPS Kot Mandi Saeedabad |  |  |  |  | District : Jamshoro
School Id :422020214 |  |  |  |  | Talka Sehwan
Bill No. 2(ii)- Civil Works New Construction_Under Ground Water Tank
Part-A-Composite Scheduled Rate 2012
Item No. | Description | Unit | T.Quantity | Rate |  | Amount ( Rs.)
|  |  |  | Rs// Unit (In Figure) | Rs// Unit (In Words) | Rs.
1.1 | EARTH WORK IN EXCAVATION
Excavation in foundation of building, bridges and other structures including dagbelling, dressing, refilling around structure with earth watering and ramming lead upto 5ft. (Page # 4, Item # 18)
| In ordinary soil. | Cft | 600 | 3.18 |  | 1908
1.2 | BACK FILLING
| Filling, watering and ramming earth in floors with surplus earth from foundation lead upto one chain and lift upto 5 feet. (Page # 4, Item # 21) | Cft | 180 | 1.51 |  | 271.8
1.3 | CONCRETE WORKS
1.3.1 | Providing and laying lean concrete having 1450 PSI cylindrical strength ( ready mixed concrete) including placing compactng finishing curing compelete and screening and washing of crushed stone aggregate excluding the cost of shuttering.
| (Page # 111,Item # 98) | Cft | 50 | 171.97 |  | 8598.5
1.4 | BITUMEN COATING
| Bitumen coating to plastered or cement concrete surface. (Page # 70,item # 9) | Sft | 140 | 7.78 |  | 1089.2
1.5 | Providing C.I Manhole Cover & Frame i/c cost of material (Ch: P.Health Page#35,Item # J-1 | Kg | 10 | 140 |  | 1400
[5 empty] | Total Amount Bill No.2(ii) Part-A_UGT Rs. | 13267.5
Carried Farward to Summary

## civil_New_UGT_Non_Scheduled
Project Management Implementation Unit (SERP-II) Education and Literacy Deptarment Govt. of Sindh |  |  |  |  | District : Jamshoro Talka : Sehwan GBPS Kot Mandi Saeedabad
Bill Of Quantities
School Name :GBPS Kot Mandi Saeedabad |  |  |  |  | District : Jamshoro
School Id :422020214 |  |  |  |  | Talka Sehwan
Bill No. 2(ii)- Civil Works New Construction_Under Ground Water Tank
Part-A-Composite Scheduled Rate 2012
Item No. | Description | Unit | T.Quantity | Rate |  | Amount ( Rs.)
|  |  |  | Rs// Unit (In Figure) | Rs// Unit (In Words) | Rs.
1 | CONCRETE WORKS
1.1 | Reinforcement cement concrete work including all labour and material except the cost of steel reinforcement and its labour for bending and binding which will be paid seperately. This rates also includes all kinds of forms moulds, lifting shuttering, curing, rendering and finishing the exposed surface (including screening and washing of shingle). (Page # 16, Item # 6)
R.C. work in roof slab, beams, columns, rafts, lintels and other structural members laid in situ or precast laid in position complete in all recpects.
| With SR Cement Ratio 1:2:4 | Cft
| a) Foundation |  | 32 |  |  | 0
| b) Walls |  | 75 |  |  | 0
| c) Slab |  | 32 |  |  | 0
139
1.2 | PLASTER WORK
| Providing and applying cement plaster 1/2" thick in 1:4 cement sand mortar with Pudlo 5 lbs of pudlo per bag of cement for Over Head Water Tank & Under Ground Water Tank include all corners, recesses, jams and racking mortar to walls, and base etc. and making of chamfer on all corner of UGWT, OHWT .and water curing as per engineering Specification | Sft | 238 |  |  | 0
1.3 | STEEL REINFORCEMENT
| (a) Fabrication of Deformed bars reinforcement for cement concrete including cutting, bending, laying in position, making joints and fastenings including cost of binding wire (also includes removal of rust from bars | Ton | 0.366 |  |  | 0
1.4 | Supply and fixing of Pvc of 6" water stopper | Rft | 24 |  |  | 0
[5 empty] | Total Amount Bill No.2(ii) Part-B_UGT Rs. | 0
Carried Farward to Summary

## Bill 3_Plumbing_Sched
Project Management Implementation Unit (SERP-II) Education and Literacy Deptarment Govt. of Sindh |  |  |  |  | District : Jamshoro Talka : Sehwan GBPS Kot Mandi Saeedabad
Bill Of Quantities
School Name :GBPS Kot Mandi Saeedabad |  |  |  |  | District : Jamshoro
School Id :422020214 |  |  |  |  | Talka Sehwan
Bill No. 3 Plumbing Work
Part-A-Composite Scheduled Rate 2012
Item No. | Description | Unit | T.Quantity | Rate |  | Amount ( Rs.) | Sindh Scheduled Items (2012) | Non Scheduled Items | unit | Schedule rates | Convert per sft/cft
|  |  |  | Rs// Unit (In Figure) | Rs// Unit (In Words) | Rs.
1.1 | MANHOLE OR INSPECTION CHAMBER
| Construction manhole or inspection chamber for the required diameter of circular sewer and 3'-6" depth and with walls of B.B in cement sand mortar 1:3 cement plastered 1:3, 1/2: thick inside of walls and 1" thick oer benching and channel i/c fixing C.I manhole cover with frame of clear opening 1-1/2" x 1-1/2" of 1.75 cwt embaded in plain C.C 1:2:4 and fixing 1" dia M.S steps 6" wide projecting 4" from the face of wall at 12" C/C duly painted etc. Complete as per standard specification and drawing. (Page # 46, Item # P) | No | 1 | 13310.2 |  | 13310.2
(a) 4" x 12" dia. 2' x 2' x 2'-6"
1.2 | BIB COCK
Supplying & fixing in position C.P. Bib cock. ( For Water supply & Sanitary Items,Ch # 06,Page # 2, Item # 2- I))
| (b) 1/2" dia C.P. bib cock, standard pattern. | No | 5 | 150.92 |  | 754.6
1.3 | ASIAN WATER CLOSET
Providing and fixing squating type white glazed earthern ware w.c. pan with including the cost of flushing cistern with internal fitting and flush pipe with bend & making requisite number of holes in walls plinth & floor for pipe connections & making good in cement concrete 1:2:4. Ch # 01, For Water supply & Sanitary Items,Page # 1, Item # 1)
| B (i) W.C of not less than 19" clear opening between flushing rims and 3 gallons flushing tank with 4" dia. C.I. trap and C.I. thumble. | No | 2 | 4802.6 |  | 9605.2
1.4 | WASH HAND BASIN
| Providing and fixing 24" x 18" lavatory basin in white glazed earthern ware complete with & I/c the cost W.T. or C.I. cantilever brackets 6 inches built into wall, painted white in two coats after a primary coat of red lead paint, a pair of 1/2" dia rubber plug & chrome plate brass chain 1-1/4" dia malloable iron or c.p brass traps malloable iron or brass unions and making requisite number of holes in walls, olinth & floor for pipe connection and making good in cement concrete 1:2:4 (Standard pattern). ( Ch # 01, For Water supply & Sanitary Items,Page # 3 ,Item # 8) | No | 2 | 4253.7 |  | 8507.4
1.5 | UPVC PIPES AND FITTINGS
Providing, laying Upvc pressure pipes of Class 'B' (equivalent make) fixing in trench i/c cutting, fitting and jointing with "Z" joint with one rubber ring i/c testing with water to a head 61 meter or 200ft. (P.Health Engineering ,Ch # II,Page # 22, Item # E-1)
| b) 4" dia. | Rft | 40 | 137 |  | 5480
| c) 6" dia. | Rft | 90 | 262 |  | 23580
1.6 | FLOOR TRAP
| Providing and fixing C.I. trap with 4" dia inlet and 4" dia outlet of the approved self cleaning design with a C.I. grating with or without a vent arm including cost of making requiste number of holes in walls, plinth & floor for pipe connection and making goood cement concrete 1:2:4. (Page # 6, Item # 21) | No | 8 | 1671.58 |  | 13372.64
1.7 | GULLY TRAP
Providing and fixing 6" x 4" C.C. gully trap with 4" outlet complete with 4" thick 1:2:4 for bed & 1/2" thick cement plaster (1:3) to the karb, C.I. grating 6" x 6" & C.I. cover and frame 12" x 12" (inside) etc. complete. (Page # 24, Item # 1)
C.C.Gully Trap 6" x 6" x 4"
| (i) With C.I. Cover & frame. | No | 6 | 2386.34 |  | 14318.04
1.8 | EUROPEAN WATER CLOSET
| Providing and fixing eureopean type white glazed earthern ware wash down w.c. pan complete with & I/c cost of white/black plastic seat (Best quality) & lid with c.p brass hinges best quality and buffers 3 gallons plastic flushing cistern with internal fitting and clamo 3/4" dia. and cutting & making requisite number of holes in walls, plinth & floor for pipe connection & making good in cement concrete 1:2:4. (Ch # 01, For Water supply & Sanitary Items,,Page # 2, Item # 4) | No | 1 | 5339.4 |  | 5339.4
[5 empty] | Total Amount Bill No.3 Part-A Rs. | 94267.48
Carried Farward to Summary

## Bill 3_Plumbing_Non Sched
Project Management Implementation Unit (SERP-II) Education and Literacy Deptarment Govt. of Sindh |  |  |  |  | District : Jamshoro Talka : Sehwan GBPS Kot Mandi Saeedabad
Bill Of Quantities
School Name :GBPS Kot Mandi Saeedabad |  |  |  |  | District : Jamshoro
School Id :422020214 |  |  |  |  | Talka Sehwan
Bill No. 3 Plumbing Work
Part-B-Non Scheduled Rates
Item No. | Description | Unit | T.Quantity | Rate |  | Amount ( Rs.) | Sindh Scheduled Items (2012) | Non Scheduled Items | unit | Schedule rates | Convert per sft/cft
|  |  |  | Rs// Unit (In Figure) | Rs// Unit (In Words) | Rs.
1.1 | PPRC PIPES AND FITTINGS
S/I of PPRC (Polypropylene Random Copolymer pipe Pak Arab, Karachi Pipe. make or equivalent (light quality) of following diameters.
| i) 5/8" dia | Rft | 60 |  |  | 0
| ii) 1" dia | Rft | 80
1.2 | PUMP
| S/I of Centrifugal Horizontal pumping set - motor 1 Hp. | No | 1 |  |  | 0
[5 empty] | Total Amount Bill No.3 Part-A Rs. | 0
Carried Farward to Summary

## Bill 4 Elect sched
Project Management Implementation Unit (SERP-II) Education and Literacy Deptarment Govt. of Sindh |  |  |  |  | District : Jamshoro Talka : Sehwan GBPS Kot Mandi Saeedabad
Bill Of Quantities
School Name :GBPS Kot Mandi Saeedabad |  |  |  |  | District : Jamshoro
School Id :422020214 |  |  |  |  | Talka Sehwan
School: GBPS Wali Muhammad Laghari
School ID: 402030259
Item No. | Description | Unit | T.Quantity | Rate |  | Amount ( Rs.)
|  |  |  | Rs// Unit (In Figure) | Rs// Unit (In Words) | Rs.
1.1 | WIRING FOR LIGHT OR FAN POINT
| Wiring for light or fan point with 1/1.13 (3/0.029") PVC insulated wire in 20mm(3/4") channel patti on surface as required. (Electrical Works, Sub Head II,Point Wiring,Page # 15, Item # 129) | Point | 37 | 910 |  | 33670
1.2 | WIRING FOR PLUG POINT
| Wiring for plug point with 1/1.13 (3/0.029") PVC insulated wire in 20mm(3/4") channel patti as required. (Electrical Works, Sub Head II,Point Wiring,Page # 15, Item # 130) | Point | 8 | 742 |  | 5936
1.3 | POWER CABLE
| Providing and laying (Main or Sub Main) PVC insulated with size 2-7/.064 (16mm2) copper conductor in 1" dia PVC conduit on surface. (Electrical Works, Sub Head I,Mains & Sub Mains Page # 1, Item # 7) | Rft | 70 | 184.4 |  | 12908
1.4 | FLUSH TYPE SWITCHES
| Providing and fixing one way SP 5amp switch surface type. (Electrical Works, Sub Head Xi,Electrical Accessories, Page # 33, Item # 216) | No | 8 | 34 |  | 272
1.5 | 2 PIN, 5 AMPS PLUG- SOCKET
| Providing and fixing two pin 5amp plug & socket. (Electrical Works, Sub Head Xi,Electrical Accessories,Page # 33, Item # 222) | No | 8 | 80 |  | 640
1.6 | 3 PIN, 15 AMPS PLUG- SOCKET
| Providing and fixing f3 pin 10/15amp plug & socket. (Electrical Works, Sub Head Xi,Electrical Accessories,Page # 33, Item # 224) | No | 2 | 151 |  | 302
1.7 | CEILING FANS
| Providing and fixing brass ceiling fan 56" (good quality). (Electrical Works, Sub Head Xi, Electrical Accessories,Page # 34, Item # 235) | No | 8 | 3185 |  | 25480
1.8 | JUNCTION BOX
Providing and fixing junction box as per following specification following:
| Size of box 8" x 6" x 4", MS plate size 16 SWG thick, clamp with nuts & bolts, cover plate with screw, painting two coats of rust preventive red oxide & two coats of ICI oil paint as per site requirement & instruction of EI. (Electrical Works, Sub Head VI Junction Box,Page # 24, Item # 158) | No | 1 | 800 |  | 800
1.9 | SUB HEAD CIRCUIT BREAKERS
| Providing and fixing circuit breakers 10,20SP (TB-5S) on prepared board as required. (Electrical Works, Sub Head X Circuit Breakers,Page # 31, Item # 203) | No | 3 | 916 |  | 2748
| Providing and fixing circuit breakers 10,20,30,40,50 & 60 amp TP (XE-100CS) on prepared board as required. (Electrical Works, Sub Head X Circuit Breakers,Page # 31, Item # 206) | No | 6 | 5521 |  | 33126
1.1 | CEILING ROSE
| Providing and fixing ceiling rose with two terminals. (Electrical Works, Sub Head XI Electrical Accessories,Page # 33, Item # 228) | No | 8 | 72 |  | 576
[5 empty] | Total Amount Bill No.4 Part-A Rs. | 116458
Carried Farward to Summary

## Bill 4 Elect Non Sched
Project Management Implementation Unit (SERP-II) Education and Literacy Deptarment Govt. of Sindh |  |  |  |  | District : Jamshoro Talka : Sehwan GBPS Kot Mandi Saeedabad
Bill Of Quantities
School Name :GBPS Kot Mandi Saeedabad |  |  |  |  | District : Jamshoro
School Id :422020214 |  |  |  |  | Talka Sehwan
Bill No. 4 Electrical Work
Part-B-Non Scheduled Rates
Item No. | Description | Unit | T.Quantity | Rate |  | Amount ( Rs.)
|  |  |  | Rs// Unit (In Figure) | Rs// Unit (In Words) | Rs.
1.1 | FAN CLAMPS
| Providing and fixing mild steel bar fan clamps 15.8 mm (5/8") dia suitable for R.C.C. roof | No. | 8 |  |  | 0
1.2 | EARTHING SET
| P/F earthing set with 2'x 2'x 1/2" copper plate burried in ground at a depth of 12 or less f water comes out fronm the ground level with salt and chorcoal, etc ,in/c. making the pit 12" deep by excavation of all type of soil. Earth plate to be connected with No. 8 S.W.G. bare copper wire run in 1/2" G.L. pipe straght from the earth plate upto the metallic Electrical assesary i/e providing necessary Tee. | Job | 1 |  |  | 0
1.3 | EARTH CONDUCTOR
| providing & fixing hard drawn bare copper wire no.10 S.w.g. as earth continuity with any given mains or sub-mains in all system of wiring including metallic Electrical assesary. | Rft | 80 |  |  | 0
1.4 | LIGHT FIXTURE
| Providing and fixing bulb holder complete with 23 watts philips CFL i/c necessary electric connection and fixing on wall or ceiling etc. | No | 29 |  |  | 0
1.5 | DISTRIBUTION BOARD
Supply, installation, connection of wires/cables, testing and commissioning of 500 volts, 50 Hz, 3-Phase and neutral distribution boards (DBs) concealed type, wall mounted to be installed as and where shown on drawings,made of M.S. sheet 16 SWG with hinged door, handle, catcher, earthing bar, neutral strip, internal wiring from MCCBs terminating on cable terminal blocks. One coat of antirust and anti-corrosive paint with further two coats of enamelled paint of approved colour, all necessary materials complete in all respects and manufactured by any one of the approved manufacturers: conforming to single line diagram. D.B
| 4-Ways, 3-Phase | Job | 1 |  |  | 0
[5 empty] | Total Amount Bill No.4 Part-B Rs. | 0
Carried Farward to Summary

## Bill 5 Supply Material
Project Management Implementation Unit (SERP-II) Education and Literacy Deptarment Govt. of Sindh |  |  |  |  | District : Jamshoro Talka : Sehwan GBPS Kot Mandi Saeedabad
Bill Of Quantities
School Name :GBPS Kot Mandi Saeedabad |  |  |  |  | District : Jamshoro
School Id :422020214 |  |  |  |  | Talka Sehwan
Bill: Supply Of Material
Part-B-Non Scheduled Rates
Item No. | Description | Unit | T.Quantity | Rate |  | Amount ( Rs.)
|  |  |  | Rs// Unit (In Figure) | Rs// Unit (In Words) | Rs.
1.1 | Supplying installation and testing of fire extinguisher CO2.
|  | No | 2 |  |  | 0
1.2 | Supplying installation and testing of fire extinguisher dry cheical powder (6Kg).
|  | No | 1 |  |  | 0
[5 empty] | Total Amount Bill Part -B Rs. | 0
Carried Farward to Summary

## Measuremnt
Project Management Implementation Unit (SERP-II) Education and Literacy Deptarment Govt. of Sindh |  |  |  | District : Jamshoro Talka : Sehwan GBPS Kot Mandi Saeedabad
Measurement Sheet
School Name :GBPS Kot Mandi Saeedabad |  |  |  |  | District : Jamshoro
School Id :422020214 |  |  |  |  | Talka Sehwan
SCHOOL: New Construction
Sr# | Description | Units | Qty | L (ft) | B (ft) | H (ft) | Total Qty | Remarks
1 | Renovation Work
Excavation
|  | Cft |  |  |  |  | 2970.4981
[5 empty] | Total |  | 2970.4981
2 | Lean Concrete
1450 Psi
|  | Cft |  |  |  |  | 507.2349
| Above Beginning Lev | Cft |  |  |  |  | 1329.4375
[5 empty] | Total |  | 1836.6724
SRC | 3000 Psi
|  | Cft |  |  |  |  | 713.28
[5 empty] | Total |  | 713.28
3 | RCC
SRC | Foundation | Cft |  |  |  |  | 264
| Columns | Cft |  |  |  |  | 60.049
| Plinth Beam | Cft |  |  |  |  | 653.3525
[5 empty] | Total |  | 977.4015
OPC | Columns above Plinth | Cft |  |  |  |  | 295.0448
| Roof Beam | Cft |  |  |  |  | 653.3525
| Roof Slab | Cft |  |  |  |  | 1195.4375
[5 empty] | Total |  | 2143.8348
Steel
|  | kg |  |  |  |  | 9760
|  | Tons |  |  |  |  | 9.76
4 | Back Filling of Excavated Earth |  |  |  | Total |  | 772.5817
Borrow Earth
| Classes Block | Cft | 1 | 51 | 36.6 | 0.5 | 933.3
| Staff-Toilet Block | Cft | 1 | 30.25 | 17.5 | 0.5 | 264.6875
[5 empty] | Total |  | 1197.9875
5 | Stone Solling 6" Thick
| Classes Block | Cft | 1 | 51 | 36.6 | 0.5 | 933.3
| Staff-Toilet Block | Cft | 1 | 30.25 | 17.5 | 0.5 | 264.6875
[5 empty] | Total |  | 1197.9875
Antitermite Treatment
| Classes Block | Rft | 1 | 175 |  |  | 175
| Staff-Toilet Block | Rft | 1 | 95.5 |  |  | 95.5
[5 empty] | Total |  | 270.5
PCC For Flooring
| Classes Block | CFT | 1 | 51 | 36.5 | 0.25 | 465.375
| Staff-Toilet Block | CFT | 1 | 30.25 | 17.5 | 0.25 | 132.3438
[5 empty] | Total |  | 597.7188
Terrazzo Flooring
| Classes Block | sft | 1 | 51 | 36.5 |  | 1861.5
| Staff block | sft | 1 | 16 | 10.75 |  | 172
[5 empty] | Total |  | 2033.5
Tile Flooring
Floor
| Filter Plant | sft | 1 | 7.5 | 5.33 |  | 39.975
| Staff Toilet | sft | 1 | 8 | 5.33 |  | 42.64
| Girls Toilet | sft | 1 | 5 | 5 |  | 25
| Boys Toilet | sft | 1 | 5 | 5 |  | 25
| Toil Passage | sft | 1 | 5 | 5.33 |  | 26.65
Walls
Filter Plant
| Long wall | sft | 2 | 7.5 |  | 4 | 60
| Short Wall | sft | 2 | 5.33 |  | 4 | 42.64
Staff Toilet
| Long wall | sft | 2 | 8 |  | 4 | 64
| Short Wall | sft | 2 | 5.33 |  | 4 | 42.64
Girls Toilet
| Long wall | sft | 2 | 5 |  | 4 | 40
| Short Wall | sft | 2 | 5 |  | 4 | 40
Boys Toilet
| Long wall | sft | 2 | 5 |  | 4 | 40
| Short Wall | sft | 2 | 5 |  | 4 | 40
Toil Passage
| Long wall | sft | 2 | 5 |  | 4 | 40
| Short Wall | sft | 2 | 5.33 |  | 4 | 42.64
[5 empty] | Total |  | 611.185
Block Masonary
| 8" Thick Hollow | Cft |  |  |  |  | 2043.0844
| 6" Thick Wall Block | Cft |  |  |  |  | 381.8125
| 4" Thick Wall Block | Cft |  |  |  |  | 132.909
| Walk Way Edges | Cft |  |  |  |  | 50
564.7215
1.2 | Plaster Work
| a) Internal Rooms Walls | [5 empty] | 5520.7775 |  | 571
| b) External Walls | [5 empty] | 2343.99 |  | 0.070312
| c) Ceiling Plaster | [5 empty] | 4300.475 |  | 40.1484
[5 empty] | Total |  | 12165.2425
1.3 | Interior Painting Work
Painting Plastic Emulsion paint (Internal Wall)
[5 empty] | Total |  | 5616.9275
1.4 | Ceiling Paint
Distempering with vinyle distemper (ICI) Dulux / removal of old paint if any
[5 empty] | Total |  | 2343.99
Exterior Paint Work
1.5 | Painting three coats with weather shield paint deluxe (ICI) out side of building
[5 empty] | Total |  | 6300.475
1.7 | New Wooden Door and Window provide
| D1 (Single Leaf) | sft | 7 | 3.5 |  | 8 | 196
| D2 (Single Leaf) | sft | 2 | 2.5 |  | 8 | 40
| DW door with window | sft | 2 | 2.5 |  | 8 | 40
|  | sft | 2 | 2 |  | 4 | 16
| W1 | sft | 12 | 3.5 |  | 5.5 | 231
| W2 (Double Leaf) | sft | 1 | 6 |  | 6 | 36
| W3 | sft | 1 | 4 |  | 4 | 16
| V1 | sft | 1 | 2 |  | 4 | 8
[5 empty] | Total |  | 583
Frames
| D1 (Single Leaf) | sft | 7 | 19.5 |  | 0.75 | 102.375
| D2 (Single Leaf) | sft | 2 | 18.5 |  | 0.75 | 27.75
| DW door with window | sft | 2 | 18.5 |  | 0.75 | 27.75
|  | sft | 2 | 12 |  | 0.75 | 18
| W1 | sft | 12 | 18 |  | 0.75 | 162
| W2 (Double Leaf) | sft | 1 | 24 |  | 0.75 | 18
| W3 | sft | 1 | 16 |  | 0.75 | 12
| V1 | sft | 1 | 12 |  | 0.75 | 9
[5 empty] | Total |  | 376.875
Enamel Paint On door
| D1 (Single Leaf) | sft | 14 | 3.5 |  | 8 | 392
| D2 (Single Leaf) | sft | 4 | 2.5 |  | 8 | 80
| DW door with window | sft | 4 | 2.5 |  | 8 | 80
|  | sft | 4 | 2 |  | 4 | 32
| W1 | sft | 24 | 3.5 |  | 5.5 | 462
| W2 (Double Leaf) | sft | 2 | 6 |  | 6 | 72
| W3 | sft | 2 | 4 |  | 4 | 32
| V1 | sft | 2 | 2 |  | 4 | 16
[5 empty] | Total |  | 1166
1.8 | Roof screeding
| Classes Block | sft | 1 | 51 | 36.5 |  | 1861.5
| Staff-Toilet block | sft | 1 | 30.25 | 17.5 |  | 529.375
[5 empty] | Total |  | 2390.875
1.9 | Plinth Protection
| Classes Block | sft | 1 | 138.5 |  | 3 | 415.5
| Staff-Toilet block | sft | 1 | 35 |  | 3 | 105
[5 empty] | Total |  | 520.5
1.1 | R.C.C Pergola
| Rooms Side | Cft | 11 | 16 | 0.75 | 0.75 | 99
| Boundary Side | Cft | 9 | 11.5 | 0.75 | 0.75 | 58.2188
[5 empty] | Total |  | 157.2188
1.11 | P.C.C Grill
| PCC Grill | Sft | 4 | 16 |  | 10 | 640
| PCC Grill | Sft | 6 | 6 |  | 10 | 360
[5 empty] | Total |  | 1000
1.12 | Walk Way
|  | Sft | 1 | 100 | 6 |  | 600
[5 empty] | Total |  | 600

## Calculation (hidden)
Proposed School 1 Govt
S.No | Description | Unit | Qty | Length | Bredith | Height | Total
1 | Excavation
| Footing | CFT | 24 | 4.666 | 4.666 | 4 | 2090.0694
Plinth Beam
| A/1-2,2-3,3-4,5-6 B/1-2,2-3,3-4 | CFT | 7 | 5.75 | 1.5 | 2 | 120.75
| B/1-2,2-3 C/2-3,3-4 | CFT | 4 | 15.666 | 1.5 | 2 | 187.992
| B/3-4,5-6 C/1-2,5-6 | CFT | 4 | 15.25 | 1.5 | 1.5 | 137.25
| B-C/5-6 | CFT | 1 | 16.75 | 1.5 | 1.5 | 37.6875
| B-C/1,2,3,4,5,6 | CFT | 6 | 21.25 | 1.5 | 1.5 | 286.875
| D-E/5 & 6 | CFT | 2 | 16.75 | 1.5 | 1.5 | 75.375
| E/5-6 | CFT | 1 | 15.333 | 1.5 | 1.5 | 34.4993
2970.4981
2 | Lean Concrete
1450 PSI
| Footing | CFT | 22 | 4.666 | 4.666 | 0.5 | 239.4871
Plinth Beam
| A/1-2,2-3,3-4,5-6 B/1-2,2-3,3-4 | CFT | 7 | 5.75 | 1.5 | 0.5 | 30.1875
| B/1-2,2-3 C/2-3,3-4 | CFT | 4 | 15.666 | 1.5 | 0.5 | 46.998
| B/3-4,5-6 C/1-2,5-6 | CFT | 4 | 15.25 | 1.5 | 0.5 | 45.75
| B-C/5-6 | CFT | 1 | 16.75 | 1.5 | 0.5 | 12.5625
| B-C/1,2,3,4,5,6 | CFT | 6 | 21.25 | 1.5 | 0.5 | 95.625
| D-E/5 & 6 | CFT | 2 | 16.75 | 1.5 | 0.5 | 25.125
| E/5-6 | CFT | 1 | 15.333 | 1.5 | 0.5 | 11.4998
507.2349
| Classes Block | CFT | 1 | 51 | 36.5 | 0.5 | 930.75
| Staff-Toilet Block | CFT | 1 | 30.25 | 17.5 | 0.5 | 264.6875
| H.M Room | CFT | 1 | 16.75 | 16 | 0.5 | 134
1329.4375
SRC | 3000 PSI
Wall Below Plinth
| A/1-2,2-3,3-4 B/1-2,2-3,3-4 | CFT | 7 | 5.75 | 0.666 | 3 | 80.4195
| B/1-2,2-3 C/2-3,3-4 | CFT | 4 | 15.666 | 0.666 | 3 | 125.2027
| B/3-4,5-6 C/1-2,5-6 | CFT | 4 | 15.25 | 0.666 | 3 | 121.878
| B-C/5-6 | CFT | 1 | 16.75 | 0.666 | 3 | 33.4665
| B-C/1,2,3,4,5,6 | CFT | 6 | 21.25 | 0.666 | 3 | 254.745
| D-E/5 & 6 | CFT | 2 | 16.75 | 0.666 | 3 | 66.933
| E/5-6 | CFT | 1 | 15.333 | 0.666 | 3 | 30.6353
713.28
3 | Concrete
| Footing | CFT | 22 | 4 | 4 | 0.75 | 264
264
Plinth Beam
| A/1-2,2-3,3-4 D/1-2,2-3,3-4 | CFT | 7 | 5.75 | 0.666 | 2.5 | 67.0162
| B/1-2,2-3 C/2-3,3-4 | CFT | 4 | 15.666 | 0.666 | 2.5 | 104.3356
| B/3-4,5-6 C/1-2,5-6 | CFT | 4 | 15.25 | 0.666 | 2.5 | 101.565
| B-C/5-6 | CFT | 1 | 16.75 | 0.666 | 2.5 | 27.8888
| B-C/1,4,5,6 | CFT | 4 | 21.25 | 0.666 | 2.5 | 141.525
| B-C/2,3 | CFT | 2 | 21.25 | 0.5 | 2.5 | 53.125
| A-B/1,4,5,6 | CFT | 4 | 6 | 0.666 | 2.5 | 39.96
| C-D/1,4,5,6 | CFT | 4 | 5.5 | 0.666 | 2.5 | 36.63
| D-E/5 & 6 | CFT | 2 | 16.75 | 0.666 | 2.5 | 55.7775
| E/5-6 | CFT | 1 | 15.333 | 0.666 | 2.5 | 25.5294
| Total | CFT |  |  |  |  | 653.3525
| Column Upto Plinth | [7 empty] | 0.7855 | 1 | 0.7855
| Round Columns | CFT | 10 | 0.785 |  | 2.75 | 21.5875
| Rect. Columns | CFT | 14 | 1.5 | 0.666 | 2.75 | 38.4615
60.049
Column Above Plinth
| Round Columns | CFT | 10 | 0.7855 |  | 15.75 | 123.7163 | 3.142/4 x (d)^2 |  | 0.7855 | 1 | 0.7855
| Rect. Columns | CFT | 14 | 1.5 | 0.666 | 12.25 | 171.3285
295.0448
Roof Beam
| A/1-2,2-3,3-4 D/1-2,2-3,3-4 | CFT | 7 | 5.75 | 0.666 | 2.5 | 67.0162
| B/1-2,2-3 C/2-3,3-4 | CFT | 4 | 15.666 | 0.666 | 2.5 | 104.3356
| B/3-4,5-6 C/1-2,5-6 | CFT | 4 | 15.25 | 0.666 | 2.5 | 101.565
| B-C/5-6 | CFT | 1 | 16.75 | 0.666 | 2.5 | 27.8888
| B-C/1,4,5,6 | CFT | 4 | 21.25 | 0.666 | 2.5 | 141.525
| B-C/2,3 | CFT | 2 | 21.25 | 0.5 | 2.5 | 53.125
| A-B/1,4,5,6 | CFT | 4 | 6 | 0.666 | 2.5 | 39.96
| C-D/1,4,5,6 | CFT | 4 | 5.5 | 0.666 | 2.5 | 36.63
| D-E/5 & 6 | CFT | 2 | 16.75 | 0.666 | 2.5 | 55.7775
| E/5-6 | CFT | 1 | 15.333 | 0.666 | 2.5 | 25.5294
| Total | CFT |  |  |  |  | 653.3525
Roof Slab
| Classes Block | CFT | 1 | 51 | 36.5 | 0.5 | 930.75
| Staff-Toilet Block | CFT | 1 | 30.25 | 17.5 | 0.5 | 264.6875
1195.4375
Block Masonary
8 inch Thick Wall
| A/1-2,2-3,3-4 B/1-2,2-3,3-4 | CFT | 7 | 5.75 | 0.666 | 10.25 | 274.7666
| B/1-2,2-3 C/2-3,3-4 | CFT | 4 | 15.666 | 0.666 | 10.25 | 427.7758
| B/3-4,5-6 C/1-2,5-6 | CFT | 4 | 15.25 | 0.666 | 10.25 | 416.4165
| B-C/5-6 | CFT | 1 | 16.75 | 0.666 | 10.25 | 114.3439
| B-C/1,4,5,6 | CFT | 4 | 21.25 | 0.666 | 10.25 | 580.2525
| A-B/1,4,5,6 | CFT | 4 | 6 | 0.666 | 10.25 | 163.836
| C-D/1,4,5,6 | CFT | 4 | 5.5 | 0.666 | 10.25 | 150.183
| D-E/5 & 6 | CFT | 2 | 16.75 | 0.666 | 10.25 | 228.6877
| E/5-6 | CFT | 1 | 15.333 | 0.666 | 10.25 | 104.6707
Deduction
| D1 | CFT | 8 | -3.6 | 0.666 | 8 | -153.4464
| D2 | CFT | 2 | -2.5 | 0.666 | 8 | -26.64
| W1 | CFT | 15 | -3.6 | 0.666 | 5.5 | -197.802
| W2 | CFT | 1 | -6 | 0.666 | 6 | -23.976
| W3 | CFT | 1 | -4 | 0.666 | 4 | -10.656
| V1 | CFT | 1 | -2 | 0.666 | 4 | -5.328
| Total | CFT |  |  |  |  | 2043.0844
6 inch Thick Wall
| B-C/2,3 | CFT | 2 | 21.25 | 0.5 | 10.25 | 217.8125
| B-C/2-3 | CFT | 2 | 16 | 0.5 | 10.25 | 164
381.8125
4 inch Thick Wall
| Filter plant Wall | CFT | 1 | 7.5 | 0.33 | 10 | 24.75
| Staff Toil. Long Wall | CFT | 1 | 8 | 0.33 | 10 | 26.4
| Staff Toil. Short Wall | CFT | 1 | 5.33 | 0.33 | 10 | 17.589
| G & Boys Door Wall | CFT | 2 | 5 | 0.33 | 10 | 33
| H.M & Staff Toilet | CFT | 2 | 7.5 | 0.33 | 10 | 49.5
| H.M & Staff Toilet | CFT | 1 | 5.5 | 0.33 | 10 | 18.15
| W3 | CFT | 1 | -4 | 0.75 | 4 | -12
| V1 | CFT | 1 | -2 | 0.75 | 4 | -6
| DW | CFT | 2 | -2.5 | 0.33 | 8 | -13.2
|  | CFT | 2 | -2 | 0.33 | 4 | -5.28
132.909
5 | Plaster Work
Inner Plaster
1 | Class Room 1,2,3
| Long Wall | Sft | 6 | 22 |  | 12.25 | 1617
| Short Wall | Sft | 6 | 16 |  | 12.25 | 1176
2 | Staff Room
| Long Wall | Sft | 2 | 16 |  | 12.25 | 392
| Short Wall | Sft | 2 | 10.75 |  | 12.25 | 263.375
3 | Staff Toilet
| Long Wall | Sft | 2 | 8 |  | 8.25 | 132
| Short Wall | Sft | 2 | 5.33 |  | 8.25 | 87.945
4 | Filter Plant
| Long Wall | Sft | 2 | 7.5 |  | 8.25 | 123.75
| Short Wall | Sft | 2 | 5.33 |  | 8.25 | 87.945
5 | Girls Toilet
| Long Wall | Sft | 2 | 5 |  | 8.25 | 82.5
| Short Wall | Sft | 2 | 5 |  | 8.25 | 82.5
6 | Boys Toilet
| Long Wall | Sft | 2 | 5 |  | 8.25 | 82.5
| Short Wall | Sft | 2 | 5 |  | 8.25 | 82.5
7 | Toil Passage
| Long Wall | Sft | 2 | 5.5 |  | 8.25 | 90.75
| Short Wall | Sft | 2 | 4.75 |  | 8.25 | 78.375
9 | Paraphet Wal
| Long Wall | Sft | 2 | 51 |  | 3.5 | 357
| Short Wall | Sft | 2 | 36.5 |  | 3.5 | 255.5
10 | Logo Wall
|  | Sft | 1 | 30.25 |  | 8.25 | 249.5625
11 | H.M Room
| Long Wall | Sft | 2 | 16 |  | 12.25 | 392
| Short Wall | Sft | 2 | 11.25 |  | 12.25 | 275.625
12 | H.M Toilet
| Long Wall | Sft | 2 | 7.5 |  | 8.25 | 123.75
| Short Wall | Sft | 2 | 5.5 |  | 8.25 | 90.75
Deduction
| D1 | CFT | 8 | -3.6 | 0.75 | 8 | -172.8
| D2 (Both Sides) | CFT | 6 | -2.5 | 0.75 | 8 | -90
| DW (Both Sides) | CFT | 4 | -2.5 | 0.75 | 8 | -60
|  | CFT | 2 | -2 | 0.75 | 4 | -12
| W1 | CFT | 15 | -3.6 | 0.75 | 5.5 | -222.75
| W2 | CFT | 1 | -6 | 0.75 | 6 | -27
| W3 | CFT | 1 | -4 | 0.75 | 4 | -12
| V1 | CFT | 1 | -2 | 0.75 | 4 | -6
[5 empty] | Total |  | 5520.7775
Ceiling Plaster
1 | Class Room 1,2,3 | Sft | 3 | 22 | 16 |  | 1056
2 | Staff Room | Sft | 1 | 16 | 10.75 |  | 172
3 | Staff Toilet | Sft | 1 | 8 | 5.33 |  | 42.64
4 | Filter Plant | Sft | 1 | 7.5 | 5.33 |  | 39.975
5 | Girls Toilet | Sft | 1 | 5 | 5 |  | 25
6 | Boys Toilet | Sft | 1 | 5 | 5 |  | 25
7 | Toil Passage | Sft | 1 | 5.5 | 4.75 |  | 26.125
8 | Corridoor A-B | Sft | 4 | 16 | 6 |  | 384
9 | Corridoor C-D | Sft | 4 | 16 | 5.5 |  | 352
10 | H.M Room | Sft | 1 | 16 | 11.25 |  | 180
11 | H.M Toilet | Sft | 1 | 7.5 | 5.5 |  | 41.25
[5 empty] | Total |  | 2343.99
Exterior Plaster
1 | Classes Block | Sft | 1 | 149 |  | 12.75 | 1899.75
| Paraphet Wall | Sft | 1 | 175 |  | 3.5 | 612.5
2 | Staff - Toilet Block | Sft | 1 | 136 |  | 12.75 | 1734
| Logo Wall | Sft | 1 | 36.5 |  | 8.25 | 301.125
3 | Out Door Coloumn | Sft | 10 | 1 |  | 12.75 | 127.5
Deduction
| D1 | CFT | 7 | -3.6 | 0.75 | 8 | -151.2
| W1 | CFT | 12 | -3.6 | 0.75 | 5.5 | -178.2
| W2 | CFT | 1 | -6 | 0.75 | 6 | -27
| W3 | CFT | 1 | -4 | 0.75 | 4 | -12
| V1 | CFT | 1 | -2 | 0.75 | 4 | -6
[5 empty] | Total |  | 4300.475
6 | Paint
Inner Paint
1 | Class Room 1,2,3
| Long Wall | Sft | 6 | 22 |  | 12.25 | 1617
| Short Wall | Sft | 6 | 16 |  | 12.25 | 1176
2 | Staff Room
| Long Wall | Sft | 2 | 16 |  | 12.25 | 392
| Short Wall | Sft | 2 | 10.75 |  | 12.25 | 263.375
3 | Staff Toilet
| Long Wall | Sft | 2 | 8 |  | 8.25 | 132
| Short Wall | Sft | 2 | 5.33 |  | 8.25 | 87.945
4 | Filter Plant
| Long Wall | Sft | 2 | 7.5 |  | 8.25 | 123.75
| Short Wall | Sft | 2 | 5.33 |  | 8.25 | 87.945
5 | Girls Toilet
| Long Wall | Sft | 2 | 5 |  | 8.25 | 82.5
| Short Wall | Sft | 2 | 5 |  | 8.25 | 82.5
6 | Boys Toilet
| Long Wall | Sft | 2 | 5 |  | 8.25 | 82.5
| Short Wall | Sft | 2 | 5 |  | 8.25 | 82.5
7 | Toil Passage
| Long Wall | Sft | 2 | 5.5 |  | 8.25 | 90.75
| Short Wall | Sft | 2 | 4.75 |  | 8.25 | 78.375
9 | Paraphet Wal
| Long Wall | Sft | 2 | 51 |  | 3.5 | 357
| Short Wall | Sft | 2 | 36.5 |  | 3.5 | 255.5
10 | Logo Wall
|  | Sft | 1 | 30.25 |  | 8.25 | 249.5625
11 | H.M Room
| Long Wall | Sft | 2 | 16 |  | 12.25 | 392
| Short Wall | Sft | 2 | 11.25 |  | 12.25 | 275.625
12 | H.M Toilet
| Long Wall | Sft | 2 | 7.5 |  | 8.25 | 123.75
| Short Wall | Sft | 2 | 5.5 |  | 8.25 | 90.75
Deduction
| D1 | CFT | 7 | -3.6 | 0.75 | 8 | -151.2
| D2 (Both Sides) | CFT | 4 | -2.5 | 0.75 | 8 | -60
| DW (Both Sides) | CFT | 4 | -2.5 | 0.75 | 8 | -60
|  | CFT | 2 | -2 | 0.75 | 4 | -12
| W1 | CFT | 12 | -3.6 | 0.75 | 5.5 | -178.2
| W2 | CFT | 1 | -6 | 0.75 | 6 | -27
| W3 | CFT | 1 | -4 | 0.75 | 4 | -12
| V1 | CFT | 1 | -2 | 0.75 | 4 | -6
[5 empty] | Total |  | 5616.9275
Ceiling Paint
1 | Class Room 1,2,3 | Sft | 3 | 22 | 16 |  | 1056
2 | Staff Room | Sft | 1 | 16 | 10.75 |  | 172
3 | Staff Toilet | Sft | 1 | 8 | 5.33 |  | 42.64
4 | Filter Plant | Sft | 1 | 7.5 | 5.33 |  | 39.975
5 | Girls Toilet | Sft | 1 | 5 | 5 |  | 25
6 | Boys Toilet | Sft | 1 | 5 | 5 |  | 25
7 | Toil Passage | Sft | 1 | 5.5 | 4.75 |  | 26.125
8 | Corridoor A-B | Sft | 4 | 16 | 6 |  | 384
9 | Corridoor C-D | Sft | 4 | 16 | 5.5 |  | 352
10 | H.M Room | Sft | 1 | 16 | 11.25 |  | 180
11 | H.M Toilet | Sft | 1 | 7.5 | 5.5 |  | 41.25
[5 empty] | Total |  | 2343.99
Exterior Paint
1 | Classes Block | Sft | 1 | 149 |  | 12.75 | 1899.75
| Paraphet Wall | Sft | 1 | 175 |  | 3.5 | 612.5
2 | Staff - Toilet Block | Sft | 1 | 136 |  | 12.75 | 1734
| Logo Wall | Sft | 1 | 36.5 |  | 8.25 | 301.125
3 | Out Door Coloumn | Sft | 10 | 1 |  | 12.75 | 127.5
4 | PCC Grill | Sft | 8 | 16 |  | 10 | 1280
5 | PCC Grill | Sft | 12 | 6 |  | 10 | 720
Deduction
| D1 | CFT | 7 | -3.6 | 0.75 | 8 | -151.2
| W1 | CFT | 12 | -3.6 | 0.75 | 5.5 | -178.2
| W2 | CFT | 1 | -6 | 0.75 | 6 | -27
| W3 | CFT | 1 | -4 | 0.75 | 4 | -12
| V1 | CFT | 1 | -2 | 0.75 | 4 | -6
[5 empty] | Total |  | 6300.475