## D ESTIMAE in CM
SHEDULE-B
Name of work:- |  | SCHEDULE "B" FOR THE WORK OF "CONSTRUCTION OF ONE CLASS ROOM BUILDING IN SHELTERLESS PRIMARY SCHOOLS TALUKA DAHILI & CHACHRO DISTRICT THARPARKAR (15-UNITS) COMMUNITY DEVELOPMENT PROGRAMME UNDER SDGS (PS-63) @ GBPS SADEYA PARO MOOSA JI DHANI.
S.N: | ITEM OF WORK |  | QTY |  |  |  | RATE |  |  | UNIT |  |  |  | AMOUNT
1 | Excavation in foundation of Building, Bridges and other structures i/c degbelling dressing, refilling around structure with excavated earth watering and ramming (In ordinary soil) lead upto 5 ft .(S.I.No: 18-b, P.No: 4)
|  |  |  | 713 | Cft. |  | @ Rs: |  | 3176.25 |  |  | %0 Cft. |  | Rs. | 2265 | /=
(Rs. Three Thousan One Hundred Seventy Sixty & Ps. Twenty Five only)
2 | Cement concrete brick or stone ballast 1½” to 2” guage ratio 1:5:10. (S.I.No.4-c, P.No.15).
|  |  |  | 430 | Cft. |  | @ Rs: |  | 8694.95 |  |  | % Cft. |  | Rs. | 37388 | /=
(Rs. Eight Thousand Six Hundred Nienty Four & Ps. Ninety Five Only)
3 | Pacca brick work in foundation and plinth in cement sand morter (1:6) Ratio.(S.I.No: 4-e, P.No: 21)
|  |  |  | 772 | Cft. |  | @ Rs: |  | 11948.36 |  |  | % Cft. |  | Rs. | 92241 | /=
(Rs. Eleven Thousand Nine Hundred Fourty Eight & Ps. Thirty six)
4 | Reinforced cement concrete work including all labour and material except the cost of steel reinforcement and its labour for bending and binding which will be paid separately.This rate also includes all kinds of forms moulds: lifting shuttering curring rendering and finishing the exposed surface including screening and washing of shingle.R.C work in roof slab, beams, columns rafts, lintels and other structural members laid in situ or pre-cost laid in position complete in all respects.Ratio 1:2:4. (S.I.No: 6-a/I, PNo: 17)
|  |  |  | 126 | Cft. |  | @ Rs: |  | 337 |  |  | Per Cft. |  | Rs. | 42462 | /= | 42462
(Rs. Three Hundred Thirty Seven Only)
5 | Fabrication of mild steel reinforcement for cement concrete including cutting, bending, laying in position, making joints and fastenings including cost of binding wire (also includes removal of rust from bars).
A | Using Tor Bars (S.I.No. 8-b, P.No. 17).
|  |  |  | 4.5 | Cwt | @ Rs: |  | 5001.7 |  |  | P.Cwt |  |  | Rs. | 22508 | /=
(Rs. Five Thousand One & Ps. Seventy Only)
B | Using M.S Bars (S.I.No. 8-a, P.No. 17).
|  |  |  | 0.56 | Cwt | @ Rs: |  | 4820.2 |  |  | P.Cwt |  |  | Rs. | 2699 | /=
(Rs. Four Thousand Eight Hundred Twenty & Ps. Twenty Only)
6 | Filling, watering and ramming earth in floors with surplus earth from foundation lead upto one chain and lift upto 5 feet . (S.I.No: 21, P.No: 4).
|  |  |  | 475 | Cft. |  | @ Rs: |  | 1512.5 |  |  | %0 Cft. |  | Rs. | 718 | /=
(Rs. One Thousand Five Hundred Twelve & Ps. Fifty only)
7 | Filling, watering and ramming earth under floor with new earth (Excavated from outside) lead up to one chain and lift upto 5 feet. (S.I.No. 22, P.No: 4).
|  |  |  | 414 | Cft. |  | @ Rs: |  | 3630 |  |  | %0 Cft. |  | Rs. | 1503 | /=
(Rs. Three Thousand Six Hundred Thirty Only)
8 | Pacca brick work in mud mortar in building in Ground floor. (S.I.No. 1-b, P.No: 20).
|  |  |  | 1109 | Cft. |  | @ Rs: |  | 9954.31 |  |  | % Cft. |  | Rs. | 110393 | /=
(Rs. Nine Thousand Nine Hundred Fifty Four & Ps. Thirty One Only)
9 | Supplying Girder .( Sh: of material Vol-III Part-III S.I.No.140, P.No:12).
|  |  |  | 8.57 | Cwt | @ Rs: |  | 3850 |  |  | P.Cwt |  | Rs. |  | 32995 | /= | 345172
(Rs. Three Thousand Eight Hundred Fifty Only)
10 | Supplying T-Iron .( Sh: of material Vol-III Part-III S.I.No.144, P.No:12).
|  |  |  | 6.49 | Cwt | @ Rs: |  | 3575 |  |  | P.Cwt |  | Rs. |  | 23202 | /= | 123866 | 81404
(Rs. Three Thousand Five Hundred Seventy Five Only)
11 | Errection rolled steel beams or old rails in roof etc, erection and fixing in position. (S.I.No. 6, P.No. 91).
|  |  |  | 15.06 | Cwt | @ Rs: |  | 186.34 |  |  | P.Cwt |  | Rs. |  | 2806 | /=
(Rs. One Hundred Eight Six & PS. Thirty Four Only)
12 | First class tile roofing consisting of 4" earth and 1" mud plaster with Gobri leaping over 1/2" thick cement plaster 1:6 with 34 Lbs. Of hot bitumen coating sand blinded provided over 2 layers of tiles 12"x6"x1 1/4" laid in 1:6 cement mortar with 1/2" thick sand witched layer 1:6 cement mortar including 1:2 cement pointing underside of tiles complete including curing etc. (S.I.No. 1, P.No. 33 ).
|  |  |  | 338 | Sft. | @ Rs: |  | 11443.1 |  |  | %Sft. |  | Rs. |  | 38678 | /=
(Rs. Eleven Thousand Four Hundred Fourty Three & Ps. Ten Only)
S.N: | ITEM OF WORK |  | QTY |  |  |  | RATE |  |  | UNIT |  |  |  | AMOUNT
13 | Making and fixing steel grated doors with 1/16" thick sheeting including angle iron frame 2" X 2" X 3/8" and 3/4" sq: bars 4" center to center complete with locking arrangement.(S.I.No. 24, P.No. 92 ).
|  |  |  | 76 | Sft | @ Rs: |  | 726.72 |  |  | P.Sft |  | Rs. |  | 55231 | /=
(Rs. Seven Hundred Twenty Six & Ps. Seventy Two Only))
14 | Supplying and fixing in position iron/steel grill of 3/4" X 1/4" size flat iron of approved design including painting 3 coats etc. complete (weight not to be less then 3.7 lbs/ sq. foot of finished grill. (S.I.No. 26, P.No. 93).
|  |  |  | 91 | Sft | @ Rs: |  | 180.5 |  |  | P.Sft |  | Rs. |  | 16426 | /=
(Rs. One Hundred Eighty & PS. Fifty Only)
15 | Cement plaster 1:6 ratio 1/2" thick upto 12' ft height (S.I.No.13-b, P.No.52).
|  |  |  | 2536 | Sft. | @ Rs: |  | 2206.6 |  |  | %Sft. |  | Rs. |  | 55959 | /=
(Rs. Two Thousand Two Hundred Six & Ps. Sixty Only)
16 | Cement plaster 1:4 ratio 3/8" thick upto 12' ft height (S.I.No.11-a, P.No. 52).
|  |  |  | 2536 | Sft. | @ Rs: |  | 2197.52 |  |  | %Sft. |  | Rs. |  | 55729 | /=
(Rs. Twenty One Hndred Ninety Seven & Ps. Fifty Two Only)
17 | Laying floor of approved with glazed tile ¼” thick in white cement 1:2 over ¾” thick cement morter 1:2 complete. (S.I.No. 24, P.No.43).
|  |  |  | 330 | Sft. | @ Rs: |  | 27678.86 |  |  | %Sft. |  | Rs. |  | 91340 | /=
(Three thousand One hundred Seventy six Rupees and Twenty five paisa)
18 | Tile (size 12" X 6" X 2" ) laid in 1:6 cement mortar over a bed of 3/4" thick cement mortar 1:6 . (S.I.No. 11, P.No.41).
|  |  |  | 574 | Sft. | @ Rs: |  | 3056.35 |  |  | %Sft. |  | Rs. |  | 17543 | /=
(Rs. Twenty Seven Thousand Six Hundred Seventy Eight & Ps. Eighty Six Only)
19 | Providing and laying 2" thick topping cement concrete (1:2:4) including surface finishing and dividing into panels. (S.I.No. 16-c, P.No.42).
|  |  |  | 12 | Sft. | @ Rs: |  | 3275.5 |  |  | %Sft. |  | Rs. |  | 393 | /=
(Rs. Thir Two Hundred Seventy Five & Ps. Fifty Only
20 | Making notice board made with cement sand.
|  |  |  | 24 | Sft. | @ Rs: |  | 58.11 |  |  | P.Sft. |  | Rs. |  | 1395 | /=
(Rs. Fifty Eight & Ps. Eleven Only)
21 | Khasi Parnalas in cement and sand mortar (1:2) 12" out side width finished smooth with a floating coat of neat cement. (S.I.No.17, P.No.36).
|  |  |  | 11 | Rft. | @ Rs: |  | 70.34 |  |  | P.Rft. |  | Rs. |  | 774 | /=
(Rs. Seventy & Ps. Thirty four only)
22 | White wash three coats. (S.I.No. 26-c, P.No: 54 ).
|  |  |  | 320 | Sft. | @ Rs: |  | 829.95 |  |  | %Sft. |  | Rs. |  | 2656 | /=
(Rs. Eight Hundred Twenty Nine & Ps. Ninety Five Only)
23 | Colour wash two coats i/c one coat of white wash .(S.I.No. 25-b+26-a, P.No. 54).
|  |  |  | 2089 | Sft. |  | @ Rs: |  | 1276.53 |  |  | %Sft. |  | Rs. | 26667 | /=
(Rs. One Thousand Two Hundred Seventy Six & Ps. Fifty Three Only)
24 | Painting new surface guards, bars, gates, iron bars, gratings,railings(including standards braces,etc).And similar open work three coats (S.I.No. 5-d, P.No: 70 ).
|  |  |  | 352 | Sft. | @ Rs: |  | 1270.83 |  |  | %Sft. |  | Rs. |  | 4473 | /=
(Rs. One Thousand Two Hundred Seventy & Ps. Eighty Three Only)
[10 empty] | Total |  |  | Rs. |  | 738444 | /=
________________________ % Above / below on the rates of CSR ADD / Ded _____________% Rs __________
[10 empty] | Total |  |  | Rs.
Total (A\ = (a+b) in words & figures______________________________________________________
___________________________________________________________________________________
CONTRACTOR

## W S & S F HS (hidden)
SHEDULE-B
PART-B
WATER SUPPLY & SANATARY FITTING
Name of work:- |  | ESTABLISHMENT OF SINGLE SECTION HIGH SCHOOLS IN SINDH (53-UNITS) ADP NO: 1170 OF 2008-09 @ GBHS GOGASAR LADHANI U/C GADHRO TALUKA CHACHRO DISTRICT THARPARKAR.
S.N: | ITEM OF WORK |  | QTY |  |  | RATE |  | UNIT |  |  | AMOUNT
1 | Providing and fixing squatting type white glazed earthen ware w.c pan with i/c cost of flushing cistern with internal fitting & flush pipe with bend and making requisite numbers of holes in walls plinth and floor for pipe connection and making good in cement concrete 1:2:4 .W.C pan of not less than 19” clear opening between flushing rims and 3 gallons flushing tank with 4”dia earthe ware trape & plastic thumble .S.I,No:1/b-ii/P-01. ).
|  |  |  | 9 | Nos: | @ Rs: | 4846.6 |  | Each |  | Rs. | 43619 | /=
(Three thousand Two hundred Six Rupees and Thirteen Paisa)
2 | Providing and fixing 22”x16" Lavatory basin in white glazed earthen ware complete with and i/c the cost of W.I or C.I cantilever brackets 6 inches built into walls painted white in two coats after a primary coats if ked paint aq pair of ½ dia chrone platted piller taps 1-1/2” dial rubber plugandchrone brasswater of approved pattern 1-1/4” dia malleable iron c-p brass unions and making traps . Malleable iron or brass requisi9te number of holes in wall plinth and floor traps for pipe connection and making good in cement concrete 1:2:4 Standard pattern.(S.I.No:12 / P-4).
|  |  |  | 5 | Nos: | @ Rs: | 4694.8 |  | Each |  | Rs. | 23474 | /=
(Three thousand Two hundred Six Rupees and Thirteen Paisa)
3 | Add extra labour for providing and fixing of earthern ware pedestalwhite or coloured glazed standard pattern).(S.I.No:11 / P-3).
|  |  |  | 2 | Nos: | @ Rs: | 2533.47 |  | Each |  | Rs. | 5067 | /=
(Three thousand Two hundred Six Rupees and Thirteen Paisa)
4 | Providing and fixing 6”x2”x or 6”x3’C.I floor trap of the approved self cleaning self cleaning design with a C.I screwed down gritting with or without a vent aem complete with and i/c making required number or holes in walls plinth and floor for pipe connection & making good in C.C1:2:4 (S.I,No: 20/P-6)
|  |  |  | 5 | Nos: | @ Rs: | 2042.43 |  | Each |  | Rs. | 10212 | /=
(Three thousand Two hundred Six Rupees and Thirteen Paisa)
5 | Providing and fixing in position nylon connections complete with ½” bars srop cock with pair of bars nuts and lining joints o nylon connection (S.I.No:23-P-6)
|  |  |  | 5 | Nos: | @ Rs: | 447.15 |  | Each |  | Rs. | 2236 | /=
(Three thousand Two hundred Six Rupees and Thirteen Paisa)
6 | Providing & fixing chrome plated bars towel rail complete with brackets fixing on wooden cleats with I” long C.P bars screw (iii) Towel rails 24” long (a) ¾” dia round or squire pattern (S.No: 1-iii-p-7)
|  |  |  | 5 | Nos: | @ Rs: | 1269.95 |  | Each |  | Rs. | 6350 | /=
(Three thousand Two hundred Six Rupees and Thirteen Paisa)
7 | Providing and fixing 15”x 12”belvelled eage mirror of Belgium glass complete with 1/8” thick bard board and c.p screw fixed to wooden pleat (a) Standars pattern (S.I.No:4-a /P-7)
|  |  |  | 5 | Nos: | @ Rs: | 1161.6 |  | Each |  | Rs. | 5808 | /=
(Three thousand Two hundred Six Rupees and Thirteen Paisa)
8 | Supplying and fixing soap tray of made of plastic of superior quality and design with fine finishing with c.p screws etc complete (S.I.No: 6/p-8)
|  |  |  | 5 | Nos: | @ Rs: | 169.4 |  | Each |  | Rs. | 847 | /=
(Three thousand Two hundred Six Rupees and Thirteen Paisa)
9 | Providing and fixing 4”dia C.I soil & vent pipes including costing & fitting and extra painting to match the colour of building (S.I.NO: 01.p-9).
|  |  |  | 48 | Rft. | @ Rs: | 333.29 |  | P.Rft |  | Rs. | 15998 | /=
(Three thousand Two hundred Six Rupees and Thirteen Paisa)
10 | Providing & fixing M.S Clamps of the approved design to 4” dia CI Pipes sockets including the coat of cutting and making good to walt or M.S bolts & nuts4” into wall including pipe distance pieces eaxtra painting to match the colour of the building (S.I.No: 2-P-9)
|  |  |  | 8 | Nos: | @ Rs: | 72.16 |  | Each |  | Rs. | 577 | /=
(Three thousand Two hundred Six Rupees and Thirteen Paisa)
11 | Providing and fixing 4”x4” dia C.I branch of the required degree including extra painting to match the color of the building .(S.I.No: 6/p-No; 9).
|  |  |  | 8 | Nos: | @ Rs: | 201.5 |  | Each |  | Rs. | 1612 | /=
(Three thousand Two hundred Six Rupees and Thirteen Paisa)
S.N: | ITEM OF WORK |  | QTY |  |  | RATE |  | UNIT |  |  | AMOUNT
12 | Providing & fixing 4”dia C.I plain bend of the required degree including extra painting to match the Colour of the building (S.I.No:10-p- 10).
|  |  |  | 8 | Nos: | @ Rs: | 566.7 |  | Each |  | Rs. | 4534 | /=
(Three thousand Two hundred Six Rupees and Thirteen Paisa)
13 | Providing & fixing 4” dia C.I.terminal guard including extra painting to match the colour f the building (S.I.No:11-p-10).
|  |  |  | 8 | Nos: | @ Rs: | 389.7 |  | Each |  | Rs. | 3118 | /=
(Three thousand Two hundred Six Rupees and Thirteen Paisa)
14 | Providing G.I pipes Specials & Clamps etc including fixing cutting and fitting complete with & i/c the coat of breaking through walls and roof making good etc painting two coats after cleaning the Pipe etc with white wash /ink paint pigment to match the colour of building and testing with water to a pressure head of 200 feet and handling (S.I.No:1-P-12).
A. | 1/2” dia:-
|  |  |  | 200 | Rft. | @ Rs: | 73.21 |  | P.Rft |  | Rs. | 14642 | /=
(Three thousand Two hundred Six Rupees and Thirteen Paisa)
B. | 3/4” dia:-
|  |  |  | 100 | Rft. | @ Rs: | 95.79 |  | P.Rft |  | Rs. | 9579 | /=
(Three thousand Two hundred Six Rupees and Thirteen Paisa)
15 | Supplying & fixing long bib cock of superior quality with c.p head ½’ dia (S.I.No: 13a-p-19).
|  |  |  | 11 | Nos: | @ Rs: | 1109.46 |  | Each |  | Rs. | 12204 | /=
(Three thousand Two hundred Six Rupees and Thirteen Paisa)
16 | Supplying and fixing long bib-Cock of superior quality with c.p ½” dia (S.I.No:13b-p-19)
|  |  |  | 5 | Nos: | @ Rs: | 1384.24 |  | Each |  | Rs. | 6921 | /=
(Three thousand Two hundred Six Rupees and Thirteen Paisa)
17 | Supplying & fixing swan type piller cock of supper quality with crystal head (S.I.No:16b-p-19).
|  |  |  | 5 | Nos: | @ Rs: | 877.8 |  | Each |  | Rs. | 4389 | /=
(Three thousand Two hundred Six Rupees and Thirteen Paisa)
18 | Providing R.C.C pipe with collar Class B” and dipping the trenches to required depth and fixing in position including dutting fitting & joints with composition & cement mortar 1: 1 and testing with water presume to ahead of 4 feet above to the top the highest pipe & refilling with excavated staff (S.I.No; 2-p-24) 4" dia
|  |  |  | 50 | Rft. | @ Rs: | 146.57 |  | P.Rft |  | Rs. | 7329 | /=
(Three thousand Two hundred Six Rupees and Thirteen Paisa)
19 | Providing Asbestos pipe with collars Dedes or equivalent i/c digging the trench to require depth and fixing to position and joining with fiber rings including testing to water, pressure head of 200 feet. (S.I.No:3/p.25) 4" dia
|  |  |  | 50 | Rft. | @ Rs: | 188.44 |  | P.Rft |  | Rs. | 9422 | /=
(Three thousand Two hundred Six Rupees and Thirteen Paisa)
20 | Providing & fixing Handle valves (china) (S.N.O: 5/P-17).
A. | 1/2” dia:-
|  |  |  | 8 | Nos: | @ Rs: | 200.42 |  | Each |  | Rs. | 1603 | /=
(Three thousand Two hundred Six Rupees and Thirteen Paisa)
B. | 3/4” dia:-
|  |  |  | 8 | Nos: | @ Rs: | 271.92 |  | Each |  | Rs. | 2175 | /=
(Three thousand Two hundred Six Rupees and Thirteen Paisa)
22 | Supplying & Fixing Fiber Glass Tank of approved quality and design and wall thickness as specified i/c coat of nut bolts and fixing in plate of cement concrete 1:3:6 and making connection for in let & out let & over flow pipes etc complete (S.I,No; 3/p-21) 250 gallons
|  |  |  | 3 | Nos: | @ Rs: | 21989.61 |  | Each |  | Rs. | 65969 | /=
(Three thousand Two hundred Six Rupees and Thirteen Paisa)
23 | Water pumping set 1 H.P 2800 PRM single phase 220 vo;ts 1-1/2”x1” suction and deliver 40 ft head including base plate and also making C.C 1:3:6 plate form of required size and fixing with nuts and boluts Complete in all respect.
|  |  |  | 1 | No: | @ Rs: | 5494.59 |  | Each |  | Rs. | 5495 | /=
(Three thousand Two hundred Six Rupees and Thirteen Paisa)
[8 empty] | Total |  | Rs. |  | 263180 | /=