## CC
S.No | 27 |  | SCHEDULE "B"
PART "A" C:C WORK
Construction of CC road Barkat Gadi length 515 Rft
S.No | Item of work. | [9 empty] | Quantity |  | Rate |  |  | Unit. |  | Amount.
1 | SUB GRADE
Preaparing Sub-Grade including earth exacavation of filling to an average depth of 9" dressing to camber and consolidation with power roller.
| Say Qty. |  |  | 5202 |  | Sft |  | @ | Rs. |  | 526.28 | P %Sft |  |  | Rs. |  | 27377.0856 |  |  | / =
2 | CEMENT CONCRETE RATION 1:4:8
Cement Concrete Brick or Stone Ballast 1-1/2" to 2" gauge. Ratio 1:4:8
| Qty. |  | 1951 |  | Cft |  |  |  |  | 9416.28 |  | Per %Cft. |  |  | Rs. |  | 183712 |  | /=
3 | Cement Concrete Ratio 1:2:4
Cement Concrete Plain including placing compactiong, finishing and curing, complete (including screeing and washing of stone aggregate without shuttering (Ratio 1:2:4).
| Qty. |  | 2185 |  | Sft. |  | @ Rs |  |  | 14435.29 |  | Per % Sft. |  |  | Rs. |  | 315411.0865 |  |  | / =
4 | EARTHWORK
Earth work for road embankment by buldozers, including ploughing, mixing, clod breaking, dressing, compacting with optimum moisture content. Lead upto 100 ft and lift upto 5.0 ft. in all types of soil exceptrock( If earth work is done by other than departmental agency) Ordinary Soil)
| Say Qty. |  |  | 1040 |  | Cft |  | @ | Rs. |  | 2208.37 | P %0Cft |  |  | Rs. |  | 2296.7048 |  |  | / =
5 | Supplying and Fixing Inuaguration
Supplying and fixing inauguration Stone at Site of work including Masonry work cartage of material etc complete.
| Say Qty. |  |  | 1 |  | Job |  | @ | Rs. |  | 5000 | Each |  |  | Rs. |  | 5000 |  |  | / =
[12 empty] | Total |  |  | Rs. |  | 533796.8769 |  |  | / =
NOTE:- |  | Item / Quantities / Rates and amount are estimated provisional and will be corrected in accordance to the Detail worksing estimate sanctioned by competent authority.
CONTRACTOR | [13 empty] | EXECUTIVE ENGINEER
HIGHWAYS DIVISION
MIRPURKHAS