## Sheet3
|  | Guidelines / Regulations for Procurement of Works | [8 empty] | (Annexure A-I)
(Annexure- A)
PROCUREMENT PLAN (Development/Capital)
| Serial No/ADP* | Name of Scheme & Estimated Cost | Allocated Funds | Cost of ongoing works (Expenditure already incurred) | Funds earmarked for ongoing works | Cost of New Works (Components) | Funds for New Works (e-e) | Nature of Procurement | Method of Procurement | Anticipated / Actual Date of Advertisement | Anticipated / Actual Date of Start | Anticipated / Actual Date of Completion
| a | b | c | d | e | f | g | h | i | j | k | l
PROVINCIAL SCHEMES
Improvement of existing Public Schools in Shaheed Benzir Abad Division ADP.207 of 2015-16
| 1 | Shaheed Benzir Bhutto Public School Nawbshah (Addition of 6-Class Rooms,Retire Room,paving with pavers, under ground Tank,Rehabilitaion of Existing Building. | 23.04 | __ | __ | 23.04 | 23.04 | National Compitative Bidding | Single Stage one Envelope Procedure | 16/3/2016 | 4 .2016 | 31/10/2017
|  | Establishment of Bakhtawar Cadet Collage for Girls Shaheed Benazirabad ADP-226 of 2015-16 | 1626.91 | 810.162 | 500.4 | __ | 316.91 | Do | Do | 16/3/2016 | 4 .2016 | 31/12/2016
| 2 | Construction of Main Gate/Reception,water supply & SainataryFittings ,External Development |  |  |  | 3.1 |  | Do | Do | Do | Do | 31/12/2016
| 3 | Construction of Guard Room (W/supply & Sanitary Fittings & External Development |  |  |  | 3.1 |  | Do | Do | Do | Do | 31/12/2016
| 4 | Construction of Parade Ground |  |  |  | 22.738 |  | Do | Do | Do | Do | 31/12/2016
| 5 | Construction of Under Ground Water Tank(06 Nos) |  |  |  | 15.65 |  | Do | Do | Do | Do | 31/12/2017
| 6 | Construction Categary-l Bunglow (External Development) |  |  |  | 2.493 |  | Do | Do | Do | Do | 31/12/2016
| 7 | Construction of Hostel Block-C (External Development,Warderobs,Fly proof Doors |  |  |  | 9.2 |  | Do | Do | Do | Do | 31/12/2016
| 8 | Construction of Hostel Block-D (External Development,Warderobs,Fly proof Doors |  |  |  | 9.2 |  | Do | Do | Do | Do | 31/12/2016
| 9 | Construction of Category_IV Quarters (W/Supply & Sanitary Fittings ,External Development ). |  |  |  | 3.597 |  | Do | Do | Do | Do | 31/12/2016
| 10 | Construction of Category_V Quarters(06 Nos) (W/Supply & Sanitary Fittings ,External Development ). |  |  |  | 3.278 |  | Do | Do | Do | Do | 31/12/2016
|  | Establishment of Single Section High Schools in Sindh 2008-09 Programme ADP-161 of 2015-16. | 20.581 M | 14.12 | 1.16 |  | 5
| 11 | GBHS Pir Zakri (Balance Work) |  |  |  | 5 |  | Do | Do | Do | Do | 30/4/2017
|  | Rehabilitaion of Existng High/Higher Secondry Schools in Sindh 2008-09 programme ADP-164 of 2015-16 | 12.85 | 2.709 | __ | __ | 10.14
| 12 | GBHS Bandhi |  |  | __ | 10.14 | __ | Do | Do | Do | Do | 31/3/2017
|  | Construction of Building of Degree Collage for Boys at Qazi Ahmed District SBA 2011-12 Programme ADP-235 of 2105-16 1st Floor (Electric Work) | 97.164 | 68.9 | __ |  | 28.264 | Do | Do | Do | Do | 30/10/2016
| 13 | Construction/Re-constt: of existing elementry School GGPS Saint Anthony N,shah District SBA.2010-11 Prog: | 19.105 | 18.647 | __ | 0.46 | 0.46 | Do | Do | Do | Do | 30/06/2016
|  | Construction// Addition of C/rooms in existing Elementry/Secondry Schools of Distt:SBA (14-units) 2010-11 Programme | 18.052 | 16.62 | Nil |  | 1.43
| 14 | GGPS Linepar Model School N,shah(5-R) U.C -8 Nawabshah |  |  | __ | 1.43 | __ | Do | Do | Do | Do | 30/06/2016
|  | SINDH PUBLIC PROCUREMENT REGULATORY AUTHORITY | [8 empty] | Page 62