## F.R (2)
Financial Review
Name of Work:- Nawab Shah Package for Education ADP No. 2293/2012- 13 Rehabilitation of existing primary school & Middle school in District SBA At GBPS Haji Ali Bux Magsi (Revised Estimate) Taluka Sakrand
S.No. | Description | PC-I Cost | Expenditur upto date Rs: |  | Total | Expenditure to be done Rs: |  | Grand Total Rs: | Remarks
|  |  | Civil | Electric |  | Civil | Electric
A | GBPS Haji Ali Bux Magsi
1 | Main Building | 703380 | 802593 | 62197 | 864790 | 142210 | 0 | 1007000 | Work has been executed
2 | W/S & S/Fitting | 46892 | [6 empty] | as per site requirment
3 | Electrification | 55530 | [6 empty] | and local public demond
4 | Internal Path | 35220 | [6 empty] | and education deptt:
5 | Compound Wall | 58725
| Total | 899747 | 802593 | 62197 | 864790 | 142210 | 0 | 1007000
| Say | 900000
B | GGPS Mohd Khan Magsi
1 | Main Building | 650100 | 820811 | 62880 | 883691 | 0 | 0 | 883691 | Certificate that the scheme
2 | W/S & S/Fitting | 82740 | [6 empty] | No. (B) is completed and
3 | Electrification | 73284 | [6 empty] | Hand over for education
4 | Internal Path | 73500 | [6 empty] | departement and there
5 | Compound Wall | 120600 | [6 empty] | clear cut saving of
| Total | 1000224 | 820811 | 62880 | 883691 | 0 | 0 | 883691 | Rs: 116309/- which being
| Say | 1000000 | [6 empty] | used for unit (A).
| Grand Total (A+ B) | 1900000 | 1623404 | 125077 | 1748481 | 142210 | 0 | 1890691
| Excess/Saving | 1900000.0 - 1890691.0 = |  | 9309 | Saving
| i.e | 9309/1900000x100 = 0.489% Saving from PC-1 | [5 empty] | Assistant Engineer
Education Works Sub- Division
Sakrand

## Detail
SCHEDULE - B
Name of Work:- Establishment of single section High School in Sindh 2008-09 Programme ADP 187 @ GBHS Pir Zakri ( W/S & S/Fitting)Ext: Dev: Taluka Sakrand District Shaheed Benazirabad
S.NO | Description | Quantity |  | Unit |  | Rate | Amount
1 | Excavation in foundation of building bridges and other structures including dagbelling
dressing refilling around structure with excavated earth watering and ramming lead upto
5ft. In ordinary soil. (SI, NO: 18 (b) P. 5)
|  |  |  | = | 4447 | Cft
[5 empty] | @ | 3176.25 | %0cft | Rs: | 14125 | 14124.7838
2 | Cement concrete brick or stone bllast 1½" to 2" gauge.(SI, NO: 4 P. 15)
Ratio 1:5:10
|  |  |  | = | 1760 | Cft
[5 empty] | @ | 8694.95 | %cft | Rs: | 155640 | 153031.12
3 | Reinforced cement concrete work including all labour and material except the cost of steel
reinforcement and its labour for bending and binding which will be paid separately. This rate
also includes all kinds of forms moulds. Lifting shuttering curing rendering and finishing the
exposed surface (including screening and washing of shingle)
R.C. work in roof slab, beams columns rafts. Lintels and other structural members laid in
situ or precast laid in position completed in all respects. 1:1-1/2:3. (SI, NO: 6i P. 19)
[5 empty] | 1118 | Cft
[5 empty] | @ | 337 | P.cft | Rs: | 376766 | 376766
4 | Fabrication of mild steel reinforcement for cement concrete including cutting bending,
laying in position making joints and fastenings including cost of binding wire (also includes
removal of rust from bars.) Using Tor Bars. (SI, NO: 7 (b) P.20)
[5 empty] | 54.9 | Cwt
[5 empty] | @ | 5001.7 | P.cwt | Rs: | 274593 | 274593.33
5 | Pacca brick work in foundation and plinth in.1:6. (SI,NO: 4( I )e. P. 25)
|  |  |  | = | 3930 | Cft
[5 empty] | @ | 11948.36 | %cft | Rs: | 469571 | 469570.548
6 | Filling watering and ramming earth under floor with new earth excavated from outside lead
upto one chain and lift upto 5feet. (SI, NO: 22 P.5)
|  |  |  | = | 5045 | Cft
[5 empty] | @ | 3630 | %0cft | Rs: | 18313 | 18313.35
7 | Pacca brick work in ground floor in Cement sand mortar 1:6. (SI, NO: 5( I )e P. 25)
|  |  |  | = | 755 | Cft
[5 empty] | @ | 12674.36 | %cft | Rs: | 95691 | 95691.418
8 | Pacca brick work other than building i/c Striking of joints upto 20 ft height
Cement sand mortar 1:6. (SI, NO: 7( e ) P. 21)
|  |  |  | = | 2636 | Cft
[5 empty] | @ | 12346.65 | %Cft | Rs: | 325458 | 325457.694
9 | Cement plaster 1:6 upto 20" height.(b) ½" thick. (SI, NO: 13(b) P. 58)
|  |  |  | = | 6208 | Sft
[5 empty] | @ | 2206.6 | %sft | Rs: | 136986 | 136985.728
10 | Cement plaster 1:4 upto 20" height.(a) ⅜" thick. (SI, NO: 11(a) P. 58)
|  |  |  | = | 6208
[5 empty] | @ | 2197.52 | %sft | Rs: | 136422 | 136422.0416
11 | Cement Plaster 1:4 Upto 20'Ft Height 3/4" thick (S.I.No.11© P-51)
|  |  |  | = | 575 | Sft
[5 empty] | @ | 3015.76 | %sft | Rs: | 17341 | 17340.62
12 | Cement Pointing Struck joint on walls Ratio 1:2 (S.I.No.19(a) P-52)
[5 empty] | 4422 | Sft
[5 empty] | @ | 1287.44 | %Sft | Rs: | 56930 | 56930.5968
13 | Extra labour rate for making cement plaster pattas/band around straight or curved opening &
around the edges of roof slabs the width not less than 6" with fine finishing as directed by Engineer
incharge.(S.I.No.35 P-54)
|  |  |  | = | 1150 | Rft |  |  |  | 0
[5 empty] | @ | 19.36 | PRft | Rs: | 22264 | 22264
Providing & Fixing in position Chip Board 3/4" thick for filling space between expansion joint
of building.(S.I.No.93P.108)
|  |  |  | = | 108 | Rft |  |  |  | 0
[5 empty] | @ | 43.26 | PSft | Rs: | 4672 | 4672.08
14 | Providing and laying 1" thick topping cement concrete (1:2:4) including surface finishing and
dividing into panels. (SI, NO: 16 P. 47)
2" thick
|  |  |  | = | 4489 | Sft
[5 empty] | @ | 3275.5 | %sft | Rs: | 147037 | 147037.195
3" thick
|  |  |  | = | 1063 | Sft |  |  |  | 0
[5 empty] | @ | 4411.82 | %sft | Rs: | 46898 | 46897.6466
15 | Two coats of bitumen laid hot using 34 lbs for %sft over roof and blinded with sand at one
Cft per % Sft. (SI, NO: 13 P.41)
[5 empty] | 2839 | Sft
[5 empty] | @ | 1887.4 | %sft | Rs: | 53583 | 53583.286
16 | Cement concrete plain including placing compacting,finishing and curing complete (including
screening and washing of stone aggregate without shuttering.(S.I.No.05(h) P- 15)
Ratio 1:3:6
|  |  |  | = | 450 | Cft
[5 empty] | @ | 12595 | %cft | Rs: | 56678 | 56677.5
17 | Primary Coat of Chalk under distembering ( S.I.No. 23 P-54).
|  |  |  | = | 5879 | Sft
[5 empty] | @ | 442.75 | %Sft | Rs: | 26029 | 26029.2725
18 | Preparing the and painting with Matt finish i/c rubbing the surface with Bathy filling voids with
zink/chalk/plaster of pairs mixture applying first coat premix, making the surface smooth and
then painting 3-coats with matt finish of approved make etc.(S.I.No.36(A) P# 55)
|  |  |  | = | 15922 | Sft
[5 empty] | @ | 3444.38 | %sft | Rs: | 548414 | 548414.1836
19 | Distembering 3 - Coats (S.I.No. 24 P# 53)
|  |  |  | = | 5879 | Sft
[5 empty] | @ | 1079.65 | %sft | Rs: | 63473 | 63472.6235
20 | Painting doors and windows any type three coats.( S.I.No.5© P- 69)
New Surface
|  |  |  | = | 2455 | Sft
[5 empty] | @ | 2116.41 | % Sft | Rs: | 51958 | 51957.8655
21 | Preparing surface and painting guard bars,gate of iron bars,gratings,raillings i/c
standard braces, etc similar opening work.(S.I.No.5(d) P- 69.
New Surface
|  |  |  | = | 120 | Sft |  |  |  | 0
[5 empty] | @ | 1270.83 | %Sft | Rs: | 1525 | 1524.996
22 | Colour Washing (S.I.No.25(b) P- 53)
Two Coats
|  |  |  | = | 4422 | Sft
[5 empty] | @ | 859.9 | %Sft | Rs: | 38025 | 38024.778
23 | Preparing the surface and painting with wheather coat i/c rubbing the surface with rubbing
bricks /sand paper,filling the voids with chalk/plaster of pairs and then painting wiyh weather
coat of approved make.(S.I.No.38 P-55)
|  |  |  | = | 10446
[5 empty] | @ | 1948.1 | %Sft | Rs: | 203499 | 203498.526
24 | Providing & Fixing angle iron Vertical posts for barbed wire fencing of size 2" x 2" x1/4'
embeded in Rcc/Masonary pillers i/c Making cuts/holders @ 12" i/c fixing in pillers
by chiseling and filling the with cement sand mortor,saprining & finishing the surface.(S.I.No.6 P-94)
|  |  |  | = | 280 | Rft |  |  |  | 0
[5 empty] | @ | 169.18 | P.Rft | Rs. | 47370 | 47370.4
25 | Providing & Fixing barbed wire fencing with 12 guage 4 points @ 6" apart barded wire i/c
straightening & fixing in angle iron vertical post.(S.I.No.9 P-95)
[5 empty] | 2400 | Rft |  |  |  | 0
[5 empty] | @ | 8.38 | Prft | Rs: | 20112 | 20112
Making & Fixing Steel grated door with 1/16" thick sheeting i/c angle iron frame 2"x 2"x 3/8"
and 3/4" square bars 4" c/c with locking arrangement.(S.I.No.24 P-91)
|  |  |  | = | 60 | Sft
[5 empty] | @ | 726.72 | P.Sft | Rs. | 43603 | 43603.2
26 | Erection and removal of centering for R.C.C or plain concrete works of Partal wood(2nd-Class)
Vertical (S.I.No. 19(b) ii P# 18)
|  |  |  | = | 1200 | Sft
[5 empty] | @ | 3127.41 | %Sft | Rs: | 37529 | 37528.92
27 | Barrowpit excation undressed lead upto 100ft.(S.I.No.3 P# 01)
|  |  |  | = | 26000 | Cft |  |  |  | 0
[5 empty] | @ | 2117.5 | %ocft | Rs: | 55055 | 55055
28 | Dressing and levelling of earth work to design section etc complete.(S.I.No.11(b) P# 3)
|  |  |  | = | 26000 | Cft
[5 empty] | @ | 187.55 | %ocft | Rs: | 4876 | 4876.3
29 | S/F Calighaphic tile of approved size in required colour and design of specification jiontd
in white cement and pigment over base of 3/4".(R.A)
|  |  |  | = | 20 | Sft
[5 empty] | @ | 623 | PSft | Rs: | 12460 | 12460
30 | P/L Halla or pattern tile glazed 6"x6"x1/4" on floor or wall facing in required colour and pattern
of STILE specification jointd in white cement and pigment over a base of 1:2 grey cement mortar
and pigment over a base of 1:2 grey cement mortar 3/4" thick i/c washing and filling of joints with
slury of white cement pigment in desired shape with finishing cleaning the cost of Wax polish
etc complete i/c cutting tile proper profile.(S.I.No.61 P# 47)
|  |  |  | = | 84 | Sft |  |  |  | 0
[5 empty] | @ | 47651.56 | PSft | Rs: | 40027 | 40027.3104
31 | Hard wood railling of any shape and design including bends and corners fixed in position
including polishing complete as directed.
|  |  |  | = | 30 | Sft
[5 empty] | @ | 375.78 | PSft | Rs: | 11273
32 | Providing and Fixing ornamental Cement Jalli 2" thick 1: 2:4 without steel.(S.I.No.11 P# 18)
|  |  |  | = | 128 | Sft
[5 empty] | @ | 226.02 | PSft | Rs: | 28931
33 | Supplying & fixing in position iron / steel grill of ¾" x ¼" size flat iron of approved
designe including painting 3 coats etc. complete wight not tobe less than 3.7 Lbs/sq foot of
finished grill.(SI, NO: 26 P.97)
|  |  |  | = | 64 | Sft
[5 empty] | @ | 180.5 | P.sft | Rs: | 11552 | 11552
34 | Supply of clean jscreened (River or Pit) sand within 5 chains i/c removal of Top crust of earth
or over burden and royalty to the Government or cost to the private owner.(S.I.No.36 P# 6)
|  |  |  | = | 900 | Cft |  |  |  | 0
[5 empty] | @ | 420 | %0 Cft | Rs: | 378 | 3780
35 | RCC spout i/c fixing in position with top in bottom khuras.(S.I.No. 27 P# 19)
|  |  |  | = | 10 | Nos:
[5 empty] | @ | 524.98 | P.No. | Rs: | 5250
36 | Khaprail of cement concrete 12"x8"x1" of approved design /shape laid flate in 1:2 grey
cement mortar over a bed of 3/4" thick grey cement mortar (1;2).(S.I.No.39P-37)
|  |  |  | = | 329 | Sft
[5 empty] | @ | 8977.9 | %Sft | Rs: | 29537 | 29537.291
37 | Laying white marble flooring fine dressed in the surface without winding set in the lime mortar
(1:2) i/c rubbing & polishing of the joints.(S.I.No.28 P# 42)
|  |  |  | = | 350 | Sft
[5 empty] | @ | 567.48 | P.sft | Rs: | 198618 | 198618
38 | Providing and fixing ⅜" thick marble tiles of approved quality & colour shade size
8" x 4/6" x 4" in dado skirting & facing removal / tucking of existing plaster surface etc.
over ½" thick of cement mortar 1:3 setting mortar base including filling the joints &
washing the tiles with white cement slurry, current, finishing cleaning and polishing etc.
complete.(SI,NO: 68 P.55)
|  |  |  | = | 130
[5 empty] | @ | 186.04 | P.sft | Rs: | 24185 | 24185.2
39 | Making & Fixing grating in oppening i/c fixing at site with flat iron 2"x3/8"&3/4" square
bar at 4" c/c.(S.I.No.25P.91)
|  |  |  | = | 75
[5 empty] | @ | 293.15 | P.sft | Rs: | 21986 | 21986.25
40 | Add extra labour for brick work First Floor.(S.I.No. 6 P# 22)
|  |  |  | = | 455 | Cft
[5 empty] | @ | 438.63 | %Cft | Rs: | 1996 | 1995.7665
41 | Add extra labour for R.C.C First Floor.(S.I.No. 6 P# 17)
|  |  |  | = | 381 | Cft
[5 empty] | @ | 12.1 | PCft | Rs: | 4610 | 4610.1
|  |  | Total |  |  |  |  | Rs: | 3941239 | 3941239

## M.St
MATERIAL STATEMENT
Name of Work:- Establishment of Single Section High School in Sindh 2008 -09 programme @ GBHS Pir Zakri(Balance Work & W/S & S/F)
Taluka Sakrand Dist: SBA
S.No | Particulars | Quantity | Cement | Sand | Stone | Bajri | Steel | Brick | Earth Filling
1 | Cement Concrete brick stone 1:5:10 | 1760 | 137.28 | 862.4 | 1724.8
2 | P.Brick work 1:6 | 7321 | 251.8424 | 1881.497 |  |  |  | 98833.5
3 | Reinforced Cement Concrete 1:2:4 | #REF! | #REF! | #REF! |  | #REF!
4 | Fabrication | #REF! | - | - | - | - | #REF!
5 | C.C Topping 2" thick | 4489 | 134.67 | 332.186 |  | 659.883
6 | C.C Topping 3" thick | 1063 | 46.772 | 116.93 |  | 233.86
7 | Cement Plaster 1/2 ratio 1:6 | 6208 | 32.9024 | 248.32
8 | Cement Plaster 3/8" ratio 1:4 | 6208 | 35.3856 | 186.24
9 | Cement Plaster 3/4" ratio 1:4 | 575 | 6.555 | 31.625
10 | Cement Concrete plain 1:3:6 | 450 | 58.5 | 207 |  | 414
11 | Cement Pointing Ratio 1:2 | 4422 | 31.8384 | 79.596
12 | Earth Filling | 31945 | - | - | - | - | - | - | 31945
Qunatity |  |  | #REF! | #REF! | 1724.8 | #REF! | #REF! | 98833.5 | 31945
Rate |  |  | 44.13 | 2986.04 | 2855.8 | 3441.88 | 499.528 | 617.54 | 771.96
Amount |  |  | 40688 | 130221 | 49263 | 78888 | 1371 | 58533 | 246603
| Total Amount Rs. | 605567
| Sub-Engineer | [5 empty] | Assistant Engineer
Education works Sub-Division
Sakrand
|  |  | 922 | 4361 | 1725 | 2292 | 2.745 | 94784 | 31945
|  |  | 40687.86 | 130221.2044 | 49262.55 | 78887.8896 | 1371.2044 | 58532.9114 | 246602.622
605566.2417

## Sum
SUMMARY OF COST
Name of Work:- |  | Establishment of Single Section High School in sindh 2008 -09 programme at GBHS Pir Zakri(Balance work & W/S & S/F) Taluka Sakrand District Shaheed Benazirabad.
Part - A
| 01) | Cost of Schedule Items |  | Rs. | 3810228
| 02) | Cost of Carriage of Material |  | Rs. | 605567
| 03) | Cost of Non Schedule Item |  | Rs. | 12460
4428255
Part - B
| 04) | Cost of S.I | = | Rs. | 184861
| 05) | Cost of Non-Schedulled Items | = | Rs. | 145595
| 06) | Add Contigency 2% |  | Rs. | 76205 | 76204.56
|  |  | Grand Total | Rs. | 4834916
|  |  | Say | Rs. | 4835000
| Sub:Engineer |  |  | Assistant Engineer
Education Works Sub:Division
Sakrand

## F.R
Financial Review
Name of Work:- Establishment of Single Section High School in Sindh 2008 -09 Programme @ GBHS Pir Zakri (balance Work & W/S & S/F) Taluka Sakrand District Shaheed Benazirabad
S.No. | Description | PC-I Cost | Amount Taken for Estimate Rs: | Expenditur upto date Rs: | Expenditure to be done Rs: | Grand Total Rs:
1) | Main Building | 8877160 | 8877160 | 16003572 | 4835000 | 20838572
| W/S & S/Fitting | 1288620 | 1288620
| Electrification | 1145440 | -
| Sui Gas | 429540 | -
2 | Compound Wall | 2108000 | 2108000
5 | U.G /O.H Tank | 1160000 | 1160000
6 | Add 15% Ext: devlop: | 1761114 | 1761114
1 | Face Lifting | 1125000 | 1125000
2 | Energization provision | 500000 | -
3 | Soil Investigation | 50000 | -
| Antitermite Treatment | 200000 | 200000
H) | Escalation 3 Years | 1732120 | 1732120
|  | 20376994 | 18252014 | 16003572 | 4835000 | 20838572
| Excess/Saving | 18252014.00 - 20838572.00 = - 2586558 Excess
| i.e | 2586558/18252014x100 = - 14.17% Excess from PC-1
Which is within the permissible limit of 15%.
| Sub-Engineer |  | Assistant Engineer
Education Works Sub.Division
Sakrand

## Face Sheet
Face Sheet
FUND HEAD |  |  | : | Government of sindh
MAJOR HEAD |  |  | : | 09 - education affairs and Services (Capital) 092 Secondary education Affairs and Services 092 secondary education Affairs and services 0921 - Secondary education.
SERVICE HEAD |  |  | : | Education Works
DEPARTMENT HEAD |  |  | : | ESTABLISHMENT OF SINGLE SECTION HIGH SCHOOL IN SINDH
2008-09 PROGRAMME AT GBHS PIR ZAKRI (BALANCE WORK & W/S &
S/F ) TALUKA SAKRANDDISTRICT SHAHEED BENAZIRABAD.
This Estimate has been frammed in the office of Executive Engineer education Works
Division Shaheed Benazirabad. The probable Expenditure incurred on the above named work will be chargeable
against the head of Accountas Above.
Estimate Cost Rs.
GENERAL DESCRIPTION:-
|  | Government of Sindh has been approved the above scheme under ADP NO 1170 |  |  |  |  | during
2008 -09 which is to be executed by the education works Division Shaheed Benazirabad
The above said scheme is one of the approved scheme hence this estimate is mainly Based are
provided in the composite schedule of the rate of finished item work Vol: III Part-III sindh education Edition 2012
SCOPE:- |  | This estimate is frammed for all related components of the scheme as per PC-I approved
by the Sindh Government is within the permissible limit of administrative approval.
LAND :- | The Education Department District Shaheed Benazirabd provided plot for construction of the proposed
work/scheme.
METHOD OF EXECUTION:-
The wotk has been carried out in accordance with the schedule of Rates 2012 Building for
finished item of building items of approved rates by the copetent auithority in case of non schedule items.
The work will be let out through open competative tenders and executed as per Technical sanction by the
compitant authority.
No lead weather small or long for carriage of material for items as per schedule is to be paid
sepretaly. However the provision of the cost of carriage of material from predetermined approved sources of supply
detailed below are made in the estimate.
Bajri |  |  |  | From |  | Thana Bola Khan
Stone Ballast |  |  |  | From |  | Nihal Shah
Hill Sand |  |  |  | From |  | Bolhari
Steel & Cement |  |  |  | From |  | Hyderabad
|  | Assistant Engineer |  |  |  | Executive Engineer
| Education Works Sub- Division |  |  |  |  | Education Works Division
|  | Sakrand |  |  |  | Shaheed Benazirabad

## Compatibility Report
Compatibility Report for Mode School NShah New Rates Rechek.xls
Run on 3/13/2013 12:40
The following features in this workbook are not supported by earlier versions of Excel. These features may be lost or degraded when you save this workbook in an earlier file format.
Minor loss of fidelity | # of occurrences
Some formulas in this workbook are linked to other workbooks that are closed. When these formulas are recalculated in earlier versions of Excel without opening the linked workbooks, characters beyond the 255-character limit cannot be returned. | 6
'M.St'!D18:H18
'M.St'!J18