## Sheet1
ANNUAL PROCUREMENT PLAN FINANCIAL YEAR 2015-16
EXECUTIVE ENGINEER HIGHWAYS DIVISION (W&S) TANDO ALLAHYAR
S.# | Description of Procurement | Quantity (where applicable) | Estimated Unit cost (where applicable million) | Funds allocated in million | Souree of funds (ADPs / Non-ADPs) | Proposed Procurement Method | Timing of Procurements |  |  |  | Remarks
[7 empty] | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Provincial Annual Development Programme 2015-16
1 | Widening / Re-Conditioning of link road from Tail Mori to Tando Allahyar Sugar Mill via Sobhraj mile 4/4-5/1 (1.00Km) | Road Work | 12.978 | 10 | Prov:ADP | Single stage one Envolep Procurement | Yes | - | - | -
Annual Development Programme 2015-16 (New)
1 | Reconditioning of Link road from Tando Adam Tando Allahyar road Qaiser Goth stop to village Panah Shah mile 0/0-0/5 (1.00KM) | Road Work | 4.565 | 1.1413 | ADP | Single stage one Envolep Procurement | Yes | - | - | -
2 | Construction of mettaled road from Majno Loharani to Mohammad Urs Loharani mile 0/0-0/2 (0.40 km) | Road Work | 3.195 | 0.79875 | ADP | Single stage one Envolep Procurement | Yes | - | - | -
3 | Construction of mettaled road from Allah Dino Khaskheli to Yousif Narejo mile 0/0-0/3 (0.60 Km) (1st Phase) | Road Work | 4.382 | 1.0955 | ADP | Single stage one Envolep Procurement | Yes | - | - | -
4 | Construction of mettaled road from Shah Latif Colony Bukera road to Naseeba Colony mile 0/0-0/2 (0.40 Km) | Road Work | 2.951 | 0.73775 | ADP | Single stage one Envolep Procurement | Yes | - | - | -
5 | Construction of mettaled road from Rajo Lashari road to Babo Abdul Hafiz Halepoto mile 0/0-0/3 (0.60 Km) | Road Work | 4.417 | 1.1042 | ADP | Single stage one Envolep Procurement | Yes | - | - | -
6 | Reconditioning of link road from Hadiki Distry to Allah Rakhio Pathan mile 0/0-0/5 (1.0 Km) | Road Work | 4.89 | 1.2225 | ADP | Single stage one Envolep Procurement | Yes | - | - | -
7 | Reconditioning of link road from Mall Khan Thebo road to Mirabad Dhora Portion mile 0/4-5/0 (1.0 Km in portion) | Road Work | 4.5 | 1.125 | ADP | Single stage one Envolep Procurement | Yes | - | - | -
8 | Reconditioning of link road from Ahmed Kolachi to Dargah Gajelo Sharif Gate mile 0/0-0/6 (1.20 Km) | Road Work | 4.942 | 1.2355 | ADP | Single stage one Envolep Procurement | Yes | - | - | -
9 | Reconditioning of link road from Tando Adam Mirpurkhas road to village Old Mirabad mile 0/0-0/4 i/c approaches | Road Work | 3.9 | 0.975 | ADP | Single stage one Envolep Procurement | Yes | - | - | -
10 | Construction of approach road from Sultanabad road to Kacthi Colony 2 furlong (0.40Km) | Road Work | 3 | 0.75 | ADP | Single stage one Envolep Procurement | Yes | - | - | -
11 | Construction of link road village Chanesar Chutto 1 furlong mile 0/0-0/1 (0.20 KM) | Road Work | 1.543 | 0.38575 | ADP | Single stage one Envolep Procurement | Yes | - | - | -
12 | Reconditioning of link road from Bukera By Pass road to Bachal Kerio mile 0/0-0/2+330’ (0.50Km) | Road Work | 2.457 | 0.61425 | ADP | Single stage one Envolep Procurement | Yes | - | - | -
13 | Construction Link Road for Jaffer Senhro mile 0/0-0/2+330' =0.5 Km | Road Work | 3.524 | 0.881 | ADP | Single stage one Envolep Procurement | Yes | - | - | -
14 | Construction Link Road from Baloch Chandio to Imam Bargha 1 Furlong =0.20Km | Road Work | 1.784 | 0.446 | ADP | Single stage one Envolep Procurement | Yes | - | - | -
15 | Construction of Link road from village Bacho Thebo to Dhani Bux Mari Via Dargha Saman Shah 0/0-0/3 (0.6 Km) | Road Work | 4.5 | 1.125 | ADP | Single stage one Envolep Procurement | Yes | - | - | -
16 | Construction of Link road from village Haji Darya Khan Mari to Muhammad Saleh Mari 0/0-0/2+330" (0.50 Km) | Road Work | 3.774 | 0.9435 | ADP | Single stage one Envolep Procurement | Yes | - | - | -
17 | Construction of Link road from Mir Wah road to Village Shafi Mari 0/0-0/1 +330' (0.30 Km) | Road Work | 2.2 | 0.55 | ADP | Single stage one Envolep Procurement | Yes | - | - | -
18 | Construction of link road from Mehran Farm road to village Yaqoob Mari mile 0/0-0/3 (0.60 KM) | Road Work | 4.43 | 1.1075 | ADP | Single stage one Envolep Procurement | Yes | - | - | -
| TOTAL |  | 64.954 | 16.2385
| G-TOTAL |  | 77.932 | 26.2385
EXECUTIVE ENGINEER
HIGHWAYS DIVISION
TANDO ALLAHYAR