## M. Khan Shoro-I
Annexure A-1
(Annexure-A)
PROCUREMENT PLAN (Development)
Serial No/ ADP No: | Name of Scheme & Estimated Cost | Allocated Funds | Cost of ongoing works (Expenditure already incurred | Funds ongoing works | Cost of new works (components) | Funds for New works | Nature of Procurement | Method of Procurement | Anticipated / Actual Date of Advertisement | Anticipated/Actual Date of Start | Anticipated/Actual Date of Completion
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Provincial ADP 2015-2016
1 | Supplying Installing & Testing Pumping Machinery 20 BHP (2 Sets) i/c Inter Connection @ Water Works, Providing, Laying Jointing and Testing PVC Pipe 4” dia for Distribution System for Rural Water Supply Scheme Muhammad Khan Shoro (Dabhoo) Taluka Kotri District Jamshoro Rs:- 5.000 | 5 | 0 | 5 | Rs: - 5.000 01. Tube Well i/c Trial Bore (01 No) 02. Pump House (01 No) 03. P/Machinery 15 BHP 01 Set 04. Distribution System i. PVC Pipe 3" (2770 Rft:) ii. PVC Pipe 3" (1700 Rft:) 05. L.S.R / Storage Tank (01 No) | 5 | Execution of construction work | Single Stage Envelope | 11/2015 | After issue of Work Order | 06/2016
(RASHEED AHMED SOOMRO)
EXECUTIVE ENGINEER
PUBLIC HEALTH ENGG: DIVISION
JAMSHORO

## M. Khan Shoro-II
ANNEXURE A-II
ANNEXURE-II
PROCUREMENT PLAN (Non-Development)
S. No | Found Head & Sub head | Name of work and break up | Allocated Found and break up for different locations/sites | ltems to be executed | Method of Procurement | Anticipated/Actual of Advertisement | Anticipated/Actual Date of Start | Anticipated/Actual Date of Completion | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
--------------NIL--------------
(RASHEED AHMED SOOMRO)
EXECUTIVE ENGINEER
PUBLIC HEALTH ENGG: DIVISION
JAMSHORO

## Yameen Palari-I
Annexure A-1
(Annexure-A)
PROCUREMENT PLAN (Development)
Serial No/ ADP No: | Name of Scheme & Estimated Cost | Allocated Funds | Cost of ongoing works (Expenditure already incurred | Funds ongoing works | Cost of new works (components) | Funds for New works | Nature of Procurement | Method of Procurement | Anticipated / Actual Date of Advertisement | Anticipated/Actual Date of Start | Anticipated/Actual Date of Completion
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Provincial ADP 2015-2016
1 | Construction of Water Supply Scheme Yameen Palari, Taluka Thana Bula Khan District Jamshoro Rs:- 5.500 | 6.685 | 0 | 6.685 | Rs: - 5.500 01. Tube Well i/c Trial Bore (01 No) 02. Pump House (01 No) 03. P/Machinery 15 BHP 01 Set 04. Distribution System i. PVC Pipe 3" (2770 Rft:) ii. PVC Pipe 3" (1700 Rft:) 05. L.S.R / Storage Tank (01 No) | 6.685 | Execution of construction work | Single Stage Envelope | 11/2015 | After issue of Work Order | 06/2016
(RASHEED AHMED SOOMRO)
EXECUTIVE ENGINEER
PUBLIC HEALTH ENGG: DIVISION
JAMSHORO

## Yameen Palari-II
ANNEXURE A-II
ANNEXURE-II
PROCUREMENT PLAN (Non-Development)
S. No | Found Head & Sub head | Name of work and break up | Allocated Found and break up for different locations/sites | ltems to be executed | Method of Procurement | Anticipated/Actual of Advertisement | Anticipated/Actual Date of Start | Anticipated/Actual Date of Completion | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
--------------NIL--------------
(RASHEED AHMED SOOMRO)
EXECUTIVE ENGINEER
PUBLIC HEALTH ENGG: DIVISION
JAMSHORO

## P-Mach Subhanallah Colony-I
Annexure A-1
(Annexure-A)
PROCUREMENT PLAN (Development)
Serial No/ ADP No: | Name of Scheme & Estimated Cost | Allocated Funds | Cost of ongoing works (Expenditure already incurred | Funds ongoing works | Cost of new works (components) | Funds for New works | Nature of Procurement | Method of Procurement | Anticipated / Actual Date of Advertisement | Anticipated/Actual Date of Start | Anticipated/Actual Date of Completion
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Provincial ADP 2015-2016
1 | Supplying / Installing & Testing Pumping Machinery 30 BHP (4 Sets) i/c Diesel Engine 48 BHP @ Disposal work i/c P/L/J Testing A.C. Pipe 20" dia for Drainage Scheme Subhanallah Colony Taluka Kotri District Jamshoro Rs:- 6.570 | 6.57 | 0 | 6.57 | Rs: - 6.570 01. Tube Well i/c Trial Bore (01 No) 02. Pump House (01 No) 03. P/Machinery 15 BHP 01 Set 04. Distribution System i. PVC Pipe 3" (2770 Rft:) ii. PVC Pipe 3" (1700 Rft:) 05. L.S.R / Storage Tank (01 No) | 6.57 | Execution of construction work | Single Stage Envelope | 12/2015 | After issue of Work Order | 06/2016
(RASHEED AHMED SOOMRO)
EXECUTIVE ENGINEER
PUBLIC HEALTH ENGG: DIVISION
JAMSHORO

## Annexure-I
(Annexure-A)
PROCUREMENT PLAN (Development)
Serial No/ ADP No: | Name of Scheme & Estimated Cost | Allocated Funds | Cost of ongoing works (Expenditure already incurred | Funds ongoing works | Cost of new works (components) | Funds for New works | Nature of Procurement | Method of Procurement | Anticipated / Actual Date of Advertisement | Anticipated/Actual Date of Start | Anticipated/Actual Date of Completion
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Provincial ADP 2015-2016
1 | Renovation of Existing scheme for Removal of hazardous dirty water accumulated behind village Bakhar Jamali Taluka Saeedabad, District Matiari. (2.920) | 12 | 0 | 0 | Rs: 2.920 1. Repair of Surface Drain T-A =650.0 Rft Drain T-B= 650.0 Rft 2, Constrruction of C/Wall 112.00 Rft 3.C.C Block 5600.0Sft 4. Collecting Tann 15' ft Dia 1 No. 5. Screening Chamber 8' x 5' 1 No. 6. Pump House (10'x12') 1 No. 7. Rising Main 6" dia 200.00 Rft 8. Repair of Pmping Machinery 1 Job. 3. S/I Pumping Machin- ery 10 BHP 1 Set | 2 | Execution of construction work | Single Stage Envelope | 15/03/2015 | After issue of Work Order | 12/2016
2 | Construction of RCC Collecting Tank, Screening Chamber, Inter connection & Pump House for Removal of hazardous dirty water accumulated behind village Bakhar Jamali Taluka Saeedabad District Matiari. (5.360) | 12 | 0 | 0 | Rs. 5.360 1. Construction of Collecting tank 30' ft dia 2 Nos. 2.Constrtuction Screening Chamber 10' dia 1 No. 3. Construction of Pump House (16'x20') 1 No. | 5 | Execution of construction work | Single Stage Envelope | 15/03/2015 | After issue of Work Order | 12/2016
3 | Construction of RCC Feeding Channel (1000 Rft) for Removal of hazardous dirty water accumulated behind village Bakhar Jamali Taluka Saeedabad District Matiari. (12.900) | 12 | 0 | 0 | Rs. 12.900 1. Construction of RCC feeding Channel 1000.00 Rft | 5 | Execution of construction work | Single Stage Envelope | 15/03/2015 | After issue of Work Order | 12/2016
4 | Construction of Staff quarter, Compound Wall i/c C.C Block for Rural Drainage scheme Sanghar Soomro Taluka & District Matiari. (5.465) | 4.27 | 0 | 0 | Rs. 5.465 1. Construction of Staff Quarter No.01. 2. Construction of Compound Wall 335.00 Rft 3. C.C Block 46410.00 Sft | 1.6 | Execution of construction work | Single Stage Envelope | 15/03/2015 | After issue of Work Order | 12/2016
5 | Construction of Surface Drains Type-A & B for Rural Drainage Scheme Sanghar Soomro Taluka & District Matiari. (4.475) | 4.27 | 0 | 0 | Rs.4.475 1.Open Surface Drain Type-I Drain 4990.00 Rft Type-II Drain 2150.00 Rft. | 1.6 | Execution of construction work | Single Stage Envelope | 15/03/2015 | After issue of Work Order | 12/2016
6 | Construction of Collecting Tank 10’ ft dia, Screening Chamber (8’ x 5’), Pump House i/c Pumping Machinery 5.50 BHP, Diesel Engine 8 BHP & PVC Rising Main 4” dia for Rural Drainage Scheme Sanghar Soomro Taluka & District Matiari. (2.380 | 4.27 | 0 | 0 | Rs. 2.380 1. Collecting Tank 10' dia 1 No. 2. Screening Chamber (5'x8') 1 No. 3.Pump House (10'12') 1 No. 4. Pumping Machinery 5.5 BHP Electric 1 No. 5. Diesel Engine 8 HP 1 No. 6. Rising Main 4" dia 1000.00 Rft | 1.07 | Execution of construction work | Single Stage Envelope | 15/03/2015 | After issue of Work Order | 12/2016
7 | Construction of Collecting Tank 10’ ft dia , Screening chamber (8’ x 5’ ), Pump House, Pumping Machinery 7.50 BHP, Diesel Engine 12 BHP & PVC Rising Main 6” dia for Rural Drainage Scheme Ameen Lakho Taluka Saeedabad District Matiari. (4.200) | 6.25 | 0 | 0 | Rs. 4.200 1. Construction of Collecting Tank 10' ft dia 1 No. 2. Constrruction screening Chamber (5'x8') 1 No. 3. Pump House (10'x12') 1 No. 4. P/ I Pumping Machinery 7.50 BHP 1 set 5. Providing Diesel Engine 12 BHP 1 Set 6. Rising Main 6" dia 5800.00 Rft | 2.5 | Execution of construction work | Single Stage Envelope | 15/03/2015 | After issue of Work Order | 12/2016
8 | Construction of C.C Block for Rural Drainage Scheme Ameen Lakho Taluka Saeedabad, District Matiari. (4.000) | 6.25 | 0 | 0 | Rs. 4.000 1. Construction of C.C Block 38200.00 Sft | 1.25 | Execution of construction work | Single Stage Envelope | 15/03/2015 | After issue of Work Order | 12/2016
9 | Construction of Surface Drains Type A ,B & C for Rural Drainage Scheme Ameen Lakho, Taluka Saeedabad District Matiari. (7.400) | 6.25 | 0 | 0 | Rs.7.400 1. Open Surface Drain Type-A= 6205.00 Rft Type-B=2085.00 Rft Type-C=1850.00 Rft | 2.5 | Execution of construction work | Single Stage Envelope | 15/03/2015 | After issue of Work Order | 12]/2016
(MUHAMMAD AKBAR BALOCH)
EXECUTIVE ENGINEER
PUBLIC HEALTH ENGG:DIVISION
MATIARI

## Annexure-II
ANNEXURE A-II
ANNEXURE-II
PROCUREMENT PLAN (Non-Development)
S. No | Found Head & Sub head | Name of work and break up | Allocated Found and break up for different locations/sites | ltems to be executed | Method of Procurement | Anticipated/Actual of Advertisement | Anticipated/Actual Date of Start | Anticipated/Actual Date of Completion | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
--------------NIL--------------
(MUHAMMAD AKBAR BALOCH)
EXECUTIVE ENGINEER
PUBLIC HEALTH ENGG: DIVISION
MATIARI