## M. Khan Shoro-I
Annexure A-1
(Annexure-A)
PROCUREMENT PLAN (Development)
Serial No/ ADP No: | Name of Scheme & Estimated Cost | Allocated Funds | Cost of ongoing works (Expenditure already incurred | Funds ongoing works | Cost of new works (components) | Funds for New works | Nature of Procurement | Method of Procurement | Anticipated / Actual Date of Advertisement | Anticipated/Actual Date of Start | Anticipated/Actual Date of Completion
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Provincial ADP 2015-2016
1 | Supplying Installing & Testing Pumping Machinery 20 BHP (2 Sets) i/c Inter Connection @ Water Works, Providing, Laying Jointing and Testing PVC Pipe 4” dia for Distribution System for Rural Water Supply Scheme Muhammad Khan Shoro (Dabhoo) Taluka Kotri District Jamshoro Rs:- 5.000 | 5 | 0 | 5 | Rs: - 5.000 01. Tube Well i/c Trial Bore (01 No) 02. Pump House (01 No) 03. P/Machinery 15 BHP 01 Set 04. Distribution System i. PVC Pipe 3" (2770 Rft:) ii. PVC Pipe 3" (1700 Rft:) 05. L.S.R / Storage Tank (01 No) | 5 | Execution of construction work | Single Stage Envelope | 11/2015 | After issue of Work Order | 06/2016
(RASHEED AHMED SOOMRO)
EXECUTIVE ENGINEER
PUBLIC HEALTH ENGG: DIVISION
JAMSHORO

## M. Khan Shoro-II
ANNEXURE A-II
ANNEXURE-II
PROCUREMENT PLAN (Non-Development)
S. No | Found Head & Sub head | Name of work and break up | Allocated Found and break up for different locations/sites | ltems to be executed | Method of Procurement | Anticipated/Actual of Advertisement | Anticipated/Actual Date of Start | Anticipated/Actual Date of Completion | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
--------------NIL--------------
(RASHEED AHMED SOOMRO)
EXECUTIVE ENGINEER
PUBLIC HEALTH ENGG: DIVISION
JAMSHORO

## Yameen Palari-I
Annexure A-1
(Annexure-A)
PROCUREMENT PLAN (Development)
Serial No/ ADP No: | Name of Scheme & Estimated Cost | Allocated Funds | Cost of ongoing works (Expenditure already incurred | Funds ongoing works | Cost of new works (components) | Funds for New works | Nature of Procurement | Method of Procurement | Anticipated / Actual Date of Advertisement | Anticipated/Actual Date of Start | Anticipated/Actual Date of Completion
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Provincial ADP 2015-2016
1 | Construction of Water Supply Scheme Yameen Palari, Taluka Thana Bula Khan District Jamshoro Rs:- 5.500 | 6.685 | 0 | 6.685 | Rs: - 5.500 01. Tube Well i/c Trial Bore (01 No) 02. Pump House (01 No) 03. P/Machinery 15 BHP 01 Set 04. Distribution System i. PVC Pipe 3" (2770 Rft:) ii. PVC Pipe 3" (1700 Rft:) 05. L.S.R / Storage Tank (01 No) | 6.685 | Execution of construction work | Single Stage Envelope | 11/2015 | After issue of Work Order | 06/2016
(RASHEED AHMED SOOMRO)
EXECUTIVE ENGINEER
PUBLIC HEALTH ENGG: DIVISION
JAMSHORO

## Yameen Palari-II
ANNEXURE A-II
ANNEXURE-II
PROCUREMENT PLAN (Non-Development)
S. No | Found Head & Sub head | Name of work and break up | Allocated Found and break up for different locations/sites | ltems to be executed | Method of Procurement | Anticipated/Actual of Advertisement | Anticipated/Actual Date of Start | Anticipated/Actual Date of Completion | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
--------------NIL--------------
(RASHEED AHMED SOOMRO)
EXECUTIVE ENGINEER
PUBLIC HEALTH ENGG: DIVISION
JAMSHORO

## P-Mach Subhanallah Colony-I
Annexure A-1
(Annexure-A)
PROCUREMENT PLAN (Development)
Serial No/ ADP No: | Name of Scheme & Estimated Cost | Allocated Funds | Cost of ongoing works (Expenditure already incurred | Funds ongoing works | Cost of new works (components) | Funds for New works | Nature of Procurement | Method of Procurement | Anticipated / Actual Date of Advertisement | Anticipated/Actual Date of Start | Anticipated/Actual Date of Completion
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Provincial ADP 2015-2016
1 | Supplying / Installing & Testing Pumping Machinery 30 BHP (4 Sets) i/c Diesel Engine 48 BHP @ Disposal work i/c P/L/J Testing A.C. Pipe 20" dia for Drainage Scheme Subhanallah Colony Taluka Kotri District Jamshoro Rs:- 6.570 | 6.57 | 0 | 6.57 | Rs: - 6.570 01. Tube Well i/c Trial Bore (01 No) 02. Pump House (01 No) 03. P/Machinery 15 BHP 01 Set 04. Distribution System i. PVC Pipe 3" (2770 Rft:) ii. PVC Pipe 3" (1700 Rft:) 05. L.S.R / Storage Tank (01 No) | 6.57 | Execution of construction work | Single Stage Envelope | 12/2015 | After issue of Work Order | 06/2016
(RASHEED AHMED SOOMRO)
EXECUTIVE ENGINEER
PUBLIC HEALTH ENGG: DIVISION
JAMSHORO

## Annexure-I
(Annexure-A)
PROCUREMENT PLAN (Development)
Serial No/ ADP No: | Name of Scheme & Estimated Cost | Allocated Funds | Cost of ongoing works (Expenditure already incurred | Funds ongoing works | Cost of new works (components) | Funds for New works | Nature of Procurement | Method of Procurement | Anticipated / Actual Date of Advertisement | Anticipated/Actual Date of Start | Anticipated/Actual Date of Completion
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
T
1 | Rehabilitation of Rural Drainage Scheme Arzi Hakro i/c One Year Operation & Maintenance Taluka & District Matiari. | 9 | 0 | 0 | Rs. 1.Surface Drains (Reapair & New) 2. Costruction of C.C Block. 3. Repair of C/Wall 4. Silt Clerance of Oxidation Pond 5. Repair of Screen- ing Chamber. 6. Repair of C/tank 7. Repair of Staff Quarter & Chowki- dar Hut 8. Repair of P/House ( 3 Nos) 9. Repair & Replace- ment of Rising Main. 10.Repair of Pumping Machinery. 11. Repair of Transformer 3 Nos. | 9 | Execution of construction work | Single Stage Envelope | 15/3/2016 | After issue of Work Order | 01/2017
2 | Rehabilitation of Rural Drainage Scheme Darya Khan Talpur i/c One Year Operation & Maintenance Taluka & District Matiari. | 9 | 0 | 0 | Rs. 1. Providing/ Repair of P/Machenery 2. Repair of Pump House & New. 3. Construction of Screening Chamber 4. Inter Connection. 5. Construction & Repairof Surface Drain & Brick pavement. 6. Repair &Providing Rising Main 6" dia. 7. Development of Khud Oxidation Bund of existing Khud. 8. Repair of C/Wall. | 9 | Execution of construction work | Single Stage Envelope | 15/3/2016 | After issue of Work Order | 01/2017
3 | Rehabilitation of Rural Drainage Scheme Bachal Warya i/c One Year Operation & Maintenance Taluka & District Matiari | 5 | 0 | 0 | Rs. 13.000 1. Repair /New Surface Drains. 2. Construction of C/Tank i/c Screening chamber Inter connection. 3. Construction of Pump House (New) 4. Repair /New Pumping Machinery. 5. A.C Rising Main 4"dia. | 5 | Execution of construction work | Single Stage Envelope | 15/3/2016 | After issue of Work Order | 01/2017
4 | Rehabilitation of Rural Drainage Scheme Misri Jakhrejo i/c One Year Operation & Maintenance Taluka & District Matiari. | 5 | 0 | 0 | Rs. 1. Repair/ New Surface Drains. 2. Construction of C/Tank i/c Sccreening chamber & Inter Connection. 3. Construction of Pump House ( New) 4. Repair / New Pumping Machinery. 5. PLJ Rising Main 4" dia. 6. Repair of C/Wall, P/House & Comound wall. | 5 | Execution of construction work | Single Stage Envelope | 15/3/2016 | After issue of Work Order | 01/2017
5 | Rehabilitation of Rural Drainage Scheme Khando i/c One Year Operation & Maintenance Taluka Hala District Matiari. | 6 | 0 | 0 | Rs. 1. Construction of Surface Drain (New & Repair). 2. Repair of C/Wall. 3. Construction of C.C Block. 4. Repair of C/Tank. 5. Repair of Pump House. 6. Repair of Staff Quarter. 7. Repair /Replacement of R/Main 6"dia. 8. Repair/New Pumping Machinery 9. Repair of Transformer. | 6 | Execution of construction work | Single Stage Envelope | 15/3/2016 | After issue of Work Order | 01/2017
6 | Rehabilitation of Rural Drainage Scheme Old Saeedabad i/c One Year Operation & Maintenance Taluka Saeedabad District Matiari. | 5 | 0 | 0 | Rs. 1. Construction of Surface Drain (New & Repair). 2. Repair of C/Wall. C/Tank & S/Chamber 3. Construction of C.C Block. 4. Repair of Staff Quarter 5. Repair /Replacement Rising Main 6" dia. 6. Pumping Machinery (Repair). 7. Transformer (Repair) | 5 | Execution of construction work | Single Stage Envelope | 15/3/2016 | After issue of Work Order | 01/2017
(MUHAMMAD AKBAR BALOCH)
EXECUTIVE ENGINEER
PUBLIC HEALTH ENGG:DIVISION
MATIARI
Note on B8: Indus:

## Annexure-II
ANNEXURE A-II
ANNEXURE-II
PROCUREMENT PLAN (Non-Development)
S. No | Found Head & Sub head | Name of work and break up | Allocated Found and break up for different locations/sites | ltems to be executed | Method of Procurement | Anticipated/Actual of Advertisement | Anticipated/Actual Date of Start | Anticipated/Actual Date of Completion | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
--------------NIL--------------
(MUHAMMAD AKBAR BALOCH)
EXECUTIVE ENGINEER
PUBLIC HEALTH ENGG: DIVISION
MATIARI