STANDARD BIDDING DOCUMENT

PROCUREMENT OF WORKS

(For Contracts Costing up to Rs 2.5 MILLION)

Standard Bidding Document is intended as a model for admeasurements (Percentage Rate/unit price for unit rates in a Bill of Quantities) types of contract. The main text refers to admeasurements contracts.

Draft Bidding Document for Works up to 2.5 M

Instructions to Bidders/ Procuring Agencies.

General Rules and Directions for the Guidance of Contractors.

This    section    of    the    bidding    documents    should    provide    the    information    necessary    for bidders to prepare responsive bids, in accordance with the requirements of the Procuring Agency. It should also give information on bid submission, opening and evaluation, and on the award of contract.

Matters governing    ggygyg the    performance    of    the Contract    or payments    under the    Contract,    or matters    affecting    the    risks, rights,    and    obligations    of    the parties    under the    Contract    are included as Conditions of Contract and Contract Data .

The Instructions to Bidders will not be part of the Contract and will cease to have effect once the contract is signed.

1. All work proposed to be executed by contract shall be notified in a form of Notice Inviting    Tender    (NIT)/Invitation    for    Bid    (IFB)    hoisted    on    website    of    Authority    and Procuring Agency and also in printed media where ever required as per rules.

NIT must state the description of the work, dates, time and place of issuing, submission, opening    of    bids,    completion    time,    cost    of    bidding    document    and    bid    security    either    in lump    sum    or    percentage    of    Estimated    Cost/Bid    Cost.    The    interested    bidder    must    have valid NTN also.

2. Content    of    Bidding    Documents    must    include    but    not    limited    to:    Conditions    of contract,    Contract    Data,    specifications    or    its    reference,    Bill    of    Quantities    containing description    of    items    with    scheduled/item    rates    with    premium    to    be    filled    in    form    of percentage above/ below or on item rates to be quoted, Form of Agreement and drawings.

3.      Fixed    Price    Contracts: The    Bid    prices    and    rates    are    fixed    during    currency    of contract    and    under    no    circumstance    shall    any    contractor    be    entitled    to    claim    enhanced rates for any item in this contract.

4. The Procuring Agency shall have right of rejecting all or any of the tenders as per provisions of SPP Rules 2010.

5. Conditional    Offer :    Any    person    who    submits    a    tender    shall    fill    up    the    usual printed form    stating    at    what percentage    above or    below    on the    rates    specified    in Bill of Quantities    for    items    of work    to be carried    out:    he    is willing    to undertake the    work    and also    quote    the    rates    for    those    items    which    are    based    on    market rates. Only    one    rate    of such percentage, on all the Scheduled Rates shall be framed. Tenders, which propose any alternative in    the works    specified in the said    form    of invitation    to tender or    in the    time

2 Sindh Public Procurement Regulatory Authority | www.pprasindh.gov.pk

Draft Bidding Document for Works up to 2.5 M

allowed for carrying out the work, or which contain any other conditions, will be liable to rejection. No printed form of tender shall include a tender for more than one work, but if contractor wish    to tender    for two    or    more works,    they shall submit a separate tender    for each.

The    envelope    containing the    tender    documents    shall    refer    the    name and    number of    the work.

6. All works shall be measured by standard instruments according to the rules.

7. Bidders    shall    provide    evidence of    their    eligibility    as and    when    requested    by    the Procuring Agency.

8. Any      bid        received        by      the      Agency after the deadline for submission of bids shall be rejected and returned unopened to the bidder.

9. Prior    to    the    detailed    evaluation    of    bids,    the    Procuring    Agency    will    determine whether the bidder fulfills all codal requirements of eligibility criteria given in the

tender notice such as registration with tax authorities, registration with PEC (where applicable),    turnover    statement,    experience    statement,    and    any    other    condition mentioned in the NIT and bidding document. If the bidder does not fulfill any of these conditions, it shall not be evaluated further.

10. Bid without bid security of required amount and prescribed form shall be rejected.

11. Bids determined to be substantially responsive shall be checked for any arithmetic errors. Arithmetical errors shall be rectified on the following basis;

(A)    In    case    of    schedule    rates ,    the    amount    of    percentage    quoted    above    or    below will    be    checked    and added    or    subtracted    from    amount    of bill of    quantities    to arrive the final bid cost.

(B)      In    case of item    rates, .If there    is    a    discrepancy    between the    unit rate and the total cost that is obtained by multiplying the unit rate and quantity, the unit rate

shall prevail    and    the  total    cost    will    be    corrected    unless    in    the    opinion    of    the Agency there is an obvious misplacement of the decimal point in the unit rate, in which case the total cost as quoted will govern and the unit rate corrected. If there is a discrepancy between the total bid amount and the sum of total costs, the    sum    of    the    total    costs    shall    prevail    and    the    total    bid    amount    shall    be corrected.

(C) Where there is a discrepancy between the amounts in figures and in words, the amount in words will govern.

3 Sindh Public Procurement Regulatory Authority | www.pprasindh.gov.pk

1

Draft Bidding Document for Works up to 2.5 M

BIDDING DATA

(This section should be filled in by the Engineer/Procuring Agency before issuance of the Bidding Documents).

(a). Name of Procuring Agency Executive Engineer, Provincial Buildings Division No.II, Karachi.

(b). Brief Description of Works M/R TO SINDH SECRETARIAT NO.III, (OLD KDA BUILDING) KARACHI (REPAIR/RENOVATION WORK IN COURT ROOM OF APPELLATE TRIBUNAL COUNCIL MEZZANINE    FLOOR).

(c).Procuring Agency’s address: Barrack No.18, Block 4-A, Sindh Secretariat    Saddar Karachi.

(d). Estimated Cost: RS. 432800/-

(e). Amount of Bid Security:- 2% of the Bid (2% of the Bid amount will be converted into performance guarantee after successful bidding.) (Fill in lump sum amount or in % age of bid amount /estimated cost, but not exceeding 5%)

(f).Period of Bid Validity (days):- 60 days (Not more than sixty days).

(g).Security Deposit :-( including bid security):- 10% (2% performance guarantee and 8% will be deducted in running payment), (in % age of bid amount /estimated cost equal to 10%)

(h). Percentage, if any, to be deducted from bills:-Income Tax 7.50%

(i). Deadline for Submission of Bids along with time:-    06.04.2016 @ 1.00 P.M.

(j). Venue, Time, and Date of Bid Opening:- 06.04.2016 @ 2.00 P.M. above address.

(k). Time for Completion from written order of commence: -       Three Months.

(L).Liquidity    damages:-    NIL ( 0.05)    of    Estimated    Cost    or    Bid    cost

per day of delay, but total not exceeding 10%)

(m). Deposit Receipt No: Date: Amount: (in words and figures) Rs: 1000/-(Rupees One Thousand) only.

(Executive Engineer/Authority issuing bidding document)

4 Sindh Public Procurement Regulatory Authority | www.pprasindh.gov.pk

EXECUTIVE ENGINEER,

Provincial Buildings Division No.II,

Karachi.

Draft Bidding Document for Works up to 2.5 M

Conditions of Contract

Clause    –    1:Commencement    &    Completion    Dates    of    work. The    contractor    shall    not enter    upon    or    commence    any    portion    or    work    except    with    the    written    authority    and instructions of the Engineer-in-charge or of in subordinate-in-charge of the work. Failing such authority the contractor shall have no claim to ask for measurements of or payment for work.

The contractor shall proceed with the works    with due expedition and without delay and complete the works in    the time allowed for carrying out the work as entered in the tender shall be strictly observed by the contractor and shall reckoned from the date on which the order to commence work is given to the contractor. And further to ensure good progress during    the    execution    of    the    wok,    contractor    shall    be    bound,    in    all    in    which    the    time allowed    for    completion    of    any    work    exceeds    one    month,    to    achieve    progress    on    the prorate basis.

Clause    –    2:Liquidated    Damages. The    contractor    shall    pay    liquidated    damages    to    the Agency at the rate per day stated in the bidding data for each day that the c ompletion date

is later than the Intended    completion date; the amount of liquidated damage paid by the contractor to the Agency shall not exceed 10 per cent of the contract price. Agency may deduct liquidated    damages    from payments  due    to    the    contractor. Payment of    liquidated damages does not affect the contractor's liabilities.

Clause – 3: Termination of the Contract.

(A) Procuring    Agency/Executive Engineer may terminate the    contract if either of the following conditions exits:-

(i)      contractor causes a breach of any clause of the Contract; (ii)      the    progress    of    any    particular    portion    of    the    work    is    unsatisfactory    and

notice of 10 days has expired; (iii)      in the case of abandonment of the work owing to the serious illness or death

of the contractor or any other cause. (iv)    contractor can also request for termination of contract if a payment certified

by the Engineer    is    not    paid to    the    contractor within 60    days    of the date of the submission of the bill;

(B) The    Executive    Engineer/Procuring    Agency    has    power    to    adopt    any    of    the following courses as may deem fit:-

(i)    to    forfeit    the    security    deposit    available    except    conditions    mentioned    at    A (iii) and (iv) above;

(ii)    to finalize the work by measuring the work done by the contractor.

5 Sindh Public Procurement Regulatory Authority | www.pprasindh.gov.pk

Draft Bidding Document for Works up to 2.5 M

(C) In    the    event    of    any    of    the    above    courses    being    adopted    by    the    Executive Engineer/Procuring Agency, the contractor shall have:-

(i)      no    claim to compensation for any    loss    sustained by    him by    reason    of    his having    purchased    or    procured    any    materials,    or    entered    into    any engagements,    or made    any    advances    on account    of, or    with    a    view    to    the execution of the work or the performance of the contract,

(ii)        however, the contractor can claim for the work done at site duly certified by the executive    engineer in    writing    regarding    the    performance    of such work and has not been paid.

Procuring Agency/Engineer may invite fresh bids for remaining work. Clause 4:    Possession of the site and claims for compensation for delay. The Engineer

shall give possession of all parts of the site to the c ontractor.    If    possession of site    is not given by    the date    stated    in the    contract    data,    no    compensation    shall    be    allowed for any delay caused in starting of the work on account of any acquisition of land, water standing in    borrow pits/ compartments or in according    sanction to    estimates.    In such    case,    either date    of    commencement    will    be    changed    or    period    of    completion    is    to    be    extended accordingly.

Clause –5: Extension of Intended Completion Date. The Procuring Agency either at its own    initiatives    before the    date    of completion or on    desire of    the contractor may extend the intended completion date, if an event (which hinders the execution of contract) occurs or    a    variation    order    is    issued    which    makes    it    impossible    to    complete    the    work    by    the intended    completion    date    for    such    period    as    he    may    think    necessary    or    proper.    The decision    of    the    Executive    Engineer    in    this    matter    shall    be    final;    where    time    has    been extended under this or any other clause of this agreement, the date for completion of the work shall    be the date fixed by the order giving the extension or by the aggregate of all such orders, made under this agreement. When    time    has    been    extended    as    aforesaid,    it    shall    continue    to    be    the    essence    of    the contract and all clauses of the contract shall continue to be operative during the extended period.

Clause –6: Specifications. The    contractor shall execute the whole and every    part of the work    in    the    most    substantial    and    work-man-like    manner    and    both    as    regards    materials and all    other    matters    in    strict    accordance    with    the specifications    lodged    in    the    office    of the Executive Engineer and initialed by the parties, the said specification being a part of the contract. The contractor shall also confirm exactly, fully and faithfully to the designs, drawing, and instructions in writing relating to the work signed by the Engineer-in-charge and lodge in his office and to which the contractor shall be entitled to have access at such office    or    on    the    site    of    work    for    the    purpose    of inspection    during    office    hours    and    the contractor shall, if he so requires, be entitled at his own expense to make or cause to    be made copies of the specifications, and of all such designs, drawings, and instructions    as aforesaid.

6 Sindh Public Procurement Regulatory Authority | www.pprasindh.gov.pk

Draft Bidding Document for Works up to 2.5 M

Clause – 7: Payments.

(A)      Interim/Running Bill. A bill shall be submitted by the contractor as frequently as the progress of the work may justify for all work executed and not included in any previous    bill    at    least    once    in    a    month    and    the    Engineer-in-charge    shall    take    or cause to    be taken    the requisite measurements for the    purpose of having the same verified and the claim, as for as admissible, adjusted, if possible before the expiry of ten    days    from    the    presentation    of the    bill,    at any    time depute a subordinate    to measure up the said work in the presence of the contractor or his authorized agent, whose    countersignature    to    the measurement    list will be sufficient    to    warrant and the Engineer-in-charge may prepare a bill from such list which shall be binding on the contractor in all respects.

The    Engineer    /Procuring    Agency    shall    pass/certify    the    amount    to    be    paid    to    the contractor,    which    he    considers    due    and    payable    in    respect    thereof,    subject    to deduction of security deposit, advance payment if any made to him and taxes.

All such intermediate payment shall    be regarded as payments by way of advance against    the    final    payment    only    and    not    as    payments    for    work    actually    done    and completed,    and    shall    not    preclude    the    Engineer-in-charge    from    recoveries    from final bill and rectification of defects and unsatisfactory items of works pointed out to him during defect liability period.

(B)      The Final Bill. A bill shall be submitted by the contractor within one month of the date    fixed    for    the    completion    of    the    work    otherwise    Engineer-in-charge’s certificate of the measurements and of the total amount payable for the works shall be final and binding on all parties.

Clause    –    8: Reduced    Rates. In    cases    where    the    items    of    work    are    not    accepted    as    so completed, the Engineer-in-charge may    make payment on account of such items at such reduced    rates    as    he    may  consider    reasonable    in    the    preparation    of    final    or    on    running account bills with reasons recorded in writing.

Clause – 9: Issuance of Variation and Repeat Orders.

(A) Agency    may issue a Variation    Order for procurement of works,    physical services from    the    original    contractor    to    cover    any    increase    or    decrease    in    quantities, including    the    introduction    of    new    work    items    that    are    either    due    to    chang e    of

plans, design or alignment to suit actual field conditions, within the general scope and physical boundaries of the contract.

(B) Contractor shall not perform a variation until the Procuring Agency has authorized the variation in    writing    subject to    the limit    not exceeding the    contract cost    by of 15% on the same conditions in    all    respects    on which he agreed to do them    in the

7 Sindh Public Procurement Regulatory Authority | www.pprasindh.gov.pk

Draft Bidding Document for Works up to 2.5 M

work, and at the same rates, as are specified in the tender for the main work. The contractor    has    no    right    to    claim    for    compensation    by    reason    of    alterations    or curtailment of the work.

(C) In case    the nature of the work in    the variation    does    not    correspond    with items    in the Bill    of Quantities, the quotation by the    contractor    is to be in    the form of new rates for the relevant items of work, and if the Engineer-in-charge is satisfied that the rate quoted is within the rate worked out by him on detailed rate analysis, and then only he shall allow him that rate after approval from higher authority.

(D) The time for the completion of the work shall be extended in the proportion that the additional work bear to the original contact work.

(E) In case of quantities of work executed result the Initial Contract Price to be xceeded by    more    than    15%,    and    then    Engineer    can    adjust    the    rates    for    those    quantities causing    excess    the    cost    of    contract    beyond    15%    after    approval    of    Superintending Engineer.

(F)    Repeat    Order: Any    cumulative    variation,    beyond    the    15%    of    initial    contract amount,    shall    be    subject    of    another    contract    to    be    tendered    out    if    the    works    are separable from the original contract.

Clause-10: Quality Control.

(A)      Identifying    Defects: If at any    time before the security    deposit    is    refunded    to the contractor/during    defect    liability    period    mentioned    in    bid    data,    the    Engineer-incharge    or    his    subordinate-incharge    of    the    work    may    instruct    the    contractor    to uncover and    test any part of the works which he considers may have a defect due to    use    of unsound    materials    or    unskillful    workmanship    and    the    contractor    has    to carry out a test at his own cost irrespective of work already approved or paid.

(B)    Correction    of    Defects: The    contractor    shall    be    bound    forthwith    to rectify    or remove and reconstruct the work so specified in whole or in part, as the case may require.    The    contractor    shall    correct    the    notified    defect    within    the    Defects Correction Period mentioned in notice.

(C)    Uncorrected Defects:

(i) In    the    case    of    any    such    failure,    the    Engineer-in-charge    shall    give    the contractor    at    least    14    days    notice    of    his    intention    to    use    a    third    party    to correct    a    defect.    He    may    rectify    or    remove,    and    re-execute    the    work    or remove and replace the materials or articles complained of as the case may be at the risk and expense in all respects of the contractor.

8 Sindh Public Procurement Regulatory Authority | www.pprasindh.gov.pk

Draft Bidding Document for Works up to 2.5 M

(ii) If    the    Engineer    considers    that    rectification/correction    of    a    defect    is    not essential    and    it    may    be    accepted    or    made    use    of;    it    shall    be    within    his discretion to accept the same at such reduced rates as he may fix therefore.

Clause – 11:

(A)      Inspection    of    Operations. The    Engineer    and    his    subordinates,    shall    at    all reasonable    times    have access to    the    site for supervision    and inspection of works under    or    in    course    of  execution    in    pursuance    of    the    contract    and    the    contractor shall afford    every    facility    for    and every    assistance in obtaining    the    right    to    such access.

(B)      Dates    for    Inspection    and    Testing. The    Engineer    shall    give    the    contractor reasonable notice of the intention of the Engineer-in-charge or his    subordinate    to visit    the    work    shall    have    been    given    to    the contractor, then he    either    himself    be present    to    receive    orders    and instructions,    or    have    a    responsible    agent    duly accredited in writing present for that purpose, orders given to the contractor’s duly

authorized agent shall be considered to have the same force an effect as if they had been given to the contractor himself.

Clause – 12: Examination of work before covering up.

(A) No    part    of    the    works    shall    be    covered    up    or    put    out    of    view/beyond    the    reach without giving notice of not less than five days to the Engineer whenever any such part    of    the    works    or    foundations    is    or    are    ready    or    about    to    be    ready    for examination    and    the    Engineer    shall,    without    delay,    unless    he    considers    it unnecessary    and    advises    the    contractor    accordingly,    attend    for    the    purpose    of examining    and    measuring    such    part    of    the    works    or    of    examining    such foundations;

(B) If    any    work    is    covered    up    or    placed    beyond    the    reach    of    measurement    without such    notice    having    been    given,    the    same    shall    be    uncovered    at    the    contractor’s

expense,    and  in    default thereof    no payment    or allowance shall    be    made for    such work, or for the materials with which the same was executed.

Clause – 13: Risks . T he contractor shall be responsible for all risks of loss of or damage to physical property or facilities or related services at the premises and of personal injury and    death which    arise    during    and in consequence    of its performance    of the    contract.    if

any    damage    is    caused    while    the    work    is    in    progress    or    become    apparent    within    three months    of    the    grant    of    the    certificate    of    completion,    final    or    otherwise,    the    contractor shall make good the same at his own expense, or in    default the Engineer may    cause    the same to be made good by other workmen, and deduct the expenses from retention money lying with the Engineer.

9 Sindh Public Procurement Regulatory Authority | www.pprasindh.gov.pk

Draft Bidding Document for Works up to 2.5 M

Clause-14:    Measures    for    prevention    of    fire    and    safety    measures. The    contractor shall    not    set    fire    to    any    standing    jungle,    trees,    bush-wood    or    grass    without    a    written permit    from    the    Executive    Engineer.        When such    permit is    given,    and    also    in    all cases when destroying, cutting or uprooting trees, bush-wood, grass, etc by fire, the contractor shall take    necessary    measures    to    prevent    such    fire    spreading    to    or    otherwise    damaging surrounding    property.    The    contractor    is    responsible    for    the    safety    of    all    its    activities including protection of the environment on and off the site. Compensation of all damage done intentionally or unintentionally on or off the site by the contractor’s labour shall be paid by him.

Clause-15:Sub-contracting . The contractor shall not subcontract the whole of the works, except    where    otherwise    provided    by    the    contract.    The    contractor    shall    not    subcontract any part of the works without the prior consent of the Engineer.    Any such consent shall not relieve the contractor from any    liability or obligation under the contract and he shall be    responsible    for    the    acts,    defaults    and    neglects    of    any    subcontractor,    his    agents, servants or workmen as if these acts, defaults or neglects were those of the contractor, his

agents’    servants    or    workmen.    The    provisions    of    this    contract    shall    apply    to    such subcontractor or his employees as if he or it were employees of the contractor.

Clause – 16: Disputes. All disputes arising in connection with the present contract, and which    cannot    be    amicably    settled    between    the    parties,    ,    the    decision    of    the Superintending    Engineer    of    the    circle/officer/one    grade    higher    to    awarding    authority shall    be    final,    conclusive    and    binding    on  all    parties    to    the    contract    upon    all    questions relating    to    the    meaning    of    the    specifications,    designs    drawings,    and    instructions, hereinbefore mentioned    and    as to    the    quality of    workmanship, or    materials    used on    the work or    as    to    any    other questions,    claim,    right,    matter,    or thing whatsoever in    any    way arising    out    of,    or    relating    to    the    contract    design,    drawings,    specifications,    estimates, instructions,    orders    or    these    conditions    or    otherwise    concerning  the    works,    or    the execution,    of    failure    to    execute    the    same,    whether    arising,    during    the    progress    of    the work, or after    the completion or abandonment thereof.

Clause    – 17:    Site    Clearance. On    completion    of    the    work,    the    contractor    shall    be furnished with a certificate by the Executive Engineer (hereinafter called the Engineer incharge) of such completion, but neither such certificate shall be given nor shall the work be    considered    to    be    complete    until    the    contractor    shall    have    removed    all    temporary structures and materials brought at site either for use or for operation facilities including cleaning debris and dirt at the site. If the contractor fails to comply with the requirements of this clause then Engineer-in-charge,    may at the expense of the contractor remove and

dispose    of    the    same    as    he    thinks    fit    and    shall    deduct    the    amount    of    all    expenses    so incurred    from    the    contractor’s    retention    money.    The    contractor    shall    have    no    claim    in respect of any    surplus materials as aforesaid    except    for any sum actually    realized by the sale thereof.

10 Sindh Public Procurement Regulatory Authority | www.pprasindh.gov.pk

Draft Bidding Document for Works up to 2.5 M

Clause –18: Financial Assistance /Advance Payment.

(A) Mobilization advance is not allowed.

(B)      Secured Advance against materials brought at site. (i) Secured    Advance    may    be    permitted    only    against    imperishable

materials/quantities anticipated to be consumed/utilized on the work within a    period    of    three    months    from    the    date    of    issue    of    secured    advance    and definitely    not    for    full    quantities    of    materials    for    the    entire    work/contract. The    sum    payable    for    such    materials    on    site    shall    not    exceed    75%    of    the market price of materials;

(ii) Recovery    of    Secured    Advance    paid    to    the    contractor    under    the    above provisions    shall    be    affected    from    the    monthly    payments    on    actual consumption basis,    but not later than period more than three    months (even if unutilized).

Clause –19: Recovery as arrears of Land Revenue . Any sum due to    the Government by the contractor shall be liable for recovery as arrears of Land Revenue.

Clause    –20:    Refund    of    Security    Deposit/Retention    Money. On    completion    of    the whole of the works (a work should    be considered    as    complete for    the purpose of refund of security deposit to a contractor from the last date on which its final measurements are checked by a competent authority, if such check is necessary otherwise from the last date of    recording    the final    measurements), the    defects    notice    period    has    also passed    and    the Engineer    has    certified    that    all    defects    notified    to    the    contractor    before    the    end    of    this period    have    been    corrected,    the    security    deposit    lodged    by    a    contractor    (in    cash    or recovered in installments from his bills) shall be refunded to him after the expiry of three months from the date on which the work is completed.

Divisional Accountant

Contractor                                                                                                                      Executive Engineer/Procuring Agency

11 Sindh Public Procurement Regulatory Authority | www.pprasindh.gov.pk

BILL OF QUANTITIES 
(A) Description and rate of Items based on Composite Schedule of Rates.

| Item No | Quantities | Description of item to be executed at site | Rate | Unit | Amount in Rupees |
| --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 |

Amount TOTAL (a)

% above/below on the rates of CSR.	Amount to be added/deducted on the basis

Of premium quoted.	TOTAL (b)

Total (A) = a+b in words & figures:

Contractor	Executive Engineer/Procuring Agency

(B) Description and rate of Items based on Market (Offered rates

| Item No | Quantities | Description of item to be executed at site | Rate | Unit | Amount in Rupees |
| --- | --- | --- | --- | --- | --- |

Total (B) in words & figures:

Contractor	Executive Engineer/Procuring Agency

Summary of Bill of Quantities.

Cost of Bid	Amount

- (A) Cost based on Composite Schedule of Rates

- (B) Cost based on Non/Offered Schedule of Rates.

TOTAL COST OF BID (C) = Total (A) + Total (B)

Contractor	Executive Engineer/Procuring Agency