## P.Plan 2015-16
REVISED PROCUREMENT PLAN 2015-2016 (HIGHWAYS DIVISION KAMBER-SHAHDADKOT)
CONSTRUCTION/RECONDITIONING OF ROADS & MASONARY STRUCTURES DISTRICT KAMBER-SHAHDADKOT.
S.No. | Description of Procurement | Quantity (Where applicable) | Estimated unit cost (where applicable) (in Million) | Estimated total cost | Funds allocated (in Million) | Source of funds (ADPs/Non ADPs) | Proposed Procurement metohd | Timing of Procurement |  |  |  | Remarks
[8 empty] | 1st Qtr: | 2nd Qtr: | 3rd Qtr: | 4th Qtr:
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1 | Reconditioning of link road from Qubo Saeed Khan via Lundi Shakh to Saifullah shakh U/C Qubo Saeed Khan Taluka Qubo Saeed Khan Mile 0/0-3/1 (5.0 KMs). | 5 | 26.135 | 26.135 | 185.844 | Provincial ADP-1129 | Single Stage One Envelope Method | 6.5338 | 6.5338 | 6.5338 | 6.5338
2 | Reconditioning of link road from Qubo Saeed Khan RD-97000 Pull U/C Bago Daro Taluka Qubo Saeed Khan mile 0/0-3/6 (6.0 KMs). | 6 | 31.591 | 31.591 | 185.844 | Provincial ADP-1129 | Single Stage One Envelope Method | 7.8978 | 7.8978 | 7.8978 | 7.8978
3 | Construction of link road from Sultan Ahmed Khuhawar Pump to Koto Moto Chowk mile 0/0-0/5 (1.0 KMs). | 1 | 19.856 | 19.856 | 185.844 | Provincial ADP-1129 | Single Stage One Envelope Method | 4.964 | 4.964 | 4.964 | 4.964
4 | Construction of link road from Hasrani Pump via Sijawal Phatak to Bus Stand U/c Shahdadkot-III mile 0/0-1/4+330' (2.50 KMs). | 2.5 | 50.881 | 50.881 | 185.844 | Provincial ADP-1129 | Single Stage One Envelope Method | 12.7203 | 12.7203 | 12.7203 | 12.7203
5 | Construction of link road from Mir Noorullah Khan Magsi Bungalow to village Faiz Muhammad Brohi U/C Shahdadkot-I mile 0/0-0/5 (1.0 KM). | 1 | 20.349 | 20.349 | 185.844 | Provincial ADP-1129 | Single Stage One Envelope Method | 5.0873 | 5.0873 | 5.0873 | 5.0873
6 | Construction of link road from Shaheed Nawab Saifullah Khan Library U/C Shahdadkot-I mile 0/0-0/3 (0.60 KMs). | 0.6 | 3.84 | 3.84 | 185.844 | Provincial ADP-1129 | Single Stage One Envelope Method | 0.96 | 0.96 | 0.96 | 0.96
7 | Construction of link road from Koto Moto Chowk to Station road U/c Shahdadkot Taluka Shahdadkot Mile 0/0-1/7 (3.0 KMs). | 3 | 57.742 | 57.742 | 185.844 | Provincial ADP-1129 | Single Stage One Envelope Method | 14.4355 | 14.4355 | 14.4355 | 14.4355
8 | Construction of link road from Single Section High School road to Kala Makan U/C Shahdadkot Taluka Shahdadkot Mile 0/0-0/5+330' (1.10 KMs). | 1.1 | 6.767 | 6.767 | 185.844 | Provincial ADP-1129 | Single Stage One Envelope Method | 1.6918 | 1.6918 | 1.6918 | 1.6918
9 | Construction of link road from Green Star Hotel via Lakh Pati road U/C Shahdadkot-I Mile 0/0-0/7+330' (1.50 KMs). | 1.5 | 28.868 | 28.868 | 185.844 | Provincial ADP-1129 | Single Stage One Envelope Method | 7.217 | 7.217 | 7.217 | 7.217
10 | Construction of link road from Public Health Office to Civil Hospital U/C Shahdadkot-I Taluka Shahdadkot mile 0/0-0/5 (1.0 KM). | 1 | 19.208 | 19.208 | 185.844 | Provincial ADP-1129 | Single Stage One Envelope Method | 4.802 | 4.802 | 4.802 | 4.802
11 | Reconditioning of link road from Katchi Pull to Chukhi U/C Bago Daro Taluka Qubo Saeed Khan Mile 0/0-2/4 (4.0 KMs). | 4 | 21.154 | 21.154 | 185.844 | Provincial ADP-1129 | Single Stage One Envelope Method | 5.2885 | 5.2885 | 5.2885 | 5.2885
12 | Construction of link road from Imam Bux Jamali road to village Nadirabad via Yousifabad U/c Aitbar Khan Chandio Taluka Shahdadkot mile 0/0-3/1 (5.0 KMs). | 5 | 37.647 | 37.647 | 185.844 | Provincial ADP-1129 | Single Stage One Envelope Method | 9.4117 | 9.4117 | 9.4117 | 9.4117
13 | Construction/Reconditioning of road from Grid Station Kamber via Sain Hussain Shah Dargah to Muhammad Hussain Magsi Shop to Bhutta Hotel U/C Kamber Taluka Kamber mile 0/0-1/6 (2.82 KMs). | 2.82 | 57.208 | 57.208 | 185.844 | Provincial ADP-1129 | Single Stage One Envelope Method | 14.302 | 14.302 | 14.302 | 14.302
14 | Construction of link road to village Lal Khan Magsi mile 0/0-1/0 (1.60 KMs) Taluka Qubo Saeed Khan. | 1.6 | 10.349 | 10.349 | 185.844 | Provincial ADP-1129 | Single Stage One Envelope Method | 2.5873 | 2.5873 | 2.5873 | 2.5873
15 | Construction of link road to village Haji Ali Khan Magsi mile 0/0-0/5 (1.0 KM) Taluka Qubo Saeed Khan. | 1 | 7.045 | 7.045 | 185.844 | Provincial ADP-1129 | Single Stage One Envelope Method | 1.7612 | 1.7612 | 1.7612 | 1.7612
16 | Construction of link road to village Haji Kamber Magsi mile 0/0-0/5 (1.0 KM) Taluka Qubo Saeed Khan. | 1 | 7.352 | 7.352 | 185.844 | Provincial ADP-1129 | Single Stage One Envelope Method | 1.838 | 1.838 | 1.838 | 1.838
17 | Construction of link road from Wagan Chowk to By Pass imam Bargah to SP Chowk (1.0 KM) Taluka Kamber. | 1 | 8.243 | 8.243 | 185.844 | Provincial ADP-1129 | Single Stage One Envelope Method | 2.0608 | 2.0608 | 2.0608 | 2.0608
18 | Construction of link road to Ghulam Shabir Chandio mile0/0-1/2 (2.0 KM) Taluka Shahdadkot. | 2 | 13.63 | 13.63 | 185.844 | Provincial ADP-1129 | Single Stage One Envelope Method | 3.4075 | 3.4075 | 3.4075 | 3.4075
19 | Construction of link road to village Arzi Markhand mile0/0-1/2 (2.0 KM) Taluka Shahdadkot. | 2 | 13.63 | 13.63 | 185.844 | Provincial ADP-1129 | Single Stage One Envelope Method | 3.4075 | 3.4075 | 3.4075 | 3.4075
20 | Reconditioning of road from Darya Khan Mastoi via Chakiyani to Dr Mehboob Shah village mile 0/0-2/7+330' (4.70 KM) Taluka Shahdadkot. | 4.7 | 20.511 | 20.511 | 185.844 | Provincial ADP-1129 | Single Stage One Envelope Method | 5.1277 | 5.1277 | 5.1277 | 5.1277
21 | Construction and Reconditioning road to village Umaid Ali Junejo mile 0/0-1/2 (2.0 KM) Taluka Shahdadkot. | 2 | 12.648 | 12.648 | 185.844 | Provincial ADP-1129 | Single Stage One Envelope Method | 3.162 | 3.162 | 3.162 | 3.162
22 | Construction of link road from Motorway to Dholyo Khoso mile 1/0-2/7 (3.10 KM) Taluka Qubo Saeed Khan. | 3.1 | 20.78 | 20.78 | 185.844 | Provincial ADP-1129 | Single Stage One Envelope Method | 5.195 | 5.195 | 5.195 | 5.195
23 | Construction of link road to Hakim Shah Shori Shakh Pasha Shah Muhammad Khuhro to village Ali Gohar Khoso mile 0/0-1/4 (2.40 KM) Taluka Miro Khan. | 2.4 | 15.445 | 15.445 | 185.844 | Provincial ADP-1129 | Single Stage One Envelope Method | 3.8613 | 3.8613 | 3.8613 | 3.8613
24 | Construction of link road to village Rais Ali Dost Aadmani mile 0/0-0/5 (1.0 KM) Taluka Shahdadkot. | 1 | 6.265 | 6.265 | 185.844 | Provincial ADP-1129 | Single Stage One Envelope Method | 1.5662 | 1.5662 | 1.5662 | 1.5662
25 | Construction of link road to village Ali Hassan Brohi Qalandrani mile 0/0-0/5 (1.0 KM) Taluka Qubo Saeed Khan. | 1 | 7.536 | 7.536 | 185.844 | Provincial ADP-1129 | Single Stage One Envelope Method | 1.884 | 1.884 | 1.884 | 1.884
26 | Construction of link road from Hayat Gopang to Tilan Jatoi road @ Point 0/5 to village Tilan Jatoi (Missing Length) mile 0/0-2/2 (3.60 KM) Taluka Sijawal. | 3.6 | 20.542 | 20.542 | 185.844 | Provincial ADP-1129 | Single Stage One Envelope Method | 5.1355 | 5.1355 | 5.1355 | 5.1355
27 | Construction of link road from Sirrai wah via village Luqman Siyal to village Ustad Ghulam Rasool Leghari mile 0/0-2/0 (3.20 KM) Taluka Shahdadkot. | 3.2 | 20.222 | 20.222 | 185.844 | Provincial ADP-1129 | Single Stage One Envelope Method | 5.0555 | 5.0555 | 5.0555 | 5.0555
28 | Reconditioning of road to village Baharo Gurgage mile 0/0-3/6 (6.0 KM) Taluka Shahdadkot. | 6 | 36.919 | 36.919 | 185.844 | Provincial ADP-1129 | Single Stage One Envelope Method | 9.2297 | 9.2297 | 9.2297 | 9.2297
29 | Construction of link road from Ghulam Mustafa Jarwar to Saifullah Magsi Branch mile 0/0-1/0 (1.60 KM) Taluka Qubo Saeed Khan. | 1.6 | 10.379 | 10.379 | 185.844 | Provincial ADP-1129 | Single Stage One Envelope Method | 2.5947 | 2.5947 | 2.5947 | 2.5947
30 | Construction of link road to village Mir Hassan Magsi Dahalkhani mile 0/5-1/2 (1.0 KM) Taluka Qubo Saeed Khan. | 1 | 6.586 | 6.586 | 185.844 | Provincial ADP-1129 | Single Stage One Envelope Method | 1.6465 | 1.6465 | 1.6465 | 1.6465
31 | Reconditioning of road from Imam Bux Jamali to Kot Chattu mile 0/0-2/4 (4.0 KM) Taluka Qubo Saeed Khan. | 4 | 19.474 | 19.474 | 185.844 | Provincial ADP-1129 | Single Stage One Envelope Method | 4.8685 | 4.8685 | 4.8685 | 4.8685
32 | Construction of link road from Abad Jani Bund road to village Thariri Hajiran, mile 0/0-1/7 (Remaining work) Taluka Warah. | 3 | 6 | 16.73 | 4 | ADP 111 | Single Stage One Envelope Method | 1.5 | 1.5 | 1.5 | 1.5
33 | Construction of link road from Miran Machi road to Qaim Khan Hasrani with Sim Shakh @ Meenhal Shakh mile 0/0-0/5 (Masonary Structure) Taluka Miro Khan. | 1 | 1.662 | 10 | 1.662 | ADP 153 | Single Stage One Envelope Method | 0.4155 | 0.4155 | 0.4155 | 0.4155
34 | Construction of link road from Shah Beg Shakh to Dayo-Jo-Goth, Kandio, Noorullah Khan, Choudhry Ramzan, Sobidar village and Zulifqar Karozie Goth mile 0/5-1/2 (Remaining work) Taluka Shahdadkot. | 1 | 7.5 | 15 | 0.05 | ADP 290 | Single Stage One Envelope Method | 1.875 | 1.875 | 1.875 | 1.875
35 | Construction of road from Shahdadkot Qubo Saeed Khan to village Mustafaabad with Tanwari Shakh via Khadim Hussain Langah via Shah Muhammad Seelro via Deepar village via Allah Dino Magsi mile 0/0-0/5 (Remaining work) Taluka Shahdadkot | 1 | 8.5 | 15 | 4.8 | ADP 309 | Single Stage One Envelope Method | 2.125 | 2.125 | 2.125 | 2.125
36 | Construction of Retaining Wall at link road from Dhing Allah Bux Leghari to Wasand-Ji-Wandh mile 0/0-1/0 Taluka Shahdadkot. | 1.6 | 1.5 | 7.5 | 3 | ADP 329 | Single Stage One Envelope Method | 0.375 | 0.375 | 0.375 | 0.375
37 | Construction of link road from Lohi Pull Shahdadkot road to village Chakar Sultan Rid mile 0/0-1/2 (Remaining work) Taluka Miro Khan. | 2 | 5 | 10.353 | 0.05 | ADP 339 | Single Stage One Envelope Method | 1.25 | 1.25 | 1.25 | 1.25
38 | Construction of link road from Lohi Pull Shahdadkot road to village Balouch Khan Mastoi mile 0/0-1/2 (Remaining work) Taluka Miro Khan. | 2 | 5 | 9.646 | 0.05 | ADP 340 | Single Stage One Envelope Method | 1.25 | 1.25 | 1.25 | 1.25
39 | Construction of link road from Gharhi Khairo road to Abdul Qadir Magsi, mile 0/5-1/2 (Remaining work) Taluka Shahdadkot. | 1 | 5.3 | 10.393 | 1.071 | ADP 388 | Single Stage One Envelope Method | 1.325 | 1.325 | 1.325 | 1.325
40 | Construction of Bridge at road from Motorway Zareen Petrol Pump to village Gul Hassan Brohi upto Sobho Kariro mile 0/0-0/5 (Bridge) Taluka Shahdadkot. | 1 | 1 | 5.284 | 1 | ADP 390 | Single Stage One Envelope Method | 0.25 | 0.25 | 0.25 | 0.25
41 | Construction of link road from Kamber Dost Ali road to village Roshan Ali Khoso mile 0/0-0/5 (Remaining work) Taluka Miro Khan. | 1 | 5 | 4.5 | 0.05 | ADP 398 | Single Stage One Envelope Method | 1.25 | 1.25 | 1.25 | 1.25
42 | Construction of link road from Ayo Phulpoto road to village Ghulam Nabi Phulpoto mile 0/0-1/7 (Remaining work) Taluka Nasirabad. | 3 | 16.3 | 15 | 1 | ADP 380 | Single Stage One Envelope Method | 4.075 | 4.075 | 4.075 | 4.075
43 | Construction of link road from Ali Bux Panhwar to village Koreja mile 0/5-0/7 (Remaining work) Taluka Kamber. | 0.4 | 2.942 | 4.572 | 0.799 | ADP 391 | Single Stage One Envelope Method | 0.7355 | 0.7355 | 0.7355 | 0.7355
44 | Construction of Retaining Wall (540'Rft) at link road from Miro Khan road to Hasulla Shakh to Ibrahim Magsi village to Sher Ali Mugheri mile 0/0-0/6 (Retaining Wall 540'Rft) Taluka Kamber. | 1.2 | 2.478 | 7.044 | 2.2 | ADP 371 | Single Stage One Envelope Method | 0.6195 | 0.6195 | 0.6195 | 0.6195
45 | Construction of link road from Miro Khan Kot Lahori road to village Mukhtiar Ali Magsi mile 0/0-1/4 Taluka Miro Khan. | 2.4 | 27 | 0 | 0 | Non-ADP | Single Stage One Envelope Method | 6.75 | 6.75 | 6.75 | 6.75
46 | Construction of link road from Tanwari Shakh to village Haji Ashaque Ali Khan Mugheri mile 0/0-0/2 Taluka Shahdadkot. | 0.4 | 4.8 | 0 | 0 | Non-ADP | Single Stage One Envelope Method | 1.2 | 1.2 | 1.2 | 1.2
47 | Construction of link road from Miro Khan Mehmoodabad road to village Ghulam Umer Jatoi via Ali Nawaz Jagirani to connect Arzi Bhutto mile 0/0-1/4 Taluka Miro Khan. | 2.4 | 20 | 0 | 0 | Non-ADP | Single Stage One Envelope Method | 5 | 5 | 5 | 5
48 | Reconditioining of road from Kamber Ghaibi Dero road to village Phall Qaim Khan Shaikh mile 0/0-1/2 Taluka Kamber. | 2 | 10.872 | 0 | 0 | Non-ADP | Single Stage One Envelope Method | 2.718 | 2.718 | 2.718 | 2.718
49 | Construction of link road from Imam Bux road to village Abdul Wahab Khoso mile 0/0-0/2 Taluka Shahdadkot. | 0.4 | 3.789 | 0 | 0 | Non-ADP | Single Stage One Envelope Method | 0.94725 | 0.94725 | 0.94725 | 0.94725
50 | Construction of Bridge along Kamber Shahdadkot road to village Mir Niaz Ali Khoso near 5LA Sim Drain Taluka Miro Khan. | 0 | 1 | 0 | 0 | Non-ADP | Single Stage One Envelope Method | 0.25 | 0.25 | 0.25 | 0.25
51 | Construction of link road at village Abdul Wahab Khoso mile 400'ft Taluka Shahdadkot. | 0.1 | 1 | 0 | 0 | Non-ADP | Single Stage One Envelope Method | 0.25 | 0.25 | 0.25 | 0.25
Executive Engineer
Highways Division
Kamber-Shahdadkot