## Plan
ANNEXURE - A1
PROCUREMENT PLAN FOR THE YEAR 2015-16 FOR M&R WOKS (NON-DEVELOPMENT)
Sr. No. / ADP No. | Name of Scheme & Estimated Cost | Allocated Funds | Cost of ongoing works (Expenditure already incurred) | Funds earmarked for ongoing works | Cost of New works (Components) | Funds for New works (c - e) | Nature of Procurement | Methodof Procurement | Anticipated / Actual date of Advertisment | Anticipated / Actual date of Start | Anticipated / Actual date of Completion
A | B | C | D | E | F | G | H | I | J | K | L
M&R 2015-16 | Repair to Daro X-Regulator @ 08 of Pinyrai Branch | 0.642 | 0 | 0 | 0 | 0 | Single Stage | Single Stage | 25.03.2016 | 25.04.2016 | 25.05.2016
M&R 2015-16 | Repair to Old Gunj Bahar Ex. Mehmooda wah RD 10. | 0.289 | 0 | 0 | 0 | 0 | Single Stage | Single Stage | 25.03.2016 | 25.04.2016 | 25.05.2016
M&R 2015-16 | Repairs to Head Regulator B.C Baghar Ex. Mehmooda RD 44. | 0.297 | 0 | 0 | 0 | 0 | Single Stage | Single Stage | 25.03.2016 | 25.04.2016 | 25.05.2016
M&R 2015-16 | Repairs to Tyndel Quarter at fall Regulator RD 35 of P.F.L. | 0.268 | 0 | 0 | 0 | 0 | Single Stage | Single Stage | 25.03.2016 | 25.04.2016 | 25.05.2016
M&R 2015-16 | Repairs to AXEN Office Block and Sub-Engineer Quarter at Mullakatiar. | 0.326 | 0 | 0 | 0 | 0 | Single Stage | Single Stage | 25.03.2016 | 25.04.2016 | 25.05.2016
M&R 2015-16 | Repairs to AXEN Office Block at Darro Irrigation Sub-Division at Darro. | 0.328 | 0 | 0 | 0 | 0 | Single Stage | Single Stage | 25.03.2016 | 25.04.2016 | 25.05.2016
M&R 2015-16 | Repairs to Baghar X-Regulator at RD 64 of Miranpur Branch. | 0.399 | 0 | 0 | 0 | 0 | Single Stage | Single Stage | 25.03.2016 | 25.04.2016 | 25.05.2016
M&R 2015-16 | Repair to Khair wah X-Regulator at RD 27 of Miranpur Branch. | 0.381 | 0 | 0 | 0 | 0 | Single Stage | Single Stage | 25.03.2016 | 25.04.2016 | 25.05.2016
M&R 2015-16 | Repair to Chore wah X-Regulator Ex. Gunj Bahar Branch RD 45. | 0.22 | 0 | 0 | 0 | 0 | Single Stage | Single Stage | 25.03.2016 | 25.04.2016 | 25.05.2016
M&R 2015-16 | Repairs to Road Bridge along Shah Wah Ex. F.P.L. RD 10. | 0.258 | 0 | 0 | 0 | 0 | Single Stage | Single Stage | 25.03.2016 | 25.04.2016 | 25.05.2016
M&R 2015-16 | Repairs to Stone pitching along Fall Regulator D/s RD 35 of P.F.L. | 0.441 | 0 | 0 | 0 | 0 | Single Stage | Single Stage | 25.03.2016 | 25.04.2016 | 25.05.2016
M&R 2015-16 | Repairs to Stone Pitching along Dino shah X-Regulator D/S RD 114 of PFL. | 0.453 | 0 | 0 | 0 | 0 | Single Stage | Single Stage | 25.03.2016 | 25.04.2016 | 25.05.2016
M&R 2015-16 | Raising and Strengthening of Banks along P.F.L RD 58 I/P side. | 0.315 | 0 | 0 | 0 | 0 | Single Stage | Single Stage | 25.03.2016 | 25.04.2016 | 25.05.2016
M&R 2015-16 | Repairs to Tyndel Quarter at Darro Branch Head Regulator. | 0.242 | 0 | 0 | 0 | 0 | Single Stage | Single Stage | 25.03.2016 | 25.04.2016 | 25.05.2016
M&R 2015-16 | Raising and Strengthening of Banks along Miranpur Branch Ex. P.F.L RD 6 | 0.34 | 0 | 0 | 0 | 0 | Single Stage | Single Stage | 25.03.2016 | 25.04.2016 | 25.05.2016
M&R 2015-16 | Earth work of weak portion along Old Fuleli Canal RD 40 I/P side. | 0.351 | 0 | 0 | 0 | 0 | Single Stage | Single Stage | 25.03.2016 | 25.04.2016 | 25.05.2016
M&R 2015-16 | Earth work Excavation by Hydraulic Excavator along Bano Minor Ex. P.F.L. RD 0 to 35. | 0.484 | 0 | 0 | 0 | 0 | Single Stage | Single Stage | 25.03.2016 | 25.04.2016 | 25.05.2016
M&R 2015-16 | Earth work Excavation by Hydraulic Excavator along Baragazo Ex. PFL RD 0 to 35. | 0.474 | 0 | 0 | 0 | 0 | Single Stage | Single Stage | 25.03.2016 | 25.04.2016 | 25.05.2016
EXECUTIVE ENGINEER
Upper Pinyari Division
Hyderabad.