## Procure Plan m AND R COMMUNTY
ANNUAL PROCUREMENT PLAN WORKS OF FINANCIAL YEAR 2015-16
Serial No./ ADP No. | Name of Scheme | Estimated Cost | Allocated Funds | Cost of new works (Components) | Funds for new works (c-e) | Nature of procurement | Method of procurement | Anticipated / Actual date of Advertisement | Anticipated / Actual date of Start | Anticipated / Actual date of Completion
a | b | c | d | e | f | g | h | i | j | k
1. | M&R of 3' Span RCC Slab Culverts (2 Nos.) along road from Shah Nawaz Leghari to village Aijaz Leghari 0/0-2/0. | 0.4824 | 0.4824 | 0.4824 | 0.4824 | Non ADP | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | June, 2016
2. | M&R of (2x8') Span RCC Slab Bridge (1 No.) and 10' Span RCC Slab Bridge (1 No.) along Chuhar Jamali- Shah Bunder to village Mitho Khan Jalbani mile 0/3-0/4. | 1.1 | 1.1 | 1.1 | 1.1 | Non ADP | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | August, 2016
3. | M&R of 3' Span RCC Slab Culverts (3 Nos.) along Sujawal- Chuhar Jamali road to Marho Bulla Khan mile 0/0-6/0. | 0.6 | 0.6 | 0.6 | 0.6 | Non ADP | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | June, 2016
4. | M&R of 6' Span RCC Slab Culvert (1 No.) from Daro- Bano road mile 2/4 to village Kot Almo mile 0/0-3/1. | 0.325 | 0.325 | 0.325 | 0.325 | Non ADP | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | June, 2016
5. | M&R of 3' Span RCC Slab Culverts (3 Nos.) along Bathoro- Daro mile 1/2 Shah Nawaz Leghari mile 1/0-1/4+330'. | 0.645 | 0.645 | 0.645 | 0.645 | Non ADP | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | June, 2016
6. | M&R of 3' Span RCC Slab Culverts (3 Nos.) along Sujawal- Jati road to village Arisar Hingorjo road mile 0/0-5/6. | 0.45 | 0.45 | 0.45 | 0.45 | Non ADP | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | June, 2016
7. | M&R of road from Jati- Chach Jehan Khan to village Haji Hashim Jat road mile 0/0-0/7. | 4.5232 | 4.5232 | 4.5232 | 4.5232 | Non ADP | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | October, 2016
8. | M&R of road from Ladiun to Muhammad Yousif Chandio miel 0/0-0/2+330'. | 1.8 | 1.8 | 1.8 | 1.8 | Non ADP | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | August, 2016
9. | M&R of 3' Span RCC Slab Culvert (1 No.) along road from Bathoro- Sujawal (Amra Stop) to village Rawal Kandra road mile 0/0-3/1. | 0.15 | 0.15 | 0.15 | 0.15 | Non ADP | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | June, 2016
10. | M&R of 3' Span RCC Slab Culverts (3 Nos.) along Badin- Sujawal road to village Kando Pusio mile 0/0-2/2. | 0.6 | 0.6 | 0.6 | 0.6 | Non ADP | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | June, 2016
11. | M&R of 10' Span RCC Slab Bridge (Regulator) along Molvi Abdul Rehman Soomro to Jar road. | 0.35 | 0.35 | 0.35 | 0.35 | Non ADP | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | June, 2016
12. | M&R of 3' Span RCC Slab Culvert (1 No.) from Daro- Bano to village Feroze Magsi mile 0/0-1/0. | 0.1364 | 0.1364 | 0.1364 | 0.1364 | Non ADP | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | June, 2016
13. | M&R of 4' Span RCC Slab Cuvlert olver Old Ganj Bahar near village Murad Ali Zaur. | 0.1009 | 0.1009 | 0.1009 | 0.1009 | Non ADP | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | June, 2016
14. | M&R of 3' Span RCC Slab Culvert (3 Nos.) from Bano to Rahooth mile 0/0-3/1. | 0.615 | 0.615 | 0.615 | 0.615 | Non ADP | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | June, 2016
15. | M&R to road from Baran Abad Chack No. 153 to village Malik Ali Muhammad Baran mile 0/0-3/0 (In Portion) | 3 | 3 | 3 | 3 | Non ADP | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | October, 2016
16. | M&R of road from Chach Jehan Khan to village Mian Usman Tombs road mile 0/0-1/0. | 4.9733 | 4.9733 | 4.9733 | 4.9733 | Non ADP | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | October, 2016
17. | M&R of 4' Span RCC Slab Culvert over Sujawal - Darro mile 19/1 to village Meenh Dino Jadani mile 0/0-0/7. | 0.2728 | 0.2728 | 0.2728 | 0.2728 | Non ADP | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | June, 2016
18. | M&R of road from Bathoro- Sujawal to village Khamiso Pathan mile 0/0-1/0 Protection Wall (road in portions). | 4.922 | 4.922 | 4.922 | 4.922 | Non ADP | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | October, 2016
19. | M&R of 10' ft. Span RCC Slab Bridge (1 No.) over Sim Nali from Bathoro- Daro road mile 3/6 to village Gul Parhiyar 0/0-1/6. | 0.2308 | 0.2308 | 0.2308 | 0.2308 | Non ADP | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | June, 2016
20 | M&R of road from Shah Nawaz Leghari to village Aijaz Ali Leghari mile 1/0-2/0. | 3.5866 | 3.5866 | 3.5866 | 3.5866 | Non ADP | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | October, 2016
21 | M&R of 8' ft. Span RCC Slab Culvert over Sim Nali road from Jhoke - Daro via Abral road mile 0/0-13/0. | 0.25 | 0.25 | 0.25 | 0.25 | Non ADP | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | June, 2016
22 | M&R of road from Bathoro- Sujawal road mile 34/2 to Jar road mile 0/0-0/6. | 5.5889 | 5.5889 | 5.5889 | 5.5889 | Non ADP | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | October, 2016
23 | M&R of road from Allah Jurio Zaur to village Essa Zaur mile 0/0-0/2. | 0.5 | 0.5 | 0.5 | 0.5 | Non ADP | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | June, 2016
24 | Const: of road from village Sikander Hingorjo road to village Essa Mallah road mile 0/0-1/1 (1.80 KMs) | 10.6619 | 10.6619 | 10.6619 | 10.6619 | ADP No.55/2015-16 | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | October, 2016
25 | Construction of 12’ Span RCC Slab Bridge over Sahebani Minor @ RD: 33 near village Nazir Hingorjo. | 1.8216 | 1.8216 | 1.8216 | 1.8216 | ADP No.55/2015-16 | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | August, 2016
26 | Construction of (3x10’) Span RCC Slab Bridge over Shah Kapoor Drain @ RD: 33 near village Kabool Tharani. | 4.011 | 4.011 | 4.011 | 4.011 | ADP No.55/2015-16 | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | October, 2016
27 | Construction of (3x10’) Span RCC Slab Bridge over Begna Minor @ RD: 20 near village Patel Ismail Thaheem. | 4.0712 | 4.0712 | 4.0712 | 4.0712 | ADP No.55/2015-16 | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | October, 2016
28 | Construction of road from village Sukhio Dal road to village Jeand Zangejo road mile 0/0-1/2 (2.00 KMs) | 16.3417 | 16.3417 | 16.3417 | 16.3417 | ADP No.55/2015-16 | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | October, 2016
29 | Construction of (2x10’) Span RCC Slab Bridge over Machki Minor @ RD: 100 near village Hashim Zangejo. | 3.0926 | 3.0926 | 3.0926 | 3.0926 | ADP No.55/2015-16 | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | October, 2016
30 | Construction of road from Jumoon Machhi road mile 0/2+330’ to Kandhra mile 0/0-0/5 (1.00 KM) | 6.4811 | 6.4811 | 6.4811 | 6.4811 | ADP No.55/2015-16 | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | October, 2016
31 | Construction of C.C Block with Paver Bricks Streets at village Siddique Soomro= 2455’ RFT | 9.9732 | 9.9732 | 9.9732 | 9.9732 | ADP No.55/2015-16 | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | October, 2016
32 | Construction of C.C Block with Paver Bricks Streets at village Dodo Samejo= 2700’ RFT. | 10.1133 | 10.1133 | 10.1133 | 10.1133 | ADP No.55/2015-16 | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | October, 2016
33 | Construction of 15’ Span RCC Slab Bridge over Raj Wah Opposite village Doso Hamaiti. | 2.155 | 2.155 | 2.155 | 2.155 | ADP No.55/2015-16 | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | August, 2016
34 | Construction of 15’ ft. Span RCC Slab Bridge over Raj Wah Opposite village Bacho Shoro | 2.155 | 2.155 | 2.155 | 2.155 | ADP No.55/2015-16 | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | August, 2016
35 | Construction of C.C Blocking with Paver Bricks Streets at village Jumoon Dal= 2490’ RFT | 9.1269 | 9.1269 | 9.1269 | 9.1269 | ADP No.55/2015-16 | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | October, 2016
20. | M&R of road from Chuhar Jamali- Shah Bunder to village Haji Allah Dino Mahendro mile 0/0-0/5. | 1.5 | 3 | 1.5 | 1.5 | M&R | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | June, 2016

## NEW ADP 2015 16
Serial No./ ADP No. | Name of Scheme | Estimated Cost | Allocated Funds | Cost of Ongoing Works (Expenditure Already incurred) | Funds Earmarked for Ongoing works | Cost of new works (Components) | Funds for new works (c-e) | Nature of procurement | Method of procurement | Anticipated / Actual date of Advertisement | Anticipated / Actual date of Start | Anticipated / Actual date of Completion
a | b |  | c | d | e | f | g | h | i | j | k | l
1 | Construction of road from Qureshi Farm road mile 1/2 to Dargah Shah Nasar mile 0/0-1/6 (2.80 KMs) | 18.03 |  | 0 | 0 | 18.03 |  | Construction of Road | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | April, 2018 24 Months
38. | Construction of road from Waryalo road mile 1/3 to Bello link road mile 0/0-0/6+330’ (1.30 KMs) | 8.805 |  | 0 | 0 | 8.805 |  | Construction of Road | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | October, 2018 18 Months
39. | Construction of road from Bidan Sahito road mile 1/3 to village Mohammad Khan Laghari mile 0/0-0/5 (1.00 KM) | 7.25 |  | 0 | 0 | 7.25 |  | Construction of Road | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | April, 2017 12 Months
40. | Construction of road from Qasim Soomro road mile 0/2 to village Abdul Kareem Soomro mile 0/0-0/5 (1.00 KM) | 6.97 |  | 0 | 0 | 6.97 |  | Construction of Road | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | April, 2017 12 Months
41. | Construction of road from Bello to Ranta road mile 4/1-4/4 (0.60 KM) | 3.215 |  | 0 | 0 | 3.215 |  | Construction of Road | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | April, 2017 12 Months
42. | Construction of road from Wali Mohammad Soomro to Bello link road mile 0/0-0/2+330’ (0.50 KM) | 2.87 |  | 0 | 0 | 2.87 |  | Construction of Road | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | April, 2017 12 Months
43. | Construction of road from Ranta - Kot Almo road mile 1/7 to village Sahib Dino Palijo mile 0/0-0/2 (0.40 KM) | 2.795 |  | 0 | 0 | 2.795 |  | Construction of Road | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | April, 2017 12 Months
44. | Re-conditioning of road from Bassar Charan road mile 1/7 to village Juman Charan road mile 0/0-0/1 (0.20 KM) | 1.58 |  | 0 | 0 | 1.58 |  | Construction of Road | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | April, 2017 12 Months
45. | Construction of road from Bello- Darro- Ranta road to village Dodo Jakhro mile 0/0-0/5 (1.00 KM) | 6.425 |  | 0 | 0 | 6.425 |  | Construction of Road | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | April, 2017 12 Months
46. | Construction of road from Damdamo- Matla road to Fish Farm mile 0/0-0/5 (1.00 KM) | 6.685 |  | 0 | 0 | 6.685 |  | Construction of Road | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | April, 2017 12 Months
47. | Construction of road from kando pussio road mile 2/2 to village jaffer shah road mile 0/0- 0/6 (1.2 kms) | 2.8 |  | 0 | 0 | 2.8 |  | Construction of Road | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | April, 2017 12 Months
48. | Construction of 10’ span RCC slab bridge over dars minor opposite village aijaz ali khwaja | 12.44 |  | 0 | 0 | 12.44 |  | Construction of Bridge | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | October, 2018 18 Months
49. | Construction of link road from Karimpur nali road mile 1/2 to village Ramzan Memon road mile 0/0-1/0+550’ (1.752 KMs) | 14.89 |  | 0 | 0 | 14.89 |  | Construction of Road | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | April, 2018 24 Months
50. | Construction of link road from (Gul Parhiar) Manzoor Parhiar mile 4/2 to village Khuda Bux Detho mile 0/0-1/3 (2.20 Kms) | 10.58 |  | 0 | 0 | 10.58 |  | Construction of Road | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | April, 2018 24 Months
51. | Construction of link road from Majnoon Keerano road mile 0/5 to Bathoro Sim Drain mile 0/0-0/6 (1.20 KMs) | 17.67 |  | 0 | 0 | 17.67 |  | Construction of Road | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | April, 2018 24 Months
52. | Construction of link road from Wali Mohammad Khore road mile 0/5 to village Sain Dino Parhiyar mile 0/0-1/3 (2.20 KMs) | 19.26 |  | 0 | 0 | 19.26 |  | Construction of Road | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | April, 2018 24 Months
53. | Const: of link road from Moosa Kotai road mile 0/4 to village Ismail Dal mile 0/0-0/6 (1.20 KMs) | 4.78 |  | 0 | 0 | 4.78 |  | Construction of Road | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | April, 2017 12 Months
54. | Construction of link road from Mithan Jat road mile 1/1 to village Guloo Jat mile 0/0-0/3 (0.60 KM) | 3.57 |  | 0 | 0 | 3.57 |  | Construction of Road | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | April, 2017 12 Months
55. | Const: of link road from Badin- Sujawal mile 25/7 to vill: Ali Ahmed Khokhar mile 0/0-0/2 (0.40 KM) | 15.08 |  | 0 | 0 | 15.08 |  | Construction of Road | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | April, 2018 24 Months
56. | Construction of link road from Badin- Sujawal road mile 25/1 to village Rajib Bhutto mile 0/0-0/3+330’ (0.70 KM) | 9.56 |  | 0 | 0 | 9.56 |  | Construction of Road | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | October, 2018 18 Months
57. | Const: of 10’ Span RCC Slab Bridge over Baghar Wah Opposite village Sanwilo Khore @ RD: 22. | 6.08 |  | 0 | 0 | 6.08 |  | Construction of Bridge | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | April, 2017 12 Months
58. | Construction of 10’ Span RCC Slab Bridge over Sim Nali link drain Opposite village Haji Usman Zaur/ Anwar Zaur Deh Chowbandi U.C Ali Akbar Shah | 4.5 |  | 0 | 0 | 4.5 |  | Construction of Road | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | April, 2017 12 Months
59. | Re-coniditioning/ Construction of road from Badin- Sujawal road mile 31/4 (R/S) to village Qasim Ali Shah mile 0/0-1/4 (2.40 KMs) | 4.9 |  | 0 | 0 | 4.9 |  | Reconditioning /Construction of Road | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | April, 2017 12 Months
60. | Construction of 10’ SPAN RCC SLAB BRIDGE OVER CHOR WAH OPPOSITE VILLAGE AHMED KHAN RIND | 1.98 |  | 0 | 0 | 1.98 |  | Construction of Road | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | April, 2017 12 Months
61. | Construction of (2x10’) span RCC slab bridge over shah wah near village ghazi khan chang. | 2.175 |  | 0 | 0 | 2.175 |  | Construction of Road | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | April, 2017 12 Months
62. | Construction of road from Jati- Chach Jehan Khan @ Khdhi Nali to village Allah Rakhiyo Thaheemore road mile 0/0-1/2 (2.00 KMs) | 14.65 |  | 0 | 0 | 14.65 |  | Construction of Road | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | April, 2018 24 Months
63. | Construction of road from village Ladho Mallah road to village Gullan Mallah road mile 0/0-0/5 (1.00 KM) | 13.36 |  | 0 | 0 | 13.36 |  | Construction of Road | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | April, 2018 24 Months
64. | Const: of road from Tango Minor road to village Hassan Thaheem road mile 0/0-0/5 (1.00 KM) | 16.87 |  | 0 | 0 | 16.87 |  | Construction of Road | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | April, 2018 24 Months
65. | Construction of road from Maliya Mori road @ mile 2/4 to village Siddoo Mandhro road mile 0/0-2/4 (4.00 Kms) Taken up length mile 0/0-0/5 (1.00 KM) | 6.4 |  | 0 | 0 | 6.4 |  | Construction of Road | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | April, 2017 12 Months
66. | Construction of road from Jati- Khor Wah road to village Ibrahim Ladho road mile 0/0-1/2 (2.00 KMs) | 6.13 |  | 0 | 0 | 6.13 |  | Construction of Road | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | April, 2017 12 Months
67. | Construction of road from village Ramzan Jat road to village Dada Aagedino Jat road mile 0/0-1/2 (2.00 KMs) | 6.47 |  | 0 | 0 | 6.47 |  | Construction of Road | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | April, 2017 12 Months
68. | Construction of road from Bathoro- Jati road to village Nimro Jat road mile 0/0-0/5 (1.00 KM) | 13.43 |  | 0 | 0 | 13.43 |  | Construction of Road | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | April, 2018 24 Months
69. | Construction of road from Mir Khana- Baran Abad road to village Usman Kheenro via Haji Umer Kheenro road mile 0/0-1/2 (2.00 KMs) Taken up length mile 0/0-0/5 (1.00 KM) | 13.19 |  | 0 | 0 | 13.19 |  | Construction of Road | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | April, 2018 24 Months
70. | Construction of road from Ahsan Abad road to village Usman Hingorjo road mile 0/0-0/3 (0.60 KM) | 6.54 |  | 0 | 0 | 6.54 |  | Construction of Road | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | April, 2017 12 Months
71. | Construction of road from Sujawal- Chuhar Jamali road @ Wadi Goongri to village Usman Lund via Babu Chang road mile 0/0-1/2 (2.00 KMs) | 6.615 |  | 0 | 0 | 6.615 |  | Construction of Road | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | April, 2017 12 Months
72. | Const: of road from Dargah Bai Budhi road to vill: Ghulam Nabi Baran road mile 0/0-0/6 (1.20 KMs) | 4.195 |  | 0 | 0 | 4.195 |  | Construction of Road | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | April, 2017 12 Months
73. | Construction of road from Dargah Amir Shah road to village Khan Tharani road mile 0/0-1/7 Taken up length mile 0/0-0/5 (1.00 KMs) | 12.09 |  | 0 | 0 | 12.09 |  | Construction of Road | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | April, 2018 24 Months
74. | Construction of road from village Amin Jat road to village Sajan Jat road mile 0/0-1/2 (2.00 KMs) | 7.935 |  | 0 | 0 | 7.935 |  | Construction of Road | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | April, 2017 12 Months
75. | Construction of road from Jati- Chach Jehan Khan @ Kothi Mori to village Ghulam Muhammad Arain road mile 0/0-0/3 (0.60 KM) | 6.75 |  | 0 | 0 | 6.75 |  | Construction of Road | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | April, 2017 12 Months
76. | Construction of road from village Ibrahim Khoso road to village Muhammad Khan Lodho road mile 0/0-2/0 (3.20 KMs) Taken up length mile 0/0-0/5 (1.00 KMs) | 6.385 |  | 0 | 0 | 6.385 |  | Construction of Road | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | April, 2017 12 Months
77. | Improvement/ Construction of road from Sujawal- Jati road to village Meer Muhammad Garho/ Gul Muhammad Garho & village Bachu Jat mile 0/0-1/4 (2.40 KMs) Taken up length mile 0/0-0/1+330' (0.30 KM) | 13.575 |  | 0 | 0 | 13.575 |  | Construction of Road | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | April, 2018 24 Months
78. | Construction of road from Din Muhammad Lashari to Rawat Khan Jamali road mile 0/0-1/5 (2.60 KMs) Taken up length mile 0/0-1/2 (2.00 KMs) | 4.415 |  | 0 | 0 | 4.415 |  | Construction of Road | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | April, 2017 12 Months
79. | Construction of road from Chach Jehan Khan- Shah Bunder road to village Molvi Moledino Mandhrio road mile 0/0-1/0 (1.60 KMs) | 6.445 |  | 0 | 0 | 6.445 |  | Construction of Road | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | April, 2017 12 Months
80. | Construction of road from Rawat Khan Jamali/ Haji Mamoo Khan Jamali to village Anwar Kanth road mile 0/0-0/7 (1.40 KMs) | 9.3 |  | 0 | 0 | 9.3 |  | Construction of Road | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | April, 2017 12 Months
81. | Construction of road from Dargah Tilan Shah Jalali to Primary School Tilan Shah road mile 0/0-0/3 (0.60 KM) | 13.27 |  | 0 | 0 | 13.27 |  | Construction of Road | Single Stage Single Envelope | Ist Week of April 2016 | Ist Week of May 2016 | April, 2018 24 Months