## Above 10 Lac
PROCUREMENT PLAN 2015-16
IN RESPECT OF BUILDINGS DIVISION SUKKUR
S.No | ADP No. | Name of Scheme | Estimated Cost | Source of Funds ADP / Non ADP | Proposed procurement method | Cost of New works | Funds for New works | Nature of procurement | Timing of procurement
[9 empty] | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
NEW ADP 2015-16
1 |  | Renovation of Genral Library @ Solangi Mohalla UC-17 Sukkur. | [5 empty] | Renovation of Genral Library @ Solangi Mohalla UC-17 Sukkur. |  |  |  |  | 0.95
|  | Civil Work | 0.946 | District ADP | N.CB | 0.946 | 0.946 | Civil Work | 0.2365 | 0.2365 | 0.2365 | 0.2365
|  | Electric Work | 0.054 | District ADP | N.CB | 0.054 | 0.054 | Electric Work | 0.0135 | 0.0135 | 0.0135 | 0.0135
2 |  | Renovation of Gate Sardar Ali Gohar Khan Mahar @ Village Tamachani UC-20 SUkkur. | [5 empty] | Renovation of Gate Sardar Ali Gohar Khan Mahar @ Village Tamachani UC-20 SUkkur.
|  | Civil Work | 1 | District ADP | N.CB | 1 | 1 | Civil Work | 0.25 | 0.25 | 0.25 | 0.25
3 |  | Construction of CC Block (300ft) to Malik House UC-40 Nouraja Pano Akil. | [5 empty] | Construction of CC Block (300ft) to Malik House UC-40 Nouraja Pano Akil.
|  | Civil Work | 1 | District ADP | N.CB | 1 | 1 | Civil Work | 0.25 | 0.25 | 0.25 | 0.25
4 |  | Construction of CC Block (300ft) to Mozal Shah House to Nusrat Shah House UC-40 Nouraja Pano Akil. | [5 empty] | Construction of CC Block (300ft) to Mozal Shah House to Nusrat Shah House UC-40 Nouraja Pano Akil.
|  | Civil Work | 1 | District ADP | N.CB | 1 | 1 | Civil Work | 0.25 | 0.25 | 0.25 | 0.25
5 |  | Construction of Hall, Musafir Khana & Dispensary UC-19 Sukkur. | [5 empty] | Construction of Hall, Musafir Khana & Dispensary UC-19 Sukkur.
|  | Civil Work | 0.9392 | District ADP | N.CB | 0.9392 | 0.9392 | Civil Work | 0.2348 | 0.2348 | 0.2348 | 0.2348
|  | Electric Work | 0.0608 | District ADP | N.CB | 0.0608 | 0.0608 | Electric Work | 0.0152 | 0.0152 | 0.0152 | 0.0152
6 |  | Installation of Solar Lights @ Mohalla Bashirabad Military Road Sukkur UC-15. | [5 empty] | Installation of Solar Lights @ Mohalla Bashirabad Military Road Sukkur UC-15.
|  | Electric Work | 1 | District ADP | N.CB | 1 | 1 | Electric Work | 0.25 | 0.25 | 0.25 | 0.25
7 |  | Construction of Pavers Block & CC Drain @ Pir Mohammad Shah Street UC-13 Sukkur. | [5 empty] | Construction of Pavers Block & CC Drain @ Pir Mohammad Shah Street UC-13 Sukkur.
|  | Civil Work | 0.5 | District ADP | N.CB | 0.5 | 0.5 | Civil Work | 0.125 | 0.125 | 0.125 | 0.125
8 |  | Construction of CC Block & Pavers @ Chachar Mohalla Islam Colony New Pind UC-13 New Sukkur. | [5 empty] | Construction of CC Block & Pavers @ Chachar Mohalla Islam Colony New Pind UC-13 New Sukkur.
|  | Civil Work | 1 | District ADP | N.CB | 1 | 1 | Civil Work | 0.25 | 0.25 | 0.25 | 0.25
9 |  | Renovation of Adam Shah Takri / Colony Mohammadi Masjid Sukkur. | [5 empty] | Renovation of Adam Shah Takri / Colony Mohammadi Masjid Sukkur.
|  | Civil Work | 0.845 | District ADP | N.CB | 0.845 | 0.845 | Civil Work | 0.21125 | 0.21125 | 0.21125 | 0.21125
|  | Electric Work | 0.155 | District ADP | N.CB | 0.155 | 0.155 | Electric Work | 0.03875 | 0.03875 | 0.03875 | 0.03875
10 |  | Renovation of Masjid Circuit House Sukkur. | [5 empty] | Renovation of Masjid Circuit House Sukkur.
|  | Civil Work | 0.95 | District ADP | N.CB | 0.95 | 0.95 | Civil Work | 0.2375 | 0.2375 | 0.2375 | 0.2375
|  | Electric Work | 0.05 | District ADP | N.CB | 0.05 | 0.05 | Electric Work | 0.0125 | 0.0125 | 0.0125 | 0.0125
11 |  | Renovation & Installation of Solar Light at Lab-E-Mehran Sukkur. | [5 empty] | Renovation & Installation of Solar Light at Lab-E-Mehran Sukkur.
|  | Electric Work | 1 | District ADP | N.CB | 1 | 1 | Electric Work | 0.25 | 0.25 | 0.25 | 0.25
12 |  | Construction of Shedo Army Selection & Recrument Centre Pano Akil District Sukkur. | [5 empty] | Construction of Shedo Army Selection & Recrument Centre Pano Akil District Sukkur.
|  | Civil Work | 0.945 | District ADP | N.CB | 0.945 | 0.945 | Civil Work | 0.23625 | 0.23625 | 0.23625 | 0.23625
|  | Electric Work | 0.055 | District ADP | N.CB | 0.055 | 0.055 | Electric Work | 0.01375 | 0.01375 | 0.01375 | 0.01375
13 |  | Renovation of Suprentending Engineer Works & Services Official Residence A-8 Quarter ADC Colony Sukkur. | [5 empty] | Renovation of Suprentending Engineer Works & Services Official Residence A-8 Quarter ADC Colony Sukkur.
|  | Civil Work | 0.9445 | District ADP | N.CB | 0.9445 | 0.9445 | Civil Work | 0.23613 | 0.23613 | 0.23613 | 0.23613
|  | Electric Work | 0.0555 | District ADP | N.CB | 0.0555 | 0.0555 | Electric Work | 0.013875 | 0.013875 | 0.013875 | 0.013875
14 |  | Renovation of Deputy Commissioner Office of Other Revenue Department Buildings Sukkur.. | [5 empty] | Renovation of Deputy Commissioner Office of Other Revenue Department Buildings Sukkur..
|  | Electric Work | 1 | District ADP | N.CB | 1 | 1 | Electric Work | 0.25 | 0.25 | 0.25 | 0.25
EXECUTIVE ENGINEER
BUILDINGS DIVISION
SUKKUR

## 10 Lacs
PROCUREMENT PLAN 2015-16
IN RESPECT OF BUILDINGS DIVISION SUKKUR
S.No | ADP No. | Name of Scheme | Estimated Cost | Source of Funds ADP / Non ADP | Proposed procurement method | Cost of New works | Funds for New works | Nature of procurement | Timing of procurement
[9 empty] | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
COMMUNITY DEVELOPMENT PROGRAMME FOR SDG 2015-16
1 |  | Renovation of Markazi Imam Bargah Hussaini Arain Sukkur | [5 empty] | Renovation of Markazi Imam Bargah Hussaini Arain Sukkur |  |  |  |  | 0.95
|  | Civil Work | 1 | MPA Programme | N.CB | 1 | 1 | Civil Work | 0.25 | 0.25 | 0.25 | 0.25
2 |  | Renovation of Masjid Imam Mehdi (A.S) Soomara Mohalla New Pind Sukkur. | [5 empty] | Renovation of Masjid Imam Mehdi (A.S) Soomara Mohalla New Pind Sukkur.
|  | Civil Work | 0.9 | MPA Programme | N.CB | 0.9 | 0.9 | Civil Work | 0.225 | 0.225 | 0.225 | 0.225
|  | Electric Work | 0.1 | MPA Programme | N.CB | 0.1 | 0.1 | Electric Work | 0.025 | 0.025 | 0.025 | 0.025
3 |  | Construction of Jamia Masjid Nabvi Hanfi Madarsa Taleemul Quara Micro Tower Sukkur | [5 empty] | Construction of Jamia Masjid Nabvi Hanfi Madarsa Taleemul Quara Micro Tower Sukkur
|  | Civil Work | 1 | MPA Programme | N.CB | 1 | 1 | Civil Work | 0.25 | 0.25 | 0.25 | 0.25
4 |  | Construction of Compound Wall Graveyard Dargah Hyder Ali Shah Khahi Taluka Rohri. | [5 empty] | Construction of Compound Wall Graveyard Dargah Hyder Ali Shah Khahi Taluka Rohri.
|  | Civil Work | 1 | MPA Programme | N.CB | 1 | 1 | Civil Work | 0.25 | 0.25 | 0.25 | 0.25
5 |  | Construction / Renovation of Madarsa Jamiat Raza Kot Mir Yaqoob Ali Shah Taluka Rohri. | [5 empty] | Construction / Renovation of Madarsa Jamiat Raza Kot Mir Yaqoob Ali Shah Taluka Rohri.
|  | Civil Work | 1 | MPA Programme | N.CB | 1 | 1 | Civil Work | 0.25 | 0.25 | 0.25 | 0.25
6 |  | Laying Paver Block & Open Drain in 10 Wards Municiple Committee Taluka Rohri. | [5 empty] | Laying Paver Block & Open Drain in 10 Wards Municiple Committee Taluka Rohri.
|  | Ward No.1 | 1 | MPA Programme | N.CB | 1 | 1 | Ward No.1 | 0.25 | 0.25 | 0.25 | 0.25
|  | Ward No.2 | 1 | MPA Programme | N.CB | 1 | 1 | Ward No.2 | 0.25 | 0.25 | 0.25 | 0.25
|  | Ward No.3 | 1 | MPA Programme | N.CB | 1 | 1 | Ward No.3 | 0.25 | 0.25 | 0.25 | 0.25
|  | Ward No.5 | 1 | MPA Programme | N.CB | 1 | 1 | Ward No.5 | 0.25 | 0.25 | 0.25 | 0.25
|  | Ward No.6 | 1 | MPA Programme | N.CB | 1 | 1 | Ward No.6 | 0.25 | 0.25 | 0.25 | 0.25
|  | Ward No.7 | 1 | MPA Programme | N.CB | 1 | 1 | Ward No.7 | 0.25 | 0.25 | 0.25 | 0.25
|  | Ward No.8 | 1 | MPA Programme | N.CB | 1 | 1 | Ward No.8 | 0.25 | 0.25 | 0.25 | 0.25
|  | Ward No.9 | 1 | MPA Programme | N.CB | 1 | 1 | Ward No.9 | 0.25 | 0.25 | 0.25 | 0.25
EXECUTIVE ENGINEER
BUILDINGS DIVISION
SUKKUR