## summaryYY
BILL OF QUANTITIES
OF
CONSTRUCTION OF SCHOOL
AT
GHS ROHRI (418020392)
GHS ROHRI
SUMMARY OF BID
|  | Cost of Items | Premium Quoted by Contractor (CIVIL WORKS ONLY) | Amount quoted of Non-Scheduled items | Total Cost
|  | Items (Rs.) |  |  | (Rs.)
NEW WORK
| Civil Works | 16927106.2308
| Schedule Item | 15338722.7874 |  |  | 15338722.7874
| Non Schedule Item |  |  |  | 9519408
Plumbing Works
| Schedule Item | 429505.38 | NA |  | 429505.38
| Non Schedule Item |  |  |  | 1027755
Electrical Works
| Schedule Item | 171230.4 | NA |  | 171230.4
| Non Schedule Item |  |  |  | 304291.3
REHABILITATION WORK
Civil Works
| Schedule Item | 861835.2967 | - | - | 861835.2967
| Non Schedule Item |  |  |  | 16731658.65
Plumbing works
| Schedule item | 131380.12 |  |  | 131380.12
Non-schedule item
Electrical works
| Schedule item | 278886.3 |  |  | 278886.3
| Non-schedule item |  |  |  | 406597.8
| TOTAL |  |  |  | 45201271.0342

## Rehabil (m.s) 1
MEASUREMENT SHEET OF REHABILATION
|  |  | BUILDING 3 | [7 empty] | BUILDING 4 |  |  |  |  | BUILDING 6 | [6 empty] | BUILDING 7 |  |  |  | BUILDING 8 | [6 empty] | TOILET BLOCK 1
S.No | Description | Unit | EXTERNAL | ROOM 1 | ROOM 2 | ROOM 3 | ROOM 4 | ROOM 5 | ROOM 6 | CORRIDOR | EXTERNAL | ROOM 1 | ROOM 2 | ROOM 3 | CORRIDOR | EXTERNAL | ROOM 1 | ROOM 2 | ROOM 3 | ROOM 4 | ROOM 5 | CORRIDOR | EXTERNAL | ROOM 1 | ROOM 2 | CORRIDOR | EXTERNAL | ROOM 1 | ROOM 2 | ROOM 3 | ROOM 4 | ROOM 5 | CORRIDOR |  | Total
A | CIVIL
1 | Distemper Coat | Sft |  | 320 | 320 | 320 | 320 | 320 | 320 | 905 |  | 245 | 245 | 245 | 505 |  | 160 | 440 | 441 | 600 | 600 | 1110 |  | 450 | 450 | 400 |  | 590 | 357 | 357 | 357 | 411 | 789 | 304 | 12475.05
2 | Matt finish | Sft |  | 864 | 864 | 864 | 864 | 864 | 864 | 3156 |  | 534 | 534 | 534 | 1980 |  | 672 | 1008 | 1008 | 1200 | 1200 | 3024 |  | 1032 | 1032 | 1200 |  | 1080 | 912 | 912 | 912 | 984 | 2208 | 866 | 32730.6
3 | Weather Coat | Sft | 3768 | [7 empty] | 3285 |  |  |  |  | 4500 | [6 empty] | 2550 |  |  |  | 4260 | [7 empty] | 19281.15
4 | External Plaster | Sft | 628 | [12 empty] | 600 | [6 empty] | 340 | [11 empty] | 1646.4
5 | Internal Plaster | Sft | [7 empty] | 263 | [24 empty] | 276.15
6 | Ceiling Plaster | Sft | [14 empty] | 160 | 440 | [16 empty] | 630
7 | Internal Plaster ( Seepage DPC ) | Sft |  | 216 | 216 | 216 | 216 | 216 | 216 | 526 |  | 267 | 267 | 267 | 330 |  | 252 | 252 | 252 | 300 | 300 | 504 |  | 258 | 258 | 300 |  | 270 | 228 | 228 | 228 | 246 | 552 |  | 7750.05
8 | Screeding plus water proof on roof | Sft |  | 320 | 320 | 320 | 320 | 320 | 320 | 905 |  | 490 | 490 | 490 | 505 |  | 160 | 440 | 440 | 600 | 600 | 1110 |  | 450 | 450 | 400 |  | 590 | 357 | 357 | 357 | 411 | 789 | 304 | 13245.75
9 | Cracks repair on wall , col, beam stair etc. | Sft | 200 | 20 | 10 | 10 | 10 | 10 | 10 | 20 |  |  |  |  | 15 |  |  |  |  | 40 | 40 | 20 | 170 | 30 | 30 | 20 | 284 | 30 | 25 | 10 | 10 | 10 | 222 |  | 1308.3
10 | Anti termite on existing wall | Sft | 380 | 90 | 864 | 346 | 346 | 346 | 346 | 632 | 657 | 110 | 110 | 110 | 198 |  | 70 | 100 | 100 | 120 | 120 | 305 |  | 105 | 105 |  |  | 108 | 92 | 92 | 92 | 100 | 222 |  | 6579.3
11 | 1:2:4 ratio 2" thick flooring | Sft |  | 32 | 64 | 32 | 32 | 32 | 32 | 905 | [6 empty] | 32 |  |  | 60 | 60 | [13 empty] | 1345.05
12 | Porcelin tile on existing floor | Sft |  | 320 | 320 | 320 | 320 | 320 | 320 | 905 | [6 empty] | 160 | 440 | 441 | 600 | 600 | 1110 |  | 450 | 450 | 400 |  | 590 | 357 | 357 | 357 | 411 | 789 |  | 10853.85
13 | skirting | Sft |  | 36 | 36 | 36 | 36 | 36 | 36 | 132 | [6 empty] | 28 | 42 | 42 | 50 | 50 | 126 |  | 43 | 43 | 50 |  | 50 | 38 | 38 | 38 | 41 | 97 |  | 1180.2
14 | Marble on stair | Sft | [8 empty] | 130 | [15 empty] | 300 | [7 empty] | 451.5
15 | New door including chowkhat | Sft | [15 empty] | 28 | 29 | 28 | 28 |  |  | 28 | 28 |  |  | 28 | 28 | 28 | 28 | 28 |  |  | 324.45
16 | New Window/ venti including chowkhat | Sft | [14 empty] | 4 | 80 | 80 | 100 | 100 |  |  | 114 | 114 |  |  | 268 | 40 | 60 | 60 | 60 |  |  | 1134
17 | New Steel Grill | Sft | [23 empty] | 180 | [6 empty] | 432 |  | 642.6
18 | Painting of doors | Sft | [9 empty] | 56 | 56 | 56 |  |  | 56 | 56 | 56 | 56 | 56 | 516 |  | 56 | 56 |  |  | 56 | 56 | 56 | 56 | 56 |  |  | 1423.8
19 | Painting of widows & ventilators | Sft | [9 empty] | 96 | 96 | 96 |  |  | 8 | 160 | 160 | 200 | 200 |  |  | 228 | 228 |  |  | 536 | 80 | 120 | 120 | 120 |  |  | 2570.4
20 | Enamel paint on grill | Sft | [9 empty] | 48 | 48 | 48 | 420 |  |  | 80 | 80 | 100 | 100 | 516 |  | 100 | 100 | 180 |  | 268 | 40 | 60 | 60 | 60 | 432 |  | 2877
21 | New RCC Work 1:1.5:3 concrete | Cft | [14 empty] | 80 | 220 | [16 empty] | 315
22 | steel reinforcement | Cwt | [14 empty] | 5 | 14 | [16 empty] | 19.95
23 | Glaze tile | Sft | [31 empty] | 168 | 176.4
24 | Dado tile | Sft | [31 empty] | 742 | 779.1
25 | Blackboard repair and paint | Each | [9 empty] | 1 | 1 | 1 |  |  |  | 1 | 1 | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 21 | bar: ROOM 1 to ROOM 6
26 | B/WALL EXTENSION | rft | [31 empty] | 550 | 577.5
B | PLUMBING
1 | W.C | Each | [32 empty] | 0
2 | Flash tank | Each | [32 empty] | 0
3 | Floor trap | Each | [32 empty] | 0
4 | Soap tray | Each | [32 empty] | 0
5 | wash basin | Each | [32 empty] | 0
6 | Pedestal | Each | [32 empty] | 0
7 | Muslim Shower | Each | [32 empty] | 0
8 | Bib Cock | Each | [32 empty] | 0
9 | Gun metal Valve | Each | [32 empty] | 0
C | ELECTRIFICATION
1 | Saver | Each |  | 4 | 4 | 4 | 4 | 4 | 4 | 10 |  | 4 | 4 | 4 | 8 |  | 2 | 4 | 4 | 4 | 4 | 10 |  | 4 | 4 | 6 |  | 4 | 4 | 4 | 4 | 4 | 10 | 6 | 132.3
2 | Fans | Each |  | 4 | 4 | 4 | 4 | 4 | 4 |  |  | 2 | 2 | 2 |  |  | 2 | 4 | 4 | 4 | 4 |  |  | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 |  |  | 79.8
3 | Dimmer | Each |  | 4 | 4 | 4 | 4 | 4 | 4 |  |  | 2 | 2 | 2 |  |  | 2 | 4 | 4 | 4 | 4 |  |  | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 |  |  | 79.8
4 | Switch board | Each |  | 2 | 2 | 2 | 2 | 2 | 2 | 3 |  | 2 | 2 | 2 | 2 |  | 1 | 2 | 2 | 2 | 2 | 3 |  | 2 | 2 | 2 |  | 2 | 2 | 2 | 2 | 2 | 3 | 6 | 56.7
5 | Wirring point for fan | Point |  | 4 | 4 | 4 | 4 | 4 | 4 |  |  | 2 | 2 | 2 |  |  | 2 | 4 | 4 | 4 | 4 | 10 |  | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 |  |  | 90.3
7 | Switches | No |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 |  | 6 | 6 | 6 | 8 |  | 4 | 10 | 10 | 10 | 10 | 10 |  | 10 | 10 | 6 |  | 10 | 10 | 10 | 10 | 10 | 10 |  | 247.8
8 | 2 pin switch | No |  | 2 | 2 | 2 | 2 | 2 | 2 | 3 |  | 2 | 2 | 2 | 2 |  | 1 | 2 | 2 | 2 | 2 | 3 |  | 2 | 2 | 2 |  | 2 | 2 | 2 | 2 | 2 | 3 |  | 56.7
10 | fan clamp | No |  | 4 | 4 | 4 | 4 | 4 | 4 |  |  | 2 | 2 | 2 |  |  | 2 | 4 | 4 | 4 | 4 |  |  | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 |  |  | 79.8
11 | Batten holder | No |  | 4 | 4 | 4 | 4 | 4 | 4 | 10 |  | 4 | 4 | 4 | 8 |  | 2 | 4 | 4 | 4 | 4 | 10 |  | 4 | 4 | 6 |  | 4 | 4 | 4 | 4 | 4 | 10 | 6 | 132.3
12 | Bulb point | No |  | 4 | 4 | 4 | 4 | 4 | 4 | 10 |  | 4 | 4 | 4 | 8 |  | 2 | 4 | 4 | 4 | 4 | 10 |  | 4 | 4 | 6 |  | 4 | 4 | 4 | 4 | 4 | 10 | 6 | 132.3

## Rehabil( est) 1
BILL OF QUANTITIES
OF
REHABILITION OF SCHOOL
AT
GHS ROHRI (418020392)
N.B: | These items and their rates given in the are based on Schedule Rate 2012 of Govt. of Sindh. However Rates of Non-Schedule Items and Premium are to be filled by the Contractor .
1) SCHEDULE OF ITEM (A)
S.No | Description of Item | Unit | Qty | Rate | Amount
(Rs.)
1 | Reinforced cement concrete work including all labour and material except the cost of steel reinforcement and its labour for bending and binding which will be paid separately. This rate also includes all kinds of forms moulds lifting shuttering curing rendering and finsihing the exposed surface .
a) R.C work in roof slab, beams columns rafts,lintels and other structural members laid in situ or precast laid in position complete in all respects.
| (I) Ratio (1:1 1/2:3) or more 90 Lbs cement 2 Cft sand 4 Cft. Shingle 1/8" to 1/4" guage.must have cylinder strength >3750psi (S.I. No.6(a)(ii)/P-16). | P.Cft | 315 | 349 | 109935
1 | Preparing the surface and painting with weather coat including rubbing the surface with rubbing brick / sand paper filling the voids with chalk / plaster of paris and then painting with weather coat of approved make (S.I No. (A) 38/P-55). | %Sft | 19281.15 | 1328.25 | 256101.8749
| 2nd & subsequent coat (S.I No. (B) 38/P-55). | %Sft | 19281.15 | 619.85 | 119514.2083
2 | Providing and laying cement sand plaster in walls and ceiling including applying nero. Mixing and applying mortar to perfect line & level as per drawings, specifications (S.I. No. 11 & 13/P-51).
| a. In walls 3/4 inches thick (1:6) (External Plaster) | %Sft | 1646.4 | 2590.5 | 42649.992
| b. In walls 1/2" inches thick (1:4) (Internal Plaster)) | %Sft | 276.15 | 2283.93 | 6307.0727
| c. 3/8" inches thick (1:4) (Ceiling) | %Sft | 630 | 2197.52 | 13844.376
3 | Providing and laying topping cement concrete (1:2:4) including surface finishing and dividing into panels (S.I. No. 16(c)/P-41).
| a. 2" thick (Under Floor) | %Sft | 1345.05 | 3275.5 | 44057.1127
4 | Providing and laying floor of approved coloured glazed tiles 1/4" thick laid in white cement and pigment on bed of 3/4" thick cement mortar 1:2, complete in all respect as per drawing and specification or as directed by the engineer.
| Floors (S.I. No. 25/P-42). | %Sft | 176.4 | 27747.06 | 48945.8138
5 | Supply & fixing glazed tile dado 1/4" thick laid in pigment over 1:2 cement sand mortar 3/4" thick including finishing Dado (S.I. No. 38/P-44). | %Sft | 779.1 | 28299.3 | 220479.8463
|  |  |  | TOTAL= | 861835.2967
1B) SCHEDULE OF ITEM (B), PLUMBING WORKS
S.No | Description of Item | Unit | Qty | Rate | Amount
|  |  |  | (Rs.) | (Rs.)
1 | Providing & fixing 1/2" dia, lead connection complete with a 1/2" dia brass stop cock, two brass nuts & lining jointed to lead pipe with plumber wiped solder joints 1/2" inches lead pipe to be of not less than 4lbs per lineal yard (S.I. No. 22/P-6). | Each | 5 | 689.7 | 3448.5
2 | Providing & fixing in position nylon connections complete with 1/2" dia brass stop cock with pair of brass nuts and lining joints to nylon connection (S.I. No. 23/P-6). | Each | 5 | 447.15 | 2235.75
3A | Providing & fixing M.S clamps of the approved design to 4" i/c the cost of cutting and making good to wall or M.S bolts and nuts, 4" into wall including pipe distance pieces extra painting to match the colour of the building (S.I. No. 2/P-9). | Each | 9 | 72.16 | 649.44
3B | Providing & fixing M.S clamps of the approved design to 3" i/c the cost of cutting and making good to wall or M.S bolts and nuts,3" into wall including pipe distance pieces extra painting to match the colour of the building (S.I. No. 14/P-10). | Each | 9 | 264 | 2376
4 | (b) S/Fixing concealed Tee stop cock of superior quality with c.p head 1/2" dia (S.I.No. 14(A)/P-18).
|  | Each | 5 | 1097 | 5485
5 | (b) S/Fixing long bib-cock of superior quality with c.p head 1/2" dia (S.I. No. 13(a)/P-19).
|  | Each | 5 | 1109.46 | 5547.3
6 | Providing and fixing orisa type white or color glazed earthen ware w.c pan with cost of low level plastic flush tank of 3 gallons capacity of approved quality i/c making requiste numbers of holes in walls , plinth & floor and making good in cement concrete 1:2:4 W.C pan orisa type 23" with plastic tank of low down 3 gallons C.I trap & C.I thumble (Superior Quality ) With 4" dia. earthen ware trap and plastic thumble (S.No 3 / P-2 ) | Each | 5 | 6166.6 | 30833
7 | Providing & fixing 24" x 18" lavatory basin in white glazed earthen ware complete with and including the cost of W.I or C.I cantilever brackets 6 inches built into wall, painted white in to two coats after a primary coat of red lead paint , a pair of 1/2" dia rubber plug & chrome plate brass chain 1-1/4" dia malloable iron or c.p brass traps malloable iron or brass unions and making requiste number of holes in wall plinth & floor for pipe connection and making good in cement concrete 1:2:4 (Standard pattern ) (S.No 8 / P-3 ) | Each | 3 | 4253.9 | 12761.7
8 | Add extra for labour for providing and fixing of earthen ware pedestal white or coloured glazed (S.No 9 / P-3 | Each | 3 | 938.47 | 2815.41
9 | Supplying & fixing 6" x 4" earthen gully trap with 4" outlet complete with 4" thick 1:2:4 C.C for bed & 1/2 thick cement plaster (1:3) to the karb C.I grating 6" x 6" and C.I. cover and frame 12"x12" (inside) etc Complete (b) earthen ware glazed gully trap(a) (i) 6'x6"x4" (i) With C.I Cover and Frame(S.I. No. 1(i)/P-23. | Each | 2 | 1220.67 | 2441.34
10 | Construction manhole for the required dia of circular sewer and 7'-9" depth with walls of B.B in cement mortar 1:3 cement plaster 1:3, 1/2" thick inside of wall and 1" (25mm) thick over benching and channel including fixing C.I manhole cover with frame of clear opening 2'x2' (610 x 610mm) of 4.5 cwt embedded inplain C.C 1:2:4 and two way reinforecement 6" thick includind fixing 1" (25mm) dia dia M.S steps 6" (150mm) wide projecting 4" (102mm) from the face of wall at 12" (305mm) c/c duly painted etc complete as per specification and drawing (a) 4" to 9" dia 4" x3'x7'-9" (S.I.No. 2/P-47) ).(if the depth of main hole is less than 7'-9" deduct from the cost @rate 2143/each). | Each | 1 | 42745 | 42745
11 | Supplying & fixing soap tray of made of plastic of superior quality and design with fine finishing with c.p screws etc complete (S.I. No.6/P-8). | Each | 3 | 169.4 | 508.2
12 | Providing & fixing C.P muslim shower with double bib cock & ring pipe (S.I. No.19(a)/P-19). | Each | 5 | 3432 | 17160
13 | Supplying & fixing ball valves (with unsoldered copper ball) 2" dia (S.I. No.8/P-18) | Each | 4 | 593.37 | 2373.48
Total |  |  |  |  | 131380.12
C | ELECTRIFICATION
1 | Wiring for light or fan point with (3/.029) PVC insulated wire in 20mm (3/4") PVC conduit recessed in the wall or column as required (S.No.124, Pg-15). | Point | 222.6 | 1130 | 251538
2 | Providing & fixing one way SP 5 amp switch flush type on metal board & covered with plastic sheet (S.No-219, Pg-33). | No | 247.8 | 54 | 13381.2
3 | Providing & fixing two pin 5 amp plug & socket switch flush type on metal board & covered with plastic sheet (S.No-222, Pg-33). | No | 56.7 | 83 | 4706.1
4 | Providing & fixing brass / PVC batten holder superior quality (S.No-232, Pg-33). | No | 132.3 | 70 | 9261
TOTAL = |  |  |  |  | 278886.3
2) NON - SCHEDULE OF ITEM
A | CIVIL WORKS
1 | Dampnees in wall is treated by pouring damp proof course (as item # 5 of rehabilitation drawing) by filling after chizeling along the width of wall using a mixture of Cement, Coarse Sand, Pea Gravel and Pudlo in ratio 1:1-1/2:3 as per direction given in rehabilitation sheet and as per direction of engineer in charge. | Sft | 7750.05 | 177 | 1371758.85
2 | Plaster after dampness for 2.5' (or more varying with site) height plastering will be done by first weeking the entire surface rough and its plastering the surface | Sft | 7750.05 | 42 | 325502.1
3 | Screeding on Roof with Rubber lining and bitumen while also maintaining the slope of the roof for concrete spouts. | Sft | 13245.75 | 202 | 2675641.5
4 | Cracks repair on wall , col, beam stair etc. | Sft | 1308.3 | 150 | 196245
5 | Anti termite on existing wall as per the reghabilitation drawings. | Sft | 6579.3 | 30 | 197379
6 | Porcelain tile will be laid with plastic sheet for water proofing at base. Details of layer are given in rehabilitation sheet (see figure 13&14, detail # 7 & drawing no 2 of rehabilitation). | P.Sft | 10853.85 | 282 | 3060785.7
7 | Room skirting of proceline tile by first making, or surface rough and fixing skirting after mortar and cement & sand mix as per standard and direction of engineer in charge. | Sft | 1180.2 | 186 | 219517.2
8 | Providing & fixing new panel doors and windows of diar wood where required of same design which exists or (if flush door exists) panel door design as given by architect will be used) if all doors need replacement they will be replaced by wood panel doors as direction of engineer in charge. | P.Sft | 1458.45 | 1850 | 2698132.5
9 | Window new grill provdiding and fixing new grill if design as given in drawing. Fixing to wall | P.Sft | 642.6 | 262 | 168361.2
10 | Painting door by first making the surface smooth and filling it with filler and after making the surface two coats of paint as required by engineer in charge. | P.Sft | 1423.8 | 64 | 91123.2
11 | Painting windows by first making the surface smooth with filler and later two coats of paint as required by engineer in charge. | P.Sft | 2570.4 | 64 | 164505.6
12 | Window grill painting. Cleaning existing grill with steel brush and sand paper to surface get smooth. Applying red oxide one coat and later two coats of enamel paint. | P.Sft | 2877 | 24 | 69048
13 | Extension of Boundary Wall to a height of 9' as per the method given in rehabilitation drawings. | P.Rft | 577.5 | 1817 | 1049317.5
14 | Providing and fixing 3/8" thick Verona marble tiles of approved quality and colour shade size on stairs as specified in drawings in steps and risers skirting and facing removal / tucking of existing plaster surface etc over 1/2" thick base of cement mortar 1:3 setting mortar base including fillings the joints and washing the tiles with white cement , slurry current , finishing cleaning and polishing etc complete . (a) for new work | P.Sft | 451.5 | 510 | 230265
15 | Scratch and finish the roof surface and make base for new paint using prime coat and distemper the surface with maximum of two coats. | Sft | 12475.05 | 84 | 1047904.2
16 | Scratch the rough paint of the wall and make the surface smooth and make ground by filling filler or prime coat or any other filling material and prepare a smooth surface. After preparing the surface paint it with matt finish paint (two coats) only. | Sft | 32730.6 | 91 | 2978484.6
17 | Providing and fabrication of deformed steel reinforcement of attleast Grade 60 having yield strength at 0.2% strain for cement concrete including cutting, bending, laying in position, making joints and fastenings including cost of binding wire (also including removal of rust from bars). | Ton | 0.9975 | 125000 | 124687.5
18 | Repair of Black board as per the specified method | Each | 21 | 3000 | 63000
Total= |  |  |  |  | 16731658.65
C | ELECTRICAL WORKS
1 | Providing and fixing 25 watt saver lamp Philips quality or equivalent as approved by Engineer in charge | No | 132.3 | 280 | 37044
2 | Providing & fixing ceiling fan 56" good quality (Royal/ Pak/ Millat or equivalent as directed by Engineer) | No | 79.8 | 3980 | 317604
3 | Providing and fixing 6 Amps Piano fan dimmer fixed on plastic or fiber top cover sheet on 14 SWG metal board recessed in the wall and column including connection as required. | No | 79.8 | 333 | 26573.4
4 | Providing and fixing 4 1/2" x 4 1/2" MS dia casted powder coated recessed type fan clamp box with 3/8" dia MS bar fan clamp fixed on roof at casting time as required. | No | 79.8 | 318 | 25376.4
Total= |  |  |  |  | 406597.8

## N.W.C(M.S) 1
MEASUREMENT SHEET OF NEW WORK
S.No | Description | Unit | H.M | Staff | Class 1 | Class 2 | Class 3 | Class 4 | Class 5 | Class 6 | LAB |  | LAB |  | Library |  | Corridor | Corridor | Corridor | Corridor | Corridor | Corridor | Bath 5 toilet | Bath 5 toilet | existing classroom | Bath 5 toilet | LAB |  | OHWT | OHWT | UGWT 7500 | septic tank | Ramp | External dev | B/Wall | main gate + columns | TOTAL
1 | Excavation | Cft | 586 | 586 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | [6 empty] | 1055 | 1055 |  | 1055 | 375 | 375 |  |  | 3100 | 1500 |  |  | 1400 |  | 15587
2 | Lean 1:4:8 | Cft | 59 | 59 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | [6 empty] | 105 | 105 |  | 105 | 38 | 38 |  |  | 150 | 100 |  |  | 420 |  | 1635
3 | New earth outside | Cft | 687 | 687 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 600 | 600 | 600 | 600 | 600 | 600 | 750 | 750 |  | 750 | 200 | 200 |  |  |  |  | 100 | 15000 |  |  | 25124
4 | Concrete 1:1.5:3 | Cft | 653 | 653 | 468 | 468 | 468 | 468 | 468 | 468 | 468 | 468 | 468 | 468 | 468 | 468 | [6 empty] | 1000 | 1000 |  | 1000 | 468 | 468 | 260 | 260 | 750 | 400 |  |  | 1680 |  | 14208
5 | Steel reinforcement | Cwt | 36 | 36 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | [6 empty] | 60 | 60 |  | 60 | 28 | 28 | 20 | 20 | 55 | 40 |  |  | 175 |  | 954
6 | 1:2:4 ( 2" thick flooring) | Sft | 369 | 369 | 319 | 319 | 319 | 319 | 319 | 319 | 319 | 319 | 319 | 319 | 319 | 319 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 |  | 300 | 319 | 319 | [8 empty] | 7904
7 | Poly thene sheet | Sft | 369 | 369 | 319 | 319 | 319 | 319 | 319 | 319 | 319 | 319 | 319 | 319 | 319 | 319 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 |  | 300 | 319 | 319 |  |  |  |  | 120 |  |  |  | 8024
8 | 1:3:6 ( 3" thick ) | Sft | 92 | 92 | 79.75 | 79.75 | 79.75 | 79.75 | 79.75 | 79.75 | 79.75 | 79.75 | 79.75 | 79.75 | 79.75 | 79.75 | 100 | 100 | 100 | 100 | 100 | 100 | 75 | 75 |  | 75 | 79.75 | 79.75 |  |  |  |  | 120 |  |  |  | 2245.5
9 | Stone filling | Cft | 185 | 185 | 159.5 | 159.5 | 159.5 | 159.5 | 159.5 | 159.5 | 159.5 | 159.5 | 159.5 | 159.5 | 159.5 | 159.5 | 60 | 60 | 60 | 60 | 60 | 60 | 150 | 150 |  | 150 | 159.5 | 159.5 |  |  |  |  | 60 |  |  |  | 3473
10 | Block masonry | Cft | 535 | 535 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | [6 empty] | 700 | 700 |  | 700 | 413 | 413 | [6 empty] | 3150 |  | 12102
11 | New door | Sft | 43 | 43 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | [6 empty] | 120 | 120 |  | 120 | 24 | 24 | [8 empty] | 782
12 | New window & ventilator | Sft | 76 | 76 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | [6 empty] | 30 | 30 |  | 30 | 72 | 72 | [8 empty] | 1250
13 | Steel grill | Sft | 76 | 76 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | [6 empty] | 30 | 30 |  | 30 | 72 | 72 | [8 empty] | 1250
14 | Painting on door | Sft | 86 | 86 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | [6 empty] | 240 | 240 |  | 240 | 48 | 48 | [8 empty] | 1564
15 | Painting on window / ventilator | Sft | 152 | 152 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | 144 | [6 empty] | 60 | 60 |  | 60 | 144 | 144 | [8 empty] | 2500
16 | Porcelin tile | Sft | 319 | 319 | 319 | 319 | 319 | 319 | 319 | 319 | 319 | 319 | 319 | 319 | 319 | 319 | 280 | 280 | 280 | 280 | 280 | 280 |  |  |  |  | 319 | 319 | [8 empty] | 6784
17 | skirting | Sft | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 27 | 27 | 27 | 27 | 27 | 27 |  |  |  |  | 37 | 37 | [8 empty] | 754
18 | Marble on stair | Sft | [14 empty] | 40 | 40 | 40 | 40 | 40 | 40 | [14 empty] | 240
19 | Glaze tile | Sft | 27 | 27 | [18 empty] | 175 | 175 |  | 175 | [10 empty] | 579
20 | Dado tile | Sft | 143 | 143 | [18 empty] | 750 | 750 |  | 750 | [10 empty] | 2536
21 | External plaster | Sft | 1232 | 1232 | 952 | 952 | 952 | 952 | 952 | 952 | 952 | 952 | 952 | 952 | 952 | 952 | [6 empty] | 1500 | 1500 |  | 1500 | 952 | 952 | 710 | 710 |  |  |  |  | 13230 |  | 34942
22 | Internal plaster | Sft | 1247 | 1247 | 952 | 952 | 952 | 952 | 952 | 952 | 952 | 952 | 952 | 952 | 952 | 952 | [6 empty] | 1550 | 1550 |  | 1550 | 952 | 952 |  |  | 570 | [5 empty] | 21042
23 | Ceiling plaster | Sft | 386 | 386 | 319 | 319 | 319 | 319 | 319 | 319 | 319 | 319 | 319 | 319 | 319 | 319 | [6 empty] | 350 | 350 |  | 350 | 319 | 319 | [8 empty] | 6288
24 | Matt finish | Sft | 1247 | 1247 | 952 | 952 | 952 | 952 | 952 | 952 | 952 | 952 | 952 | 952 | 952 | 952 | [6 empty] | 775 | 775 |  | 775 | 952 | 952 | [8 empty] | 18147
25 | Weather Coat | Sft | 1232 | 1232 | 952 | 952 | 952 | 952 | 952 | 952 | 952 | 952 | 952 | 952 | 952 | 952 | [6 empty] | 1500 | 1500 |  | 1500 | 952 | 952 | 525 | 525 |  |  |  |  | 13230 |  | 34572
26 | Distemper | Sft | 386 | 386 | 319 | 319 | 319 | 319 | 319 | 319 | 319 | 319 | 319 | 319 | 319 | 319 | [6 empty] | 350 | 350 |  | 350 | 319 | 319 | [8 empty] | 6288
27 | 3" th roofing plus water proofing | Sft | 386 | 386 | 319 | 319 | 319 | 319 | 319 | 319 | 319 | 319 | 319 | 319 | 319 | 319 | [6 empty] | 350 | 350 |  | 350 | 319 | 319 | [8 empty] | 6288
28 | DPC | Sft | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | [6 empty] | 100 | 100 |  | 100 | 50 | 50 |  |  | 570 | [5 empty] | 1670
29 | Spout | Each | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | [6 empty] | 10 | 10 |  | 10 | 4 | 4 | [8 empty] | 94
30 | Mortice lock | Each | 2 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | [6 empty] | 5 | 5 |  | 5 | 1 | 1 | [8 empty] | 33 | bar: Class 1 to Class 6
31 | 1:10 concrete | Cft | [34 empty] | 0
32 | Anti termite on existing wall | Sft | 576 | 576 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | [10 empty] | 375 | 375 | [8 empty] | 6402
33 | boring | Rft | [34 empty] | 0
34 | Sub base | Sft | [31 empty] | 5000 |  |  | 5000
35 | cemented tiles | Sft | [30 empty] | 120 | 5000 |  |  | 5120
42 | Steel gate | Sft | [34 empty] | 0
43 | Enamel paint on grill | Sft | 76 | 76 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | [6 empty] | 30 | 30 | 0 | 30 | 72 | 72 | [8 empty] | 1250
44 | Barbed wire | Rft | [31 empty] | 1600 |  |  | 1600
B | PLUMBING
1 | W.C | Each | 1 | 1 | [32 empty] | 2.3
3 | Floor trap | Each | 1 | 1 | [32 empty] | 2.3
4 | Soap tray | Each | 1 | 1 | [32 empty] | 2.3
5 | wash basin | Each | 1 | 1 | [32 empty] | 2.3
6 | Pedestal | Each | 1 | 1 | [32 empty] | 2.3
7 | Muslim Shower | Each | 1 | 1 | [12 empty] | 6 | 6 | 6 | 6 | 6 | 6 | [14 empty] | 2.3
8 | Bib Cock | Each | 1 | 1 | [32 empty] | 2.3
9 | Gun metal Valve | Each | 1 | 1 | [32 empty] | 2.3
C | ELECTRIFICATION | [15 empty] | 1 | 1 | 1 | 1 | 1 | 1 | [14 empty] | 6.9
1 | Saver | Each | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 6 | 6 | 6 | 6 | 6 | 6 | 5 | 5 |  | 5 | 4 | 4 | [8 empty] | 67
2 | Fans | Each | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | [10 empty] | 2 | 2 | [8 empty] | 35.2
3 | Dimmer | Each | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 6 | 6 | 6 | 6 | 6 | 6 | 1 | 1 |  | 1 | 2 | 2 | [8 empty] | 78.1
4 | Switch board | Each | 2 | 2 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | [6 empty] | 5 | 5 |  | 5 | 1 | 1 | [8 empty] | 36.3 | bar: Class 1 to Class 6
5 | Wirring point for fan | Point | 7 | 7 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | [10 empty] | 6 | 6 | [8 empty] | 107.8
6 | Wirring point for plug | Point | 1 | 1 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | [6 empty] | 5 | 5 |  | 5 | 1 | 1 | [8 empty] | 34.1 | bar: Class 1 to Class 6
7 | Switches | No | 7 | 7 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 |  |  |  |  | 6 | 6 | [8 empty] | 147.4
8 | 2 pin switch | No | 1 | 1 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | [10 empty] | 1 | 1 | [8 empty] | 17.6 | bar: Class 1 to Class 6
9 | Ceiling rose | No | 1 | 1 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | [10 empty] | 1 | 1 | [8 empty] | 17.6 | bar: Class 1 to Class 6
10 | fan clamp | No | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | [6 empty] | 5 | 5 |  | 5 | 2 | 2 | [8 empty] | 51.7
11 | Batten holder | No | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | [10 empty] | 4 | 4 | [8 empty] | 72.6

## CIVIL EST 1
BILL OF QUANTITIES
OF
CONSTRUCTION OF SCHOOL
AT
GHS ROHRI (418020392)
N.B: | These items and their rates given in the are based on Schedule Rate 2012 of Govt. of Sindh. However Rates of Non-Schedule Items and Premium are to be filled by the Contractor .
1) SCHEDULE OF ITEM (A), CIVIL WORKS
S.No | Description of Item | Unit | Qty | Rate | Amount
(Rs.)
1 | Excavation in foundation of building bridges and other structures including dagbelling dressing refilling around structure with excavated earth watering and ramming lead up to 5ft (S.I. No. 18 (b)/P-4) (for foundation)
| (a) In Ordinary Soil | %oCft | 15587 | 3176.25 | 49508.2087
2 | Cement concrete plain including placing compacting, finishing and curing, complete (includingscreening and washing of stone aggregate without shuttering).
| (a) Ratio 1:4:8 (S.I. No. 5(i)/P-15). | %Cft | 1635 | 11288.75 | 184571.0625
3 | Filling, watering and ramming earth under floor with new earth excavated from outside lead upto the one chain and lift upto 5 ft.(S.I. No. 22/P-4). | %oCft | 25124 | 3630 | 91200.12
4 | Reinforced cement concrete work including all labour and material except the cost of steel reinforcement and its labour for bending and binding which will be paid separately. This rate also includes all kinds of forms moulds lifting shuttering curing rendering and finsihing the exposed surface .
a) R.C work in roof slab, beams columns rafts,lintels and other structural members laid in situ or precast laid in position complete in all respects.
| (I) Ratio (1:1 1/2:3) or more 90 Lbs cement 2 Cft sand 4 Cft. Shingle 1/8" to 1/4" guage.must have cylinder strength >3750psi (S.I. No.6(a)(ii)/P-16). | P.Cft | 14208 | 349 | 4958592
5 | Providing and laying topping cement concrete (1:2:4) including surface finishing and dividing into panels (S.I. No. 16(c)/P-41).
| a. 2" thick (Under Floor) | %Sft | 7904 | 3275.5 | 258895.52
6 | Providing and laying single layer of polythene sheet 0.13mm thick for water proofing as per specification and instructions of Engineer incharge. (S.I. No. 38/P-37). | P.Sft | 8024 | 10.7 | 85856.8
7 | Cement concrete plain including placing compacting, finishing and curing, complete (includingscreening and washing of stone aggregate without shuttering). Ratio (1:3:6 ) (SNo.5 h / P - 15 ) | %Cft | 2245.5 | 12595 | 282820.725
8 | Providing and Laying stone or spawl filling on level (S.I No. 28(b)/P-31). | %Cft | 3473 | 563.86 | 19582.8578
9 | Providing & laying 1:3:6 cement concrete solid block masonary wall 6" and below in thickness set in 1:6 cement mortar in ground floor superstructure including raking out joints & curing etc complete (S.I. No. 24/P-18). | %Cft | 12102 | 15771.01 | 1908607.6302
10 | Supply & fixing first class deodar wood wrought joinery in doors and windows etc, fixed in position including chowkats hold fasts hinges, iron tower bolts, chock cleats, handles and cords with hooks, etc, Deodar paneled or paneled and glazed or fully glazed, complete in all respects as per specifications and drawings (S.I. No. 7/P-57).
| b. 1-3/4" thick | P.Sft | 2032 | 1273.76 | 2588280.32
11 | Supplying & fixing in position iron / steel grill of 3/4" x 1/4" size flat iron of approved design including painting 3 coats etc complete ( weight not be less than 3.7 lbs/sq. foot of finished grill )( S.No 26 / P-92) | P.Sft | 1250 | 180.5 | 225625
12 | Preparing surface and painting of doors and windows any type.(including Edges)(S.I. No. 5c/P-68,69).
| (i) Priming coat | %Sft | 4064 | 862.95 | 35070.288
| (ii) Two coat of paint | %Sft | 4064 | 626.73 | 25470.3072
13 | Providing and laying floor of approved coloured glazed tiles 1/4" thick laid in white cement and pigment on bed of 3/4" thick cement mortar 1:2, complete in all respect as per drawing and specification or as directed by the engineer.
| Floors (S.I. No. 25/P-42). | %Sft | 579 | 27747.06 | 160655.4774
14 | Supply & fixing glazed tile dado 1/4" thick laid in pigment over 1:2 cement sand mortar 3/4" thick including finishing Dado (S.I. No. 38/P-44). | %Sft | 2536 | 28299.3 | 717670.248
15 | Providing and laying cement sand plaster in walls and ceiling including applying nero. Mixing and applying mortar to perfect line & level as per drawings, specifications (S.I. No. 11 & 13/P-51).
| a. In walls 3/4 inches thick (1:6) (External Plaster) | %Sft | 34942 | 2590.5 | 905172.51
| b. In walls 1/2" inches thick (1:4) (Internal Plaster)) | %Sft | 21042 | 2283.93 | 480584.5506
| c. 3/8" inches thick (1:4) (Ceiling) | %Sft | 6288 | 2197.52 | 138180.0576
16 | Preparing the surface and painting with matt finish i/c rubbing the surface with bathy (Silicon carbide rubbing brick) filling the voids with zink/chalk/plaster of paris mixture, applying first coat premix making the surface smooth and then painting 3 coats with matt finish of approved make etc: complete (S.I. No. 36(a) / P-54). | %Sft | 18147 | 1989.62 | 361056.3414
17 | Preparing the surface and painting with weather coat including rubbing the surface with rubbing brick / sand paper filling the voids with chalk / plaster of paris and then painting with weather coat of approved make (S.I No. (A) 38/P-55). | %Sft | 34572 | 1328.25 | 459202.59
| 2nd & subsequent coat (S.I No. (B) 38/P-55). | %Sft | 34572 | 619.85 | 214294.542
18 | Primary coat of Chalk under distemper (for ceiling)(S.I. No. 23/P-53). | %Sft | 6288 | 442.75 | 27840.12
| Distempering (c) three coats.(for ceiling) (S.I No. 24/P-53). | %Sft | 6288 | 1079.65 | 67888.392
19 | Damp proof course with cement sand Ratio ( 1: 2 ) mixed with dampo (S.No 69 / P- 106 ) 1-1/2" Thick | %Sft | 1670 | 1934.82 | 32311.494
20 | Reinforced cement concrete spout including fixing in position 2 1/2" x 6" x 5" .(S.I. No. 14/P-17). | Each | 94 | 261.25 | 24557.5
21 | Providing and fixing approved quality mortice lock ( S.No 21 / P- 59 ) | Each | 33 | 1786.13 | 58942.29
22 | preparing sub grade including earth excavation or filling to an average depth of 9" dressing to camber and consolidation with power roller (S.l. No 9/ P-2) | %Sft | 5000 | 526.28 | 26314
23 | Cement tiles (8"x 8"x 3/4") laid flat in 1:2 cement mortar over 3/4" thick cement motar 1:2(S.No13 / P- 40 ) | %Sft | 5120 | 10916.65 | 558932.48
29 | Making and fixing steel grated doors with 1/16" thick sheeting including angle iron frame 2" x 2" x 3/8" and 3/4" squre bars 4" centre to centre with locking arrangement | P.sft | 0 | 726.72 | 0
30 | Preparing the surface and painting of doors, windows and ventilator with enamel paint.(including Edges). | %Sft | 1250 | 837.1 | 10463.75
| 2 nd & subsequent coat | %Sft | 1250 | 584.65 | 7308.125
31 | Providing Anti-Termite treatment by Spraying / sprinling spreading Neptachlar 0.5% Emulsion as on overall pre-construction tretment in slab type construction under the slab and along the attached perches or entrances etc, complete as per the directiobns of Engineer Incharge (S.I No. 92/ P-108) | Sft | 6402 | 9.74 | 62355.48
27 | Providing and fixing angle iron vertical posts for barbed wire fencing of size 2" x 2" 1/4" embedded in RCC/Masonry pillars i/c making cuts/holders @12" i/c fixing in pillars by chiseling and filling with cement sand mortar, repairing & finishing the surface. (S.I NO 8/ P-94) | P.Rft | 1600 | 169.18 | 270688
28 | Providing and fixing barbed wire fencing with 12 gauge 4 points @ 6" apart barbed wire i/c straightening & fixing in angle iron vertical posts. (S.I NO 9/ P-95) | P.Rft | 4800 | 8.38 | 40224
TOTAL = |  |  |  |  | 15338722.7874
2) NON - SCHEDULE OF ITEM
1 | Providing & laying light/colour unglazed vitrified porcelain tiles (polished) not exceeding 1600 sq.cm each on wall & floors foreign make (Italian or equivalent except china make) in any floor laid with dry bond (site bond) over existing floor including jointing the tiles with joint floor of approved quality as per direction of engineer incharge. | P.Sft | 6784 | 282 | 1913088
2 | Providing & laying light/colour unglazed vitrified porcelain tiles skirting (polished) not exceeding 1600 sq.cm each on wall & floors foreign make (Italian or equivalent except china make) in any floor laid with dry bond (site bond) over existing floor including jointing the tiles with joint floor of approved quality as per direction of engineer incharge. | P.Sft | 754 | 186 | 140244
3 | Screeding on Roof with Rubber lining and bitumen while also maintaining the slope of the roof for concrete spouts. | Sft | 6288 | 202 | 1270176
4 | Providing and laying 1:10 cement concrete in flooring, laid stone soling using SR cement with screened graded bajri as specified in drawing in all respect as per instruction of engineer encharge. | Cft | 0 | 110.3 | 0
5 | New boring for water supply | Rft | 0 | 650 | 0
6 | Providing and fixing 3/8" thick Verona marble tiles of approved quality and colour shade size on stairs as specified in drawings in steps and risers skirting and facing removal / tucking of existing plaster surface etc over 1/2" thick base of cement mortar 1:3 setting mortar base including fillings the joints and washing the tiles with white cement , slurry current , finishing cleaning and polishing etc complete . (a) for new work | P.Sft | 240 | 510 | 122400
7 | Providing and fabrication of deformed steel reinforcement of attleast Grade 60 having yield strength at 0.2% strain for cement concrete including cutting, bending, laying in position, making joints and fastenings including cost of binding wire (also including removal of rust from bars). | Ton | 47.7 | 125000 | 5962500
8 | Providing and fixing M.S Railing on Ramp | Rft | 0 |  | 0
9 | Providing and fixing emergency lights | Each | 10 | 1000 | 10000
10 | Providing and fixing fire extinguishers | Each | 4 | 10000 | 40000
11 | Providing First Aid Kit | Each | 2 | 500 | 1000
12 | Providing and fixing Water Cooler. | Each | 3 | 20000 | 60000
TOTAL = |  |  |  |  | 9519408
Note on F28: iIn new grill doesn’t need paint. so grill paint only in exsisting grill

## Plumb 1
BILL OF QUANTITIES
CONSTRUCTION OF SCHOOL
AT
GHS ROHRI (418020392)
2 (B) SCHEDULE OF ITEM (B), PLUMBING WORKS
S.No | Description of Item | Unit | Qty | Rate | Amount
|  |  |  | (Rs.) | (Rs.)
1 | Providing & fixing 1/2" dia, lead connection complete with a 1/2" dia brass stop cock, two brass nuts & lining jointed to lead pipe with plumber wiped solder joints 1/2" inches lead pipe to be of not less than 4lbs per lineal yard (S.I. No. 22/P-6). | Each | 20 | 689.7 | 13794
2 | Providing & fixing in position nylon connections complete with 1/2" dia brass stop cock with pair of brass nuts and lining joints to nylon connection (S.I. No. 23/P-6). | Each | 20 | 447.15 | 8943
3A | Providing & fixing M.S clamps of the approved design to 4" i/c the cost of cutting and making good to wall or M.S bolts and nuts, 4" into wall including pipe distance pieces extra painting to match the colour of the building (S.I. No. 2/P-9). | Each | 22 | 72.16 | 1587.52
3B | Providing & fixing M.S clamps of the approved design to 3" i/c the cost of cutting and making good to wall or M.S bolts and nuts,3" into wall including pipe distance pieces extra painting to match the colour of the building (S.I. No. 14/P-10). | Each | 22 | 264 | 5808
4 | (b) S/Fixing concealed Tee stop cock of superior quality with c.p head 1/2" dia (S.I.No. 14(A)/P-18).
|  | Each | 15 | 1097 | 16455
5 | (b) S/Fixing long bib-cock of superior quality with c.p head 1/2" dia (S.I. No. 13(a)/P-19).
|  | Each | 15 | 1109.46 | 16641.9
6 | Providing and fixing orisa type white or color glazed earthen ware w.c pan with cost of low level plastic flush tank of 3 gallons capacity of approved quality i/c making requiste numbers of holes in walls , plinth & floor and making good in cement concrete 1:2:4 W.C pan orisa type 23" with plastic tank of low down 3 gallons C.I trap & C.I thumble (Superior Quality ) With 4" dia. earthen ware trap and plastic thumble (S.No 3 / P-2 ) | Each | 15 | 6166.6 | 92499
7 | Providing & fixing 24" x 18" lavatory basin in white glazed earthen ware complete with and including the cost of W.I or C.I cantilever brackets 6 inches built into wall, painted white in to two coats after a primary coat of red lead paint , a pair of 1/2" dia rubber plug & chrome plate brass chain 1-1/4" dia malloable iron or c.p brass traps malloable iron or brass unions and making requiste number of holes in wall plinth & floor for pipe connection and making good in cement concrete 1:2:4 (Standard pattern ) (S.No 8 / P-3 ) | Each | 8 | 4253.9 | 34031.2
8 | Add extra for labour for providing and fixing of earthen ware pedestal white or coloured glazed (S.No 9 / P-3 ) | Each | 8 | 938.47 | 7507.76
9 | Supplying & fixing 6" x 4" earthen gully trap with 4" outlet complete with 4" thick 1:2:4 C.C for bed & 1/2 thick cement plaster (1:3) to the karb C.I grating 6" x 6" and C.I. cover and frame 12"x12" (inside) etc Complete (b) earthen ware glazed gully trap(a) (i) 6'x6"x4" (i) With C.I Cover and Frame(S.I. No. 1(i)/P-23. | Each | 15 | 1220.67 | 18310.05
10 | Construction manhole for the required dia of circular sewer and 7'-9" depth with walls of B.B in cement mortar 1:3 cement plaster 1:3, 1/2" thick inside of wall and 1" (25mm) thick over benching and channel including fixing C.I manhole cover with frame of clear opening 2'x2' (610 x 610mm) of 4.5 cwt embedded inplain C.C 1:2:4 and two way reinforecement 6" thick includind fixing 1" (25mm) dia dia M.S steps 6" (150mm) wide projecting 4" (102mm) from the face of wall at 12" (305mm) c/c duly painted etc complete as per specification and drawing (a) 4" to 9" dia 4" x3'x7'-9" (S.I.No. 2/P-47) ).(if the depth of main hole is less than 7'-9" deduct from the cost @rate 2143/each). | Each | 3 | 42745 | 128235
11 | Supplying & fixing soap tray of made of plastic of superior quality and design with fine finishing with c.p screws etc complete (S.I. No.6/P-8). | Each | 15 | 169.4 | 2541
12 | Providing & fixing C.P muslim shower with double bib cock & ring pipe (S.I. No.19(a)/P-19). | Each | 15 | 3432 | 51480
13 | Supplying & fixing ball valves (with unsoldered copper ball) 2" dia (S.I. No.8/P-18) | Each | 15 | 593.37 | 8900.55
14 | Providing & fixing full way gun metal values with wheels threaded or flanged ends with rubber washing (S.I. No.6(A)/P-17)
| (v) 1-1/2" dia | Each | 10 | 695.42 | 6954.2
| (vii) 2" dia | Each | 10 | 956.12 | 9561.2
15 | Constructing small wheel value chamber clear inside size 12" x 12" x 12" with walls of 9" thick of B.B cement mortar 1:3 over 4" thick cement concrete 1:3:6 cement plastered 1/2" thick 1:3 inside including supplying & fixing C.I light weight manhole cover with frame and locking arrangement of 12" x 12" clear opening etc complete (S.I. No.8/P-52). | Each | 2 | 3128 | 6256
Total |  |  |  |  | 429505.38
4 (B) NON SCHEDULE OF ITEM (B), PLUMBING WORKS
1 | Supply & fix UPVC (Dadex or Equivalent or approved by engineer incharge) fitting with 'Z' joint & rubber ring etc.
| (a) Elbow / Bend 110 mm or 4" dia | Each | 20 | 3885 | 77700
| (b) Tee 110 mm dia | Each | 20 | 8076 | 161520
| (c) Socket 110 mm dia | Each | 20 | 799 | 15980
| (d) UPVC Tee With Door 110 mm dia | Each | 20 | 5517 | 110340
2 | Supply & fix UPVC (Dadex or Equivalent or approved by engineer incharge) fitting with 'Z' joint & rubber ring etc.
| (a) Elbow / Bend 75 mm or 3" dia | Each | 20 | 3118 | 62360
| (b) Tee 75 mm dia | Each | 20 | 3201 | 64020
| (c) Socket 75 mm dia | Each | 20 | 550 | 11000
| (d) UPVC Tee With Door 75 mm dia | Each | 20 | 4428 | 88560
3 | Providing & laying PPR PN-20 (Dadex or approved by engineer incharge) pipe with all fittings i.e socket, bend tee, elbow where required.
| (a) 20mm (3/4") dia PPR | Rft | 450 | 56.4 | 25380
| (b) 1 mm ( 1" ) | Rft | 400 | 72.81 | 29124
| d) 50 mm (2") dia | Rft | 400 | 264 | 105600
5 | Supply & laying UPVC (Dadex or approved by engineer incharge) soil and waste pipe complete 'Z' joint and rubber ring all as specified including socket, bend, tee all fittings 4" dia (110 mm) etc complete. | Rft | 220 | 247.19 | 54381.8
6 | Supply & laying UPVC (Dadex or approved by engineer incharge) soil and waste pipe complete 'Z' joint and rubber ring all as specified including socket, bend, tee all fittings 3" dia (75 mm) etc complete. | Rft | 220 | 165.36 | 36379.2
7 | Supply & fix UPVC Dadex or approved by engineer incharge vent cowel 110mm (4" dia) on top of vent pipe. | Each | 10 | 311 | 3110
8 | Supply & fix UPVC Dadex or approved by engineer incharge vent cowel 110mm (3" dia) on top of vent pipe. | Each | 10 | 280 | 2800
9 | Providing & fixing UPVC floor trap(DADEX or approved by engineer incharge) with 4" dia inlet and 4" dia outlet of the approved self cleaning design with a UPVC Grating with or without a vent arm i/c cost of making requisite number of holes in walls plinth and floor for pipe connectons and making good cement concrete 1:2:4. | Each | 10 | 450 | 4500
10 | Providing UPVC pipe with collars class "B" and digging the trenches to required depth and fixing imposition i/c cutting, fitting & jointing with maxphalt composition & cement mortar 1:1 and testing with water pressure to a head of 4 feet above the top of the highest pipe and refilling with excavated staff.
| a. 8" dia RCC Pipe Class B | Rft | 250 | 700 | 175000
Total |  |  |  |  | 1027755

## ELE 1
BILL OF QUANTITIES
OF
CONSTRUCTION OF SCHOOL
AT
GHS ROHRI (418020392)
N.B: | These items and their rates given in the are based on Schedule Rate 2012 of Govt. of Sindh. However Rates of Non-Schedule Items and Premium are to be filled by the Contractor .
2) SCHEDULE OF ITEM (A), ELECTRICAL WORKS
S.No | Description of Item | Unit | Quantity | Rate | Amount
|  |  |  | (Rs.) | (Rs.)
1 | Wiring for light or fan point with (3/.029) PVC insulated wire in 20mm (3/4") PVC conduit recessed in the wall or column as required (S.No.124, Pg-15). | Point | 36.3 | 1130 | 41019
2 | Wiring for plug point with (3/.029) PVC insulated wire in 20mm (3/4") PVC conduit recessed required in the wall or column as required including 1mm2 PVC insulated wire as ECC as required (S.No.126, Pg-15). | Point | 107.8 | 985 | 106183
3 | Providing & fixing one way SP 5 amp switch flush type on metal board & covered with plastic sheet (S.No-219, Pg-33). | No | 36.3 | 54 | 1960.2
4 | Providing & fixing two pin 5 amp plug & socket switch flush type on metal board & covered with plastic sheet (S.No-222, Pg-33). | No | 147.4 | 83 | 12234.2
5 | Providing & fixing three pin 5 amp plug & socket switch flush type on metal board & covered with plastic sheet (S.No-226, Pg-33). | No | 10 | 151 | 1510
6 | Providing & fixing bakelite / plastic ceiling rose with two terminals (S.No-228, Pg-33). | No | 67 | 72 | 4824
7 | Providing & fixing brass / PVC batten holder superior quality (S.No-232, Pg-33). | No | 50 | 70 | 3500
Total |  |  |  |  | 171230.4
PART B- ELECTRICAL WORKS (NON SCHEDULE)
1 | Providing and fixing 4 1/2" x 4 1/2" MS dia casted powder coated recessed type fan clamp box with 3/8" dia MS bar fan clamp fixed on roof at casting time as required. | No | 36.3 | 318 | 11543.4
2 | Providing and fixing 6 Amps Piano fan dimmer fixed on plastic or fiber top cover sheet on 14 SWG metal board recessed in the wall and column including connection as required. | No | 36.3 | 333 | 12087.9
3 | Providing and fixing 25 watt saver lamp Philips quality or equivalent as approved by Engineer in charge | No | 50 | 280 | 14000
4 | Providing & fixing ceiling fan 56" good quality (Royal/ Pak/ Millat or equivalent as directed by Engineer) | No | 67 | 3980 | 266660
Total Rs. |  |  |  |  | 304291.3