## summaryYY
BILL OF QUANTITIES
OF
CONSTRUCTION OF SCHOOL
AT
G.B.H.S FARAN SUKKUR (418030059)
SUMMARY OF BID
|  | Cost of Items | Premium Quoted by Contractor (CIVIL WORKS ONLY) | Amount quoted of Non-Scheduled items | Total Cost
|  | Items (Rs.) |  |  | (Rs.)
NEW WORK
| Civil Works | 16927106.2308 |  |  | 16927106.2308
| Schedule Item | 808108.2928 |  |  | 808108.2928
| Non Schedule Item |  |  |  | 698890
Plumbing Works
| Schedule Item | 2923.75 | NA |  | 2923.75
| Non Schedule Item | 882435.4 |  |  | 55974
Electrical Works
| Schedule Item | 6504 | NA |  | 6504
| Non Schedule Item | 217644 |  |  | 1400
REHABILITATION WORK
Civil Works
| Schedule Item | 260710.192 | - | - | 260710.192
| Non Schedule Item |  |  |  | 9300845.41
Plumbing works
| Schedule item | 83130.435 |  |  | 83130.435
| Non-schedule item |  |  |  | -
Electrical works
| Schedule item | 308016 |  |  | 308016
| Non-schedule item |  |  |  | 382325
| TOTAL |  |  |  | 11908827.0798

## Rehabil (m.s) 1
MEASUREMENT SHEET OF REHABILATION
|  |  | BUILDING 1(GROUND FLOOR | [10 empty] | BUILDING 1(1ST FLOOR) | [12 empty] | BUILDING 1(2ND FLOOR)
S.No | Description | Unit | EXTERNAL | F.A OFFICE | ROOM 1 | ROOM 2 | ROOM 3 | ROOM 4 | TOILETS | CHOWKIDAAR ROOM | SERVANT QUARTER 1 | SERVANT QUARTER 2 | SPORTS ROOM | FA OFFICE | HM OFFICE | GALLERY | ROOM 1 WITH STORE | ROOM 2 WITH STORE | STORE | TOILET | ROOM 3 | ROOM 4 WTH STORE | ROOM 5 | ROOM 6 WITH STORE | ROOM 7 | CORRIDOR | ROOM 1 | LIBRARY | ROOM 2 | STORE | Total
A | CIVIL
1 | Distemper Coat | Sft |  | 290 | 180 | 180 | 180 | 144 | 60 | 90 | 90 | 192 | 90 | 150 | 300 |  | 363 | 363 | 60 | 20 | 310 | 363 | 138 | 363 | 212 | 934 | 440 | 289 | 475 | 45 | 6510.63
2 | Matt finish | Sft |  | 936 | 672 | 672 | 672 | 576 | 320 | 480 | 480 | 696 | 480 | 588 | 1176 | 150 | 1284 | 1284 | 408 | 90 | 876 | 1284 | 564 | 1284 | 708 | 4992 | 1068 | 816 | 1128 | 432 | 24839.48
3 | Weather Coat | Sft | 12400 | [27 empty] | 12772
4 | External Plaster | Sft | [28 empty] | 0
5 | Internal Plaster | Sft | [28 empty] | 0
6 | Ceiling Plaster | Sft | [25 empty] | 90 |  |  | 92.7
7 | Internal Plaster ( Seepage DPC ) | Sft |  | 234 | 168 | 168 | 168 | 144 | 192 | 120 | 120 | 174 | 120 |  |  | 75 | 321 | 321 | 102 | 54 | 219 | 321 | 141 | 321 | 177 | 1248 | 267 | 204 | 282 | 108 | 5942.07
8 | Chiselling plaster | Sft | [28 empty] | 0
9 | Screeding plus water proof on roof | Sft | [14 empty] | 363 | 363 | 60 | 20 | 310 | 363 | 138 | 363 | 212 | 934 | 440 | 289 | 475 | 45 | 4506.25
10 | Cracks repair on wall , col, beam stair etc. | Sft | 1240 |  |  |  | 20 | 20 |  | 10 | 10 | 20 | 10 | 10 |  | 20 | 20 | 20 | 20 | 10 | 10 | 20 | 10 | 20 |  | 150 | 10 | 10 | 10 |  | 1720.1
11 | Patches on roof | Sft | [28 empty] | 0
12 | Anti termite on existing wall | Sft | 1240 | [27 empty] | 1277.2
13 | Jacketing of existing column | Sft | [28 empty] | 0
14 | 1:2:4 ratio 2" thick flooring | Sft | [16 empty] | 60 | [11 empty] | 61.8
15 | Porcelin tile on existing floor | Sft | [7 empty] | 90 | 90 | 192 | 90 | 150 | 300 |  |  |  | 60 | [5 empty] | 212 | 934 | 440 | 289 | 475 | 45 | 3468.01
16 | Dismentling of existing tile | Sft | [28 empty] | 0
17 | skirting | Sft | [7 empty] | 20 | 20 | 29 | 20 | 25 | 36 |  |  |  | 17 | [5 empty] | 30 | 208 | 45 | 34 | 47 | 18 | 565.47
18 | Marble on stair | Sft | [28 empty] | 0
19 | Door chowkhat | Rft | [28 empty] | 0
20 | Window and ventilator chowkhat | Rft | [28 empty] | 0
21 | New door including chowkhat | Sft |  | 77 | 56 | 56 | 56 | 56 | 70 | 21 | 21 | 21 | 21 |  |  |  | 56 | 56 | 28 | 28 | 56 | 56 |  | 56 | 28 |  | 168 | 56 | 168 | 28 | 1276.17
22 | New Window/ venti including chowkhat | Sft |  | 8 | [5 empty] | 16 | 16 | 32 | 16 | [17 empty] | 90.64
23 | New door without chowkhat | Sft | [28 empty] | 0
24 | New Window/ venti without chowkhat | Sft | [28 empty] | 0
25 | Door palla repair | Sft | [28 empty] | 0
26 | Window & vent. palla repair | Sft | [28 empty] | 0
27 | Repairing & fixing of grill, steel gate, wooden doors , windows & ventilator | Sft | [28 empty] | 0
28 | New Steel Grill | Sft | [28 empty] | 0
29 | Painting of doors | Sft |  | 154 | 112 | 112 | 112 | 112 | 140 | 42 | 42 | 42 | 42 | 112 | 112 |  | 224 | 224 | 56 | 56 | 112 | 224 | 112 | 224 | 56 |  | 336 | 112 | 336 | 56 | 3359.86
30 | Painting of widows & ventilators | Sft |  | 16 | [5 empty] | 32 | 32 | 64 | 32 | 64 | 96 |  | 288 | 160 |  |  | 128 | 288 | 96 | 256 | 32 |  | 160 | 128 | 160 |  | 2092.96
31 | Enamel paint on grill | Sft | [7 empty] | 16 | 16 | 32 | 16 | 32 | 48 |  | 144 | 80 |  |  | 64 | 144 | 48 | 128 | 16 |  | 80 | 64 | 80 |  | 1038.24
32 | Steel gate | Sft | [28 empty] | 0
33 | New RCC Work 1:1.5:3 concrete | Cft | [28 empty] | 0
34 | steel reinforcement | Cwt | [28 empty] | 0
35 | Glaze tile | Sft | [28 empty] | 0
36 | Dado tile | Sft | [28 empty] | 0
37 | Block masonry | Cft | [28 empty] | 0
38 | Spout | Each | [28 empty] | 0
39 | Mortice lock | Each | [28 empty] | 0
40 | Blackboard repair and paint | Each | [28 empty] | 0
41 | angle iron with barbed wire | Rft | [28 empty] | 0
42 | cemented tiles | Sft | [28 empty] | 0
43 | 1:3:6 plain C.C bed | Cft | [28 empty] | 0
44 | polyrthene sheet | Sft | [28 empty] | 0
45 | 1:10 concrete | Cft | [28 empty] | 0
46 | stone filling | Cft | [28 empty] | 0
47 | new earth outside | Cft | [28 empty] | 0
48 | Rubber lining | Sft | [28 empty] | 0
B | PLUMBING | [29 empty] | 0
1 | W.C | Each | [6 empty] | 1 | [21 empty] | 1.05
2 | Flash tank | Each | [6 empty] | 1 | [21 empty] | 1.05
3 | Floor trap | Each | [6 empty] | 1 | [21 empty] | 1.05
4 | Soap tray | Each | [6 empty] | 1 | [21 empty] | 1.05
5 | wash basin | Each | [6 empty] | 1 | [21 empty] | 1.05
6 | Pedestal | Each | [6 empty] | 1 | [21 empty] | 1.05
7 | Muslim Shower | Each | [6 empty] | 1 | [21 empty] | 1.05
8 | Bib Cock | Each | [6 empty] | 1 | [21 empty] | 1.05
9 | Gun metal Valve | Each | [6 empty] | 1 | [21 empty] | 1.05
C | ELECTRIFICATION | [29 empty] | 0
1 | Saver | Each |  | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 4 | 2 | 4 | 4 |  | 6 | 6 | 2 | 2 | 4 | 6 | 4 | 6 | 4 | 25 | 6 | 4 | 6 | 2 | 125
2 | Fans | Each |  | 2 | 4 | 4 | 4 | 4 |  | 2 | 2 | 3 |  | 2 | 4 |  | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 |  | 6 | 4 | 6 |  | 75
3 | Dimmer | Each |  | 2 | 4 | 4 | 4 | 4 |  | 2 | 2 | 3 |  | 2 | 4 |  | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 |  | 6 | 4 | 6 |  | 75
4 | Switch board | Each |  | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 2 | 1 | 2 | 2 |  | 2 | 2 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 6 | 2 | 2 | 2 | 1 | 50
5 | Wirring point for fan | Point |  | 2 | 4 | 4 | 4 | 4 |  | 2 | 2 | 3 |  | 2 | 4 |  | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 |  | 6 | 4 | 6 |  | 75
6 | Wirring point for plug | Point | [28 empty] | 0
7 | Switches | No |  | 6 | 10 | 10 | 10 | 10 | 4 | 4 | 4 | 8 | 4 | 6 | 10 |  | 10 | 10 | 2 | 2 | 10 | 10 | 10 | 10 | 10 | 25 | 12 | 10 | 12 | 2 | 221
8 | 2 pin switch | No |  | 2 | 2 | 2 | 2 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 |  | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 6 | 2 | 2 | 2 | 1 | 49
| 3 pin switch | No | [28 empty] | 0
9 | Ceiling rose | No | [28 empty] | 0
10 | fan clamp | No |  | 2 | 4 | 4 | 4 | 4 |  | 2 | 2 | 3 |  | 2 | 4 |  | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 |  | 6 | 4 | 6 |  | 75
11 | Batten holder | No |  | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 4 | 2 | 4 | 4 |  | 6 | 6 | 2 | 2 | 4 | 6 | 4 | 6 | 4 | 25 | 6 | 4 | 6 | 2 | 125
12 | Bulb point | No |  | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 4 | 2 | 4 | 4 |  | 6 | 6 | 2 | 2 | 4 | 6 | 4 | 6 | 4 | 25 | 6 | 4 | 6 | 2 | 125

## Rehabil( est) 1
BILL OF QUANTITIES
OF
REHABILITION OF SCHOOL
AT
G.B.H.S FARAN SUKKUR (418030059)
N.B: | These items and their rates given in the are based on Schedule Rate 2012 of Govt. of Sindh. However Rates of Non-Schedule Items and Premium are to be filled by the Contractor .
1) SCHEDULE OF ITEM (A)
S.No | Description of Item | Unit | Qty | Rate | Amount
(Rs.)
1 | Preparing the surface and painting with weather coat including rubbing the surface with rubbing brick / sand paper filling the voids with chalk / plaster of paris and then painting with weather coat of approved make (S.I No. (A) 38/P-55). | %Sft | 12772 | 1328.25 | 169644.09
| 2nd & subsequent coat (S.I No. (B) 38/P-55). | %Sft | 12772 | 619.85 | 79167.242
2 | Providing and laying cement sand plaster in walls and ceiling including applying nero. Mixing and applying mortar to perfect line & level as per drawings, specifications (S.I. No. 11 & 13/P-51).
| c. 3/8" inches thick (1:4) (Ceiling) | %Sft | 92.7 | 2197.52 | 2037.101
3 | Providing and laying topping cement concrete (1:2:4) including surface finishing and dividing into panels (S.I. No. 16(c)/P-41).
| a. 2" thick (Under Floor) | %Sft | 61.8 | 3275.5 | 2024.259
4 | Reinforced cement concrete spout including fixing in position 2 1/2" x 6" x 5" .(S.I. No. 14/P-17). | Each | 30 | 261.25 | 7837.5
|  |  |  | TOTAL= | 260710.192
1B) SCHEDULE OF ITEM (B), PLUMBING WORKS
S.No | Description of Item | Unit | Qty | Rate | Amount
|  |  |  | (Rs.) | (Rs.)
1 | Providing & fixing 1/2" dia, lead connection complete with a 1/2" dia brass stop cock, two brass nuts & lining jointed to lead pipe with plumber wiped solder joints 1/2" inches lead pipe to be of not less than 4lbs per lineal yard (S.I. No. 22/P-6). | Each | 5 | 689.7 | 3448.5
2 | Providing & fixing in position nylon connections complete with 1/2" dia brass stop cock with pair of brass nuts and lining joints to nylon connection (S.I. No. 23/P-6). | Each | 5 | 447.15 | 2235.75
3A | Providing & fixing M.S clamps of the approved design to 4" i/c the cost of cutting and making good to wall or M.S bolts and nuts, 4" into wall including pipe distance pieces extra painting to match the colour of the building (S.I. No. 2/P-9). | Each | 9 | 72.16 | 649.44
3B | Providing & fixing M.S clamps of the approved design to 3" i/c the cost of cutting and making good to wall or M.S bolts and nuts,3" into wall including pipe distance pieces extra painting to match the colour of the building (S.I. No. 14/P-10). | Each | 9 | 264 | 2376
4 | (b) S/Fixing concealed Tee stop cock of superior quality with c.p head 1/2" dia (S.I.No. 14(A)/P-18).
|  | Each | 5 | 1097 | 5485
5 | (b) S/Fixing long bib-cock of superior quality with c.p head 1/2" dia (S.I. No. 13(a)/P-19).
|  | Each | 1.05 | 1109.46 | 1164.933
6 | Providing and fixing orisa type white or color glazed earthen ware w.c pan with cost of low level plastic flush tank of 3 gallons capacity of approved quality i/c making requiste numbers of holes in walls , plinth & floor and making good in cement concrete 1:2:4 W.C pan orisa type 23" with plastic tank of low down 3 gallons C.I trap & C.I thumble (Superior Quality ) With 4" dia. earthen ware trap and plastic thumble (S.No 3 / P-2 ) | Each | 1.05 | 6166.6 | 6474.93
7 | Providing & fixing 24" x 18" lavatory basin in white glazed earthen ware complete with and including the cost of W.I or C.I cantilever brackets 6 inches built into wall, painted white in to two coats after a primary coat of red lead paint , a pair of 1/2" dia rubber plug & chrome plate brass chain 1-1/4" dia malloable iron or c.p brass traps malloable iron or brass unions and making requiste number of holes in wall plinth & floor for pipe connection and making good in cement concrete 1:2:4 (Standard pattern ) (S.No 8 / P-3 ) | Each | 1.05 | 4253.9 | 4466.595
8 | Add extra for labour for providing and fixing of earthen ware pedestal white or coloured glazed (S.No 9 / P-3 ) | Each | 4 | 938.47 | 3753.88
9 | Supplying & fixing 6" x 4" earthen gully trap with 4" outlet complete with 4" thick 1:2:4 C.C for bed & 1/2 thick cement plaster (1:3) to the karb C.I grating 6" x 6" and C.I. cover and frame 12"x12" (inside) etc Complete (b) earthen ware glazed gully trap(a) (i) 6'x6"x4" (i) With C.I Cover and Frame(S.I. No. 1(i)/P-23. | Each | 2 | 1220.67 | 2441.34
10 | Construction manhole for the required dia of circular sewer and 7'-9" depth with walls of B.B in cement mortar 1:3 cement plaster 1:3, 1/2" thick inside of wall and 1" (25mm) thick over benching and channel including fixing C.I manhole cover with frame of clear opening 2'x2' (610 x 610mm) of 4.5 cwt embedded inplain C.C 1:2:4 and two way reinforecement 6" thick includind fixing 1" (25mm) dia dia M.S steps 6" (150mm) wide projecting 4" (102mm) from the face of wall at 12" (305mm) c/c duly painted etc complete as per specification and drawing (a) 4" to 9" dia 4" x3'x7'-9" (S.I.No. 2/P-47) ).(if the depth of main hole is less than 7'-9" deduct from the cost @rate 2143/each). | Each | 1 | 42745 | 42745
11 | Supplying & fixing soap tray of made of plastic of superior quality and design with fine finishing with c.p screws etc complete (S.I. No.6/P-8). | Each | 1.05 | 169.4 | 177.87
12 | Providing & fixing C.P muslim shower with double bib cock & ring pipe (S.I. No.19(a)/P-19). | Each | 1.05 | 3432 | 3603.6
13 | Supplying & fixing ball valves (with unsoldered copper ball) 2" dia (S.I. No.8/P-18) | Each | 4 | 593.37 | 2373.48
14 | Providing & fixing full way gun metal values with wheels threaded or flanged ends with rubber washing (S.I. No.6(A)/P-17)
| (v) 1-1/2" dia | Each | 1.05 | 695.42 | 730.191
| (vii) 2" dia | Each | 1.05 | 956.12 | 1003.926
Total |  |  |  |  | 83130.435
C | ELECTRIFICATION
1 | Wiring for light or fan point with (3/.029) PVC insulated wire in 20mm (3/4") PVC conduit recessed in the wall or column as required (S.No.124, Pg-15). | Point | 200 | 1130 | 226000
2 | Wiring for plug point with (3/.029) PVC insulated wire in 20mm (3/4") PVC conduit recessed required in the wall or column as required including 1mm2 PVC insulated wire as ECC as required (S.No.126, Pg-15). | Point | 49 | 985 | 48265
3 | Providing & fixing one way SP 5 amp switch flush type on metal board & covered with plastic sheet (S.No-219, Pg-33). | No | 221 | 54 | 11934
4 | Providing & fixing two pin 5 amp plug & socket switch flush type on metal board & covered with plastic sheet (S.No-222, Pg-33). | No | 49 | 83 | 4067
5 | Providing & fixing bakelite / plastic ceiling rose with two terminals (S.No-228, Pg-33). | No | 125 | 72 | 9000
6 | Providing & fixing brass / PVC batten holder superior quality (S.No-232, Pg-33). | No | 125 | 70 | 8750
TOTAL = |  |  |  |  | 308016
2) NON - SCHEDULE OF ITEM
A | CIVIL WORKS
1 | Dampnees in wall is treated by pouring damp proof course (as item # 5 of rehabilitation drawing) by filling after chizeling along the width of wall using a mixture of Cement, Coarse Sand, Pea Gravel and Pudlo in ratio 1:1-1/2:3 as per direction given in rehabilitation sheet and as per direction of engineer in charge. | Sft | 5942.07 | 177 | 1051746.39
2 | Plaster after dampness for 2.5' (or more varying with site) height plastering will be done by first weeking the entire surface rough and its plastering the surface | Sft | 5942.07 | 42 | 249566.94
3 | Screeding on Roof with Rubber lining and bitumen while also maintaining the slope of the roof for concrete spouts. | Sft | 4506.25 | 202 | 910262.5
4 | Cracks repair on wall , col, beam stair etc. | Sft | 1720.1 | 150 | 258015
5 | Anti termite on existing wall as per the reghabilitation drawings. | Sft | 1277.2 | 30 | 38316
6 | Porcelain tile will be laid with plastic sheet for water proofing at base. Details of layer are given in rehabilitation sheet (see figure 13&14, detail # 7 & drawing no 2 of rehabilitation). | P.Sft | 3468.01 | 282 | 977978.82
7 | Room skirting of proceline tile by first making, or surface rough and fixing skirting after mortar and cement & sand mix as per standard and direction of engineer in charge. | Sft | 565.47 | 186 | 105177.42
8 | Providing & fixing new panel doors and windows of diar wood where required of same design which exists or (if flush door exists) panel door design as given by architect will be used) if all doors need replacement they will be replaced by wood panel doors as direction of engineer in charge. | P.Sft | 1366.81 | 1850 | 2528598.5
9 | Painting door by first making the surface smooth and filling it with filler and after making the surface two coats of paint as required by engineer in charge. | P.Sft | 3359.86 | 64 | 215031.04
10 | Painting windows by first making the surface smooth with filler and later two coats of paint as required by engineer in charge. | P.Sft | 2092.96 | 64 | 133949.44
11 | Window grill painting. Cleaning existing grill with steel brush and sand paper to surface get smooth. Applying red oxide one coat and later two coats of enamel paint. | P.Sft | 1038.24 | 24 | 24917.76
12 | Scratch and finish the roof surface and make base for new paint using prime coat and distemper the surface with maximum of two coats. | Sft | 6510.63 | 84 | 546892.92
13 | Scratch the rough paint of the wall and make the surface smooth and make ground by filling filler or prime coat or any other filling material and prepare a smooth surface. After preparing the surface paint it with matt finish paint (two coats) only. | Sft | 24839.48 | 91 | 2260392.68
Total= |  |  |  |  | 9300845.41
C | ELECTRICAL WORKS
1 | Providing and fixing 25 watt saver lamp Philips quality or equivalent as approved by Engineer in charge | No | 125 | 280 | 35000
2 | Providing & fixing ceiling fan 56" good quality (Royal/ Pak/ Millat or equivalent as directed by Engineer) | No | 75 | 3980 | 298500
3 | Providing and fixing 6 Amps Piano fan dimmer fixed on plastic or fiber top cover sheet on 14 SWG metal board recessed in the wall and column including connection as required. | No | 75 | 333 | 24975
4 | Providing and fixing 4 1/2" x 4 1/2" MS dia casted powder coated recessed type fan clamp box with 3/8" dia MS bar fan clamp fixed on roof at casting time as required. | No | 75 | 318 | 23850
Total= |  |  |  |  | 382325

## N.W.C(M.S) 1
MEASUREMENT SHEET OF NEW WORK
S.No | Description | Unit | UGWT | Filter Room | External | B/WALL | B2(ROOM 4) | B4(ROOM 1) | B4(ROOM 2) | HM Room | HM Corridor | B1(Corridor) | B1(Room 1) | B1(Room 2) | B1(Room 3) | B1(Store) | B3(ROOM) | block 1 | four toilets | 4 classrooms | passage | existing classroom | verrandah | walkway | block 2 | corridor | 2 toilet | OHWT | septic tank | filter room | pergola | main gate + columns | TOTAL
1 | Excavation | Cft | 4650 | 211 | [28 empty] | 4861
2 | Lean 1:4:8 | Cft | 225 | 21 | [28 empty] | 246
3 | New earth outside | Cft |  | 150 | [28 empty] | 150
4 | Concrete 1:1.5:3 | Cft | 1125 | 200 | [28 empty] | 1325
5 | Steel reinforcement | Cwt | 83 | 12 | [28 empty] | 95
6 | 1:2:4 ( 2" thick flooring) | Sft |  | 60 | [28 empty] | 60
7 | Poly thene sheet | Sft |  | 60 | [28 empty] | 60
8 | 1:3:6 ( 3" thick ) | Sft |  | 15 | [28 empty] | 15
9 | Stone filling | Cft |  | 30 | [28 empty] | 30
10 | Block masonry | Cft |  | 140 | [28 empty] | 140
11 | New door | Sft |  | 24 | [28 empty] | 24
12 | New window & ventilator | Sft |  | 6 | [28 empty] | 6
13 | Steel grill | Sft |  | 6 | [28 empty] | 6
14 | Painting on door | Sft |  | 48 | [28 empty] | 48
15 | Painting on window / ventilator | Sft |  | 12 | [28 empty] | 12
16 | Porcelin tile | Sft | [30 empty] | 0
17 | skirting | Sft | [30 empty] | 0
18 | Marble on stair | Sft | [30 empty] | 0
19 | Glaze tile | Sft |  | 35 | [28 empty] | 35
20 | Dado tile | Sft |  | 150 | [28 empty] | 150
21 | External plaster | Sft |  | 300 | [28 empty] | 300
22 | Internal plaster | Sft | 855 | 310 | [28 empty] | 1165
23 | Ceiling plaster | Sft |  | 70 | [28 empty] | 70
24 | Matt finish | Sft |  | 310 | [28 empty] | 310
25 | Weather Coat | Sft |  | 300 | [28 empty] | 300
26 | Distemper | Sft |  | 70 | [28 empty] | 70
27 | 3" th roofing plus water proofing | Sft |  | 70 | [28 empty] | 70
28 | DPC | Sft | 855 | 20 | [28 empty] | 875
29 | Spout | Each |  | 2 | [28 empty] | 2
30 | Mortice lock | Each |  | 1 | [28 empty] | 1
31 | 1:10 concrete | Cft | [30 empty] | 0
32 | Anti termite on existing wall | Sft | [30 empty] | 0
33 | boring | Rft | [30 empty] | 0
34 | Sub base | Sft |  |  | 1000 | [27 empty] | 1000
35 | cemented tiles | Sft |  |  | 1000 | [27 empty] | 1000
36 | Rubber lining | Sft | [30 empty] | 0
37 | Dismentaling roof | Cft | [30 empty] | 0
38 | Dismentaling door | No | [30 empty] | 0
39 | Dismentaling window/vent | No | [30 empty] | 0
40 | Dismentaling floor | Cft | [30 empty] | 0
41 | Dismentaling walls | Cft | [30 empty] | 0
42 | Steel gate | Sft | [30 empty] | 0
43 | Enamel paint on grill | Sft |  | 12 | [28 empty] | 12
B | PLUMBING
1 | W.C | Each | [30 empty] | 0
3 | Floor trap | Each | [30 empty] | 0
4 | Soap tray | Each | [30 empty] | 0
5 | wash basin | Each | [30 empty] | 0
6 | Pedestal | Each | [30 empty] | 0
7 | Muslim Shower | Each | [30 empty] | 0
8 | Bib Cock | Each | [30 empty] | 0
9 | Gun metal Valve | Each | [30 empty] | 0
C | ELECTRIFICATION | [31 empty] | 0
1 | Saver | Each | [30 empty] | 0
2 | Fans | Each | [30 empty] | 0
3 | Dimmer | Each | [30 empty] | 0
4 | Switch board | Each | [30 empty] | 0
5 | Wirring point for fan | Point | [30 empty] | 0
6 | Wirring point for plug | Point | [30 empty] | 0
7 | Switches | No | [30 empty] | 0
8 | 2 pin switch | No | [30 empty] | 0
9 | Ceiling rose | No | [30 empty] | 0
10 | fan clamp | No | [30 empty] | 0
11 | Batten holder | No | [30 empty] | 0

## CIVIL EST 1
BILL OF QUANTITIES
OF
CONSTRUCTION OF SCHOOL
AT
G.B.H.S FARAN SUKKUR (418030059)
N.B: | These items and their rates given in the are based on Schedule Rate 2012 of Govt. of Sindh. However Rates of Non-Schedule Items and Premium are to be filled by the Contractor .
1) SCHEDULE OF ITEM (A), CIVIL WORKS
S.No | Description of Item | Unit | Qty | Rate | Amount
(Rs.)
1 | Excavation in foundation of building bridges and other structures including dagbelling dressing refilling around structure with excavated earth watering and ramming lead up to 5ft (S.I. No. 18 (b)/P-4) (for foundation)
| (a) In Ordinary Soil | %oCft | 4861 | 3176.25 | 15439.7512
2 | Cement concrete plain including placing compacting, finishing and curing, complete (includingscreening and washing of stone aggregate without shuttering).
| (a) Ratio 1:4:8 (S.I. No. 5(i)/P-15). | %Cft | 246 | 11288.75 | 27770.325
3 | Filling, watering and ramming earth under floor with new earth excavated from outside lead upto the one chain and lift upto 5 ft.(S.I. No. 22/P-4). | %oCft | 150 | 3630 | 544.5
4 | Reinforced cement concrete work including all labour and material except the cost of steel reinforcement and its labour for bending and binding which will be paid separately. This rate also includes all kinds of forms moulds lifting shuttering curing rendering and finsihing the exposed surface .
a) R.C work in roof slab, beams columns rafts,lintels and other structural members laid in situ or precast laid in position complete in all respects.
| (I) Ratio (1:1 1/2:3) or more 90 Lbs cement 2 Cft sand 4 Cft. Shingle 1/8" to 1/4" guage.must have cylinder strength >3750psi (S.I. No.6(a)(ii)/P-16). | P.Cft | 1325 | 349 | 462425
5 | Providing and laying topping cement concrete (1:2:4) including surface finishing and dividing into panels (S.I. No. 16(c)/P-41).
| a. 2" thick (Under Floor) | %Sft | 60 | 3275.5 | 1965.3
6 | Providing and laying single layer of polythene sheet 0.13mm thick for water proofing as per specification and instructions of Engineer incharge. (S.I. No. 38/P-37). | P.Sft | 60 | 10.7 | 642
7 | Cement concrete plain including placing compacting, finishing and curing, complete (includingscreening and washing of stone aggregate without shuttering). Ratio (1:3:6 ) (SNo.5 h / P - 15 ) | %Cft | 15 | 12595 | 1889.25
8 | Providing and Laying stone or spawl filling on level (S.I No. 28(b)/P-31). | %Cft | 30 | 563.86 | 169.158
9 | Providing & laying 1:3:6 cement concrete solid block masonary wall 6" and below in thickness set in 1:6 cement mortar in ground floor superstructure including raking out joints & curing etc complete (S.I. No. 24/P-18). | %Cft | 140 | 15771.01 | 22079.414
10 | Supply & fixing first class deodar wood wrought joinery in doors and windows etc, fixed in position including chowkats hold fasts hinges, iron tower bolts, chock cleats, handles and cords with hooks, etc, Deodar paneled or paneled and glazed or fully glazed, complete in all respects as per specifications and drawings (S.I. No. 7/P-57).
| b. 1-3/4" thick | P.Sft | 30 | 1273.76 | 38212.8
11 | Supplying & fixing in position iron / steel grill of 3/4" x 1/4" size flat iron of approved design including painting 3 coats etc complete ( weight not be less than 3.7 lbs/sq. foot of finished grill )( S.No 26 / P-92) | P.Sft | 6 | 180.5 | 1083
12 | Preparing surface and painting of doors and windows any type.(including Edges)(S.I. No. 5c/P-68,69).
| (i) Priming coat | %Sft | 60 | 862.95 | 517.77
| (ii) Two coat of paint | %Sft | 60 | 626.73 | 376.038
13 | Providing and laying floor of approved coloured glazed tiles 1/4" thick laid in white cement and pigment on bed of 3/4" thick cement mortar 1:2, complete in all respect as per drawing and specification or as directed by the engineer.
| Floors (S.I. No. 25/P-42). | %Sft | 35 | 27747.06 | 9711.471
14 | Supply & fixing glazed tile dado 1/4" thick laid in pigment over 1:2 cement sand mortar 3/4" thick including finishing Dado (S.I. No. 38/P-44). | %Sft | 150 | 28299.3 | 42448.95
15 | Providing and laying cement sand plaster in walls and ceiling including applying nero. Mixing and applying mortar to perfect line & level as per drawings, specifications (S.I. No. 11 & 13/P-51).
| a. In walls 3/4 inches thick (1:6) (External Plaster) | %Sft | 300 | 2590.5 | 7771.5
| b. In walls 1/2" inches thick (1:4) (Internal Plaster)) | %Sft | 1165 | 2283.93 | 26607.7845
| c. 3/8" inches thick (1:4) (Ceiling) | %Sft | 70 | 2197.52 | 1538.264
16 | Preparing the surface and painting with matt finish i/c rubbing the surface with bathy (Silicon carbide rubbing brick) filling the voids with zink/chalk/plaster of paris mixture, applying first coat premix making the surface smooth and then painting 3 coats with matt finish of approved make etc: complete (S.I. No. 36(a) / P-54). | %Sft | 310 | 1989.62 | 6167.822
17 | Preparing the surface and painting with weather coat including rubbing the surface with rubbing brick / sand paper filling the voids with chalk / plaster of paris and then painting with weather coat of approved make (S.I No. (A) 38/P-55). | %Sft | 300 | 1328.25 | 3984.75
| 2nd & subsequent coat (S.I No. (B) 38/P-55). | %Sft | 300 | 619.85 | 1859.55
18 | Primary coat of Chalk under distemper (for ceiling)(S.I. No. 23/P-53). | %Sft | 70 | 442.75 | 309.925
| Distempering (c) three coats.(for ceiling) (S.I No. 24/P-53). | %Sft | 70 | 1079.65 | 755.755
19 | Damp proof course with cement sand Ratio ( 1: 2 ) mixed with dampo (S.No 69 / P- 106 ) 1-1/2" Thick | %Sft | 875 | 1934.82 | 16929.675
20 | Reinforced cement concrete spout including fixing in position 2 1/2" x 6" x 5" .(S.I. No. 14/P-17). | Each | 2 | 261.25 | 522.5
21 | Providing and fixing approved quality mortice lock ( S.No 21 / P- 59 ) | Each | 1 | 1786.13 | 1786.13
22 | preparing sub grade including earth excavation or filling to an average depth of 9" dressing to camber and consolidation with power roller (S.l. No 9/ P-2) | %Sft | 1000 | 526.28 | 5262.8
23 | Cement tiles (8"x 8"x 3/4") laid flat in 1:2 cement mortar over 3/4" thick cement motar 1:2(S.No13 / P- 40 ) | %Sft | 1000 | 10916.65 | 109166.5
24 | Preparing the surface and painting of doors, windows and ventilator with enamel paint.(including Edges). | %Sft | 12 | 837.1 | 100.452
25 | 2 nd & subsequent coat | %Sft | 12 | 584.65 | 70.158
TOTAL = |  |  |  |  | 808108.2928
2) NON - SCHEDULE OF ITEM
1 | Screeding on Roof with Rubber lining and bitumen while also maintaining the slope of the roof for concrete spouts. | Sft | 70 | 202 | 14140
2 | Providing and fabrication of deformed steel reinforcement of attleast Grade 60 having yield strength at 0.2% strain for cement concrete including cutting, bending, laying in position, making joints and fastenings including cost of binding wire (also including removal of rust from bars). | Ton | 4.75 | 125000 | 593750
3 | Providing and fixing emergency lights | Each | 10 | 1000 | 10000
4 | Providing and fixing fire extinguishers | Each | 4 | 10000 | 40000
5 | Providing First Aid Kit | Each | 2 | 500 | 1000
6 | Providing and fixing Water Cooler. | Each | 2 | 20000 | 40000
TOTAL = |  |  |  |  | 698890
Note on F28: iIn new grill doesn’t need paint. so grill paint only in exsisting grill

## Plumb 1
BILL OF QUANTITIES
CONSTRUCTION OF SCHOOL
AT
G.B.H.S FARAN SUKKUR (418030059)
2 (B) SCHEDULE OF ITEM (B), PLUMBING WORKS
S.No | Description of Item | Unit | Qty | Rate | Amount
|  |  |  | (Rs.) | (Rs.)
1 | Providing & fixing 1/2" dia, lead connection complete with a 1/2" dia brass stop cock, two brass nuts & lining jointed to lead pipe with plumber wiped solder joints 1/2" inches lead pipe to be of not less than 4lbs per lineal yard (S.I. No. 22/P-6). | Each | 1 | 689.7 | 689.7
2 | Providing & fixing in position nylon connections complete with 1/2" dia brass stop cock with pair of brass nuts and lining joints to nylon connection (S.I. No. 23/P-6). | Each | 1 | 447.15 | 447.15
3A | Providing & fixing M.S clamps of the approved design to 4" i/c the cost of cutting and making good to wall or M.S bolts and nuts, 4" into wall including pipe distance pieces extra painting to match the colour of the building (S.I. No. 2/P-9). | Each | 1 | 72.16 | 72.16
3B | Providing & fixing M.S clamps of the approved design to 3" i/c the cost of cutting and making good to wall or M.S bolts and nuts,3" into wall including pipe distance pieces extra painting to match the colour of the building (S.I. No. 14/P-10). | Each | 2 | 264 | 528
4 | Supplying & fixing ball valves (with unsoldered copper ball) 2" dia (S.I. No.8/P-18) | Each | 2 | 593.37 | 1186.74
Total |  |  |  |  | 2923.75
4 (B) NON SCHEDULE OF ITEM (B), PLUMBING WORKS
1 | Supply & fix UPVC (Dadex or Equivalent or approved by engineer incharge) fitting with 'Z' joint & rubber ring etc.
| (a) Elbow / Bend 110 mm or 4" dia | Each | 1 | 3885 | 3885
| (b) Tee 110 mm dia | Each | 1 | 8076 | 8076
| (c) Socket 110 mm dia | Each | 1 | 799 | 799
| (d) UPVC Tee With Door 110 mm dia | Each | 1 | 5517 | 5517
2 | Supply & fix UPVC (Dadex or Equivalent or approved by engineer incharge) fitting with 'Z' joint & rubber ring etc.
| (a) Elbow / Bend 75 mm or 3" dia | Each | 1 | 3118 | 3118
| (b) Tee 75 mm dia | Each | 1 | 3201 | 3201
| (c) Socket 75 mm dia | Each | 1 | 550 | 550
| (d) UPVC Tee With Door 75 mm dia | Each | 1 | 4428 | 4428
3 | Providing & laying PPR PN-20 (Dadex or approved by engineer incharge) pipe with all fittings i.e socket, bend tee, elbow where required.
| d) 50 mm (2") dia | Rft | 100 | 264 | 26400
Total |  |  |  |  | 55974

## ELE 1
BILL OF QUANTITIES
OF
CONSTRUCTION OF SCHOOL
AT
G.B.H.S FARAN SUKKUR (418030059)
N.B: | These items and their rates given in the are based on Schedule Rate 2012 of Govt. of Sindh. However Rates of Non-Schedule Items and Premium are to be filled by the Contractor .
2) SCHEDULE OF ITEM (A), ELECTRICAL WORKS
S.No | Description of Item | Unit | Quantity | Rate | Amount
|  |  |  | (Rs.) | (Rs.)
1 | Wiring for light or fan point with (3/.029) PVC insulated wire in 20mm (3/4") PVC conduit recessed in the wall or column as required (S.No.124, Pg-15). | Point | 5 | 1130 | 5650
2 | Providing & fixing one way SP 5 amp switch flush type on metal board & covered with plastic sheet (S.No-219, Pg-33). | No | 5 | 54 | 270
3 | Providing & fixing two pin 5 amp plug & socket switch flush type on metal board & covered with plastic sheet (S.No-222, Pg-33). | No | 1 | 83 | 83
4 | Providing & fixing three pin 5 amp plug & socket switch flush type on metal board & covered with plastic sheet (S.No-226, Pg-33). | No | 1 | 151 | 151
5 | Providing & fixing brass / PVC batten holder superior quality (S.No-232, Pg-33). | No | 5 | 70 | 350
Total |  |  |  |  | 6504
PART B- ELECTRICAL WORKS (NON SCHEDULE)
1 | Providing and fixing 25 watt saver lamp Philips quality or equivalent as approved by Engineer in charge | No | 5 | 280 | 1400
Total Rs. |  |  |  |  | 1400