## Cover
OFFICE OF THE EXECUTIVE ENGINEER
PUBLIC HEALTH ENGINEERING DIVISION-I LARKANO
DISTRICT ADP NEW SCHEMES
(2015-2016)
Detailed Working estimate for
Construction of C.C Drains & CC Blocks in Various Villages of U.C Mashori Shareef @ Hatti Taluka Bakrani Distt : Larkano (under District ADP New schemes 2015-16)
| Estimated cost | Rs | 5000000

## FACE SHEET
FACE SHEET
FUND HEAD: - | [ ] | District Government
MAJOR HEAD: - | [ ] | District ADP New schemes (2015-16)
SERVICE HEAD: - | [ ] | Various Villages of U.C Mashori Shareef
Detailed Working estimate for
DEPTT: HEAD: - | [ ] | Construction of C.C Drains & CC Blocks in Various Villages of U.C Mashori Shareef @ Hatti Taluka Bakrani Distt : Larkano (under District ADP New schemes 2015-16)
|  | ESTIMATED COST RS. |  | 5000000
The detailed working Estimate is framed in the Office of the Executive Engineer Public Health Engg: Division-I Larkano for the probable expenditure that will be incurred on Construction of C.C Drains & CC Blocks in Various Villages of U.C Mashori Shareef @ Hatti Taluka Bakrani Distt : Larkano (under District ADP New schemes 2015-16)
GENERAL DESCRIPTION
The District Government has been approved the schemes amounting to Rs.41.00 million (under District ADP new schemes of various UC's of Taluka Bakarani District Larkano for providing Drainage facilities to the residance of local areas
Hence the detailed working estimate is prepared and submitted for favour of necessary check further disposal please.
Rates | The rates incorporated are based approved by Standing Rates Committee
Specification | The work will be carried out as per PWD/ PHE specification
Time | The work will be completed within a period of (3) Months
Assistant Engineer. |  |  | Executive Engineer.
Public Health Engg:S/Division-II |  |  | Public Health Engg:Division-I
Larkano |  |  | Larkano

## Abstract
Detailed Working estimate for
Construction of C.C Drains & CC Blocks in Various Villages of U.C Mashori Shareef @ Hatti Taluka Bakrani Distt : Larkano (under District ADP New schemes 2015-16)
G E N E R A L A B S T R A C T
1 | Part-I | C.C drains |  |  | Rs: | 2189554.9279
2 | Part-II | C.C Blocks |  |  | Rs: | 2809554.8359
|  |  |  | G.Total: | Rs. | 4999109.7638
|  |  |  | Say | Rs. | 5000000
|  |  |  | In Million | Rs. | 5
Assistant Engineer. |  |  | Executive Engineer.
Public Health Engg:S/Division-II |  |  | Public Health Engg:Division-I
Larkano |  |  | Larkano

## Drains
Detailed Working Estimate for
Construction of C.C Drains & CC Blocks in Various Villages of U.C Mashori Shareef @ Hatti Taluka Bakrani Distt : Larkano (under District ADP New schemes 2015-16)
S.# | Qty | Item of work | [8 empty] | Rate | Unit |  | Amount
PART-I C.C DRAINS
1 | Excavation in foundation of building bridges and other structures
i/c dag belling dressing refilling around the structures with excavated
earth watering ramming lead up to 5ft (b) in ordinary soil (G.S.I-18/ P/4)
| Type -A | 1 | x | 1800 | x | 2.42 | x | 0.75 | = | 3267 | Cft
| Type - B | 1 | x | 770 | x | 3 | x | 1 | = | 2310 | Cft
[8 empty] | total | = | 5577 | Cft
| 5577 | cft | [7 empty] | @Rs | 3176.25 | P%0Cft | Rs | 17713.9463
2 | Cement concrete plain i/c placing compacting finishing
and curing complete i/c screening and washing of stone
aggregate without shuttering Ratio 1:4:8 (G.S.I-5(ii) P/17
| Type - A | 1 | x | 1800 | x | 2.42 | x | 0.25 | = | 1089 | Cft
| Type - B | 1 | x | 770 | x | 3 | x | 0.25 | = | 577.5 | Cft
[8 empty] | total | = | 1666.5 | Cft
| 1666.5 |  | Cft | [6 empty] | @Rs | 11288.75 | P%Cft | Rs | 188127.0187
3 | Construction of standard open type drains cunette block of C.C 1:2:4 in situ to the design profile i/c cost of mould as per drawing i/c applying floating cost of cement 1/32” thick to the exposed face finished smooth curing etc complete as per detailed drawing . (P.H.S.I No D, P/ 58)
| Type A | 1800 |  | Rft | [5 empty] | @Rs | 94 | P-Rft | Rs | 169200
| Type B | 770 |  | Rft | [5 empty] | @Rs | 174 | P-Rft | Rs | 133980
4 | Pacca brick work in foundation and plinth in cement sand mortar(1:6)
(G.S.I No. 4 (e) P/ 21)
| Type -A | 2 | x | 1800 | x | 0.75 | x | 1 | = | 2700
| Type -B | 2 | x | 770 | x | 0.75 | x | 1.75 | = | 2021.25
[8 empty] | total | = | 4721.25 | Cft
| 4721.25 | cft | [7 empty] | @Rs | 11948.36 | P%Cft | Rs | 564111.9465
5 | Cement plaster (1:4) up to 20’height ½”thick (G.S.I-11(b) / P/52)
| Type -A | 2 | x | 1800 | x | 1.25 |  |  | = | 4500 | sft
| Type - B | 2 | x | 770 | x | 1.5 |  |  | = | 2310 | sft
[8 empty] | total | = | 6810 | sft
| 6810 | Sft | [7 empty] | @Rs | 2283.93 | P%Sft | Rs | 155535.633
6 | R.C.C work i/c all labour and material except the cost of steel
reinforcement and its labour for bending and binding which will
be paid separately. This rate also includes all kinds of forms moulds
lifting shuttering curing rendering and finishing the exposed surface
i/c screening and washing of shingle (a) R.C work in roof slab beams
columns,rafts lintels & other structural members
laid in situ or precast laid in position complete in a respect. (i)
Ratio 1;2;4 90 lbs cement 2 cft sand 4 cft shingle 1/8” to ¼” gauge.
(G.S.I-6(a) P/17)
|  | 18 | x | 10 | x | 2.42 | x | 0.5 | = | 217.8 | Cft
|  | 12 | x | 12 | x | 3 | x | 0.5 | = | 216 | Cft
[8 empty] | total | = | 433.8 | Cft
| 433.8 |  | Cft | [6 empty] | @Rs | 337 | P-Cft | Rs | 146190.6
7 | Fabrication of mild steel reinforcement for cement concrete i/c
cutting bending laying in position making joints and fastening i/c
cost of binding wire also includes removal of rust from bars.
(G.S.I-8-b P/17)
| 433.8 | x | 4.5 | = | 17.4295 |  | Cwt
112
| 17.4295 | Cwt | [7 empty] | @Rs | 5001.7 | P-Cwt | Rs | 87180
8 | Cement concrete plain i/c placing compacting finishing
and curing complete i/c screening and washing of stone
aggregate without shuttering Ratio 1:2:4 (G.S.I-5 f P/15)
| Type - A | 26 | x | 4 | x | 2.42 | x | 0.33 | = | 83.0544 | Cft
| Type - B | 20 | x | 6 | x | 3 | x | 0.42 | = | 151.2 | Cft
[8 empty] | total | = | 234.2544 | Cft
| 234.2544 |  | Cft | [6 empty] | @Rs. | 14429.25 | P%Cft | Rs | 33801.153
[11 empty] | G.Total: |  | Rs | 1495840.2975

## Cartage-I
Cartage of Material | [7 empty] | BF | Rs. | 1495840.2975
1 | Bajri from Shadi shaheed lead |  |  | 96 | Miles)
| 3243.5519 | Cft |  |  |  | @Rs | 3702.36 | P%Cft | Rs | 120087.9671
2 | Stone from Arrore lead miles |  |  | 93
| 0 | Cft |  |  |  | @Rs | 3604.68 | P%Cft | Rs | 0
3 | Hill sand from Bolhari Lead |  |  | 220 | Miles
| 3089.3836 | Cft |  |  |  | @Rs | 7739.8 | P%Cft | Rs | 239112.1093
4 | Cement from Zeel Pak Factory Hyd lead |  |  |  |  | 218 | Miles
| 697.0704 | Bags |  |  |  | @Rs | 137.13 | P-Bags | Rs | 95589.2604
5 | Brick from nearest kiln lead |  |  | 6 | Miles)
| 63736.875 | Nos: |  |  |  | @Rs | 617.54 | P%O No: | Rs | 39360.0698
5 | Steel from Sukkur lead |  | 73 | Miles)
| 17.4295 | cwt |  |  |  | @Rs. | 29.5348 | P.cwt | Rs | 514.7757
[8 empty] | Total: | Rs | 1990504.4799
|  |  |  | Add:10% above (+) |  |  |  |  | Rs | 199050.448
[8 empty] | G.total | Rs | 2189554.9279
Assistant Engineer. |  |  |  |  | Executive Engineer.
Public Health Engg:S/Division-II |  |  |  |  | Public Health Engg:Division-I
Larkano |  |  |  |  | Larkano

## Material
Material Statement
S.# | Item |  |  |  | Qty: | Bajri | Stone | Hill sand | Cement | Bricks | Steel
1 | C.C Plain 1:4:8 |  |  |  | 1666.5 | 1599.84 | 0 | 799.92 | 159.984 | 0 | 0
2 | Pacca brick work (1:6) |  |  |  | 4721.25 | 0 | 0 | 1213.3612 | 162.411 | 63736.875 | 0
3 | Type A Drain | 1800 | x | 0.35 | 630 | 554.4 | 0 | 281.61 | 107.1 | 0 | 0
4 | Type B Drain | 770 | x | 0.74 | 569.8 | 501.424 | 0 | 250.712 | 100.2848 | 0 | 0
5 | R.C.C work (1:2:4) |  |  |  | 433.8 | 381.744 | 0 | 193.9086 | 76.3488 | 0 | 17.4295
6 | Cement Plaster (1:4) 1/2" |  |  |  | 6810 | 0 | 0 | 245.16 | 49.713 | 0 | 0
7 | C.C plain 1:2:4 (CC slabs) |  |  |  | 234.2544 | 206.1439 | 0 | 104.7117 | 41.2288 | 0 | 0
[5 empty] | Total: | 3243.5519 | 0 | 3089.3836 | 697.0704 | 63736.875 | 17.4295
[5 empty] | Say | 3243.5519 | 0 | 3089.3836 | 697.0704 | 63736.875 | 17.4295
Assistant Engineer. | [5 empty] | Executive Engineer.
Public Health Engg:S/Division-II | [5 empty] | Public Health Engg:Division-I
Larkano | [5 empty] | Larkano

## Block
Detailed Working Estimate for
Construction of C.C Drains & CC Blocks in Various Villages of U.C Mashori Shareef @ Hatti Taluka Bakrani Distt : Larkano (under District ADP New schemes 2015-16)
S.# | Qty | Item | [8 empty] | Rate | Unit |  | Amount
PART-II CC BLOCKS
1 | Barrow pit excavation undressed lead upto 100ft ordinary soil
(G.S.I. No. 3 (a) p/ 1)
|  | 1 | x | 2500 | x | 9 | x | 1.07 | = | 24075 | cft
| Deduct Qty of excavation | [7 empty] | (-) | 5577 | cft
[8 empty] | Net | = | 18498
| 18498 | Cft | [7 empty] | @Rs | 2117.5 | P%0Cft | Rs | 39169.515
2 | Laying arth in 6"thick layers levelling and dressing etc completed
(G.S.I.No. 13 a p/ 3)
| Qty: same as item No. |  |  |  | 1 |  |  |  | = | 24075 | cft
| 24075 | Cft | [7 empty] | @Rs | 263 | P%0Cft | Rs | 6331.725
3 | Extra lead for every 50' Ft: additional lead or part thereof.(GSI NO.8P-3)
| Total leads = |  | 2600 | (-) 100 | = | 2500 | /50 | = | 50 leads
| 50 leads | each 100/78 = | [5 empty] | 5039
| Qty: same as item No. |  |  |  | 1 |  |  |  | = | 18498 | cft
| 18498 | Cft | [7 empty] | @Rs | 5039 | P%0Cft | Rs | 93211.422
4 | Cement concrete bricks or stone ballest ½” to 2” gauge.(Ratio 1:4:8)
(G.SI. No. 4(b) p/ 15)
|  | 1 | x | 2500 | x | 9 | x | 0.33 | = | 7425 | cft
| 7425 | Cft | [7 empty] | @Rs | 9416.28 | P%cft | Rs | 699158.79
5 | Cement concrete plain i/c placing compacting, finishing
and curing complete i/c sreening & washing of stone aggregate
without shuttering (Ratio 1:2:4) (G.S.I No. 5 p/ 16)
|  | 1 | x | 2500 | x | 9 | x | 0.25 | = | 5625 | cft
| 5625 | Cft | [7 empty] | @Rs | 14429.25 | P%cft | Rs | 811645.3125
6 | Erection and removal of centering for R.C.C or plain C.C works
of deodar wood (2nd class) (b) for partal wood (vertical).
(G.S.I.No. 19 p/ 18)
|  | 1 | x | 2500 | x |  |  | 0.25 | = | 625 | sft
| 625 | sft | [7 empty] | @Rs | 3127.41 | P%sft | Rs | 19546.3125
7 | Supplying and fixing Marble stone board size 2x2.50 (LQR) | [10 empty] | Total: | Rs | 1669063.077
| 1 | No | [7 empty] | @Rs | 4000 | P.Each | Rs | 4000
[11 empty] | G.Total: |  | Rs | 1673063.077

## Cartage-2
Cartage of Material | [6 empty] | BF | Rs. | 1673063.077
1 | Bajri from Shadi shaheed lead |  | 96 | Miles)
| 4950 | Cft |  |  | @Rs | 3702.36 | P%Cft | Rs | 183266.82
2 | Stone from Arrore lead miles |  | 93
| 7128 | Cft |  |  | @Rs | 3604.68 | P%Cft | Rs | 256941.5904
3 | Hill sand from Bolhari Lead |  | 220 | Miles
| 6039 | Cft |  |  | @Rs | 7739.8 | P%Cft | Rs | 467406.522
4 | Cement from Zeel Pak Factory Hyd lead |  |  |  | 218 | Miles
| 1669.05 | Bags |  |  | @Rs | 137.13 | P-Bags | Rs | 228876.8265
[7 empty] | Total: | Rs | 2809554.8359
Assistant Engineer. |  |  |  | Executive Engineer.
Public Health Engg:S/Division-II |  |  |  | Public Health Engg:Division-I
Larkano |  |  |  | Larkano

## Material-2
Material Statement
S.# | Item | Qty: | Bajri | Stone | Hill sand | Cement | Bricks | Steel
1 | C.C brick or stone ballst 1:1/2" to 2"guage ratio 1:4;8 | 7425 | 0 | 7128 | 3564 | 712.8 | 0 | 0
2 | CC plain Ratio:1:2:4 | 5625 | 4950 | 0 | 2475 | 956.25 | 0 | 0
|  | Total: | 4950 | 7128 | 6039 | 1669.05 | 0 | 0
|  | Say | 4950 | 7128 | 6039 | 1669.05 | 0 | 0
Assistant Engineer. |  |  |  | Executive Engineer.
Public Health Engg:S/Division-II |  |  | Public Health Engg:Division-I
Larkano |  |  |  | Larkano

## BOQ
BILL OF QUANTITIES
(A) |  |  |  | Construction of C.C Drains & CC Blocks in Vairiou Village of U.C Mashori Shareef Taluka Bakrani (under District ADP New schemes 2015-16)
Item # | Quantities | Description and rate of Item to be executed at site |  |  |  |  | Rate | Unit | Amount in Rupees
1 | 2 | 3 |  |  |  |  | 4 | 5 | 6
| Part-I | C.C Drains
1 | Excavation in foundation of building bridges and other structures
i/c dag belling dressing refilling around the structures with excavated
earth watering ramming lead up to 5ft (b) in ordinary soil (G.S.I-18/ P/4)
| 5577 | cft |  |  |  | @Rs | 3176.25 | P%0Cft | Rs | 17713.9463
2 | Cement concrete plain i/c placing compacting finishing
and curing complete i/c screening and washing of stone
aggregate without shuttering Ratio 1:4:8 (G.S.I-5(ii) P/17
| 1666.5 |  | Cft |  |  | @Rs | 11288.75 | P%Cft | Rs | 188127.0187
3 | Construction of standard open type drains cunette block of C.C 1:2:4 in situ to the design profile i/c cost of mould as per drawing i/c applying floating cost of cement 1/32” thick to the exposed face finished smooth curing etc complete as per detailed drawing . (P.H.S.I No D, P/ 58)
| Type A | 1800 |  | Rft |  | @Rs | 94 | P-Rft | Rs | 169200
| Type B | 770 |  | Rft |  | @Rs | 174 | P-Rft | Rs | 133980
4 | Pacca brick work in foundation and plinth in cement sand mortar(1:6)
(G.S.I No. 4 (e) P/ 21)
| 4721.25 | cft |  |  |  | @Rs | 11948.36 | P%Cft | Rs | 564111.9465
5 | Cement plaster (1:4) up to 20’height ½”thick (G.S.I-11(b) / P/52)
| 6810 | Sft |  |  |  | @Rs | 2283.93 | P%Sft | Rs | 155535.633
6 | R.C.C work i/c all labour and material except the cost of steel
reinforcement and its labour for bending and binding which will
be paid separately. This rate also includes all kinds of forms moulds
lifting shuttering curing rendering and finishing the exposed surface
i/c screening and washing of shingle (a) R.C work in roof slab beams
columns,rafts lintels & other structural members
laid in situ or precast laid in position complete in a respect. (i)
Ratio 1;2;4 90 lbs cement 2 cft sand 4 cft shingle 1/8” to ¼” gauge.
(G.S.I-6(a) P/17)
| 433.8 |  | Cft |  |  | @Rs | 337 | P-Cft | Rs | 146190.6
7 | Fabrication of mild steel reinforcement for cement concrete i/c
cutting bending laying in position making joints and fastening i/c
cost of binding wire also includes removal of rust from bars.
(G.S.I-8-b P/17)
| 17.4295 | Cwt |  |  |  | @Rs | 5001.7 | P-Cwt | Rs | 87180
8 | Cement concrete plain i/c placing compacting finishing
and curing complete i/c screening and washing of stone
aggregate without shuttering Ratio 1:2:4 (G.S.I-5 f P/15)
| 234.2544 |  | Cft |  |  | @Rs. | 14429.25 | P%Cft | Rs | 33801.153
[7 empty] | Total: | (A) | Rs | 1495840.2975
Part- II CC BLOCKS
1 | Barrow pit excavation undressed lead upto 100ft ordinary soil
(G.S.I. No. 3 (a) p/ 1)
| 18498 | Cft |  |  |  | @Rs | 2117.5 | P%0Cft | Rs | 39169.515
2 | Laying arth in 6"thick layers levelling and dressing etc completed
(G.S.I.No. 13 a p/ 3)
| 24075 | Cft |  |  |  | @Rs | 263 | P%0Cft | Rs | 6331.725
3 | Extra lead for every 50' Ft: additional lead or part thereof.(GSI NO.8P-3)
| 18498 | Cft |  |  |  | @Rs | 5039 | P%0Cft | Rs | 93211.422
4 | Cement concrete bricks or stone ballest ½” to 2” gauge.(Ratio 1:4:8)
(G.SI. No. 4(b) p/ 15)
| 7425 | Cft |  |  |  | @Rs | 9416.28 | P%cft | Rs | 699158.79
5 | Cement concrete plain i/c placing compacting, finishing
and curing etc complete i/c sreening & washing of stone aggregate
without shuttering (Ratio 1:2:4) (G.S.I No. 5 p/ 16)
| 5625 | Cft |  |  |  | @Rs | 14429.25 | P%cft | Rs | 811645.3125
6 | Erection and removal of centering for R.C.C or plain C.C works
of deodar wood (2nd class) (b) for partal wood (vertical).
(G.S.I.No. 19 p/ 18)
| 625 | sft |  |  |  | @Rs | 3127.41 | P%sft | Rs | 19546.3125
[8 empty] | Total: | Rs | 1669063.077
7 | Supplying and fixing M.S iron board size (2x2.50) (LQR)
| 1 | No |  |  |  | @Rs | 4000 | P.Each | Rs | 4000
[7 empty] | Total: | (B) | Rs | 1673063.077
General Abstract
| S.# | Sub- Works |  |  | Schedule Amount |  | N/S Amount |  | G.Total:
| 1 | Part-I C.C drains |  |  | 1495840.2975 |  | 0 |  | Rs | 1495840.2975
| 2 | Part-II C.C Blocks |  |  | 1669063.077 |  | 4000 |  | Rs | 1673063.077
|  | G.total: |  |  | 3164903.3745 |  | 4000 |  | Rs | 3168903.3745
Amount Total (a)
| ---------------- % above /below on the rates CSR |  |  |  |  | Amount to be added /deducted on the
basis of premium quoted. TOTAL(b)
Total (A) = a+b in words & figure:
| CONTRACTOR |  |  |  |  | Executive Engineer
Public Health Engg:Division-I
Larkano

## Lead chart
RATE ANALYSIS CARRAIGE
SCHEDULE OF CARRAIGE RATE VALUME-III PART-IV
NAME OF WORK |  |  | Construction of C.C Drains & CC Blocks in Vairiou Village of U.C Mashori Shareef Taluka Bakrani (under District ADP New schemes 2015-16)
Carriage of 100 cft / 5 tons of all material like stone aggregate spawl, coal lime struck etc: B.G rails fastening points and crossing bridges, girds pipes sheets rails M.S bars etc: or 1000 Nos. bricks 10”x5”x3” or 150 of timer or 100 mounds of fuel wood by trucks of any other means owned by the contractor.
a) | Hill Sand From Bolhari |  |  |  | 220 | Miles )
| 1st to 6th mile | [6 empty] | Rs: | 771.96
| Remaining | 214 |  | @Rs: | 32.56 |  | P/ Mile | Rs: | 6967.84
[8 empty] | Total | 7739.8
b) | Bajri from Shadi shaheed |  |  |  | 96 | Miles )
| 1st to 6th mile | [6 empty] | Rs: | 771.96
| Remaining | 90 |  | @Rs: | 32.56 |  | P/ Mile | Rs: | 2930.4
[8 empty] | Total | 3702.36
c) | Stone ballast From Arrore |  |  |  | 93 | Miles )
| 1st to 6th mile | [6 empty] | Rs: | 771.96
| Remaining | 87 |  | @Rs: | 32.56 |  | P/ Mile | Rs: | 2832.72
[8 empty] | Total | 3604.68
d) | Bricks 1000 No. |  |  |  | 6 | Miles )
| 1st to 6th mile | [6 empty] | Rs: | 617.54
| Remaining | 0 |  | @Rs: | 26.05 |  | P/ Mile | Rs: | 0
[8 empty] | Total | 617.54
e) | Cement From Zeel Pak Hyderabad |  |  |  | 218 | Miles )
| 1st to 2nd mile | [6 empty] | Rs: | 7.53
| Remaining | 216 |  | @Rs: | 0.6 |  | P/ Mile | Rs: | 129.6
[8 empty] | Total | 137.13
f) | Steel from Sukkur lead |  |  |  | 73 | Miles )
| 1st to 6th mile | [6 empty] | Rs: | 771.96
| Remaining | 67 |  | @Rs: | 32.56 |  | P/ Mile | Rs: | 2181.52
[8 empty] | Total | 2953.48
[5 empty] | 2953.48 | / | 100 | Rs: | 29.5348
Assistant Engineer. |  |  |  |  | Executive Engineer.
Public Health Engg:S/Division-II |  |  |  |  | Public Health Engg:Division-I
Larkano |  |  |  |  | Larkano

## Miles
Total miles
1 | Hill sand | 220 | Miles
2 | Bajri | 96 | Miles
3 | Stone Ballast | 93 | Miles
4 | Cement | 218 | Miles
5 | bricks | 6 | Miles
6 | Steel | 73 | miles