## Schedule-B
Name of Work: M&R To Civil Judge & Judicial Magistrate I Bungalow Sanghar.
Schedule-B
Sr. No: | Items of Work. | Qty: |  | Rate. | Unit. | Amount. | Amount.
Part (A) Main Buidling
1 | Removing cement or lime plaster. (S.I.No:53, P-14) | 5570 | -Sft: | 121 | %-Sft: | 6739.7 | 6740
2 | Applying floating coat of cement 1/32” thick. (S.I.No:14, P-53) | 5570 | -Sft: | 660 | %-Sft: | 36762 | 36762
3 | Cement plaster 1:6 upto 20" height (b) 1/2" thick. (S.I.No:13(b) P-52) | 5570 | -Sft: | 2206.6 | %-Sft: | 122907.62 | 122908
4 | Cement plaster 1:4 upto 20" height (a) 3/8" thick. (S.I.No:11(a) P-52) | 5570 | -Sft: | 2197.52 | %-Sft: | 122401.864 | 122402
5 | Dismantling cement concrete plain 1:2:4. (S.I.No:19(c) P-10) | 328 | -Cft: | 3327.5 | %-Cft: | 10914.2 | 10914
6 | Providing and laying topping cement concrete 1:2:4 including surface finishing and dividing into panels. (S.I.No:16(c), P-42)
(c) | 2” thick topping. | 1934 | -Sft: | 3275.5 | %-Sft: | 63348.17 | 63348
7 | Pacca brick work other than building i/c skirting of joints upto 20’ height in (I-e) cement sand mortar ratio 1:6. (S.No:07(I-e) P-22) | 205 | -Cft: | 12346.65 | %-Cft: | 25310.6325 | 25311
8 | First class deodar wood wrought joinery work in wire guaze door and windows with 22 S.W.G. Galvanized wire guaze 144 mesh per square inch iron fittings complete. (S.I.No:14(d), P-59)
(d) | Galvanized wire gauze fixed to chowkats 3/4” deodar wood strips and screws. | 226 | -Sft: | 190.72 | P.Sft: | 43102.72 | 43103
9 | Making and fixing steel grated doors with 1/16" thick sheeting i/c angle iron frame 2" x 2" 3/8" and 3/4" square bars 4" centre to centre with locking arrangement. (S.I.No:24, P-92) | 0 | -Sft: | 594.57 | P.Sft: | 0 | 0
10 | Scraping ordinary distemper, oil bound distemper or paint on walls. (S.I.No:54(b) P-13) | 3209 | -Sft: | 226.88 | %-Sft: | 7280.5792 | 7281
11 | Distempering on walls 02-coats. (S.I.No:24(b) P-54) | 6418 | -Sft: | 1043.9 | %-Sft: | 66997.502 | 66998
12 | Painting Old surface. (c) Preparing surface and painting doors and windows any type 02-coats. (S.I.No:05(c-ii) P-70) | 982 | -Sft: | 674.9 | %-Sft: | 6627.518 | 6628
13 | White washing on walls (a) 01-coat. (Ist: coat over primary coat) (S.I.No:26(a), P-54) | 1444 | -Sft: | 416.63 | %-Sft: | 6016.1372 | 6016
14 | Colour washing on walls 02-coats. (S.N:25(b), P-54) | 5071 | -Sft: | 859.9 | %-Sft: | 43605.529 | 43606
15 | Glazed tile dado 1/4” thick laid in cement pigment over 1:2 cement sand mortar 3/4” thick including finishing. (S.I.No:38, P-45) | 44 | -Sft: | 28299.3 | %-Sft: | 12451.692 | 12452
|  | T o t a l :- |  |  |  | 574465.8639 | 574469
Contracotr |  |  |  | Executive Engineer Provincial Buildings Division Shaheed Benazirabad

## M.S.
Name of Work: M&R To Civil Judge & Judicial Magistrate I Bungalow Sanghar.
MEASUREMENT SHEET
S# | DESCRIPTION | [5 empty] | No. |  |  |  | L |  | B |  | D/H | TOTAL
Part (A) Main Buidling
1 | Removing cement or lime plaster. (S.I.No:53, P-14)
|  | Bungalow O/S B/S Kit |  |  |  |  | 1 | x | 9 | x | 5 |  |  |  |  | = | 0 | 0
|  | Bungalow B Side |  |  |  |  | 1 | x | 49 | x | 5 |  |  |  |  | = | 0 | 0
|  | Bungalow E/Side O/S wall |  |  |  |  | 1 | x | 40 | x | 5 |  |  |  |  | = | 0 | 0
|  | C.Y Portion |  |  |  |  | 1 | x | 12 | x | 3.5 |  |  |  |  | = | 0 | 0
|  | C.Y Portion |  |  |  |  | 1 | x | 12 | x | 2.5 |  |  |  |  | = | 0 | 0
|  | Bungalow B/Side |  |  |  |  | 1 | x | 21.25 | x | 3.58 |  |  |  |  | = | 0 | 0
|  | D/H Side O/S Wall |  |  |  |  | 1 | x | 14.5 | x | 5 |  |  |  |  | = | 0 | 0
|  | Lav Porch Side Kit |  |  |  |  | 1 | x | 49 | x | 5 |  |  |  |  | = | 0 | 0
|  | C/Wall I/Side |  |  |  |  | 1 | x | 2 | x | 100 | x | 8.33 |  |  | = | 0 | 0
|  | Pump Room I/Side o/i |  |  |  |  | 1 | x | 2 | x | 12 | x | 6.5 |  |  | = | 0 | 0
|  | Pump Room Roof Slab |  |  |  |  | 1 | x | 5 | x | 4.5 |  |  |  |  | = | 0 | 0
|  | C/Wall F/B |  |  |  |  | 1 | x | 3 | x | 46.75 | x | 8.5 |  |  | = | 0 | 0
|  | O.H.Tank i/Side |  |  |  |  | 1 | x | 2 | x( | 6 | + | 8 | )x | 6 | = | 0 | 0
|  | Roof Salb G.F |  |  |  |  | 1 | x | 3 | x | 6 | x | 8 |  |  | = | 0 | 0
|  | Kitchen Slab |  |  |  |  | 1 | x | 3.5 | x | 4 |  |  |  |  | = | 0 | 0
|  | Kitchen Chaja |  |  |  |  | 1 | x | 4 | x | 11 |  |  |  |  | = | 0 | 0
|  | Piller Lapat |  |  |  |  | 2 | x | 2 | x | 6 |  |  |  |  | = | 0 | 0
|  | Kitchen Floor |  |  |  |  | 2 | x | 6.5 | x | 8.33 |  |  |  |  | = | 0 | 0
|  | Sotre Floor |  |  |  |  | 1 | x | 15.25 | x | 7.83 |  |  |  |  | = | 0 | 0
|  | Dressing Floor |  |  |  |  | 1 | x | 5 | x | 4.5 |  |  |  |  | = | 0 | 0
|  | Dressing Floor |  |  |  |  | 1 | x | 4 | x | 4.5 |  |  |  |  | = | 0 | 0
|  | D/H Floor |  |  |  |  | 1 | x | 3.5 | x | 6 | x |  |  |  | = | 0 | 0
[7 empty] | 1 | x | 12 | x | 30 |  |  |  |  | = | 0 | 0
|  | Bath |  |  |  |  | 1 | x | 7 | x | 5 |  |  |  |  | = | 0 | 0
|  | Bath |  |  |  |  | 2 | x | 10 | x | 8 |  |  |  |  | = | 0 | 0
|  | Room |  |  |  |  | 2 | x | 2 | x( | 16 | + | 12 | )x | 3 | = | 0 | 0
[15 empty] | TOTAL |  | 0 | 0 | Sft:
2 | Applying floating coat of cement 1/32” thick. (S.I.No:14, P-53)
[7 empty] | Same Qty: as per item No.01 above. | [8 empty] | = | 0 | 0
[15 empty] | TOTAL |  | 0 | 0 | Sft:
3 | Cement plaster 1:6 upto 20" height (b) 1/2" thick. (S.I.No:13(b) P-52)
[7 empty] | Same Qty: as per item No.02 above. | [8 empty] | = | 0 | 0
[15 empty] | TOTAL |  | 0 | 0 | Sft:
4 | Cement plaster 1:4 upto 20" height (a) 3/8" thick. (S.I.No:11(a) P-52)
[7 empty] | Same Qty: as per item No.03 above. | [8 empty] | = | 0 | 0
[15 empty] | TOTAL |  | 0 | 0 | Sft:
5 | Dismantling cement concrete plain 1:2:4. (S.I.No:19(c) P-10)
|  | Room |  |  |  |  | 1 | x | 3 | x | 4 | x | 0.17 |  |  | = | 0 | 0
|  | Room Floor |  |  |  |  | 2 | x | 16 | x | 12 | x | 0.17 |  |  | = | 0 | 0
|  | Room Floor |  |  |  |  | 1 | x | 21 | x | 12 | x | 0.17 |  |  | = | 0 | 0
|  | Kit Floor |  |  |  |  | 1 | x | 18 | x | 21.75 | x | 0.17 |  |  | = | 0 | 0
|  | Kit Floor |  |  |  |  | 1 | x | 10.25 | x | 6.5 | x | 0.17 |  |  | = | 0 | 0
|  | M. Gate to Car Porch |  |  |  |  | 1 | x | 32 | x | 17 | x | 0.17 |  |  | = | 0 | 0
|  | M. Gate to Car Porch |  |  |  |  | 1 | x | 14 | x | 11.75 | x | 0.17 |  |  | = | 0 | 0
|  | Gallry |  |  |  |  | 1 | x | 21.5 | x | 5.5 |  |  |  |  | = | 0 | 0
[15 empty] | TOTAL |  | 0 | 0 | Cft.
6 | Providing and laying topping cement concrete 1:2:4 2" Thick
|  | C.Y Floor |  |  |  |  | 1 | x | 18 | x | 21.75 |  |  |  |  | = | 0 | 0
|  | C.Y Floor |  |  |  |  | 1 | x | 10.25 | x | 6.5 |  |  |  |  | = | 0 | 0
|  | M. Gate to Car Porch |  |  |  |  | 1 | x | 32 | x | 17 |  |  |  |  | = | 0 | 0
|  | M. Gate to Car Porch |  |  |  |  | 1 | x | 14 | x | 11.75 |  |  |  |  | = | 0 | 0
|  | Gallry |  |  |  |  | 1 | x | 21.5 | x | 5.5 |  |  |  |  | = | 0 | 0
|  | Passage |  |  |  |  | 1 | x | 3 | x | 4 |  |  |  |  | = | 0 | 0
[15 empty] | TOTAL |  | 0 | 0 | Sft.
7 | Pacca brick work other than building
|  | I/ Side O/ Side Door |  |  |  |  | 1 | x | 4.5 | x | 0.75 | x | 7 |  |  | = | 0 | 0
|  | Gate Piller |  |  |  |  | 2 | x | 2 | x | 2 | x | 2 |  |  | = | 0 | 0
|  | M. Hole |  |  |  |  | 2 | x | 7 | x | 1.5 | x | 0.75 | x | 2 | = | 0 | 0
|  | M. Hole |  |  |  |  | 7 | x | 2 | x | 0.75 | x | 2 |  |  | = | 0 | 0
|  | M. Hole |  |  |  |  | 2 | x | 3 | x | 3 | x | 0.75 | x | 2 | = | 0 | 0
[15 empty] | TOTAL |  | 0 | 0 | Cft.
8 | Galvanized wire gauze fixed to chowkats 3/4” deodar wood strips and screws.
|  | Bath Door Shuter |  |  |  |  | 2 | x | 2.5 | x | 7 |  |  |  |  | = | 0 | 0
|  | Ver Door Shuter |  |  |  |  | 1 | x | 3.5 | x | 7 |  |  |  |  | = | 0 | 0
|  | W |  |  |  |  | 7 | x | 3 | x | 6 |  |  |  |  | = | 0 | 0
|  | W |  |  |  |  | 3 | x | 6 | x | 4 |  |  |  |  | = | 0 | 0
|  | W |  |  |  |  | 2 | x | 3 | x | 4 |  |  |  |  | = | 0 | 0
[15 empty] | TOTAL |  | 0 | 0 | Sft.
9 | Making and fixing steel grated doors with 1/16" thick sheeting i/c angle iron frame 2" x 2" 3/8"
|  | A.C |  |  |  |  | 1 | x | 2.5 | x | 1.75 |  |  |  |  | = | 0 | 0
|  | M. |  |  |  |  | 7 | x | 1.5 | x | 1.5 |  |  |  |  | = | 0 | 0
|  | M. |  |  |  |  | 2 | x | 3 | x | 3 |  |  |  |  | = | 0 | 0
|  | Gate Rise |  |  |  |  | 2 | x | 4.5 | x | 2 |  |  |  |  | = | 0 | 0
|  | Gate Rise |  |  |  |  | 2 | x | 4.5 | x | 1 |  |  |  |  | = | 0 | 0
[15 empty] | TOTAL |  | 0 | 0 | Sft.
10 | Scraping ordinary distemper, oil bound distemper or paint on walls.
|  | Bul Room |  |  |  |  | 2 | x | 2 | x( | 16 | x | 12 | )x | 12 | = | 0 | 0
|  | Ver |  |  |  |  | 1 | x | 2 | x( | 21 | x | 12 | )x | 10 | = | 0 | 0
|  | Bath |  |  |  |  | 2 | x | 2 | x( | 10 | x | 8 | )x | 10 | = | 0 | 0
|  | Dressing |  |  |  |  | 1 | x | 2 | x( | 4 | x | 4.5 | )x | 10 | = | 0 | 0
|  | Dressing |  |  |  |  | 1 | x | 2 | x( | 3.5 | x | 6 | )x | 10 | = | 0 | 0
|  | D/Hall |  |  |  |  | 1 | x | 2 | x( | 12 | x | 30 | )x | 12 | = | 0 | 0
|  | Bath |  |  |  |  | 1 | x | 2 | x( | 7 | x | 5 | )x | 10 | = | 0 | 0
|  | Kit |  |  |  |  | 1 | x | 2 | x( | 15.25 | x | 7.83 | )x | 12 | = | 0 | 0
|  | Store |  |  |  |  | 1 | x | 2 | x( | 5 | x | 4.5 | )x | 10 | = | 0 | 0
|  | Bath |  |  |  |  | 1 | x | 2 | x( | 10 | x | 8 | )x | 10 | = | 0 | 0
[15 empty] | TOTAL |  | 0 | 0 | Sft.
Deduction.
|  | Room Door |  |  |  |  | 2 | x | 3.5 | x | 7 | x | 0 | x | 0 | = | 0 | 0
|  | Room Bath Door |  |  |  |  | 2 | x | 2.5 | x | 7 | x | 0 | x | 0 | = | 0 | 0
|  | Room W |  |  |  |  | 3 | x | 4 | x | 6 | x | 0 | x | 0 | = | 0 | 0
|  | Room W |  |  |  |  | 2 | x | 3 | x | 4 | x | 0 | x | 0 | = | 0 | 0
|  | Ver W |  |  |  |  | 7 | x | 3 | x | 6 | x | 0 | x | 0 | = | 0 | 0
|  | D/W |  |  |  |  | 2 | x | 3 | x | 4 | x | 0 | x | 0 | = | 0 | 0
|  | D/Door |  |  |  |  | 2 | x | 3.5 | x | 7 | x | 0 | x | 0 | = | 0 | 0
|  | Bath Door |  |  |  |  | 4 | x | 2.5 | x | 7 | x | 0 | x | 0 | = | 0 | 0
|  | Store |  |  |  |  | 1 | x | 3 | x | 7 | x | 0 | x | 0 | = | 0 | 0
|  | Kitchen |  |  |  |  | 1 | x | 3 | x | 7 | x | 0 | x | 0 | = | 0 | 0
[15 empty] | (b) TOTAL |  | 0 | 0 | Sft.
|  |  |  | Net Qty: (a - b) | 0 | - | 0 | [7 empty] | TOTAL |  | 0 | 0 | Sft.
11 | Preparing the surface and painting with matt finish
[7 empty] | Same Qty: as per item No.10 above. | [8 empty] | = | 0 | 0
[15 empty] | TOTAL |  | 0 | 0 | Sft.
12 | Preparing surface and painting doors and windows any type 02-coats.
|  |  | Same Qty: as per item No.11-b above. | [7 empty] | 0 | x | 2 |  |  | = | 0 | 0
[15 empty] | TOTAL |  | 0 | 0 | Sft.
13 | Distempering on walls 02-coats.
|  | Room Cilling |  |  |  |  | 2 | x | 16 | x | 12 | x | 0 | x | 0 | = | 0 | 0
|  | Bath |  |  |  |  | 2 | x | 10 | x | 8 | x | 0 | x | 0 | = | 0 | 0
|  | Dressing |  |  |  |  | 2 | x | 4 | x | 4.5 | x | 0 | x | 0 | = | 0 | 0
|  | Ver Cilling |  |  |  |  | 1 | x | 21 | x | 12 | x | 0 | x | 0 | = | 0 | 0
|  | D/Hall Cilling |  |  |  |  | 1 | x | 12 | x | 30 | x | 0 | x | 0 | = | 0 | 0
|  | D/Hall Bath |  |  |  |  | 1 | x | 7 | x | 5 | x | 0 | x | 0 | = | 0 | 0
|  | Kit: Cilling |  |  |  |  | 1 | x | 15 | x | 7.83 | x | 0 | x | 0 | = | 0 | 0
|  | Store |  |  |  |  | 1 | x | 5 | x | 4 | x | 0 | x | 0 | = | 0 | 0
|  | Bath |  |  |  |  | 1 | x | 10 | x | 8 | x | 0 | x | 0 | = | 0 | 0
|  | Bungalow B/S Kit: |  |  |  |  | 1 | x | 9 | x | 14 | x | 0 | x | 0 | = | 0 | 0
|  | Bungalow B/S |  |  |  |  | 1 | x | 49 | x | 14 | x | 0 | x | 0 | = | 0 | 0
|  | Bungalow E/S |  |  |  |  | 1 | x | 40 | x | 10 | x | 0 | x | 0 | = | 0 | 0
|  | B/Side |  |  |  |  | 1 | x | 21.25 | x | 12 | x | 0 | x | 0 | = | 0 | 0
|  | D/H O/ Side |  |  |  |  | 1 | x | 14.5 | x | 12 | x | 0 | x | 0 | = | 0 | 0
|  | Car Porch i/Side |  |  |  |  | 1 | x | 49.67 | x | 12 | x | 0 | x | 0 | = | 0 | 0
|  | C/Wall i/Side |  |  |  |  | 2 | x | 100 | x | 8.33 | x | 0 | x | 0 | = | 0 | 0
|  | C/Wall R/B |  |  |  |  | 3 | x | 46.75 | x | 8.33 | x | 0 | x | 0 | = | 0 | 0
[15 empty] | TOTAL |  | 0 | 0 | Sft.
14 | Laying floors of approved coloured glazed tiles 1/4" thick
|  | Room Floor |  |  |  |  | 2 | x | 16 | x | 12 | x | 0 | x | 0 | = | 0 | 0
|  | Dressing Floor |  |  |  |  | 1 | x | 6 | x | 7.33 | x | 0 | x | 0 | = | 0 | 0
|  | Dressing Floor |  |  |  |  | 1 | x | 5 | x | 4 | x | 0 | x | 0 | = | 0 | 0
|  | Bath Floor |  |  |  |  | 2 | x | 8 | x | 6 | x | 0 | x | 0 | = | 0 | 0
|  | Kit: Floor |  |  |  |  | 1 | x | 11.59 | x | 8.59 | x | 0 | x | 0 | = | 0 | 0
|  | Dressing Floor |  |  |  |  | 1 | x | 12 | x | 20 | x | 0 | x | 0 | = | 0 | 0
|  | Bath Floor |  |  |  |  | 1 | x | 4.5 | x | 7 | x | 0 | x | 0 | = | 0 | 0
[15 empty] | TOTAL |  | 0 | 0 | Sft.
15 | Glazed tile dado 1/4” thick laid in cement pigment over 1:2
|  | Bath Dado |  |  |  |  | 2 | x | 2 | x( | 8 | + | 6 | )x | 5 | = | 0 | 0
|  | Kitchen |  |  |  |  | 1 | x | 2 | x( | 11.59 | + | 8.59 | )x | 0.5 | = | 0 | 0
|  | Slab |  |  |  |  | 1 | x | 11 | x | 3 | x |  | x |  | = | 0 | 0
|  | Room Floor |  |  |  |  | 1 | x | 2 | x( | 16 | + | 12 | )x | 0.5 | = | 0 | 0
|  | Dressing |  |  |  |  | 1 | x | 2 | x( | 6 | + | 7.33 | )x | 0.5 | = | 0 | 0
|  | Bath Dado |  |  |  |  | 1 | x | 2 | x( | 5 | + | 4 | )x | 5 | = | 0 | 0
|  | Dressing Hall |  |  |  |  | 1 | x | 2 | x( | 12 | + | 20 | )x | 0.5 | = | 0 | 0
|  | Bath Dado |  |  |  |  | 1 | x | 2 | x( | 4.5 | + | 7 | )x | 5 | = | 0 | 0
[15 empty] | TOTAL |  | 0 | 0 | Sft.
#REF!
1 | P/F squatting type white glazed earthen ware w.c
[7 empty] | 1 | x | 3 | x | 0 | x | 0 | x | 0 | = | 0 | 0
[15 empty] | TOTAL |  | 0 | 0 | Nos:
2 | P/F 25“ x 18’’ lavatory basin in white glazed earthen ware complete
[7 empty] | 1 | x | 3 | x | 0 | x | 0 | x | 0 | = | 0 | 0
[15 empty] | TOTAL |  | 0 | 0 | Nos:
3 | Add extra for labour for providing & fixing of earthen ware pedestal
[7 empty] | 1 | x | 3 | x | 0 | x | 0 | x | 0 | = | 0 | 0
[15 empty] | TOTAL |  | 0 | 0 | Nos:
4 | P/F 24"x 18” beveled edge mirror of Belgium glass complete
[7 empty] | 1 | x | 3 | x | 0 | x | 0 | x | 0 | = | 0 | 0
[15 empty] | TOTAL |  | 0 | 0 | Nos:
5 | Supplying & fixing Towel rail 24” long (b) 3/4” dia
[7 empty] | 1 | x | 3 | x | 0 | x | 0 | x | 0 | = | 0 | 0
[15 empty] | TOTAL |  | 0 | 0 | Nos:
6 | S/F cancealed tee stop cock of superior quality with crystal head ½” dia.
[7 empty] | 1 | x | 6 | x | 0 | x | 0 | x | 0 | = | 0 | 0
[15 empty] | TOTAL |  | 0 | 0 | Nos:
7 | P/F in position nyloon connections complete with 1/2” dia,
[7 empty] | 1 | x | 6 | x | 0 | x | 0 | x | 0 | = | 0 | 0
[15 empty] | TOTAL |  | 0 | 0 | Nos:
8 | S/F long bib cock of superior quality with crystal head 1/2” dia.
[7 empty] | 1 | x | 12 | x | 0 | x | 0 | x | 0 | = | 0 | 0
[15 empty] | TOTAL |  | 0 | 0 | Nos:
9 | P/F 6” x 2” or 6” x 3” C.I. floor trap of the approved selt cleaning design
[7 empty] | 1 | x | 7 | x | 0 | x | 0 | x | 0 | = | 0 | 0
[15 empty] | TOTAL |  | 0 | 0 | Nos:
10 | S/F swan type pillar cock of superior quality with crystal head 1/2" dia.
[7 empty] | 1 | x | 3 | x | 0 | x | 0 | x | 0 | = | 0 | 0
[15 empty] | TOTAL |  | 0 | 0 | Nos:
11 | Steel sink stainless sized 33” x 18” local make. (Standard Pattern)
[7 empty] | 1 | x | 1 | x | 0 | x | 0 | x | 0 | = | 0 | 0
[15 empty] | TOTAL |  | 0 | 0 | Nos:
12 | P/F 6” x 4” C.C gully trap with 4” out let complete with 4” thick
[7 empty] | 1 | x | 3 | x | 0 | x | 0 | x | 0 | = | 0 | 0
[15 empty] | TOTAL |  | 0 | 0 | Nos:
13 | Providing & fixing handle valve (China).
| (i) | ½” dia
[7 empty] | 1 | x | 3 | x | 0 | x | 0 | x | 0 | = | 0 | 0
[15 empty] | TOTAL |  | 0 | 0 | Nos:
| (ii) | ¾” dia
[7 empty] | 1 | x | 3 | x | 0 | x | 0 | x | 0 | = | 0 | 0
[15 empty] | TOTAL |  | 0 | 0 | Nos:
| (iii) | 1” dia
[7 empty] | 1 | x | 2 | x | 0 | x | 0 | x | 0 | = | 0 | 0
[15 empty] | TOTAL |  | 0 | 0 | Nos:
14 | Providing G.I. Pipe, specials and clamps etc, i/c fixing cutting
| (i) | ½” dia G.I.Pipe.
[7 empty] | 1 | x | 100 | x | 0 | x | 0 | x | 0 | = | 0 | 0
[15 empty] | TOTAL |  | 0 | 0 | Rft:
| (ii) | ¾” dia G.I Pipe
[7 empty] | 1 | x | 100 | x | 0 | x | 0 | x | 0 | = | 0 | 0
[15 empty] | TOTAL |  | 0 | 0 | Rft:
| (iii) | 1” dia G.I.Pipe.
[7 empty] | 1 | x | 90 | x | 0 | x | 0 | x | 0 | = | 0 | 0
[15 empty] | TOTAL |  | 0 | 0 | Rft:
15 | S/F Fiber glass tank of approved quality and design and all thickness
|  | 250 Gallons |  |  |  |  | 1 | x | 1 | x | 0 | x | 0 | x | 0 | = | 0 | 0
[15 empty] | TOTAL |  | 0 | 0 | Nos:
#REF!
1 | Providing, laying RCC pipe & collar of class ‘B’ and fixing
|  | 9" Dia |  |  |  |  | 1 | x | 50 | x | 0 | x | 0 | x | 0 | = | 0 | 0
[15 empty] | TOTAL |  | 0 | 0 | Rft:
2 | Constructing manhole or inspection chamber for the required diameter
[7 empty] | 1 | x | 4 | x | 0 | x | 0 | x | 0 | = | 0 | 0
[15 empty] | TOTAL |  | 0 | 0 | Nos:
SUB ENGINEER PROVINCIAL BUILDING SUB DIVISION SANGHAR | [11 empty] | ASSISTANT ENGINEER PROVINCIAL BUILDING SUB DIVISION SANGHAR