## Sheet1 (hidden)
|  | COMPLETED |  |  |  | Tender | Plot not | others | Approved | Funds | Expendt: | %Age of
Name of Sub-Sector | Approved | Upto | During | Advance | Initial | Under | received | Problem | Cost | Releases | During | Utilization | Upto
| Cost | 30-06-2000. | 2000-01 | Stage | Stage | Process |  |  |  | 2000-01 | 2000-01 | 2000-01 | 2005-07-01

## Sheet2 (2) (hidden)
STATEMENT SHOWING THE PHYSICAL / FINANCIAL POSITION OF M & R WORKS 2000-01
Education Works Division -II Karachi City Government
(Rs. in Million)
Sr.# | Name of Units | District | Estimated | Expenditure | Allocation 2000-01 |  |  | Expenditure 2000-01 |  | Anticipated | Total | Total | Physical Progress
|  |  | Cost | Upto | Upto | During | Total | Upto | Expenditure | Expenditure | Expenditure | Expenditure
|  |  |  | 30-06-2000. | 4/2001. | 5/2001. |  | 28-05-2001. | after | During | During | Since
[9 empty] | 28-05-2001. | June 2001. | 2000-01 | Start
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
[5 empty] | Funds Released |  | 3.83
1 | GBSS Happy Dale Nazim'd. | Central | 0.55 | 0 | 0 | 0 | 0 | 0.244 | 0 | 0 | 0.244 | 0.244 | Completed
2 | GBSS Jamia Tajia 15/A Buffar
| zone Zone North Karachi. | Central | 0.381 | 0 | 0 | 0 | 0 | 0.238 | 0 | 0 | 0.238 | 0.238 | Completed
3 | GBSS Happy Dale Nazimabad | Central | 0.358 | 0 | 0 | 0 | 0 | 0.209 | 0 | 0 | 0.209 | 0.209 | Completed
4 | Sir Syed Town 11/ G N'Kyc | Central | 0.496 | 0 | 0 | 0 | 0 | 0.46 | 0 | 0 | 0.46 | 0.46 | Completed
5 | GBSS Karachi Elemantry | Central | 0.142 | 0 | 0 | 0 | 0 | 0.094 | 0 | 0 | 0.094 | 0.094 | Completed
North Nazimabad Karachi
6 | GGSS 5/D New Karachi. | Central | 0.511 | 0 | 0 | 0 | 0 | 0.503 | 0 | 0 | 0.503 | 0.503 | Completed
7 | GGSS Relax Cinema Nazim'd | Central | 0.237 | 0 | 0 | 0 | 0 | 0.225 | 0 | 0 | 0.225 | 0.225 | Completed
| Total Secondary Edu: |  | 2.675 | 0 | 0 | 0 | 3.83 | 1.973 | 0 | 0 | 1.973 | 1.973
(Rs. in Million)
Sr.# | Name of Units | District | Estimated | Expenditure | Allocation 2000-01 |  |  | Expenditure 2000-01 |  | Anticipated | Total | Total | Physical Progress
|  |  | Cost | Upto | Upto | During | Total | Upto | Expenditure | Expenditure | Expenditure | Expenditure
|  |  |  | 30-06-2000. | 4/2001. | 5/2001. |  | 28-05-2001. | after | During | During | Since
[9 empty] | 28-05-2001. | June 2001. | 2000-01 | Start
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
COLLEGE EDUCATION
11 | Government College For | [11 empty] | Completed
| Men Nazimabad Karachi | Central | 0.397 | 0 | 0 | 0 | 0 | 0.35 | 0 | 0 | 0.35 | 0.35
12 | Govt. shipowner College North | [11 empty] | Completed
| Nazimabad Karachi. | Central | 0.485 | 0 | 0 | 0 | 0 | 0.43 | 0 | 0 | 0.43 | 0.43
13 | Govt. College For Women
| Nazimabad Karachi. | Central | 0.498 | 0 | 0 | 0 | 0 | 0.511 | 0 | 0 | 0.511 | 0.511 | Completed
completed
14 | ….do..( W/S & S/I) | Central | 0.22 | 0 | 0 | 0 | 0 | 0.221 | 0 | 0 | 0.221 | 0.221
| ….do..(Antitermite TreatmentI) | Central | 0.05 | 0 | 0 | 0 | 0 | 0.048 | 0 | 0 | 0.048 | 0.048 | completed
15 | …….do…. ( Gas Fitting ) | Central | 0.226 | 0 | 0 | 0 | 0 | 0.227 | 0 | 0 | 0.227 | 0.227 | Completed
16 | Govt. APWA College For
| Women F.B.Ara Karachi. | Central | 0.07 | 0 | 0 | 0 | 0 | 0.067 | 0 | 0 | 0.067 | 0.067 | Completed
(Barbad Wire)
| Total College Edu: |  | 1.946 | 0 | 0 | 0 | 0 | 1.854 | 0 | 0 | 1.854 | 1.854
| Grand Total Sec: + College |  | 4.621 | 0 | 0 | 0 | 3.83 | 3.827 | 0 | 0 | 3.827 | 3.827
DISTRICT OFFICER
EDUCATION WORKS DIVISON-II
KARACHI CITY GOVERNMENT

## Procurement Plan
REVISED PROCUREMENT PLAN
(WORKS, GOODS & SERVICES)
OFFICE OF THE EXECUTIVE ENGINEER, EDUCATION WORKS DIVISION-II, EDUCATION & LITERACY DEPARTMENT, GOVERNMENT OF SINDH KARACHI
FOR THE FINANCIAL YEAR 2015-2016
Sr. NO. / ADP NO: 2015-2016 | Description of Procurement | Quantity (Where Applicable) | Estimated Unit Cost (Where Applicable) | Estimated Total Cost | Funds Allocated | Source of Funds | Proposed Procurement Method | Balance Available | Timing of Procurements |  |  |  | Remarks
[9 empty] | 1st Qtr. | 2nd Qtr. | 3rd Qtr. | 4th Qtr.
1 | UP-GRADATION OF PRIMARY SCHOOL TO MIDDLE |  |  | 8.8 | 15 | ADP | Single
***/135 | SCHOOLS IN KARACHI DISTRICT MALIR KARACHI | [5 empty] | envelope
| @ GBPS HAJI RAZOO JOKHIO GADAP MALIR | [5 empty] | method
2 | UP-GRADATION OF PRIMARY SCHOOL TO MIDDLE |  |  | 8.8 | 15 | ADP | Single
***/135 | SCHOOLS IN KARACHI DISTRICT MALIR KARACHI | [5 empty] | envelope
| @ GBPS RAHOO GHORAN GADAP MALIR | [5 empty] | method
3 | UP-GRADATION OF PRIMARY SCHOOL TO MIDDLE |  |  | 8.8 | 15 | ADP | Single
***/135 | SCHOOLS IN KARACHI DISTRICT MALIR KARACHI | [5 empty] | envelope
| @ GBPS MUHAMMAD KHAN JOKHIO GADAP | [5 empty] | method
4 | UP-GRADATION OF PRIMARY SCHOOL TO MIDDLE |  |  | 8.8 | 15 | ADP | Single
***/135 | SCHOOLS IN KARACHI DISTRICT MALIR KARACHI | [5 empty] | envelope
| @ GBPS GUL HASSAN AMELANO GADAP MALIR | [5 empty] | method
5 | INTERVENTION FOR REHABILITATION OF EXISTING |  |  | 15 | 5 | ADP | Single
***/152 | ELEMENTARY COLLEGES IN KARACHI & SUKKUR | [5 empty] | envelope
| @ Elementary College for Women Hussainabad F.B.Area | [5 empty] | method
6 | REHABILITATION OF EXISTING HIGH SCHOOLS |  |  | 49.865 | 14 | ADP | Single
***/198 | & HIGHER SECONDARY SCHOOLS DISTRICT | [5 empty] | envelope
| KARACHI CENTRAL @ GGSS I.A.Bhai Block-20 F.B.Area | [5 empty] | method
7 | RE-CONSTRUCTION OF DANGEROUS ELEMENTARY/ |  |  | 47.305 | 14 | ADP | Single
***/201 | SECONDARY SCHOOLS IN DISTRICT KARACHI | [5 empty] | envelope
| CENTRAL @ I.A.B. G/B Elementary School Block-15 | [5 empty] | method
8 | IMPROVEMENT OF EXISTING PUBLIC SCHOOLS IN |  |  | 47.305 | 10 | ADP | Single
***/203 | KARACHI DIVISION | [5 empty] | envelope
| @ Public School & College Sir Syed Town 11/C North Kyc | [5 empty] | method
9 | REPAIR & RENOVATION OF EXISTING PRIMARY & |  |  | 60 | 15 | ADP | Single
***/211 | SECONDARY SCHOOLS (BOYS & GIRLS) AT | [5 empty] | envelope
| GULSHAN-E-IQBAL & NEW KARACHI TOWNS | [5 empty] | method
10 | RE-CONSTRUCTION OF DANGEROUS GBSS CAMP NO. 4 |  |  | 58.835 | 15 | ADP | Single
***/212 | & REPAIR OF GGSS CAMP NO. 5 PAF BASE FAISAL | [5 empty] | envelope
| @ GBSS Camp No. 4 & GGSS Camp No. 5 | [5 empty] | method
11 | COVERING OF DRAINAGE NALLA PASSING THROUGH |  |  | 46.711 | 50 | ADP | Single
***/213 | SINDH GOVT. SCHOOLS AT PAF BASE FAISAL KARACHI | [5 empty] | envelope
method
12 | REHABILITATION & PROVISION OF MISSING FACILITIES |  |  | 403.036 | 50 | ADP | Single
***/250 | IN EXISTING COLLEGES IN SINDH (17 Units) | [5 empty] | envelope
method
13 | REHABILITATION OF EXISTING COLLEGES @ GOVT. |  |  | 27.5 | 15 | ADP | Single
***/263 | DEGREE COLLEGE MALIR CANTT: GULSHAN'IQBAL | [5 empty] | envelope
| KARACHI (ADMINISTRATION BLOCK & ALLIED WORK) | [5 empty] | method
14 | REHABILITATION OF EXISTING COLLEGES @ GOVT. |  |  | 17 | 15 | ADP | Single
***/263 | GIRLS DEGREE COLLEGE SHAIKH ZAID GULSHAN | [5 empty] | envelope
| -E-IQBAL KARACHI (ALLIED WORK) | [5 empty] | method
15 | CONSTRUCTION/REPAIR/RAISING OF COMPOUND WALL |  |  | 118.27 | 10 | ADP | Single
***/276 | OF COLLEGES IN SINDH (SECURITY THREATENED | [5 empty] | envelope
| COLLEGES) (13 UNITS) | [5 empty] | method
16 | PROVISION OF SPORTS FACILITIES IN HIGH |  |  | 14.127 | 10 | ADP | Single
***/282 | SCHOOLS / COLLEGES OF KARACHI DIVISION | [5 empty] | envelope
| (5 UNITS) | [5 empty] | method
17 | CONSTRUCTION OF SCOUTING FACILITIES & ADMINIS- |  |  | 57.319 | 33.2 | ADP | Single
520/291 | TRATION BLOCK AT TRAINING CENTRE GULSHAN-E- | [5 empty] | envelope
| IQBAL & PROVISION OF MISSING FACILITIES AT | [5 empty] | method
PROVINCIAL SCOUTS SADDAR HEAD QUARTER
KARACHI (MAIN BUILDING, KITCHEN & STORE)
EXECUTIVE ENGINEER
EDUCATION WORKS DIVISION-II
KARACHI

## MP-Public Schools (hidden)
MONTHLY PROGRESS REPORT OF PUBLIC SCHOOL DISTRICT CENTRAL ( CITY DISTRICT GOVERNMENT KARACHI)
FOR THE MONTH OF " D E C E M B E R - 2 0 0 5 "
EDUCATION WORKS -II (WORKS & SERVICES DEPARTMETN )CITY DISTRICT GOVERNMENT KARACHI
Sr. No: | Category |  | Town | Approved Cost | Allocation | E X P E N D I T U R E |  |  |  | Physical | Actual
ADP # |  | Name of Scheme/ |  |  |  | Upto | During the | During the | Total | Progress | Date of
NON-ADP |  | Project / Location |  |  | 2005-06 | 6-2005. | Month | Year | Since | Remarks | Completion
2005-06 | [7 empty] | 2005-06 | Comme:
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 |  | NON-RESIDENTIAL | Revised>> | 48.38 | 11.5
I |  | Academic Block Higher | New Karachi
|  | Secondary ( XI-XII) |  | 3.673 | 0 | 7.638 | 0 | 0 | 7.638 | Completed | 2002-11-04
II |  | Secondary ( IX-X) |  | 3.649 | 0 | *** | *** | *** | *** | Completed
III |  | Compound Wall |  | 0.529 | 0 | 0.9 | 0 | 0 | 0.9 | Completed | 2002-03-14
2 |  | RESIDENTIAL
I |  | Principal Residence |  | 0.575 | 0 | 0 | 0 | 0 | 0 | Completed | 2002-08-16
II |  | Vice Principal Residence |  | 0.383 | 0 | 3.059 | 0 | 0 | 3.059 | Completed
III |  | Jr.staff Residence(A+B) |  | 1.067 | 0 | 0 | 0 | 0 | 0
3 |  | W/Supply & S/Installation
I |  | Academic Block |  | 0.591 | 0 | 0.339 | 0 | 0 | 0.339 | Completed
II |  | Principal Residence |  |  | 0 | 0.119 | 0 | 0 | 0.119 | Completed | 2002-08-19
III |  | Vice Principal Residence |  | 0.036 | 0 | 0.186 | 0 | 0 | 0.186 | Completed | 2002-08-19
4 |  | OTHER FACILITIES:
I |  | Gymnasium Hall |  | 2.747 | 0 | 6.698 | 0 | 0 | 6.698 | Squash Court & Side Portion roof laid B/Masonary &
Column above lintel level, Main Roof in Progress
II |  | Over Head Tank |  | 0.35 | 0 | 0.061 | 0 | 0 | 0.061 | Sepratly OHT for each Completed | 2002-06-14
III |  | Under Ground tank |  | 0.35 | 0 | 0.335 | 0 | 0 | 0.335 | Completed | 1999-01-13
IV |  | Auditorium |  | 1.7 | 0 | 2.81 | 1.707 | 1.707 | 4.517 | Plinth in Progress
V |  | Pump Room |  | 0.036 | 0 | 0 | 0 | 0 | 0 | Completed
VI |  | Clinic |  | 0.281 | 0 | 0.526 | 0 | 0 | 0.526 | Completed | 2002-10-29
VII |  | Ext: Deve: & Path Way |  | 0.22 | 0 | 2.359 | 0 | 0 | 2.359 | Completed | 2003-07-17
VIII |  | Cost of Land |  | 1 | 0 | 0 | 0 | 0 | 0 | Not Paid
5 |  | EXTRA COURRICULAR ACTIVITIES
I |  | Hockey Ground |  | 0.32 | 0 | 0.602 | 0 | 0 | 0.602 | Completed | 2002-08-07
II |  | Cricket Ground |  | 0.35 | 0 | 0.52 | 0 | 0 | 0.52 | Completed | 2002-11-08
III |  | Tennis Court |  | 0.14 | 0 | 0.377 | 0 | 0 | 0.377 | Completed | 2000-08-05
IV |  | Purchase of Funs |  | 0.145 | 0 | 0.146 | 0 | 0 | 0.146 | Completed
6 |  | MISCELLANCE
I |  | Counsultance Charges |  | 0.318 | 0 | 0.318 | 0 | 0 | 0.318
ii |  | Electric Works |  | 1.24 | 0 | 1.782 | 0 | 0 | 1.782
|  | (Transfer to Electrical Division) |  |  |  | 0.3 | 0 | 0 | 0.3
|  |  |  | 19.7 | 11.5 | 29.075 | 1.707 | 1.707 | 30.782
MONTHLY PROGRESS REPORT OF PUBLIC SCHOOL GADAP KARACHI
(Rs in Million )
Sr. No: | Category |  | Town | Approved Cost | Allocation | E X P E N D I T U R E |  |  |  | Physical | Actual
ADP # |  | Name of Scheme/ |  |  |  | Upto | During the | During the | Total | Progress | Date of
NON-ADP |  | Project / Location |  |  | 2005-06 | 6-2005. | Month | Year | Since | Remarks | Completion
2005-06 | [7 empty] | 2005-06 | Comme:
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
|  | PUBLIC SCHOOL GADAP | Revised >> | 87.785 | 9.3
1 |  | Secondary School ( VI - V ) | Gadap | 11.485
[5 empty] | 0 | 14.377 | 0 | 0 | 14.377 | Colouring Stage
2 |  | Higher Secondary School
3 |  | Hostel Block |  | 13.675 | [5 empty] | Colouring Stage
[5 empty] | 0 | 9.484 | 0 | 0 | 9.484
4 |  | Residential Block
5 |  | Gymnasium Hall |  | 0 | 0 | 0.742 | 0 | 0 | 0.742 | Plinth Level
6 |  | Over Head Tank |  | 1.4 | 0 | 1.435 | 0 | 0 | 1.435 | Pump room progress
7 |  | Compound Wall |  | 2.498 | 0 | 2.225 | 0 | 0 | 2.225 | Completed
8 |  | Auditorium Hall |  | 0 | 0 | 6.5 | 4.029 | 4.404 | 10.904 | Ver Roof Laid
9 |  | Clinic, Mini Market, & Etc |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 29.058 | 9.3 | 34.763 | 4.029 | 4.404 | 39.167
|  | TOTAL (PUBLIC SCHOOL CENTRAL) |  | 19.7 | 11.5 | 29.075 | 1.707 | 1.707 | 30.782
|  | TOTAL(PUBLIC SCHOOL GADAP) |  | 87.785 | 9.3 | 34.763 | 4.029 | 4.404 | 39.167
|  | Grand Total (Public School) |  | 107.485 | 20.8 | 63.838 | 5.736 | 6.111 | 69.949
DISTRICT OFFICER
EDUCATION WORKS -II (W & S DEPTT)
CITY DISTRICT GOVERNMENT KARACHI

## Weekly Report (hidden)
MONITORING OF CIVIL WORKS( WEEKLY REPORT)
Position as Stood on 2nd . Week of May-2001
Education Works Division-II Karachi City Government
Sr. No | Name of Sub-Sector | Total | Utilization | Utilization | Utilization | Financial | Utilization during | Target of Physical work | Progress | Remarks
|  | Allocation | Upto | Upto | Upto | Targets | 2nd. Week of |  | (Physical) | if any
|  |  | 2005-02-02 | 2005-03-02 | April-01 | for May-01 | May-2001. |  | visit of P.D
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
A | SOCIAL ACTION PROGRAMME
1 | Middle School Education. | 0.238 | 0.115 | 0.238 | 0.238 | 0 | 0
| Total Social Action Programme | 0.238 | 0.115 | 0.238 | 0.238 | 0 | 0
B | NON-SOCIAL ACTION PROGRAMME
2 | Secondary Education | #REF! | 3.021 | 5.246 | 6.755 | 0.8 | 0.567
3 | Technical Education | #REF! | 1.251 | 1.722 | 1.882 | 0.1 | 0.032
4 | College Education | #REF! | 6.202 | 10.117 | 13.153 | 1 | 0.742
5 | Education Administration | 0 | 0 | 0 | 0 | 0 | 0
| Total Non-Social Programme:- | #REF! | 10.474 | 17.085 | 21.79 | 1.9 | 1.341
C | OTHER PROGRAMME
6 | Public School (Under T.S.P) | 0 | 0 | 0 | 0 | 0 | 0
7 | Priority Programme | #REF! | 0.362 | 0.976 | 1.786 | 1 | 0.747
8 | M/R "6-314" for 2000-01 | 4.1 | 3.626 | 3.627 | 3.648 | 0.05 | 0
| Total (SAP) | #REF! | 3.988 | 4.603 | 5.434 | 1.05 | 0.747
| GRAND TOTAL:- | #REF! | 14.577 | 21.926 | 27.462 | 2.95 | 2.088
DISTRICT OFFICER
EDUCATION WORKS DIVISION-II
KARACHI CITY GOVERNMENT

## Prog ress Gymkhana (hidden)
STATEMENT SHOWING THE PROGRESS OF WORK @ HINDU GYMKHANA KARACHI
OF CULTURE & TOURISM DEPARTMENT GOVERNMENT OF SINDH ( DEPOSIT WORK)
Education Works Division-II Karachi City Government
Sr. # | Name of Scheme | Estimated Cost. |  | Funds Released | Released | Expenditure | Physical Progress | Remarks
|  | Original Cost | Ammended |  | Amount
/ Revised Cost
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
1 | Fiber Glass at Hindu | [5 empty] | I) RCC structure of Pavation completed | Refer this Office No: XEN/EWDC/Estt:/2000-01/
| Gymkhana Karachi | 1.066 | 1.49 |  |  | 0.909 |  | / 137 / Karachi dated:- 03-04-2001. Rs.. 0.490 (M) Wherein it was
|  |  |  | By PLS following |  |  |  | requested that Rs.0.490(M) are further required to complete the work.
|  |  |  | cheques:- |  |  | ii) Pavalion almost completed. | It is requested that the same may please be arranged and placed at the
|  |  |  | 1- Cheque No;16311/ |  |  |  | disposal of this office, so the work in question could be got completed
|  |  |  | 559273,dt:19-10-2000 Rs:- | 0.5 |  |  | at the earliest.
iii) Burnt Tile Flooring in front of Culture
Heritage Buildings completed.
2- Cheque No: 19373/
|  |  |  | 635801, dt:16-11-2000 Rs:- | 0.5 |  | iv) Temprary shad for accomodating
sweeper, completed.
| Total | 1.066 | 1.49 | *** | 1 | 0.909
DISTRICT OFFICER
EDUCATION WORKS DIVISION-II
KARACHI CITY GOVERNMENT

## Sheet3 (hidden)
DISTRICT / DIVISON WISE DEMAND / REQUIREMENT OF FUNDS FOR MAINTAINANCE & REPAIRS.
NAME OF DIVISION :- Education Works Division Central Karachi
Sr. No: | Name of Division | Description | Present | Final | EXCESS | SURRENDER | Remarks
|  |  | Allocation | Demand for
|  |  | for 2000-01 | 2000-01
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
1 | Education Works
Division Central Karachi
|  | S.A.P | 0 | 0 | 0 | 0
NON-S.A.P
a) A.O.R
|  |  | 4.73 | 3.83 | 0 | 0.9
b) S.R
|  | Total | 4.73 | 3.83 | 0 | 0.9
EXECUTIVE ENGINEER
EDUCATION WORKS DIVISION CENTRAL
KARACHI

## Meeting (hidden)
STATEMENT SHOWING THE FINANCIAL / PHYSICAL POSITION IN RESPECT OF DEVELOPMENT SCHEMES BEING EXECUTED BY
EDUCATION WORKS DIVISION CENTRAL KARACHI DURING 2001-02
Sr.# | Gategory | Name of Scheme / Location | taluka | District | Approved | Date of | Total | Amount | Amount | Physical Progress | Anticipated
ADP # |  |  |  |  | cost | Start | expenditure | Required for | Required for | Upto 30/6/2001 | Date of
[7 empty] | Upto June | Completion | Consumption |  | Compl:
2001
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
MIDDLE SCHOOL
1 | UP-GRADATION OF PRIMARY TO MIDDLE
811/617 | SCHOOL IN R/AREA KARACHI DISION (1990-91)
1 | GBPS | Chutta Gabol Karachi | Kyc | Central | 0.966 | 1996-12-24 | 0.989 | 0 | 0
|  | Total |  |  | 0.966 | *** | 0.989 | 0 | 0 | Completed & H/Over
2 | UP-GRADATION OF PRIMARY TO MIDDLE
821/626 | SCHOOL IN R/AREA KARACHI DISION (1992-93)
1 | GBPS | Khawasti Brohi. | Kyc | Central | 1.452 | 1999-04-16 | 1.157 | 0 | 0
|  | Total |  |  | 1.452 | *** | 1.157 | 0 | 0 | Completed & H/Over
3 | CONSTT:/RE-CONSTT: OF BUILDING FOR
825/630 | EXISTING MIDDLE SCHOOL ( 1990-91)
1 | GBLSS | Karachi Elemantry | Kyc | Central | 1.014 | 1995-10-06 | 1.183 | 0 | 0 | Completed & H/Over
2 | GBLSS | Moon Ligh 5/G-1 N/K | Kyc | Central | 1.014 | 1995-09-23 | 1.159 | 0 | 0 | Completed & H/Over
3 | GBLSS | 5/A Buffarzone N/K | Kyc | Central | 1.014 | 1995-10-07 | 0.975 | 0 | 0 | Completed & H/Over
4 | GBLSS | 11/E U.P Society | Kyc | Central | 1.014 | 1995-10-07 | 1.12 | 0.1 | 0.1 | Completed & H/Over
5 | GBLSS | Bright Grammar N/Naz: | Kyc | Central | 1.014 | 1995-10-07 | 1.111 | 0 | 0 | Completed & H/Over
6 | GBLSS | Zia-ul-Uloom Firdous Col | Kyc | Central | 1.014 | 1995-09-29 | 0.727 | 0 | 0 | Under Litigation lying abandoned at roof Level
7 | GBLSS | 5/G New Karachi. | Kyc | Central | 1.014 | 1995-10-02 | 1.098 | 0 | 0 | Completed & H/Over
|  | Total |  |  | 7.098 | *** | 7.373 | 0.1 | 0.1
4 | UP-GRADATION OF PRIMARY TO MIDDLE
833/638 | IN SINDH ( 1991-92)
1 | GBPS | 5/A-3, New Karachi | Kyc | Central | 2.195 | 1996-06-07 | 2.007 | 0 | 0 | Completed & H/Over
2 | GBPS | 5/G-1, New Karachi | Kyc | Central | 2.195 | 1995-06-09 | 0.814 | 1.71 | 1 | G/F Structure upto P/ Level
3 | GBPS | 5/D-1,New Karachi. | Kyc | Central | 2.195 | 1995-06-07 | 0.936 | 1.588 | 1 | G/F upto Structure Complete
4 | GBPS | 5/E-II, New Karachi. | Kyc | Central | 2.195 | 1996-06-17 | 0.794 | 1.73 | 1 | G/F upto Structure Complete
|  | Total |  |  | 8.78 | *** | 4.551 | 5.028 | 3 | (PC-1, Under Revision)
Works Lying abandoned
|  | Total Middle School |  |  | 18.296 | *** | 14.07 | 5.128 | 3.1 | due to non-availability of funds
|  | Grand Total Middle School |  |  | 18.296 | *** | 14.07 | 5.128 | 3.1
Sr.# | Gategory | Name of Scheme / Location | taluka | District | Approved | Date of | Total | Amount | Amount | Physical Progress | Anticipated
ADP # |  |  |  |  | cost | Start | expenditure | Required for | Required for | Upto 30/6/2001 | Date of
[7 empty] | Upto June | Completion | Consumption |  | Compl:
2001
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
SECONDARY EDUCATION
5 |  | UP-GRADATION OF MIDDLE SCHOOL
870/ 662 |  | TO HIGH SCHOOL(1991-92)
1 | GGPS | Wazir Jahan Karachi. | KYC | Central | 3.278 | 1999-04-17 | 3.685 | 0 | 0 | Completed & Handed Over
2 | GBLSS | Major Zia Uddin Memorial | KYC | Central | 3.278 | 1996-06-12 | 3.539 | 0 | 0 | Completed & Handed Over
[5 empty] | 6.556 | *** | 7.224 | 0 | 0
6 | CONSTT / RE-CONSTT: OF BUILDING
875/ 667 |  | FOR EXISTING HIGH SCHOOL (1988-89).
1 | GBPS | Block # 9 F.B area Kyc: | KYC | Central | 2.28 | 1993-05-14 | 2.577 | 0 | 0 | Completed & Handed Over
2 | GBSS | Green Land Premises | KYC | Central | 2.28 | 1993-05-11 | 2.241 | 0 | 0 | Completed & Handed Over
Happy Dale Nazim'd Kyc
3 | GGSS | Al Zohra Karachi. | KYC | Central | 2.28 | 1999-11-07 | 2.477 | 0 | 0 | Completed & Handed Over
4 | GBPS | Technical Age F.B.Area | KYC | Central | 2.28 | 1996-04-03 | 2.484 | 0 | 0 | Completed & Handed Over
(Shifted to Ibrahim Ali
Bhai B# 15 F.B.Area Kyc)
[5 empty] | 9.12 | *** | 9.779 | 0 | 0
7 | CONSTT/ RE-CONST:OF BUILDING
880/672 | FOR EXISTING SCHOOL KCY. (1991-92)
1 | GGSS | Mujeeb-un-Nisa Karachi | KYC | Central | 4.551 | *** | 4.489 | 0 | 0 | Completed & Handed Over
[5 empty] | 4.551 | *** | 4.489 | 0 | 0
8 |  | ADDITION OF C/ROOM IN EXIST:
885/ 675 |  | SCHOOL IN KARACHI (1991-92)
1 | GGSS | 5/B New Karachi 5 C/R | KYC | Central | 1.215 | 1996-06-07 | 1.24 | 0 | 0 | Completed & Handed Over
2 | SSHS | Liaquatabad No:3(3 C/R) | KYC | Central | 0.729 | 1996-05-05 | 0.586 | 0 | 0 | Completed & Handed Over
3 | GBSS | Liaquatabad No:2(3 C/R) | KYC | Central | 0.729 | 1996-06-07 | 0.772 | 0 | 0 | Completed & Handed Over
4 | GBSS | Liaquatabad No:3(3 C/R) | KYC | Central | 0.729 | 1996-07-15 | 0.8 | 0 | 0 | Completed & Handed Over
5 | GGSS | Liaquatabad No:2(3C/R) | KYC | Central | 0.729 | 1996-06-07 | 0.759 | 0 | 0 | Completed & Handed Over
[5 empty] | 4.131 | *** | 4.157 | 0 | 0
9 |  | ADD C/R IN EXISTING SECONDARY
887/677 | SCHOOL IN KARACHI (1992-93) (2 C/R)
1 | GGSS | F.C Area Karachi. | KYC | Central | 0.682 | *** | 0.115 | 0.6 | 0.6 | Structure Completed
2 | GGBS | Karachi Combridge No:1 | KYC | Central | 0.682 | 2003-12-14 | 0.493 | 0 | 0 | Completed & Handed Over
[5 empty] | 1.364 | *** | 0.608 | 0.6 | 0.6
Sr.# | Gategory | Name of Scheme / Location | Taluka | District | Approved | Date of | Total | Amount | Amount | Physical Progress | Anticipated
ADP # |  |  |  |  | cost | Start | expenditure | Required for | Required for | Upto 30/6/2001 | Date of
[7 empty] | Upto June | Completion | Consumption |  | Compl:
2001
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
10 |  | OPENING OF DOUBLE SECTION HGH SCHOOL
890/ 680 |  | IN SINDH KARACHI DIVISION (1991-92)
1 |  | 5/A North Karachi. | KYC | Central | 6.342 | 1996-06-11 | 5.983 | 0 | 0 | Completed & H/Over
2 |  | 11/B North Karachi. | KYC | Central | 6.342 | 2004-06-15 | 4.353 | 2.9 | 2 | Plastering in Progress
[5 empty] | 12.684 | *** | 10.336 | 2.9 | 2
11 |  | INTRODUCTION / ADD: OF XI-XII CLASSES IN EXISTING
906/ 696 |  | HIGH SECONDARY SCHOOL IN SINDH ( 1991-92)
1 | GGSS | Liaquatabad No:4, | KYC | Central | 3.97 | 1996-06-26 | 3.055 | 1.5 | 1 | Ground Floor Completed
2 | GBSS | Liaquatabad No:4, | KYC | Central | 3.97 | 1996-06-23 | 1.371 | 3.194 | 1 | Work lying due to non availability of Funds
3 | GGSS | Ishat-ul-Quran Nazim'd | KYC | Central | 3.97 | 1997-06-24 | 2.937 | 1.628 | 1 | Work lying abondend at plaster Stage
[5 empty] | 11.91 | *** | 7.363 | 6.322 | 3 | (PC-1 is Under Revision)
12 |  | UP-GRADATION OF MIDDLE TO
915/703 |  | HIGH SCHOOL IN R/AREA (1994-95)
1 | GBLSS | District Council 11/D N/K | KYC | Central | 2.479 | 2004-06-14 | 1.676 | 0.6 | 0.6 | Colouring in Progress
2 | GBLSS | 11/E New Karachi. | KYC | Central | 2.759 | 2004-06-14 | 1.726 | 0.8 | 0.8 | Colouring in Progress
[5 empty] | 5.238 | *** | 3.402 | 1.4 | 1.4
13 |  | ADDITION C/R IN EXISTING
919/706 |  | HIGH SCHOOL IN SINDH(1994-95)
1 | GGSS | Dastagir No:9 F.B.Area (4 C/R) | KYC | Central | 1.06 | *** | 0 | 1.219 | 1 | Foundaion in Progress
2 | GHSS | Ibrahim Ali Bhai F.B.Area (4 C/R) | KYC | Central | 1.06 | *** | 0.095 | 1.124 | 1 | Plinth work in Progress
3 | GBSS | Sitar-e-Hydri 11/D North | KYC | Central | 0.53 | 2003-12-16 | 0.494 | 0.115 | 0.115 | Colouring in Progress
Karachi ( 2C/Room )
4 | GGSS | Allama Iqbal Block # 16 | KYC | Central | 0.53 | 2003-12-08 | 0.483 | 0.126 | 0.126 | Completed & Handedover
F.B.Area Kyc (2 C/Room)
[5 empty] | 3.18 | *** | 1.072 | 2.584 | 2.241
| Grand Total Secondary School |  |  |  | 38.358 | *** | 27.57 | 13.206 | 8.641
14
976/762 |  | TECHNICAL EDUCATION | KYC | Central | 56.37 | *** | 50.039 | 1 | 1 | Demanded Only GOS Share
| Total Techincal Educaiton |  |  |  | 56.37 | *** | 50.039 | 1 | 1
Sr.# | Gategory | Name of Scheme / Location | Taluka | District | Approved | Date of | Total | Amount | Amount | Physical Progress | Anticipated
ADP # |  |  |  |  | cost | Start | expenditure | Required for | Required for | Upto 30/6/2001 | Date of
[7 empty] | Upto June | Completion | Consumption |  | Compl:
2001
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
COLLEGE EDUCATION.
1) 1016 | OPENING OF GOVT:DEGREE GIRLS COLLEGE | [8 empty] | Phase-I &II, Completed & H/Over
802 | GIRLS COLLEGE NEW KARACHI. |  | KYC | Central | 21.957 | 02/0393 | 21.632 | 0.2 | 0.2 | Phase-III, Completed ready to Handedover
2) 1017 | UP-GRADATION OF GOVERNMENT COLLEGE FOR
803 | WOMEN NAZIMABAD.
| (Addition of B.Sc. Classes) |  | KYC | Central | 4.174 | 1996-04-17 | 4.792 | 0 | 0 | Completed & Handedover
3) 1031 | OPENING OF GOVERNMENT DEGREE
817 | COLLEGE IN ARTS & SCIENCE
| Boys | @ New Karachi | KYC | Central | 22.149 | 1997-05-29 | 20.314 | 1 | 1 | , Completed ready to Handedover
4) 1033 | ESTABLISHMENT GOVERNMENT DEGREE COLLEGE
819 | @ LIAQUATABAD NO: (5) Near KMC | [8 empty] | Phase-I Almost Completed
| Park Karachi.Shifted to F.B.Area | [8 empty] | Phase-II, ……..do……..
| Block # 1, Karachi. |  | KYC | Central | 23.289 | 2002-10-01 | 9.438 | 13.851 | 6.5 | Phase-III, S/Structure Completed
5) 1046 | IMPROVEMENT OF RAIZ GOVT: | [8 empty] | Completed & Handedover
832 | GIRLS COLLEGE @ Liaquatabad #10 |  | KYC | Central | 8.701 | 1999-05-31 | 8.314 | 0 | 0 | Completed & Handedover
6) 1065 | CONSTT: OF GOVT DEGREE | [8 empty] | Completed ready to Handedover
851 | COLLEGE @ Buffarzone N'Karachi. |  | KYC | Central | 11.713 | 1996-08-23 | 12.119 | 0.1 | 0.1
7) 1066 | CONSTRUCTION OF GOVT:
852 | DEGREE COLLEGE at F.B. Area. |  | KYC | Central | 11.713 | 1996-11-27 | 11.974 | 0.1 | 0.1 | Completed ready to Handedover
8) 1069 | ESTABLISHEMNT OF DEGREE COLLEGE | [8 empty] | Phase-I, Completed
855 | @Shaheed-e- Millat Azizabad | [8 empty] | Phase-II, Colouring in progress
| Federal ".B".Area Karachi. |  | KYC | Central | 30.672 | 2001-09-08 | 19.325 | 15.94 | 10 | Phase-III, Flooring in Progresss
|  | Total College |  |  | 134.368 | *** | 107.908 | 31.191 | 17.9
SPECIAL PRIORITY PROGRAMME
Sr.# | Gategory | Name of Scheme / Location | taluka | District | Approved | Date of | Total | Amount | Amount | Physical Progress | Anticipated
[5 empty] | cost | Start | expenditure | Required for | Required for | Upto 30/6/2001 | Date of
[7 empty] | Upto June | Completion | Consumption |  | Compl:
2001
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
( I ) | UP-GRADATION OF PRIMARY TO
MIDDLE SCHOOL IN KARACHI
MR. KHALID BIN WALEED ( MPA)
1 | GBPS | Sector 5/C-2, N/K. | Kyc | Central | 3.562 | 2002-10-17 | 1.148 | 2.9483 | 1.5 | G/Floor Roof slab Completed
2 | GBPS | 5/B-2, N' Karachi. | Kyc | Central | 3.562 | 2002-10-18 | 1.956 | 2.1403 | 1.5 | F/Floor Roof slab Completed
MR. WAKEEL AHMED JAMALI.
3 | GBPS | Allama Iqbal Bl-16,F.B.Area | Kyc | Central | 3.562 | 2002-10-18 | 1.115 | 2.9813 | 1.5 | S/S F/Floor roof Completed
4 | GGPS | Kamyab Bl-15,F.B.Area | Kyc | Central | 3.562 | 2002-10-18 | 1.742 | 2.3543 | 1 | Structure Completed
MR: AHSAN ULLAH KHAN (MPA)
5 | GBPS | Liaquatabad No 4 Karachi. | Kyc | Central | 3.562 | 2002-10-21 | 0.704 | 3.3923 | 1.5 | Completed upto Lintel Level
|  | Total ( I ) |  |  | 17.81 | *** | 6.665 | 13.8165 | 7
( II ) | UP-GRADATION OF MIDDLE TO
HIGH SCHOOL IN KARACHI DIV:
MR. KHALID BIN WALEED ( MPA)
6 | GBLSS | 5/G Moon Light N'Karachi | Kyc | Central | 3.964 | 2002-08-05 | 1.511 | 3.0476 | 1.5 | Structure Completed
|  | Total ( II ) |  |  | 3.964 | *** | 1.511 | 3.0476 | 1.5
( III ) | ESTABLISHMENT OF SINGLE
SECTION HIGH SCHOOL IN U/AREA
MR: MUHAMMAD YOUSAF ( MPA)
7 |  | Opening of Single Section High | Kyc | Central | 4.189 | 2002-10-07 | 2.35 | 2.4674 | 1.5 | Structure Completed
School @ Bufar Zone
|  | Total ( III ) |  |  | 4.189 | *** | 2.35 | 2.4674 | 1.5
Sr.# | Gategory | Name of Scheme / Location | Taluka | District | Approved | Date of | Total | Amount | Amount | Physical Progress | Anticipated
[5 empty] | cost | Start | expenditure | Required for | Required for | Upto 30/6/2001 | Date of
[7 empty] | Upto June | Completion | Consumption |  | Compl:
2001
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
( IV ) | ADDITION OF CLASS ROOM IN
EXISTING SECONDARY SCHOOL
IN URBAN AREA KARACHI.
MR. WAKEEL AHMED JAMALI.
8 | GBSS | Allama Iqbal F.B.Area | Kyc | Central | 1.16 | 2002-07-31 | 0.263 | 1.071 | 1 | F/Floor Roof completed
( 4 Class Rooms)
9 | GBSS | New Method F.B.Area | Kyc | Central | 1.16 | 2002-08-06 | 0.687 | 0.647 | 0.647 | Roof slab Completed
( 4 Class Rooms)
10 | GBSS | Anglo Oriential Block-15, | Kyc | Central | 1.45 | 2002-08-07 | 0.944 | 0.7235 | 0.7 | Roof slab Completed
F.B.Area Karachi.( 5 C/Room)
MR: MUHAMMAD YOUSAF ( MPA)
11 | GGSS | Hyderi North Nazimabad | Kyc | Central | 1.45 | 2002-08-02 | 0.716 | 0.9515 | 9 | Roof Slab Completed
( 5 Class Rooms )
12 | GBSS | 5/A-3, New Karachi. | Kyc | Central | 1.45 | 2002-08-07 | 0.351 | 1.3165 | 1 | Upto Plinth Level
( 5 Class Rooms )
MR: AHSAN ULLAH KHAN (MPA)
13 | GGSS | Liaquatabad No:4 Karachi. | Kyc | Central | 0.87 | 2002-08-02 | 0.426 | 0.5745 | 0.574 | Colouring in Progress
( 3 Class Rooms )
14 | GBSS | Liaquatbad No:4 Karachi. | Kyc | Central | 1.16 | 2002-08-03 | 1.37 | 0 | 0 | Completed & Handed
( 4 Class Rooms )
|  | Total ( IV ) |  |  | 8.7 | *** | 4.757 | 5.284 | 12.921
( V ) | INTRODUCTION OF XI & XII IN
EXISTING ( B & G ) SECONDARY
SCHOOL IN URBAN AREA KYC.
MR. KHALID BIN WALEED ( MPA)
15 | GBSS | APWA 5/E New Karachi. | Kyc | Central | 7 | 2002-10-14 | 2.717 | 5.333 | 2 | Roof partly laid
|  | Total ( V ) |  |  | 7 | *** | 2.717 | 5.333 | 2
Sr.# | Gategory | Name of Scheme / Location | taluka | District | Approved | Date of | Total | Amount | Amount | Physical Progress | Anticipated
[5 empty] | cost | Start | expenditure | Required for | Required for | Upto 30/6/2001 | Date of
[7 empty] | Upto June | Completion | Consumption |  | Compl:
2001
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
( VI ) | ESTABLISHMENT/ OPENING OF
GOVERNMENT DEGREE COLLEGE
MR: MUHAMMAD YOUSAF ( MPA)
16 |  | North Karachi. | Kyc | Central | 26.098 | 2002-10-14 | 8 | 22.0127 | 5 | Ph: I Finishing in Progress
|  | MR: BASHIR FAROOQI ( MPA ) | [7 empty] | Ph:II, Foundation in Progress
17 |  | North Nazimabad | Kyc | Central | 26.098 | 2002-10-14 | 4.4 | 25.6127 | 5
|  | Total ( VI ) |  |  | 52.196 | *** | 12.4 | 47.6254 | 10 | Ph: I Structure in Progress
( VII ) | ADDITION OF CLASS ROOM IN | [8 empty] | G/F Plaster in progress
EXISTING GOVERNMENT COLLEGE
MR. WAKEEL AHMED JAMALI.
18 |  | Govt Girls Inter College | Kyc | Central | 1.133 | 2002-08-07 | 1.093 | 0.20995 | 0 | Completed
Block 16, F.B.Area
Karachi.( 2 C/Rooms)
MR: BASHIR FAROOQI ( MPA )
19 |  | Govt: Jinnah College Karachi. | Kyc | Central | 2.267 | 2002-08-05 | 2.174 | 0.43305 | 0 | Completed
( 4 Class Rooms)
20 |  | Abdullah Govt:College for | Kyc | Central | 2.267 | 2002-08-05 | 2.174 | 0 | 0 | Completed & Handedover
Women ( 4 Class Rooms )
21 |  | Govt Inter College North | Kyc | Central | 1.133 | *** | 1.093 | 0.20995 | 0 | Completed & Handedover
Nazimabad (2 C/ Rooms )
|  | Total ( VII ) |  |  | 6.8 | *** | 6.534 | 0.85295 | 0
(VIII ) | ADDITION OF COMPUTER CLASSES
MR. KHALID BIN WALEED ( MPA)
22 |  | Mujeeb-un-Nisa Govt Girls | Kyc | Central | 2.394 | 2002-07-08 | 1.437 | 1.3161 | 1 | Roof Slab Completed
college New Kyc.
MR: AFZAL ANWAR ( MPA)
23 |  | Sir Syed Govt college | Kyc | Central | 2.394 | 2002-08-02 | 1.418 | 1.3351 | 0 | completed
|  | Total ( VIII ) |  |  | 4.788 | *** | 2.855 | 2.6512 | 1
(IX) | ADDITION/ IMPROVEMENT OF DEGREE COLLEGE.
MR: AFZAL ANWAR ( MPA)
24 |  | Sir Syed Govt: Degree | Kyc | Central | 12.848 | 2002-10-09 | 3.65 | 11.1252 | 1 | A) Science Lab Stru: Compl:
|  | College Nazimabad (Ph-I) | [7 empty] | B) Addition of (8) C/Room
G/floor roof Liad
|  | Total ( IX ) |  |  | 12.848 | *** | 3.65 | 11.1252 | 1
Sr.# | Gategory | Name of Scheme / Location | taluka | District | Approved | Date of | Total | Amount | Amount | Physical Progress | Anticipated
[5 empty] | cost | Start | expenditure | Required for | Required for | Upto 30/6/2001 | Date of
[7 empty] | Upto June | Completion | Consumption |  | Compl:
2001
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
( X ) | ESTABLISHMENT OF MONOTECHIC INSTITUTE
AT DISTRICT CENTRAL KARACHI.
MR. WAKEEL AHMED JAMALI.
25 |  | F.B Area (Phase-I) | Kyc | Central | 21.38 | 2002-10-28 | 3.881 | 20.706 | 5 | Finishing in Progress
MR: AFZAL ANWAR ( MPA)
26 |  | Liaquatabad.(Phase-I) | Kyc | Central | 21.38 | *** | 0 | 0 | 0 | Foundation in progress
|  | Total ( X ) |  |  | 42.76 | *** | 3.881 | 20.706 | 5
( XI ) | UP-GRADATION OF SAIFEE EIDEE
ZAHABI INSTITUTE OF TECH: TO
B. TECH: LEVEL KARACHI.
MR: BASHIR FAROOQI ( MPA )
|  | North Nazimabad Karachi | Kyc | Central | 11.913 | 2002-10-20 | 4.095 | 9.605 | 2 | Phase-I Plaster in porgress
Phase-II, Partly Roof Laid
| Total ( XI ) |  |  |  | 11.913 | *** | 4.095 | 9.605 | 2
|  | Grand Total |  |  | 79.109 | *** | 21.015 | 44.9403 | 9
SHELTTERLESS SCHOOL PROGRMME
Sr.# | Gategory | Name of Scheme / Location | Taluka | District | Approved | Date of | Total | Amount | Amount | Physical Progress | Anticipated
[5 empty] | cost | Start | expenditure | Required for | Required for | Upto 30/6/2001 | Date of
[7 empty] | Upto June | Completion | Consumption |  | Compl:
2001
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Construction of Building for Exisitng
Shelterless Primary School in U/Area
of Karachi Division (S.A.P.)
1 | GBPS | Full Bright Block-16, Sohrab Goth | Karachi | Central | 1.917 | *** | 0 | 1.917 | 1.917 | Tender under process | ***
F.B.Area Karachi
2 | GBPS | Godra Muslim Anjam 11/F N ' kyc | Karachi | Central | 1.917 | *** | 0 | 1.917 | 1.917 | Tender under process | ***
3 | GBPS | 15/B North Karachi
4 | GBMSQS | Rehmani Sector No: 4 North Kyc | Karachi | Central | 1.917 | *** | 0 | 1.917 | 1.917 | Tender under process | ***
5 | GBMSQS | Siddique Sector 5/G New Kyc | Karachi | Central | 1.917 | *** | 0 | 1.917 | 1.917 | Tender under process | ***
6 | GBMSQS | Siddique Sector 5/G New Kyc | Karachi | Central | 1.917 | *** | 0 | 1.917 | 1.917 | Tender under process | ***
7 | GBMSQS | Chishtia Sector 1/A-3, Khuwaja | Karachi | Central | 1.917 | *** | 0 | 1.917 | 1.917 | Tender under process | ***
Ajmair Nagri North Karachi
8 | GBPS | New Era Dastagir No:9, F.B.Area | Karachi | Central | 1.917 | *** | 0 | 1.917 | 1.917 | Tender under process | ***
9 | GBPS | 7/D-3, North Karachi. | Karachi | Central | 1.917 | *** | 0 | 1.917 | 1.917 | Tender under process | ***
10 | GBPS | J/M Quba Block-22, Shafique | Karachi | Central | 1.917 | *** | 0 | 1.917 | 1.917 | Tender under process | ***
Colony F.B.Area
11 | GBMSQS | Bilal 5/G New Karachi | Karachi | Central | 1.917 | *** | 0 | 1.917 | 1.917 | Tender under process | ***
|  |  | Total |  | 19.17 | 0 | 0 | 19.17 | 19.17
Consolidation / Improvement of Building
in Existing Middle School in Sindh (2000-01)
12 | GBLSS | Atta Turk F.B.area Karachi | Karachi | Central | 2.608 | *** | 0 | 2.608 | 2.608 | Tender under process | ***
13 | GBLSS | Brighter Grammer, North Nazimabad | Karachi | Central | 2.608 | *** | 0 | 2.608 | 2.608 | Tender under process | ***
14 | GBLSS | Farzana 5/D New Kyc@ 5/A-3, N'Kyc | Karachi | Central | 2.608 | *** | 0 | 2.608 | 2.608 | Tender under process | ***
15 | GBLSS | Little Angle 11/E U.P Society Karachi | Karachi | Central | 2.608 | *** | 0 | 2.608 | 2.608 | Tender under process | ***
16 | GBLSS | My Ideal North Nazimabad Karachi | Karachi | Central | 2.608 | *** | 0 | 2.608 | 2.608 | Tender under process | ***
|  |  | Total |  | 13.04 | 0 | 0 | 13.04 | 13.04
TARGET TO BE ACHIVED DURING THE YEAR 2001-02
|  |  | Sr.# | Gategory | Name of Scheme / Location | taluka | District
ADP #
|  |  | 1 | 2 | 3 | 4 | 5
|  |  | 1 |  | ADD C/R IN EXISTING SECONDARY
|  |  | 887/677 | SCHOOL IN KARACHI (1992-93) (2 C/R)
|  |  | 1 | GGSS | F.C Area Karachi. | KYC | Central
|  |  | 2 |  | OPENING OF DOUBLE SECTION HGH SCHOOL
|  |  | 890/ 680 |  | IN SINDH KARACHI DIVISION (1991-92)
|  |  | 1 |  | 11/B North Karachi. | KYC | Central
|  |  | 3 |  | INTRODUCTION / ADD: OF XI-XII CLASSES IN EXISTING
|  |  | 906/ 696 |  | HIGH SECONDARY SCHOOL IN SINDH ( 1991-92)
|  |  | 1 | GGSS | Liaquatabad No:4, | KYC | Central
|  |  | 4 |  | UP-GRADATION OF MIDDLE TO
|  |  | 915/703 |  | HIGH SCHOOL IN R/AREA (1994-95)
|  |  | 1 | GBLSS | District Council 11/D N/K | KYC | Central
|  |  | 2 | GBLSS | 11/E New Karachi. | KYC | Central
|  |  | 5 |  | ADDITION C/R IN EXISTING
|  |  | 919/706 |  | HIGH SCHOOL IN SINDH(1994-95)
|  |  | 1 | GGSS | Dastagir No:9 F.B.Area (4 C/R) | KYC | Central
|  |  | 2 | GHSS | Ibrahim Ali Bhai F.B.Area (4 C/R) | KYC | Central
14
|  |  | 976/762 | Estt: of Women Poly technic Institute | Estt: of Women Poly Technic | KYC | Central
F.B.Area Karachi
|  |  | Sr.# | Gategory | Name of Scheme / Location | taluka | District
ADP #
|  |  | 1 | 2 | 3 | 4 | 5
COLLEGE EDUCATION.
|  |  | 1) 1031 | OPENING OF GOVERNMENT DEGREE
|  |  | 817 | COLLEGE IN ARTS & SCIENCE
|  |  |  | Boys | @ New Karachi | KYC | Central
|  |  | 2) 1033 | ESTABLISHMENT GOVERNMENT DEGREE COLLEGE
|  |  | 819 | @ LIAQUATABAD NO: (5) Near KMC
|  |  |  | Park Karachi.Shifted to F.B.Area Block # 1 Kyc: |  | KYC | Central
|  |  | 3) 1069 | ESTABLISHEMNT OF DEGREE COLLEGE
|  |  | 855 | @Shaheed-e- Millat Azizabad
|  |  |  | Federal ".B".Area Karachi. |  | KYC | Central
PRIORITY PROGRAMME
|  |  | ( I ) | UP-GRADATION OF PRIMARY TO
MIDDLE SCHOOL IN KARACHI
MR. KHALID BIN WALEED ( MPA)
|  |  | 1 | GBPS | Sector 5/C-2, N/K. | Kyc | Central
|  |  | 2 | GBPS | 5/B-2, N' Karachi. | Kyc | Central
|  |  | ( II ) | UP-GRADATION OF MIDDLE TO
HIGH SCHOOL IN KARACHI DIV:
MR. KHALID BIN WALEED ( MPA)
|  |  | 3 | GBLSS | 5/G Moon Light N'Karachi | Kyc | Central
|  |  | ( III ) | ESTABLISHMENT OF SINGLE
SECTION HIGH SCHOOL IN U/AREA
MR: MUHAMMAD YOUSAF ( MPA)
|  |  | 4 |  | Opening of Single Section High | Kyc | Central
School @ Bufar Zone
|  |  | Sr.# | Gategory | Name of Scheme / Location | Taluka | District
|  |  | 1 | 2 | 3 | 4 | 5
|  |  | ( IV ) | ADDITION OF CLASS ROOM IN
EXISTING SECONDARY SCHOOL
IN URBAN AREA KARACHI.
MR. WAKEEL AHMED JAMALI.
|  |  | 5 | GBSS | Anglo Oriential Block-15, | Kyc | Central
F.B.Area Karachi.( 5 C/Room)
MR: MUHAMMAD YOUSAF ( MPA)
|  |  | 6 | GGSS | Hyderi North Nazimabad | Kyc | Central
( 5 Class Rooms )
MR: AHSAN ULLAH KHAN (MPA)
|  |  | 7 | GGSS | Liaquatabad No:4 Karachi. | Kyc | Central
( 3 Class Rooms )
|  |  | ( V ) | INTRODUCTION OF XI & XII IN
EXISTING ( B & G ) SECONDARY
SCHOOL IN URBAN AREA KYC.
MR. KHALID BIN WALEED ( MPA)
|  |  | 8 | GBSS | APWA 5/E New Karachi. | Kyc | Central
|  |  | ( VI ) | ESTABLISHMENT/ OPENING OF
GOVERNMENT DEGREE COLLEGE
MR: MUHAMMAD YOUSAF ( MPA)
|  |  | 9 |  | North Karachi. | Kyc | Central
MR: BASHIR FAROOQI ( MPA )
|  |  | 10 |  | North Nazimabad | Kyc | Central
|  |  | (VIII ) | ADDITION OF COMPUTER CLASSES
MR. KHALID BIN WALEED ( MPA)
|  |  | 11 |  | Mujeeb-un-Nisa Govt Girls | Kyc | Central
college New Kyc.
MR: AFZAL ANWAR ( MPA)
|  |  | 12 |  | Sir Syed Govt college | Kyc | Central
Total ( VIII )
|  |  | Sr.# | Gategory | Name of Scheme / Location | Taluka | District
|  |  | 1 | 2 | 3 | 4 | 5
|  |  | (IX) | ADDITION/ IMPROVEMENT OF DEGREE COLLEGE.
MR: AFZAL ANWAR ( MPA)
|  |  | 13 |  | Sir Syed Govt: Degree | Kyc | Central
College Nazimabad (Ph-I)
|  |  | ( X ) | ESTABLISHMENT OF MONOTECHIC INSTITUTE
AT DISTRICT CENTRAL KARACHI.
MR: AFZAL ANWAR ( MPA)
|  |  | 14 |  | Liaquatabad.(Phase-I) | Kyc | Central

## MP-ADP (2) (hidden)
MONTHLY PROGRESS REPORT IN RESPECT OF A.D.P. SCHEMES 2001-02
EDUCATION WORKS DIVISION-II KARACHI CITY GOVERNMENT
FOR THE MONTH OF OCTOBER-2001
<<Page1>>
Rs. In Million
| Category |  | Approved Sanctioned |  |  | Allocation | Released | E X P E N D I T U R E |  |  |  | C O N T R E C T |  | Actual | Period of | Reasons | Physical | Actual
ADP # |  | Name of Scheme/ | District | Cost | Date | 2000-01 | 2001-02 | Upto | During the | During the | Total | No | Date | Date of | Completion | of Dely of | Progress | Date of
2001-02 |  | Project / Location |  |  |  | Original |  | 6-2001. | Month | Year | Since |  |  | Start | as per | Work | Remarks | Completion
[6 empty] | Modified |  |  |  | 2001-02 | Comme: |  |  |  | Workorder
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
MIDDLE SCHOOL
S.A.P (Provincial)
1 | UP-GRADATION OF PRIMARY TO MIDDLE
617 / 88 | SCHOOL IN R/AREA KARACHI DISION (1990-91) | [5 empty] | 0
1 | GBPS | Chutta Gabol Karachi | Kyc | 0.966 | 0 | 0 |  | 0.989 | 0 | 0 | 0.989 | 590 | 17/12/92. | 1996-12-24 | 24 Months | *** | Completed & H/Over | 1998-10-03
|  | Total |  | 0.966 | 0 | 0 | 0 | 0.989 | 0 | 0 | 0.989 | *** | *** | *** | *** | ***
2 | CONSTT:/RE-CONSTT: OF BUILDING FOR
630/ 90 | EXISTING MIDDLE SCHOOL ( 1990-91) | [5 empty] | 0
1 | GBLSS | Karachi Elemantry | Kyc | 1.014 | 0 | 0 | 0 | 1.183 | 0 | 0 | 1.183 | 416 | 29/9/91. | 1995-10-06 | 9 Months | *** | Completed & H/Over | 14/01/96.
2 | GBLSS | Moon Ligh 5/G-1 N/K | Kyc | 1.014 | 0 | 0 | 0 | 1.159 | 0 | 0 | 1.159 | 409 | 1995-09-22 | 1995-09-23 | 8 Months | *** | Completed & H/Over | 1996-08-22
3 | GBLSS | 5/A Buffarzone N/K | Kyc | 1.014 | 0 | 0 | 0 | 0.975 | 0 | 0 | 0.975 | 242 | 1995-10-01 | 1995-10-07 | 8 Months | *** | Completed & H/Over | 1996-07-02
4 | GBLSS | 11/E U.P Society | Kyc | 1.014 | 0 | 0 | 0 | 1.12 | 0 | 0 | 1.12 | *** | *** | 1995-10-07 | 8 Months | *** | Completed & H/Over | 2005-04-14
5 | GBLSS | Bright Grammar N/Naz: | Kyc | 1.014 | 0 | 0 | 0 | 1.111 | 0 | 0 | 1.111 | 426 | 30/9/91. | 1995-10-07 | 9 Months | *** | Completed & H/Over | 09/07/99.
6 | GBLSS | Zia-ul-Uloom Firdous Col | Kyc | 1.014 | 0 | 0 | 0 | 0.727 | 0 | 0 | 0.727 | 417 | 1995-09-27 | 1995-09-29 | 8 Months | *** | Under Litigation lying abandoned at roof Level
7 | GBLSS | 5/G New Karachi. | Kyc | 1.014 | 0 | 0 | 0 | 1.098 | 0 | 0 | 1.098 | 412 | 1997-09-26 | 1995-10-02 | 8 Months | *** | Completed & H/Over | 2004-03-31
|  | Total |  | 7.098 | 0 | 0 | 0 | 7.373 | 0 | 0 | 7.373 | *** | *** | *** | *** | ***
3 | UP-GRADATION OF PRIMARY TO MIDDLE
638/91 | IN SINDH ( 1991-92) |  |  |  |  | 0 | 0
1 | GBPS | 5/A-3, New Karachi | Kyc | 2.195 | 0 | 0 | 0 | 2.007 | 0 | 0 | 2.007 | 594 | 1996-06-01 | 1996-06-07 | 12 Months | *** | Completed & H/Over | 2005-04-14
2 | GBPS | 5/G-1, New Karachi | Kyc | 2.195 | 0 | 0 | 0 | 0.814 | 0 | 0 | 0.814 | 603 | 1996-06-03 | 1996-06-09 | 12 Months | *** | G/F Structure upto P/ Level | ***
3 | GBPS | 5/D-1,New Karachi. | Kyc | 2.195 | 0 | 0 | 0 | 0.936 | 0 | 0 | 0.936 | 959 | 1996-06-01 | 1996-06-07 | 12 Months | *** | G/F upto Structure Complete | ***
4 | GBPS | 5/E-II, New Karachi. | Kyc | 2.195 | 0 | 0 | 0 | 0.794 | 0 | 0 | 0.794 | 632 | 1996-06-11 | 1996-06-17 | 12 Months | *** | G/F upto Structure Complete | ***
|  | Total |  | 8.78 | 0 | 0 | 0 | 4.551 | 0 | 0 | 4.551 | *** | *** | *** | *** | *** | (PC-1, Under Revision)
Works Lying abandoned
|  | Total Middle School |  | 16.844 | 0 | 0 | 0 | 12.913 | 0 | 0 | 12.913 | *** | *** | *** | *** | *** | due to non-availability of funds
|  | Total Middle School (ADB Loan) |  | 7.238 |  |  | 0 | 6.689 |  |  | 6.689 | *** | *** | *** | *** | ***
|  | Grand Total Middle School |  | 24.082 | 0 | 0 | 0 | 19.602 | 0 | 0 | 19.602 | *** | *** | *** | *** | ***
<<Page2>>
| Category |  | Approved Sanctioned |  |  | Allocation | Released | E X P E N D I T U R E |  |  |  | C O N T R E C T |  | Actual | Period of | Reasons | Physical | Actual
ADP # |  | Name of Scheme/ | Taluka | Cost | Date | 2001-02 | 2001-02 | Upto | During the | During the | Total | No | Date | Date of | Completion | of Dely of | Progress | Date of
2000-01 |  | Project / Location |  |  |  | Original |  | 6-2001. | Month | Year | Since |  |  | Start | as per | Work | Remarks | Completion
[6 empty] | Modified |  |  |  | 2001-02 | Comme: |  |  |  | Workorder
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
SECONDARY EDUCATION
Non-S.A.P. ( Provincial )
r
4 | UP-GRADATION OF MIDDLE SCHOOL
662/40 | TO HIGH SCHOOL(1991-92) |  |  |  |  | 0 | 0
1 | GGPS | Wazir Jahan Karachi. | KYC | 3.278 | 0 | 0 | 0 | 3.685 | 0 | 0 | 3.685 | 297 | 1999-04-14 | 1999-04-17 | *** | *** | Completed & Handed Over | 2005-06-03
2 | GBLSS | Major Zia Uddin Memorial | KYC | 3.278 | 0 | 0 | 0 | 3.539 | 0 | 0 | 3.539 | 2410 | 1996-01-31 | 1996-06-12 | 24 Months | *** | Completed & Handed Over | 2005-06-03
|  |  |  | 6.556 | 0 | 0 | 0 | 7.224 | 0 | 0 | 7.224 | *** | *** | *** | *** | ***
5 | CONSTT / RE-CONSTT: OF BUILDING
667/124 | FOR EXISTING HIGH SCHOOL (1988-89). | [5 empty] | 0
1 | GBPS | Block # 9 F.B area Kyc: | KYC | 2.28 | 0 | 0 | 0 | 2.577 | 0 | 0 | 2.577 | 1199 | 1993-05-12 | 1993-05-14 | *** | *** | Completed & Handed Over | 12/11/90.
2 | GBSS | Green Land Premises | KYC | 2.28 | 0 | 0 | 0 | 2.241 | 0 | 0 | 2.241 | 1183 | 04/05/89. | 1993-05-11 | *** | *** | Completed & Handed Over | 08/05/91.
Happy Dale Nazim'd Kyc
3 | GGSS | Al Zohra Karachi. | KYC | 2.28 | 0 | 0 | 0 | 2.477 | 0 | 0 | 2.477 | 1682 | 1993-10-31 | 1999-11-07 | 5 Months | *** | Completed & Handed Over | 04/04/91.
4 | GBPS | Technical Age F.B.Area | KYC | 2.28 | 0 | 0 | 0 | 2.484 | 0 | 0 | 2.484 | 366 | 1996-04-02 | 1996-04-03 | *** | *** | Completed & Handed Over | 27/4/97.
(Shifted to Ibrahim Ali
Bhai B# 15 F.B.Area Kyc)
|  |  |  | 9.12 | 0 | 0 | 0 | 9.779 | 0 | 0 | 9.779 | *** | *** | *** | *** | ****
6 | CONSTT/ RE-CONST:OF BUILDING
672/141 | FOR EXISTING SCHOOL KCY. (1991-92) | [5 empty] | 0
1 | GGSS | Mujeeb-un-Nisa Karachi | KYC | 4.551 | 0 | 0 | 0 | 4.489 | 0 | 0 | 4.489 | 598 | 1996-06-02 | 1996-06-08 | 24 Months | *** | Completed & Handed Over | 2004-04-12
|  |  |  | 4.551 | 0 | 0 | 0 | 4.489 | 0 | 0 | 4.489 | *** | *** | *** | *** | ***
7 | ADDITION OF C/ROOM IN EXIST:
675/142 | SCHOOL IN KARACHI (1991-92) | [5 empty] | 0
1 | GGSS | 5/B New Karachi 5 C/R | KYC | 1.215 | 0 | 0 | 0 | 1.24 | 0 | 0 | 1.24 | 596-A | 1996-06-01 | 1996-06-07 | 12 Months | *** | Completed & Handed Over | 2001-10-01
2 | SSHS | Liaquatabad No:3(3 C/R) | KYC | 0.729 | 0 | 0 | 0 | 0.586 | 0 | 0 | 0.586 | 272 | 1996-04-28 | 1996-05-05 | *** | *** | Completed & Handed Over | ***
3 | GBSS | Liaquatabad No:2(3 C/R) | KYC | 0.729 | 0 | 0 | 0 | 0.772 | 0 | 0 | 0.772 | 588-A | 1996-05-31 | 1996-06-07 | *** | *** | Completed & Handed Over | ***
4 | GBSS | Liaquatabad No:3(3 C/R) | KYC | 0.729 | 0 | 0 | 0 | 0.8 | 0 | 0 | 0.8 | 611 | 1996-07-08 | 1996-07-15 | *** | *** | Completed & Handed Over | ***
5 | GGSS | Liaquatabad No:2(3C/R) | KYC | 0.729 | 0 | 0 | 0 | 0.759 | 0 | 0 | 0.759 | 589-A | 1996-05-31 | 1996-06-07 | *** | *** | Completed & Handed Over | ***
|  |  |  | 4.131 | 0 | 0 | 0 | 4.157 | 0 | 0 | 4.157 | *** | *** | *** | *** | ***
8 | ADD C/R IN EXISTING SECONDARY
677/ 127 | SCHOOL IN KARACHI (1992-93) (2 C/R) | [5 empty] | 0.9
1 | GGSS | F.C Area Karachi. (2 C/R) | KYC | 0.682 | 0 | 0 | 0 | 0.115 | 0.116 | 0.116 | 0.231 | *** | *** | *** | *** | *** | Structure Completed
2 | GGBS | Karachi Combridge No:1 | KYC | 0.682 | 0 | 0 | 0 | 0.493 | 0 | 0 | 0.493 | 3246 | 2003-12-10 | 2003-12-14 | 4 Months | *** | Completed & Handed Over
|  | (2 C/Room) |  | 1.364 | 0 | 0 | 0.9 | 0.608 | 0.116 | 0.116 | 0.724 | *** | *** | *** | *** | ***
<<Page3>>
| Category |  | Approved Sanctioned |  |  | Allocation | Released | E X P E N D I T U R E |  |  |  | C O N T R E C T |  | Actual | Period of | Reasons | Physical | Actual
ADP # |  | Name of Scheme/ | Taluka | Cost | Date | 2001-02 | 2001-02 | Upto | During the | During the | Total | No | Date | Date of | Completion | of Dely of | Progress | Date of
2001-02 |  | Project / Location |  |  |  | Original |  | 6-2001. | Month | Year | Since |  |  | Start | as per | Work | Remarks | Completion
[6 empty] | Modified |  |  |  | 2001-02 | Comme: |  |  |  | Workorder
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
9 | OPENING OF DOUBLE SECTION HGH SCHOOL
680/130 | IN SINDH KARACHI DIVISION (1991-92) | [5 empty] | 0.65
1 |  | 5/A North Karachi. | KYC | 6.342 | 0 | 0 | 0 | 5.983 | 0 | 0 | 5.983 | 610 | 1996-06-05 | 1996-06-11 | 24 Months | *** | Completed & H/Over | 1999-12-18
2 |  | 11/B North Karachi. | KYC | 6.342 | 0 | 0 | 0 | 4.335 | 0.347 | 0.347 | 4.682 | 565 | 2004-06-15 | 2004-06-15 | 24 Months | *** | Colouring in Progress | **
|  |  |  | 12.684 | 0 | 0 | 0.65 | 10.318 | 0.347 | 0.347 | 10.665 | *** | *** | *** | *** | ***
10 | INTRODUCTION / ADD: OF XI-XII CLASSES IN EXISTING
696/146 | HIGH SECONDARY SCHOOL IN SINDH ( 1991-92) | [5 empty] | 0
1 | GGSS | Liaquatabad No:4, | KYC | 3.97 | 0 | 0 | 0 | 3.055 | 0 | 0 | 3.055 | 646 | 1996-06-17 | 1996-06-26 | 24 Months | *** | Ground Floor Completed
2 | GBSS | Liaquatabad No:4, | KYC | 3.97 | 0 | 0 | 0 | 1.371 | 0 | 0 | 1.371 | 647 | 1996-06-17 | 1996-06-23 | 24 Months | *** | Work lying due to non availability of Funds
3 | GGSS | Ishat-ul-Quran Nazim'd | KYC | 3.97 | 0 | 0 | 0 | 2.937 | 0 | 0 | 2.937 | 1439 | 2002-04-30 | 1997-06-24 | 24 Months | *** | Work lying abondend at plaster Stage
|  |  |  | 11.91 | 0 | 0 | 0 | 7.363 | 0 | 0 | 7.363 | *** | *** | *** | *** | *** | (PC-1 is Under Revision)
11 | UP-GRADATION OF MIDDLE TO
703/147 | HIGH SCHOOL IN R/AREA (1994-95) | [5 empty] | 1.4
1 | GBLSS | District Council 11/D N/K | KYC | 1.607 | 0 | 0 | 0 | 1.676 | 0.25 | 0.25 | 1.926 | 553 | 2004-06-14 | 2004-06-14 | 12 Months | *** | Completed
2 | GBLSS | 11/E New Karachi. | KYC | 1.607 | 0 | 0 | 0 | 1.726 | 0.248 | 0.248 | 1.974 | 552 | 2004-06-14 | 2004-06-14 | 12 Months | *** | Completed & Handover
|  |  |  | 3.214 | 0 | 0 | 1.4 | 3.402 | 0.498 | 0.498 | 3.9 | *** | *** | *** | *** | ***
12 | ADDITION C/R IN EXISTING
706/148 | HIGH SCHOOL IN SINDH(1994-95) | [5 empty] | 0.45
1 | GGSS | Dastagir No:9 | KYC | 1.06 | 0 | 0 | 0 | 0 | 0.282 | 0.282 | 0.282 | *** | *** | *** | *** | *** | Plinth Completed
Federal "B" area (4 C/R)
2 | GHSS | Ibrahim Ali Bhai | KYC | 1.06 | 0 | 0 | 0 | 0.095 | 0.168 | 0.168 | 0.263 | *** | *** | *** | *** | *** | …do…
Federal "B" area (4 C/R)
3 | GBSS | Sitar-e-Hydri 11/D North | KYC | 0.53 | 0 | 0 | 0 | 0.494 | 0 | 0 | 0.494 | 3242 | 2003-12-09 | 2003-12-16 | 12 Months | *** | Completed | 2005-08-04
Karachi ( 2C/Room )
4 | GGSS | Allama Iqbal Block # 16 | KYC | 0.53 | 0 | 0 | 0 | 0.483 | 0 | 0 | 0.483 | 3233 | 2003-12-08 | 2003-12-08 | 12 Months | *** | Completed & Handedover | 2004-07-26
F.B.Area Kyc (2 C/Room)
|  |  |  | 3.18 | 0 | 0 | 0.45 | 1.072 | 0.45 | 0.45 | 1.522 | *** | *** | *** | *** | ***
| Grand Total Secondary School |  |  | 56.71 | 0 | 0 | 3.4 | 48.412 | 1.411 | 1.411 | 49.823 | *** | *** | *** | *** | ***
13 | ESTABLISHMENT OF MONO TECHNIC INSTITUTE | [5 empty] | 0
736/36 | DISTRICT CENTRAL KARACHI
1 |  | @ Sector 5/J N'Karachi. | KYC | 9.58 | 0 | 0 | 0 | 8.916 | 0 | 0 | 8.916 | 417 | 1998-06-24 | 1998-06-26 | 24 Months | *** | Completed & Handedover
| Grand Total Mono Technic |  |  | 9.58 | 0 | 0 | 0 | 8.916 | 0 | 0 | 8.916 | *** | *** | *** | *** | ***
<<Page4>>
| Category |  | Approved Sanctioned |  |  | Allocation | Released | E X P E N D I T U R E |  |  |  | C O N T R E C T |  | Actual | Period of | Reasons | Physical | Actual
ADP # |  | Name of Scheme/ | Taluka | Cost | Date | 2001-02 | 2001-02 | Upto | During the | During the | Total | No | Date | Date of | Completion | of Dely of | Progress | Date of
2001-02 |  | Project / Location |  |  |  | Original |  | 6-2001. | Month | Year | Since |  |  | Start | as per | Work | Remarks | Completion
[6 empty] | Modified |  |  |  | 2001-02 | Comme: |  |  |  | Workorder
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
DISTRICT CENTRAL KARACHI ( Non-S.A.P. District)
COLLEGE EDUCATION.
0.32
1) 802/37 | OPENING OF GOVT:DEGREE GIRLS COLLEGE |  |  |  |  | 0 |  | 21.632 | 0 | 0.051 | 21.683 | 116 | 1997-02-02 | 1997-02-03 | 36 Months | *** | Completed & Handedover
| GIRLS COLLEGE NEW KARACHI. |  | KYC | 21.957 | 0 | 0 | 0.32 | 21.632 | 0 | 0.051 | 21.683 | *** | *** | *** | *** | ***
3) 817/38 | OPENING OF GOVERNMENT DEGREE | [5 empty] | 0.88
| COLLEGE IN ARTS & SCIENCE | [6 empty] | 20.314 | 0 | 0.348 | 20.662 | 396 | 1997-05-20 | 1997-05-29 | 36 Months |  | Almost, Completed ready to Handedover | 2002-09-29
| Boys | @ New Karachi | KYC | 22.149 | 0 | 0 | 0.88 | 20.314 | 0 | 0.348 | 20.662 | *** | *** | *** | *** | ***
4) 819/39 | ESTABLISHMENT GOVERNMENT DEGREE COLLEGE
| @ LIAQUATABAD NO: (5) Near KMC Park Karachi | [5 empty] | 3.25 | [9 empty] | Phase-I Almost Completed
| .Shifted to F.B.Area Block # 1, Karachi. | [15 empty] | Phase-II, ……..do……..
|  |  | KYC | 23.289 | 0 | 0 | 3.25 | 9.483 | 0.038 | 1.327 | 10.81 | 1258 | 2002-02-22 | 2002-10-01 | 36 Months | *** | Phase-III, Plaster work in Progress | ***
0
5) 832/40 | IMPROVEMENT OF RAIZ GOVT:
| GIRLS COLLEGE @ Liaquatabad #10 |  | KYC | 8.701 | 0 | 0 | 0 | 8.314 | 0 | 0 | 8.314 | 371-A | 1999-05-31 | 1999-05-31 | 36 Months | *** | Completed & Handedover | 2001-04-03
0.1
6) 851/41 | CONSTT: OF GOVT DEGREE
| COLLEGE @ Buffarzone N'Karachi. |  | KYC | 11.713 | 0 | 0 | 0.1 | 12.119 | 0 | 0.023 | 12.142 | 693 | 1996-08-17 | 1996-08-23 | 24 Months | *** | Completed ready to Handedover | ***
0.2
7) 852/42 | CONSTRUCTION OF GOVT:
| DEGREE COLLEGE at F.B. Area. |  | KYC | 11.713 | 0 | 0 | 0.2 | 11.974 | 0 | 0 | 11.974 | 1026 | 1996-11-26 | 1996-11-27 | 24 Months | *** | Completed ready to Handedover | ***
5
8) 855/43 | ESTABLISHEMNT OF DEGREE COLLEGE | [15 empty] | Phase-I, almost Completed
| @Shaheed-e- Millat Azizabad | [15 empty] | Phase-II, Colouring in progress
| Federal ".B".Area Karachi. |  | KYC | 30.672 | 0 | 0 | 5 | 19.325 | 0.362 | 1.953 | 21.278 | 844 | 2001-09-02 | 2001-09-08 | *** | *** | Phase-III, Colouring in Progress | ***
1
9) 859/44 | ADDITION/ ALTERATION IN APWA
GOVT. COLLEGE FOR WOMEN
| Federal "B" AREA: |  | KYC | 3.93 | 0 | 0 | 1 | 3.998 | 0 | 0 | 3.998 | 18 | 1996-01-10 | 1996-01-12 | *** | *** | Completed & Handedover | 2004-11-03
|  | Total College |  | 134.124 | 0 | 0 | 10.75 | 107.159 | 0.4 | 3.702 | 110.861 | *** | *** | *** | *** | ***
<<Page5>>
| Category |  | Approved Sanctioned |  |  | Allocation | Released | E X P E N D I T U R E |  |  |  | C O N T R E C T |  | Actual | Period of | Reasons | Physical | Actual
ADP # |  | Name of Scheme/ | Taluka | Cost | Date | 2001-02 | 2001-02 | Upto | During the | During the | Total | No | Date | Date | Completion | of Dely of | Progress | Date of
2001-02 |  | Project / Location |  |  |  | Original |  | 6-2001. | Month | Year | Since |  |  | of Start | as per | Work | Remarks | Compl:
[6 empty] | Modified |  |  |  | 2001-02 | Comme: |  |  |  | Workorder
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
EDUCATION ADMINISTRATION
1) 869/180 | IMPROVEMENT OF EXISTING INSTITUTE BY
| PROVISION NECESSARY LACKING FACILITIES: | [5 empty] | 0
1 | GBPS | Sector 5/D New Karachi | KYC | 0.05 | 0 | 0 | 0 | 0.048 | 0 | 0 | 0.048 | *** | *** | *** | *** | *** | Completed & Handedover
(Over Head Tank)
2 | BOYS | Govt:Comprihensive High | KYC | 0.26 | 0 | 0 | 0 | 0.279 | 0 | 0 | 0.279 | *** | *** | *** | *** | *** | Completed & Handedover
School (External Work)
3 | GBPS | APWA 5/E New Karachi: | KYC | 0.12 | 0 | 0 | 0 | 0.124 | 0 | 0 | 0.124 | *** | *** | *** | *** | *** | Completed & Handedover
4 | GBPS | Sector 5/F New Karachi. | KYC | 0.05 | 0 | 0 | 0 | 0.0425 | 0 | 0 | 0.0425 | *** | *** | *** | *** | *** | Completed & Handedover
5 | GBPS | Sector 5/F New Karachi. | KYC | 0.098 | 0 | 0 | 0 | 0.0505 | 0 | 0 | 0.0505 | *** | *** | *** | *** | *** | Completed & Handedover
6 | GBPS | Sector 5/F New Karachi. | KYC | 0.068 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.05 | *** | *** | *** | *** | *** | Completed & Handedover
7 | GIRLS | Govt: Comprihensive High | KYC | 0.05 | 0 | 0 | 0 | 0.103 | 0 | 0 | 0.103 | *** | *** | *** | *** | *** | Completed
Norht Karachi.
8 | BOYS | Govt: Commercial Institute | KYC | 0.05 | 0 | 0 | 0 | 0.063 | 0 | 0 | 0.063 | *** | *** | *** | *** | *** | Completed
Azizabad Karachi.
9 | GBPS | Sector 5/F New Karachi | KYC | 0.05 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.05 | *** | *** | *** | *** | *** | Completed
Town Committee Karachi
10 | GBPS | Sector 5/F New Karachi | KYC | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | *** | *** | *** | *** | *** | Not Required
(Over Head Tank)
11 | GBSS | Sector 5/D New Karachi | KYC | 0.05 | 0 | 0 | 0 | 0.051 | 0 | 0 | 0.051 | *** | *** | *** | *** | *** | Completed
(Over Head Tank)
12 | GPS | Federal .B.Area Karachi. | KYC | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | *** | *** | *** | *** | *** | Not Required
(Stair Case).
|  |  |  | 0.946 | 0 | 0 | 0 | 0.861 | 0 | 0 | 0.861 | *** | *** | *** | *** | ***
|  | Grand Total |  | 225.442 | 0 | 0 | 14.15 | 184.95 | 1.811 | 5.113 | 190.063 | *** | *** | *** | *** | ***
DISTRICT OFFICER
EDUCATION WORKS DIVISION-II
KARACHI CITY GOVERNMENT
MONTHLY PROGRESS REPORT OF PUBLIC SCHOOL IN KARACHI CITY GOVERNMENT North Karachi Town
FOR THE MONTH OF " JULY- 2001"
<<Page7>>
EDUCATION WORKS DIVISION-II KARACHI CITY GOVERNMENT | [16 empty] | (Rs in Million )
| Category |  | Approved Sanctioned |  |  | Allocation | Released | E X P E N D I T U R E |  |  |  | C O N T R E C T |  | Actual | Period of | Reasons | Physical | Actual
ADP # |  | Name of Scheme/ | Taluka | Cost | Date | 2001-02 | 2001-02 | Upto | During the | During the | Total | No | Date | Date | Completion | of Dely of | Progress | Date of
2001-02 |  | Project / Location |  |  |  | Original |  | 6-2001. | Month | Year | Since |  |  | of Start | as per | Work | Remarks | Compl:
[6 empty] | Modified |  |  |  | 2001-02 | Comme: |  |  |  | Workorder
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
1 |  | NON-RESIDENTIAL
I |  | Academic Block Higher | Kyc
|  | Secondary ( XI-XII) |  | 3.673 |  |  |  | 7.638 | 0 | 0 | 7.638 | 1035 | 1997-05-09 | 2001-11-07 | 24 Months | *** | Completed | 2002-11-04
II |  | Secondary ( IX-X) |  | 3.649 |  |  |  | *** | *** | *** | *** | *** | *** | *** | *** | *** | Completed
III |  | Compound Wall |  | 0.529 |  |  |  | 0.9 | 0 | 0 | 0.9 | 1290 | 1997-05-09 | 2000-05-04 | 3 Months | *** | Completed | 2002-03-14
2 |  | RESIDENTIAL
I |  | Principal Residence |  | 0.575 |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | *** | Completed | 2002-08-16
II |  | Vice Principal Residence |  | 0.383 |  |  |  | 3.059 | 0 | 0 | 3.059 | 304 | 1998-05-15 | 1998-05-17 | 24 Months | *** | Completed
III |  | Jr.staff Residence(A+B) |  | 1.067 |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | ***
3 |  | W/Supply & S/Installation
I |  | Academic Block |  | 0.591 |  |  |  | 0.339 | 0 | 0 | 0.339 |  |  |  |  | *** | Completed
II |  | Principal Residence |  | 0.054 |  |  |  | 0.119 | 0 | 0 | 0.119 | 1274 | 2000-05-03 | 2000-05-04 | 3 Months | *** | Completed | 2002-08-19
III |  | Vice Principal Residence |  | 0.036 |  |  |  | 0.186 | 0 | 0 | 0.186 | 1295 | 2000-05-10 | 2000-05-10 | 3 Months | *** | Completed | 2002-08-19
4 |  | OTHER FACILITIES:
I |  | Gymnasium Hall |  | 2.747 |  |  |  | 1.508 | 0 | 0 | 1.508 | 355-A | 1999-05-25 | 1999-06-01 | 18 Months | *** | Squash Court & Side Portion roof laid B/Masonary &
[16 empty] | *** | Column above lintel level in prog:
II |  | Over Head Tank |  | 0.35 |  |  |  | 0.061 | 0 | 0 | 0.061 | 1142 | 2001-12-19 | 2001-12-19 | 20 Days | *** | Sepratly OHT for each Completed | 2002-06-14
III |  | Under Ground tank |  | 0.35 |  |  |  | 0.335 | 0 | 0 | 0.335 | 307 | 1998-05-15 | 1998-06-21 | 6 Months | *** | Completed | 1999-01-13
IV |  | Auditorium |  | 1.7 |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | *** | Not i/c in District Central
V |  | Pump Room |  | 0.036 |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | *** | Completed
VI |  | Clinic |  | 0.281 |  |  |  | 0.526 | 0 | 0 | 0.526 | 1291 | 2000-05-03 | 2000-05-06 | 6 Months | *** | Completed | 2002-10-29
VII |  | Ext: Deve: & Path Way |  | 0.22 |  |  |  | 2.359 | 0 | 0 | 2.359 | 1289 | 2000-05-03 | 2000-05-04 | 3 Months | *** | Completed | 2003-07-17
VIII |  | Cost of Land |  | 1 |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | *** | Not Paid
5 |  | EXTRA COURRICULAR ACTIVITIES
I |  | Hockey Ground |  | 0.32 |  |  |  | 0.602 | 0 | 0 | 0.602 | 1292 | 2000-05-03 | 2000-05-06 | 3 Months | *** | Completed | 2002-08-07
II |  | Cricket Ground |  | 0.35 |  |  |  | 0.52 | 0 | 0 | 0.52 | 1149 | 2001-12-20 | 2001-12-27 | 3 Months | *** | Completed | 2002-11-08
III |  | Tennis Court |  | 0.14 |  |  |  | 0.377 | 0 | 0 | 0.377 | 1299 | 2000-05-03 | 2000-05-06 | 3 Months | *** | Completed | 2000-08-05
IV |  | Purchase of Funs |  | 0.145 |  |  |  | 0.146 | 0 | 0 | 0.146 |  |  |  |  | *** | Completed
6 |  | MISCELLANCE
I |  | Counsultance Charges |  | 0.318 |  |  |  | 0.318 | 0 | 0 | 0.3755 |  |  |  |  | ***
ii |  | Electric Works |  | 1.24 |  |  |  | 1.782 | 0 | 0 | 1.782 |  |  |  |  | ***
|  | (Transfer to Electrical Division) | [5 empty] | 0.3 | 0 | 0 | 0.3
|  |  |  | 19.754 |  |  |  | 21.075 | 0 | 0 | 21.1325 | *** | *** | *** | *** | ***
DISTRICT OFFICER
EDUCATION WORKS DIVISION-II
KARACHI CITY GOVERNMENT
MONTHLY PROGRESS REPORT IN RESPECT OF PRIORITY PROGRAMME 1997-98
EDUCATION WORKS DIVISION-II KARACHI CITY GOVERNMENT
FOR THE MONTH OF " AUGUST- 2001"
<<Page8>>
Rs. in Million
| Category |  | Approved Sanctioned |  |  | Allocation | Released | E X P E N D I T U R E |  |  |  | C O N T R E C T |  | Actual | Period of | Reasons | Physical | Actual
ADP # |  | Name of Scheme/ | Taluka | Cost | Date | 2001-02 | 2001-02 | Upto | During the | During the | Total | No | Date | Date | Completion | of Dely of | Progress | Date of
2001-02 |  | Project / Location |  |  |  | Original |  | 6-2001. | Month | Year | Since |  |  | of Start | as per | Work | Remarks | Compl:
[6 empty] | Modified |  |  |  | 2001-02 | Comme: |  |  |  | Workorder
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
1) 46 | ADDITION/ IMPROVEMENT OF DEGREE COLLEGE: | [5 empty] | 1.5
1 | Sir Syed Govt: Degree College |  | Kyc | 12.848 | 0 | 0 |  | 3.65 | 0 | 1.015 | 4.665 | 25 | 2002-10-07 | 08/10/98. | 36 Months |  | Structure Completed
Nazimabad Karachi (Phase-I)
|  |  |  | 12.848 | 0 | 0 | 1.5 | 3.65 | 0 | 1.015 | 4.665 | *** | *** | *** | *** | ***
2) 47 | ADDITION OF COMPUTER CLASSES | [5 empty] | 1
2 | Mujeeb-un-Nisa Govt Girls College |  | Kyc | 2.394 | 0 | 0 | 0 | 1.437 | 0 | 1.548 | 2.985 | 17 | 2002-07-31 | 2002-07-08 | 24 Months |  | Plastering Work in Progress
New Karachi Distt: Central
3 | Sir Syed Government College Kyc: |  | Kyc | 2.394 | 0 | 0 | 0 | 1.416 | 0 | 0.459 | 1.875 | 19 | 2002-07-31 | 2002-08-02 | 24 Months |  | Completed
|  |  |  | 4.788 | 0 | 0 | 1 | 2.853 | 0 | 2.007 | 4.86 | *** | *** | *** | *** | ***
3) 48 | ADDITION OF CLASS ROOM IN EXISTING
| SECONDARY SCHOOL IN U/AREA KARACHI | [5 empty] | 1.1
4 | GBSS | Allama Iqbal F.B.Area | Kyc | 1.16 | 0 | 0 | 0 | 0.263 | 0 | 0 | 0.263 | 11 | 2002-07-31 | 2002-07-31 | 10 Months |  | F/Floor Roof completed
( 4 Class Rooms)
5 | GBSS | New Method F.B.Area | Kyc | 1.16 | 0 | 0 | 0 | 0.687 | 0 | 0.023 | 0.71 | 10 | 2002-07-31 | 2002-08-06 | 10 Months |  | Roof slab Completed
( 4 Class Rooms)
6 | GBSS | Anglo Oriential Block-15, | Kyc | 1.45 | 0 | 0 | 0 | 0.944 | 0 | 0.103 | 1.047 | 14 | 2002-07-31 | 2002-08-07 | 10 Months |  | Roof slab Completed
F.B.Area Karachi.( 5 C/Room)
7 | GGSS | Hyderi North Nazimabad | Kyc | 1.45 | 0 | 0 | 0 | 0.716 | 0 | 0 | 0.716 | 1 | 2002-07-26 | 2002-08-02 | 10 Months |  | Roof Slab Completed
( 5 Class Rooms )
8 | GBSS | 5/A-3, New Karachi. | Kyc | 1.45 | 0 | 0 | 0 | 0.351 | 0 | 0 | 0.351 | 12 | 2002-07-31 | 2002-08-07 | 10 Months |  | Upto Plinth Level
( 5 Class Rooms )
9 | GGSS | Liaquatabad No:4 Karachi. | Kyc | 0.87 | 0 | 0 | 0 | 0.426 | 0 | 0.093 | 0.519 | 5 | 2002-07-29 | 2002-08-02 | 6 Months |  | At Colouring Stage.
( 3 Class Rooms )
10 | GBSS | Liaquatbad No:4 Karachi. | Kyc | 1.16 | 0 | 0 | 0 | 1.099 | 0 | 0 | 1.099 | 13 | 2002-07-31 | 2002-08-03 | 10 Months |  | Completed & Handed
( 4 Class Rooms )
|  |  |  | 8.7 | 0 | 0 | 1.1 | 4.486 | 0 | 0.219 | 4.705 | *** | *** | *** | *** | ***
4) 49 | ESTABLISHMENT/ OPENING OF GOVT: DEGREE COLLEGE. | [5 empty] | 1.75 | [9 empty] | Phase- I Plaster in Progress
11 | North Nazimabad |  | Kyc | 26.098 | 0 | 0 | 1.75 | 4.4 | 0.232 | 1.203 | 5.603 | 26 | 2002-10-07 | 2002-10-14 | 36 Months
5) 50 | ESTABLISHMENT/ OPENING OF GOVT: DEGREE COLLEGE. | [5 empty] | 2.5 | [9 empty] | Ph-I, Colouring Stage
12 | North Karachi. |  | Kyc | 26.098 | 0 | 0 | 2.5 | 8 | 0.532 | 2.479 | 8.532 | 27 | 2002-10-07 | 2002-10-14 | 36 Months |  | Ph:II, upto plinth level.
<<Page9>>
| Category |  | Approved Sanctioned |  |  | Allocation | Released | E X P E N D I T U R E |  |  |  | C O N T R E C T |  | Actual | Period of | Reasons | Physical | Actual
ADP # |  | Name of Scheme/ | Taluka | Cost | Date | 2001-02 | 2001-02 | Upto | During the | During the | Total | No | Date | Date | Completion | of Dely of | Progress | Date of
2001-02 |  | Project / Location |  |  |  | Original |  | 6-2001. | Month | Year | Since |  |  | of Start | as per | Work | Remarks | Compl:
[6 empty] | Modified |  |  |  | 2001-02 | Comme: |  |  |  | Workorder
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
6) 51 | ESTABLISHMENT OF MONOTECHIC INSTITUTE
| AT DISTRICT CENTRAL KARACHI. | [5 empty] | 1.75
13 | F.B Area Karachi |  | Kyc | 21.38 | 0 | 0 |  | 3.881 | 0 | 1.75 | 5.631 | 38 | 2002-10-28 | 2002-10-28 | 36 Months |  | Ph-I) Colouring Stage
Ph-II) Plinth Work in Progress
|  |  |  | 21.38 | 0 | 0 | 1.75 | 3.881 | 0 | 1.75 | 5.631 | *** | *** | *** | *** | ***
7) 52 | ESTABLISHMENT OF SINGLE
| SECTION HIGH SCHOOL IN U/AREA | [5 empty] | 0.2
15 | Opening of Single Section High |  | Kyc | 4.189 | 0 | 0 |  | 2.35 | 0 | 0.2 | 2.55 | 24 | 2002-10-07 | 2002-10-07 | 27 Months |  | Structure Completed
School @ Bufar Zone
|  |  |  | 4.189 | 0 | 0 | 0.2 | 2.35 | 0 | 0.2 | 2.55 | *** | *** | *** | *** | ***
8) 53 | UP-GRADATION OF MIDDLE TO HIGH SCHOOL IN KYC | [5 empty] | 1.5
16 | GBLSS | 5/G Moon Light N'Karachi | Kyc | 3.964 | 0 | 0 |  | 1.511 | 0.118 | 0.363 | 1.874 | 16 | 2002-07-31 | 2002-08-05 | 24 Month |  | Structure Completed
|  |  |  | 3.964 | 0 | 0 | 1.5 | 1.511 | 0.118 | 0.363 | 1.874 | *** | *** | *** | *** | ***
9) 54 | UP-GRADATION OF SAIFEE EIDEE ZAHABI INSTITUTE
| OF TECHNOLOGY TO B.TECH LEVEL CLASSES KYC | [5 empty] | 1.5
17 | North Nazimabad Karachi |  | Kyc | 11.913 | 0 | 0 |  | 4.095 | 0 | 0.547 | 4.642 | 29 | 2002-10-13 | 2002-10-20 | 24 Months |  | Phase-I Plaster in porgress
Phase-II, Partly Roof Laid
|  |  |  | 11.913 | 0 | 0 | 1.5 | 4.095 | 0 | 0.547 | 4.642 | *** | *** | *** | *** | ***
10) 55 | UP-GRADATION OF PRIMARY TO MIDDKE SCHOOL | [5 empty] | 0.75
18 | GBPS | Sector 5/C-2, N/K. | Kyc | 3.562 | 0 | 0 |  | 1.148 | 0 | 0 | 1.148 | 30 | 2002-10-17 | 2002-10-17 | 24 Month |  | G/Floor Roof slab Completed
19 | GBPS | 5/B-2, N' Karachi. | Kyc | 3.562 | 0 | 0 |  | 1.956 | 0 | 0.363 | 2.319 | 36 | 2002-10-17 | 2002-10-18 | 48 Months |  | Plaster & Flooring in Progress
20 | GBPS | Allama Iqbal Bl-16,F.B.Area | Kyc | 3.562 | 0 | 0 |  | 1.115 | 0 | 0 | 1.115 | 32 | 2002-10-18 | 2002-10-18 | 24 Month |  | S/S F/Floor roof Completed
21 | GGPS | Kamyab Bl-15,F.B.Area | Kyc | 3.562 | 0 | 0 |  | 1.742 | 0 | 0.387 | 2.129 | 34 | 2002-10-18 | 2002-10-18 | 24 Month |  | Plaster in Progress
22 | GBPS | Liaquatabad No 4 Karachi. | Kyc | 3.562 | 0 | 0 |  | 0.704 | 0 | 0 | 0.704 | 33 | 2002-10-18 | 2002-10-21 | 6 Months |  | Completed upto Lintel Level
|  |  |  | 17.81 | 0 | 0 | 0.75 | 6.665 | 0 | 0.75 | 7.415 | *** | *** | *** | *** | ***
11) . | INTRODUCTION OF XI & XII IN CLASSES IN EXISTING
| (BOYS/GIRLS) SECONDARY SCHOOL IN U/AREA KYC: | [5 empty] | 0
23 | GBSS | APWA 5/E New Karachi. |  | 7 | 0 | 0 |  | 2.717 | 0 | 0 | 2.717 | 28 | 2002-10-07 | 2002-10-14 | 36 Months |  | Roof Partly laid, work Lying abandond
|  |  |  | 7 | 0 | 0 | 0 | 2.717 | 0 | 0 | 2.717 | *** | *** | *** | *** | ***
|  | GRAND TOTAL |  | 144.788 | 0 | 0 | 13.55 | 44.608 | 0.882 | 10.533 | 53.194 | *** | *** | *** | *** | ***
DISTRICT OFFICER
EDUCATION WORKS DIVISION
KARACHI CITY GOVERNMENT
MONTHLY PROGRESS REPORT IN RESPECT OF REPAIR WORKS 2000-01
FOR THE MONTH OF JULY- 2001
Education Works Division-II Karachi City Government
| Category |  | Approved Sanctioned |  |  | Allocation | Released | E X P E N D I T U R E |  |  |  | C O N T R E C T |  | Actual | Period of | Reasons | Physical | Actual
Sr. # |  | Name of Scheme/ | Taluka | Cost | Date | 2001-02 | 2001-02 | Upto | During the | During the | Total | No | Date | Date | Completion | of Dely of | Progress | Date of
|  | Project / Location |  |  |  | Original |  | 6-2001. | Month | Year | Since |  |  | of Start | as per | Work | Remarks | Compl:
[6 empty] | Modified |  |  |  | 2001-02 | Comme: |  |  |  | Workorder
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
|  | SECONDARY SCHOOL |  | Funds Released During 2001-02 |  |  |  | 3.880 Million
1 | GBSS | Happy Dale Nazim'd. | Kyc | 0.55 | 28/4/Y2K | 0 | 0 | 0 | 0 | 0.244 | 0.244 | 391 | 15/5/00. | 18/5/00. | 4 Months |  | Completed | 18/8/00.
2 | GBSS | Jamia Tajia 15/A Buffar
|  | zone Zone North Karachi. | Kyc | 0.381 | 13/4/Y2K | 0 | 0.101 | 0 | 0.101 | 0.339 | 0.339 | 503 | 27/5/00. | 27/5/00. | 2 Months |  | Completed | ***
3 | GBSS | Happy Dale Nazimabad | Kyc | 0.358 | 28/4/Y2K | 0 | 0 | 0.092 | 0 | 0.117 | 0.209 | 384 | 17/5/00. | 18/5/00. | 3 Months |  | Completed | 5/8/Y2k
4 | GBSS | Sir Syed Town 11/ G N'Kyc | Kyc | 0.496 | 28/5/Y2K | 0 | 0 | 0.257 | 0 | 0.19 | 0.447 | 434 | 25/5/00. | 25/5/00. | 4 Months |  | Completed | ***
5 | GBSS | Karachi Elemantry N'Naz: | Kyc | 0.142 | 20/5/Y2K | 0 | 0 | 0 | 0 | 0.094 | 0.094 | 507 | 27/5/00. | 20/5/00. | 1 Months |  | Completed | 14/6/Y2K
6 | GBSS | National Ideel 5/C-2, N'Kyc: | Kyc | 0.672 | 25/5/Y2k | 0 | 0 | 0.314 | 0 | 0.257 | 0.571 | 501 | 27/5/00. | 25/5/00. | 5 Months |  | Completed | 17/6/Y2k
7 | GGSS | 5/D New Karachi. | Kyc | 0.511 | 25/5/Y2k | 0 | 0 | 0.15 | 0 | 0.353 | 0.503 | 438 | 02/5/00. | 25/5/00. | 6 Months |  | Completed | ***
8 | GGSS | 5/B New Karachi. | Kyc. | 0.319 | 25/5/Y2k | 0 | 0 | 0.24 | 0 | 0.079 | 0.319 | 433 | 25/5/00. | 25/5/00. | 3 Months |  | Completed | 24/6/Y2k
9 | GGSS | Relax Cinema Nazimabad | Kyc; | 0.237 | 18/5/Y2k | 0 | 0 | 0 | 0.024 | 0.249 | 0.249 | 445 | 26/5/00. | 28/5/00. | 2 Months |  | Completed | ***
10 | GGSS | Mujeb-un-Nisa 11/F N'Kyc | Kyc; | 0.455 | 23/5/Y2k | 0 | 0 | 0.438 | 0 | 0.013 | 0.451 | 436 | 25/5/00. | 25/5/00. | 1 Month |  | Completed | ***
11 | GGSS | G-28, Nazimabad | Kyc; | 0.27 | 27/5/Y2k | 0 | 0 | 0.24 | 0.011 | 0.011 | 0.251 | 506 | 27/5/00. | 28/5/00. | 3 Months |  | Completed | 17/6/Y2k
| Total Secondary School |  |  | 4.391 | *** | *** | 2.3 | 1.731 | 0.136 | 1.946 | 3.677
| Category |  | Approved Sanctioned |  |  | Allocation | Released | E X P E N D I T U R E |  |  |  | C O N T R E C T |  | Actual | Period of | Reasons | Physical | Actual
Sr. # |  | Name of Scheme/ | Taluka | Cost | Date | 2001-02 | 2001-02 | Upto | During the | During the | Total | No | Date | Date | Completion | of Dely of | Progress | Date of
|  | Project / Location |  |  |  | Original |  | 6-2001. | Month | Year | Since |  |  | of Start | as per | Work | Remarks | Compl:
[6 empty] | Modified |  |  |  | 2001-02 | Comme: |  |  |  | Workorder
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
COLLEGE EDUCATION
11 |  | Government College For
|  | Men Nazimabad Karachi | Kyc; | 0.397 | 23/5/Y2k |  |  | 0 | 0 | 0.36 | 0.36 | 443 | 26/5/00. | 28/5/00. | 4 Months |  | Completed | 22/8/00.
12 |  | Govt. shipowner College North
|  | Nazimabad Karachi. | Kyc; | 0.485 | 23/5/Y2k |  |  | 0.2 | 0 | 0.153 | 0.353 | 505 | 27/5/00. | 28/5/00. | 3 Months |  | Completed | ***
13 |  | Govt. College For Women
|  | Nazimabad Karachi. | Kyc; | 0.498 | 23/5/Y2k |  |  | 0 | 0 | 0.511 | 0.511 | 446 | 26/5/00. | 26/5/00. | 3 Months
[17 empty] | Completed | ***
14 |  | ….do..( W/S & S/I) | Kyc; | 0.22 | 23/5/Y2k |  |  | 0 | 0 | 0.221 | 0.221 | 447 | 26/5/00. | 28/5/00. | 2 Months |  | completed | ***
15 |  | …….do…. ( Gas Fitting ) | Kyc; | 0.226 | *** |  |  | 0 | 0 | 0.227 | 0.227 | 611 | 27/6/00. | 04/7/00. | 2 Months |  | Completed | 20/8/00.
16 |  | ....do… ( Termite Treat't) | Kyc; | 0.05 | *** |  |  | 0 | 0.048 | 0.048 | 0.048 | 1588 | 01/6/01. | 04/6/01. | 1 Month |  | Completed | ***
17 |  | Govt. APWA College For
|  | Women F.B.Ara Karachi. | Kyc. | 1.013 | 15/3/Y2k |  |  | 0.746 | 0 | 0.205 | 0.951 | 398 | 19/5/00. | 20/5/00. | 5 Months |  | Work all most completed | ***
17/a |  | …do… (Barbad Wire) | Kyc. |  |  |  |  | 0 | 0 | 0.067 | 0.067 | 392 | 17/5/00. | 17/05/00. | 2 Months |  | Work all most completed | ***
18 |  | Govt. College for Women
|  | New Karachi. | Kyc. | 0.61 | 25/5/Y2k |  |  | 0.405 | 0 | 0.142 | 0.547 | 437 | 25/5/00. | 25/5/00. | 4 Months |  | Work all most completed | ***
| Total College Education |  |  | 3.499 | *** | *** | *** | 1.351 | 0.048 | 1.934 | 3.285
| Grand Total (School + College) |  |  | 7.89 | *** | *** | *** | 3.082 | 0.184 | 3.88 | 6.962
DISTRICT OFFICER
EDUCATION WORKS DIVISION-II
KARACHI CITY GOVERNMENT

## Sheet4 (hidden)
STATEMENT SHOWING THE PHYSICAL & FINANCIAL POSITION OF THE SCHEMES OF COLLEGE EDUCATION SUB-SECTOR
UNDER THE DISTRICT OFFICER EDUCATION WORKS-II KARACHI CITY DISTRICT GOVERNMENT
Sr. No: | Category |  | Town | Approved Cost | Allocation | Expdt: | Physical
ADP # |  | Name of Scheme/ |  |  | 2000-01 | During the | Progress
2001-02 |  | Project / Location |  |  |  | Year | Remarks
2001-02
1 | 2 | 3 | 4 | 5 | 6 | 7 | 11
COLLEGE EDUCATION.
1) 843/ 32 | ESTABLISHMENT OF GOVT. COLLEGE | [5 empty] | Block-A , Structure Completed
| OF EDUCATION B.Ed. & M.Ed. | [5 empty] | Block-B, Partly roof Laid .
| @ Darsano Channo |  | Gadap | 25.412 | 0 | 0 | Block-C, roof to be laid. (Building placed for
|  |  |  | 25.412 | 0 | 0 | auction by Govt. of Sindh)
2) 845 / 33 | ESTABLISHMENT OF GOVT. GIRLS DEGREE | [5 empty] | Block-A & B Colouring in Progress
| @ Konkar Village |  | Gadap | 17.33 | 1.435 | 0.333 | Block-C, Plinth in progress
|  |  |  | 17.33 | 1.435 | 0.333
3) 802 / 37 | OPENING OF GOVT:DEGREE GIRLS COLLEGE |  |  | 21.957 | 0.32 | 0.051 | Completed & Handedover
| GIRLS COLLEGE NEW KARACHI. |  | New Karachi | 21.957 | 0.32 | 0.051
4) 817 / 38 | OPENING OF GOVERNMENT DEGREE
| COLLEGE IN ARTS & SCIENCE |  |  | 22.149 | 0.88 | 0.418 | Almost, Completed ready to Handedover
| Boys | @ New Karachi | New Karachi | 22.149 | 0.88 | 0.418
5) 819 / 39 | ESTABLISHMENT GOVERNMENT DEGREE COLLEGE
| @ LIAQUATABAD NO: (5) Near KMC Park Karachi | [5 empty] | Phase-I Almost Completed
| .Shifted to F.B.Area Block # 1, Karachi. |  |  | 23.289 | 3.25 | 1.852 | Phase-II, ……..do……..
|  |  | F.B.area | 23.289 | 3.25 | 1.852 | Phase-III, Plaster work in Progress
6) 832 / 40 | IMPROVEMENT OF RAIZ GOVT: |  |  | 8.701 | 0 | 0
| GIRLS COLLEGE @ Liaquatabad #10 |  | Liaquatabd | 8.701 | 0 | 0 | Completed & Handedover
7) 851 / 41 | CONSTT: OF GOVT DEGREE |  |  | 11.713 | 0.1 | 0.091
| COLLEGE @ Buffarzone N'Karachi. |  | New Karachi | 11.713 | 0.1 | 0.091 | Completed ready to Handedover
8) 852 / 42 | CONSTRUCTION OF GOVT: |  |  | 11.713 | 0.1 | 0.023
| DEGREE COLLEGE at F.B. Area. |  | F.B.area | 11.713 | 0.1 | 0.023 | Completed ready to Handedover
Sr. No: | Category |  | Town | Approved Cost | Allocation |  | Physical
ADP # |  | Name of Scheme/ |  |  | 2001-02 | During the | Progress
2001-02 |  | Project / Location |  |  |  | Year | Remarks
2001-02
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
9) 855 / 43 | ESTABLISHEMNT OF DEGREE COLLEGE | [5 empty] | Phase-I, almost Completed
| @Shaheed-e- Millat Azizabad |  |  | 30.672 | 5 | 3.013 | Phase-II, Colouring in progress
| Federal ".B".Area Karachi. |  | F.B.area | 30.672 | 5 | 3.013 | Phase-III, Colouring in Progress
(Ext: Development Work in Progress)
10) 859/44 | ADDITION/ ALTERATION IN APWA GOVT.
| COLLEGE FOR WOMEN Federal "B" AREA. |  |  | 3.93 | 1 | 0 | Completed & Handedover
|  |  | Gulberg | 3.93 | 1 | 0 | (PC-1, under revision)
11) 792/59 | OPENING OF GIRLS DEGREE COLLEGE
| @ Gulshan-e-Iqbal Karachi (91-92) |  | Gulshan' Iqbal | 17.507 | 0 | 0 | Ph-I G/Floor Partly Roof complete
|  |  |  | 17.507 | 0 | 0 | Ph-II Plinth beam level completed
12) 799 / 60 | ESTABLISHMENT OF DEGREE BOYS COLLEGE | [5 empty] | Ph-I G/Floor completed
| @ Gulzair-e-Hijri, Scheme # 33 Kyc: (91-92) |  | Gulshan' Iqbal | 17.507 | 1.0865 | 0 | Ph-II, Internal Plaster Completed
|  |  |  | 17.507 | 1.0865 | 0 | Ph-III, Finishing in Progress
13) 800/63 | OPENING OF COMPOSITE DEGREE COLLEGE
| @ Gulshan-e-Iqbal (Phase-II) ( 1991-92) |  | Gulshan' Iqbal | 6.828 | 0 | 0 | Completed & handedover
|  |  |  | 6.828 | 0 | 0
14) 818 / 86 | ESTABLISHMENT OF GOVT. BOYS DEGREE
| COLLEGE @ Surjani Town Karachi |  | New Karachi | 24.105 | 0 | 2.496 | Plaster in Progress
|  |  |  | 24.105 | 0 | 2.496
15 ) 853/89 | ESTABLISHMENT OF GOVT. DEGREE
| COLLEGE FOR MAN @ Mangopir |  | Gadap | 26.77 | 0 | 1.714 | At Finishing stage
|  |  |  | 26.77 | 0 | 1.714
|  | Total College |  | 269.583 | 11.7365 | 9.991
Sr. No: | Category |  | Town | Approved Cost | Allocation | Expdt: | Physical
ADP # |  | Name of Scheme/ |  |  | 2001-02 | During the | Progress
2001-02 |  | Project / Location |  |  |  | Year | Remarks
2001-02
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
1) 46 | ADDITION/ IMPROVEMENT OF DEGREE COLLEGE:
1 | Sir Syed Govt: Degree College Nazimabad Karachi (Phase-I) |  | Liaquatabad | 12.848 | 1.5 | 2.905
|  |  |  | 12.848 | 1.5 | 2.905
2) 47 | ADDITION OF COMPUTER CLASSES |  |  |  | 1
2 | Mujeeb-un-Nisa Govt Girls College New Karachi Distt: Central |  | New Karachi | 2.394 | 0 | 0.572
3 | Sir Syed Government College Kyc: |  | Liaquatabad | 2.394 | 0 | 0
|  |  |  | 4.788 | 1 | 0.572
4) 49 | ESTABLISHMENT/ OPENING OF GOVT: DEGREE COLLEGE.
11 | North Nazimabad |  | N'Nazim'd | 26.098 | 1.75 | 3.476
|  |  |  | 26.098 | 1.75 | 3.476
5) 50 | ESTABLISHMENT/ OPENING OF GOVT: DEGREE COLLEGE.
12 | North Karachi. |  | New Karachi | 26.098 | 2.5 | 4.979
|  |  |  | 26.098 | 2.5 | 4.979
1) 69 | ADDITION OF COMPUTER CLASSES IN COLLEGE OF KCY REGION
1 | Govt. Boys College Gulshan-e-Iqbal |  | Gulshan'Iqbal | 2.394 | 0 | 0
|  |  |  | 2.394 | 0 | 0
2) 70 | ESTABLISHMENT/ OPENING OF GOVT: DEGREE
| COLLEGE FOR BOYS AT |  |  |  | 0
1 | Gulshan-e-Johar scheme # 36 |  | Gulshan'Iqbal | 26.098 | 0 | 0
|  |  |  | 26.098 | 0 | 0
4) 74 | IMPROVEMENT OF KHATOON-E-PAKISTAN
| GOVT. GIRLS COLLEGE KARACHI: |  |  |  | 0.53
I | Repair to College Main Building |  | Gulshan'Iqbal | 4.146 | 0 | 0
2 | Repair to Block-A |  | Gulshan'Iqbal | 0 | 0 | 0
3 | Repair to Block-B ( B.Sc Block) |  | Gulshan'Iqbal | 0 | 0 | 0
4 | Addition of Computer Classes |  | Gulshan'Iqbal | 2.394 | 0 | 0.52
|  |  |  | 6.54 | 0.53 | 0.52
8) . | ADDITION OF CLASS ROOM IN EXISTING COLLEGE BUILDING :
0
1 | Rana Liaquat Ali Khan Govt. College Homeconomic ( 2 c/Room) |  | Gulshan'Iqbal | 1.133 | 0 | 0
2 | Govt. Degree College Shahrah-e-Iqbal (2 C/Room) |  | Gulshan'Iqbal | 1.133 | 0 | 0
|  |  |  | 2.266 | 0 | 0
|  | GRAND TOTAL |  | 107.13 | 7.28 | 12.452

## Public Malir (hidden)
Sr. No: | NMAE OF COMPONENTS | PCI COST (Original) In Million Rs. | PC-1 COST (Re-Structured) In Million Rs | ESTIMATED COST In Million Rs. | EXPENDITURE SINCE COMMENCEMENT (Rs in Million) | ALLOCATION REQUIRED WORK (Rs in Million) | JUSTIFICATION
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
A | NON RESIDENTIAL / ACADEMIC BLOCK
1 | Secondary School ( VI - X ) | 3.649 | 11.485 | 10.468 | 9.977 | 0.8 | Colouring Stage
2 | Higher Secondary School ( XI- XII) | 3.673
|  | 7.322 | 11.485 | 10.468 | 9.977 | 0.8
B | RESIDENTIAL
1 | Hostel Block ( 3 Nos) | 12.111 | 13.675 | 15.075 | 9.484 | 5.59 | Plastering Stage
2 | Dining Hall ( 2 Nos) | 3.14
3 | Principal's Residence | 0.69 | 1 | 5.535 | 5.27 | 1.5
4 | Vice Principal's Residence | 0.459 | 0.666 |  | 5.27 | 1.5 | Colouring Stage
5 | BPS-1 Flats | 0.857 | 1.418
6 | Double Storey Flats for Junior Staffs | 1.294 | 2.142
|  | 18.551 | 18.901 | 20.61 | 14.754 | 7.09
C | OTHER FACILITIES
1 | Gymnasium | 2.757 | 0 | 0 | 0.742 | 0 | (Deleted)
2 | Over Head Tank/Under Ground Tank | 0.7 | 1.4 | 1.48 | 1.318 | 0.5 | Nearing Completion
3 | Mini Market | 0.687 | 0 | 0 | 0 | 0 | (Deleted)
4 | Pump House | 0.036 | 0.051 | 0 | 0 | 0 | (Deleted)
5 | Clinic | 0.281 | 0 | 0 | 0 | 0 | (Deleted)
|  | 4.461 | 1.451 | 1.48 | 2.06 | 0.5
|  | 30.334 | 31.837 | 32.558 | 26.791 | 8.39
D | EXTERNAL DEVELOPMENT 15% | 4.5501 | 3.82 | 3.82 | 3.82 | 1.624 | Allied Work in Progress
1 | Cost of Land | 2 | 0 | 0 | 0 | 0 | This Plot is Govt. Property
2 | Compound Wall | 0.867 | 2.498 | 2.572 | 2.296 | 0.3 | Colouring Stage
3 | Consultant's Fee | 0.5 | 0.5 | 0.5 | 0.2 | 0.3 | Will be paid to Consultant
4 | Foot Ball Ground | 0.32 | 0 | 0 | 0 | 0 | (Deleted)
5 | Hockey Ground | 0.32 | 0 | 0 | 0 | 0 | (Deleted)
6 | Circket Ground | 0.35 | 0 | 0 | 0 | 0 | (Deleted)
7 | Tennis Court | 0.14 | 0 | 0 | 0 | 0 | (Deleted)
8 | Energization | 0 | 0.3 | 0.3 | 0 | 1.5 | Will be paid to KESC/ etc.
9 | Cost of Escallation | 2.393 | 2.819 | 0 | 2.819 | 0 | ***
|  | 41.7741 | 41.774 | 39.75 | 35.926 | 12.114

## Town wise ADP (hidden)
MONTHLY PROGRESS REPORT IN RESPECT OF NEW KARACHI TOWN A.D.P. SCHEMES 2001-02
EDUCATION WORKS-II KARACHI CITY GOVERNMENT
FOR THE MONTH OF SEPTEMBER-2001
<<Page1>>
Rs. In Million
| Category |  | Approved Sanctioned |  |  | Allocation | Released | E X P E N D I T U R E |  |  |  | Physical | Actual
ADP # |  | Name of Scheme/ | Taluka | Cost | Date | 2000-01 | 2001-02 | Upto | During the | During the | Total | Progress | Date of
2001-02 |  | Project / Location |  |  |  | Original |  | 6-2001. | Month | Year | Since | Remarks | Completion
[6 empty] | Modified |  |  |  | 2001-02 | Comme:
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 18 | 19
NEW KARACHI TOWN
MIDDLE SCHOOL
1 | CONSTT:/RE-CONSTT: OF BUILDING FOR
630/ 90 | EXISTING MIDDLE SCHOOL ( 1990-91)
1 | GBLSS | Moon Ligh 5/G-1 N/K | Kyc | 1.014 | 0 | 0 | 0 | 1.159 | 0 | 0 | 1.159 | Completed & H/Over | 1996-08-22
2 | GBLSS | 11/E U.P Society | Kyc | 1.014 | 0 | 0 | 0 | 1.12 | 0 | 0 | 1.12 | Completed & H/Over | 2005-04-14
3 | GBLSS | 5/G New Karachi. | Kyc | 1.014 | 0 | 0 | 0 | 1.098 | 0 | 0 | 1.098 | Completed & H/Over | 2004-03-31
|  | Total |  | 3.042 | 0 | 0 | 0 | 3.377 | 0 | 0 | 3.377
2 | UP-GRADATION OF PRIMARY TO MIDDLE
638/91 | IN SINDH ( 1991-92) |  |  |  |  | 0 | 0
1 | GBPS | 5/A-3, New Karachi | Kyc | 2.195 | 0 | 0 | 0 | 2.007 | 0 | 0 | 2.007 | Completed & H/Over | 2005-04-14
2 | GBPS | 5/G-1, New Karachi | Kyc | 2.195 | 0 | 0 | 0 | 0.814 | 0 | 0 | 0.814 | G/F Structure upto P/ Level | ***
3 | GBPS | 5/D-1,New Karachi. | Kyc | 2.195 | 0 | 0 | 0 | 0.936 | 0 | 0 | 0.936 | G/F upto Structure Complete | ***
4 | GBPS | 5/E-II, New Karachi. | Kyc | 2.195 | 0 | 0 | 0 | 0.794 | 0 | 0 | 0.794 | G/F upto Structure Complete | ***
|  | Total |  | 8.78 | 0 | 0 | 0 | 4.551 | 0 | 0 | 4.551 | (PC-1, Under Revision)
Works Lying abandoned
|  | Total Middle School |  | 11.822 | 0 | 0 | 0 | 7.928 | 0 | 0 | 7.928 | due to non-availability of funds
|  | Grand Total Middle School |  | 11.822 | 0 | 0 | 0 | 7.928 | 0 | 0 | 7.928
DISTRICT OFFICER
EDUCATION WORKS-II KARACHI
CITY GOVERNMENT
<<Page2>>
| Category |  | Approved Sanctioned |  |  | Allocation | Released | E X P E N D I T U R E |  |  |  | Physical | Actual
ADP # |  | Name of Scheme/ | Taluka | Cost | Date | 2000-01 | 2001-02 | Upto | During the | During the | Total | Progress | Date of
2001-02 |  | Project / Location |  |  |  | Original |  | 6-2001. | Month | Year | Since | Remarks | Completion
[6 empty] | Modified |  |  |  | 2001-02 | Comme:
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 18 | 19
New Karachi town | NEW KARACHI TOWN
SECONDARY EDUCATION
3 | CONSTT/ RE-CONST:OF BUILDING
672/141 | FOR EXISTING SCHOOL KCY. (1991-92) | [5 empty] | 0
1 | GGSS | Mujeeb-un-Nisa Karachi | KYC | 4.551 | 0 | 0 | 0 | 4.489 | 0 | 0 | 4.489 | Completed & Handed Over | 2004-04-12
|  |  |  | 4.551 | 0 | 0 | 0 | 4.489 | 0 | 0 | 4.489
4 | ADDITION OF C/ROOM IN EXIST:
675/142 | SCHOOL IN KARACHI (1991-92) | [5 empty] | 0
1 | GGSS | 5/B New Karachi 5 C/R | KYC | 1.215 | 0 | 0 | 0 | 1.24 | 0 | 0 | 1.24 | Completed & Handed Over | 2001-10-01
|  |  |  | 1.215 | 0 | 0 | 0 | 1.24 | 0 | 0 | 1.24
5 | OPENING OF DOUBLE SECTION HGH SCHOOL
680/130 | IN SINDH KARACHI DIVISION (1991-92)
1 |  | 5/A North Karachi. | KYC | 6.342 | 0 | 0 | 0 | 5.983 | 0 | 0 | 5.983 | Completed & H/Over | 1999-12-18
2 |  | 11/B North Karachi. | KYC | 6.342 | 0 | 0 | 0 | 4.335 | 0.105 | 0.652 | 4.987 | Colouring in Progress | **
|  |  |  | 12.684 | 0 | 0 | 0 | 10.318 | 0.105 | 0.652 | 10.97
6 | UP-GRADATION OF MIDDLE TO
703/147 | HIGH SCHOOL IN R/AREA (1994-95)
1 | GBLSS | District Council 11/D N/K | KYC | 1.607 | 0 | 0 | 0 | 1.676 | 0.085 | 0.588 | 2.264 | Completed
2 | GBLSS | 11/E New Karachi. | KYC | 1.607 | 0 | 0 | 0 | 1.726 | 0.541 | 0.541 | 2.267 | Completed & Handedover
|  |  |  | 3.214 | 0 | 0 | 0 | 3.402 | 0.626 | 1.129 | 4.531
7 | ADDITION C/R IN EXISTING
706/148 | HIGH SCHOOL IN SINDH(1994-95)
1 | GBSS | Sitar-e-Hydri 11/D North | KYC | 0.53 | 0 | 0 | 0 | 0.494 | 0 | 0 | 0.494 | Completed | 2005-08-04
Karachi ( 2C/Room )
|  |  |  | 0.53 | 0 | 0 |  | 0.494 | 0 | 0 | 0.494
| Grand Total Secondary School |  |  | 22.194 | 0 | 0 |  | 19.943 | 0.731 | 1.781 | 21.724
8 | ESTABLISHMENT OF MONO TECHNIC INSTITUTE
736/36 | DISTRICT CENTRAL KARACHI
1 |  | @ Sector 5/J N'Karachi. | KYC | 9.58 | 0 | 0 | 0 | 8.916 | 0 | 0 | 8.916 | Completed & Handedover
| Grand Total Mono Technic |  |  | 9.58 | 0 | 0 | 0 | 8.916 | 0 | 0 | 8.916
<<Page3>>
| Category |  | Approved Sanctioned |  |  | Allocation | Released | E X P E N D I T U R E |  |  |  | Physical | Actual
ADP # |  | Name of Scheme/ | Taluka | Cost | Date | 2000-01 | 2001-02 | Upto | During the | During the | Total | Progress | Date of
2001-02 |  | Project / Location |  |  |  | Original |  | 6-2001. | Month | Year | Since | Remarks | Completion
[6 empty] | Modified |  |  |  | 2001-02 | Comme:
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 18 | 19
NEW KARACHI TOWN
COLLEGE EDUCATION.
Phase-I & II, Completed & H/Over
1) 802/37 | OPENING OF GOVT:DEGREE GIRLS COLLEGE |  |  |  |  | 0 |  | 21.632 | 0 | 0.051 | 21.683 | Phase-III, Completed ready to Handedover
| GIRLS COLLEGE NEW KARACHI. |  | KYC | 21.957 | 0 | 0 | 0 | 21.632 | 0 | 0.051 | 21.683
2) 817/38 | OPENING OF GOVERNMENT DEGREE
| COLLEGE IN ARTS & SCIENCE | [6 empty] | 20.314 | 0.068 | 0.416 | 20.73 | Almost, Completed ready to Handedover | 2002-09-29
| Boys | @ New Karachi | KYC | 22.149 | 0 | 0 | 0 | 20.314 | 0.068 | 0.416 | 20.73
|  | Total College |  | 44.106 | 0 | 0 | 0 | 41.946 | 0.068 | 0.467 | 42.413
DISTRICT OFFICER
EDUCATION WORKS-II KARACHI
CITY GOVERNMENT
<<Page4>>
| Category |  | Approved Sanctioned |  |  | Allocation | Released | E X P E N D I T U R E |  |  |  | Physical | Actual
ADP # |  | Name of Scheme/ | Taluka | Cost | Date | 2000-01 | 2001-02 | Upto | During the | During the | Total | Progress | Date of
2001-02 |  | Project / Location |  |  |  | Original |  | 6-2001. | Month | Year | Since | Remarks | Completion
[6 empty] | Modified |  |  |  | 2001-02 | Comme:
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 18 | 19
NEW KARACHI TOWN
EDUCATION ADMINISTRATION
1) 869/180 | IMPROVEMENT OF EXISTING INSTITUTE BY
| PROVISION NECESSARY LACKING FACILITIES: | [5 empty] | 0
1 | GBPS | Sector 5/D New Karachi | KYC | 0.05 | 0 | 0 | 0 | 0.048 | 0 | 0 | 0.048 | Completed & Handedover
(Over Head Tank)
3 | GBPS | APWA 5/E New Karachi: | KYC | 0.12 | 0 | 0 | 0 | 0.124 | 0 | 0 | 0.124 | Completed & Handedover
4 | GBPS | Sector 5/F New Karachi. | KYC | 0.05 | 0 | 0 | 0 | 0.0425 | 0 | 0 | 0.0425 | Completed & Handedover
5 | GBPS | Sector 5/F New Karachi. | KYC | 0.098 | 0 | 0 | 0 | 0.0505 | 0 | 0 | 0.0505 | Completed & Handedover
6 | GBPS | Sector 5/F New Karachi. | KYC | 0.068 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.05 | Completed & Handedover
7 | GBPS | Sector 5/F New Karachi | KYC | 0.05 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.05 | Completed
Town Committee Karachi
8 | GBPS | Sector 5/F New Karachi | KYC | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Required
(Over Head Tank)
9 | GBSS | Sector 5/D New Karachi | KYC | 0.05 | 0 | 0 | 0 | 0.051 | 0 | 0 | 0.051 | Completed
(Over Head Tank)
|  |  |  | 0.536 | 0 | 0 | 0 | 0.416 | 0 | 0 | 0.416
|  | Grand Total |  | 88.238 | 0 | 0 | 0 | 79.149 | 0.799 | 2.248 | 81.397
DISTRICT OFFICER
EDUCATION WORKS-II KARACHI
CITY GOVERNMENT
MONTHLY PROGRESS REPORT IN RESPECT OF NEW KARACHI TOWN PRIORITY PROGRAMME 1997-98
EDUCATION WORKS-II KARACHI CITY GOVERNMENT
FOR THE MONTH OF "SEPTEMBER- 2001"
| Category |  | Approved Sanctioned |  |  | Allocation | Released | E X P E N D I T U R E |  |  |  | Physical | Actual
ADP # |  | Name of Scheme/ | Taluka | Cost | Date | 2001-02 | 2001-02 | Upto | During the | During the | Total | Progress | Date of
2001-02 |  | Project / Location |  |  |  | Original |  | 6-2001. | Month | Year | Since | Remarks | Compl:
[6 empty] | Modified |  |  |  | 2001-02 | Comme:
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 18 | 19
NEW KARACHI TOWN
1) 47 | ADDITION OF COMPUTER CLASSES
1 | Mujeeb-un-Nisa Govt Girls College |  | Kyc | 2.394 | 0 | 0 | 1 | 1.437 | 0.349 | 0.46 | 1.786 | Plastering Work in Progress
New Karachi Distt: Central
|  |  |  | 2.394 | 0 | 0 | 1 | 1.437 | 0.349 | 0.46 | 1.786
2) 48 | ADDITION OF CLASS ROOM IN EXISTING
| SECONDARY SCHOOL IN U/AREA KARACHI | [5 empty] | 1.1
2 | GBSS | 5/A-3, New Karachi. | Kyc | 1.45 | 0 | 0 | 0 | 0.351 | 0 | 0 | 0.351 | Upto Plinth Level
( 5 Class Rooms )
|  |  |  | 1.45 | 0 | 0 | 1.1 | 0.351 | 0 | 0 | 0.351
3) 49 | ESTABLISHMENT/ OPENING OF GOVT: DEGREE COLLEGE. | [10 empty] | Ph-I, Colouring in Progress
1 | North Karachi. |  | Kyc | 26.098 | 0 | 0 | 1.75 | 8 | 0.59 | 0.971 | 8.59 | Ph:II, upto plinth level.
4) 53 | UP-GRADATION OF MIDDLE TO HIGH SCHOOL IN KYC
1 | GBLSS | 5/G Moon Light N'Karachi | Kyc | 3.964 | 0 | 0 | 1.5 | 1.511 | 0.192 | 0.244 | 1.755 | Plastering in Progress
|  |  |  | 3.964 | 0 | 0 | 1.5 | 1.511 | 0.192 | 0.244 | 1.755
5) 55 | UP-GRADATION OF PRIMARY TO MIDDKE SCHOOL | [5 empty] | 0.75
1 | GBPS | Sector 5/C-2, N/K. | Kyc | 3.562 | 0 | 0 | 0 | 1.148 | 0 | 0 | 1.148 | G/Floor Roof slab Completed
2 | GBPS | 5/B-2, N' Karachi. | Kyc | 3.562 | 0 | 0 | 0 | 1.956 | 0.363 | 0.363 | 2.319 | colouring in Progress
|  |  |  | 7.124 | 0 | 0 | 0.75 | 3.104 | 0.363 | 0.363 | 3.467
6) . | INTRODUCTION OF XI & XII IN CLASSES IN EXISTING
(BOYS/GIRLS) SECONDARY SCHOOL IN U/AREA KYC:
1 | GBSS | APWA 5/E New Karachi. |  | 7 | 0 | 0 | 0 | 2.717 | 0 | 0 | 2.717 | Roof Partly laid work lying
|  |  |  | 7 | 0 | 0 | 0 | 2.717 | 0 | 0 | 2.717 | abaandond.
|  | GRAND TOTAL |  | 48.03 | 0 | 0 | 6.1 | 17.12 | 1.494 | 2.038 | 18.666
MONTHLY PROGRESS REPORT IN RESPECT OF NORTH NAZIMABAD TOWN A.D.P. SCHEMES 2001-02
EDUCATION WORKS-II KARACHI CITY GOVERNMENT
FOR THE MONTH OF SEPTEMBER-2001
<<Page1>>
Rs. In Million
| Category |  | Approved Sanctioned |  |  | Allocation | Released | E X P E N D I T U R E |  |  |  | Physical | Actual
ADP # |  | Name of Scheme/ | Taluka | Cost | Date | 2000-01 | 2001-02 | Upto | During the | During the | Total | Progress | Date of
2001-02 |  | Project / Location |  |  |  | Original |  | 6-2001. | Month | Year | Since | Remarks | Completion
[6 empty] | Modified |  |  |  | 2001-02 | Comme:
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 18 | 19
NORTH NAZIMABAD TOWN
MIDDLE SCHOOL
1 | CONSTT:/RE-CONSTT: OF BUILDING FOR
630/ 90 | EXISTING MIDDLE SCHOOL ( 1990-91) | [5 empty] | 0
1 | GBLSS | Karachi Elemantry | Kyc | 1.014 | 0 | 0 | 0 | 1.183 | 0 | 0 | 1.183 | Completed & H/Over | 14/01/96.
2 | GBLSS | 5/A Buffarzone N/K | Kyc | 1.014 | 0 | 0 | 0 | 0.975 | 0 | 0 | 0.975 | Completed & H/Over | 1996-07-02
3 | GBLSS | Bright Grammar N/Naz: | Kyc | 1.014 | 0 | 0 | 0 | 1.111 | 0 | 0 | 1.111 | Completed & H/Over | 09/07/99.
|  | Total |  | 3.042 | 0 | 0 | 0 | 3.269 | 0 | 0 | 3.269
Works Lying abandoned
|  | Total Middle School |  | 3.042 | 0 | 0 | 0 | 3.269 | 0 | 0 | 3.269 | due to non-availability of funds
|  | Grand Total Middle School |  | 3.042 | 0 | 0 | 0 | 3.269 | 0 | 0 | 3.269
DISTRICT OFFICER
EDUCATION WORKS-II KARACHI
CITY GOVERNMENT
<<Page2>>
| Category |  | Approved Sanctioned |  |  | Allocation | Released | E X P E N D I T U R E |  |  |  |  | Actual
ADP # |  | Name of Scheme/ | Taluka | Cost | Date | 2001-02 | 2001-02 | Upto | During the | During the | Total | Physical Progress | Date of
2000-01 |  | Project / Location |  |  |  | Original |  | 6-2001. | Month | Year | Since | Remarks | Completion
[6 empty] | Modified |  |  |  | 2001-02 | Comme:
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 18 | 19
NORTH NAZIMABAD TOWN
COLLEGE EDUCATION.
Phase-I & II, Completed & H/Over
2) 851/41 | CONSTT: OF GOVT DEGREE
| COLLEGE @ Buffarzone N'Karachi. |  | KYC | 11.713 | 0 | 0 | 0 | 12.119 | 0.019 | 0.019 | 12.138 | Completed ready to Handedover | ***
|  | Total College |  | 11.713 | 0 | 0 | 0 | 12.119 | 0.019 | 0.019 | 12.138
DISTRICT OFFICER
EDUCATION WORKS-II KARACHI
CITY GOVERNMENT
MONTHLY PROGRESS REPORT IN RESPECT OF NORTH NAZIMABAD TOWN PRIORITY PROGRAMME 1997-98
EDUCATION WORKS-II KARACHI CITY GOVERNMENT
FOR THE MONTH OF "SEPTEMBER- 2001"
| Category |  | Approved Sanctioned |  |  | Allocation | Released | E X P E N D I T U R E |  |  |  | Physical | Actual
ADP # |  | Name of Scheme/ | Taluka | Cost | Date | 2001-02 | 2001-02 | Upto | During the | During the | Total | Progress | Date of
2001-02 |  | Project / Location |  |  |  | Original |  | 6-2001. | Month | Year | Since | Remarks | Compl:
[6 empty] | Modified |  |  |  | 2001-02 | Comme:
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 18 | 19
NORTH NAZIMABAD TOWN
1) 50 | ESTABLISHMENT/ OPENING OF GOVT: DEGREE COLLEGE. | [10 empty] | Phase-I Plaster in Progress
1 | North Nazimabad |  | Kyc | 26.098 | 0 | 0 | 2.5 | 4.4 | 1.465 | 1.947 | 5.865
2) 52 | ESTABLISHMENT OF SINGLE
SECTION HIGH SCHOOL IN U/AREA
1 | Opening of Single Section High |  | Kyc | 4.189 | 0 | 0 | 0.2 | 2.35 | 0.055 | 0.2 | 2.55 | Structure Completed
School @ Bufar Zone
|  |  |  | 4.189 | 0 | 0 | 0.2 | 2.35 | 0.055 | 0.2 | 2.55
3) 54 | UP-GRADATION OF SAIFEE EIDEE ZAHABI INSTITUTE
OF TECHNOLOGY TO B.TECH LEVEL CLASSES KYC
3 | North Nazimabad Karachi |  | Kyc | 11.913 | 0 | 0 | 1.5 | 4.095 | 0.491 | 0.547 | 4.586 | Phase-I Plaster in porgress
Phase-II, Partly Roof Laid
|  |  |  | 11.913 | 0 | 0 | 1.5 | 4.095 | 0.491 | 0.547 | 4.586
|  | GRAND TOTAL |  | 42.2 | 0 | 0 | 4.2 | 10.845 | 2.011 | 2.694 | 13.001
DISTRICT OFFICER
EDUCATION WORKS-II KARACHI
CITY GOVERNMENT
MONTHLY PROGRESS REPORT IN RESPECT OF GULBER TOWN A.D.P. SCHEMES 2001-02
EDUCATION WORKS-II KARACHI CITY GOVERNMENT
FOR THE MONTH OF SEPTEMBER-2001
Rs. In Million
| Category |  | Approved Sanctioned |  |  | Allocation | Released | E X P E N D I T U R E |  |  |  | Physical | Actual
ADP # |  | Name of Scheme/ | Taluka | Cost | Date | 2000-01 | 2001-02 | Upto | During the | During the | Total | Progress | Date of
2001-02 |  | Project / Location |  |  |  | Original |  | 6-2001. | Month | Year | Since | Remarks | Completion
[6 empty] | Modified |  |  |  | 2001-02 | Comme:
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 18 | 19
GULBERG TOWN
SECONDARY EDUCATION
1 | UP-GRADATION OF MIDDLE SCHOOL
662/40 | TO HIGH SCHOOL(1991-92) |  |  |  |  | 0 | 0
1 | GGPS | Wazir Jahan Karachi. | KYC | 3.278 | 0 | 0 | 0 | 3.685 | 0 | 0 | 3.685 | Completed & Handed Over | 2005-06-03
|  |  |  | 3.278 | 0 | 0 | 0 | 3.685 | 0 | 0 | 3.685
2 | CONSTT / RE-CONSTT: OF BUILDING
667/124 | FOR EXISTING HIGH SCHOOL (1988-89). | [5 empty] | 0
1 | GBPS | Block # 9 F.B area Kyc: | KYC | 2.28 | 0 | 0 | 0 | 2.577 | 0 | 0 | 2.577 | Completed & Handed Over | 12/11/90.
2 | GBPS | Technical Age F.B.Area | KYC | 2.28 | 0 | 0 | 0 | 2.484 | 0 | 0 | 2.484 | Completed & Handed Over | 27/4/97.
(Shifted to Ibrahim Ali
Bhai B# 15 F.B.Area Kyc)
|  |  |  | 4.56 | 0 | 0 | 0 | 5.061 | 0 | 0 | 5.061
3 | ADDITION C/R IN EXISTING
706/148 | HIGH SCHOOL IN SINDH(1994-95) | [5 empty] | 0.45
1 | GGSS | Dastagir No:9 | KYC | 1.06 | 0 | 0 | 0 | 0 | 0 | 0.282 | 0.282 | Plinth Completed
Federal "B" area (4 C/R)
2 | GHSS | Ibrahim Ali Bhai | KYC | 1.06 | 0 | 0 | 0 | 0.095 | 0.168 | 0.168 | 0.263 | …do…
Federal "B" area (4 C/R)
3 | GGSS | Allama Iqbal Block # 16 | KYC | 0.53 | 0 | 0 | 0 | 0.483 | 0 | 0 | 0.483 | Completed & Handedover | 2004-07-26
F.B.Area Kyc (2 C/Room)
|  |  |  | 2.65 | 0 | 0 | 0.45 | 0.578 | 0.168 | 0.45 | 1.028
| Grand Total Secondary School |  |  | 10.488 | 0 | 0 | 0.45 | 9.324 | 0.168 | 0.45 | 9.774
<<Page2>>
| Category |  | Approved Sanctioned |  |  | Allocation | Released | E X P E N D I T U R E |  |  |  |  | Actual
ADP # |  | Name of Scheme/ | Taluka | Cost | Date | 2001-02 | 2001-02 | Upto | During the | During the | Total | Physical Progress | Date of
2001-02 |  | Project / Location |  |  |  | Original |  | 6-2001. | Month | Year | Since | Remarks | Completion
[6 empty] | Modified |  |  |  | 2001-02 | Comme:
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 18 | 19
GULBERG TOWN
COLLEGE EDUCATION.
[7 empty] | 0.32 |  |  |  |  | Phase-I & II, Completed & H/Over
1) 819/39 | ESTABLISHMENT GOVERNMENT DEGREE COLLEGE
| @ LIAQUATABAD NO: (5) Near KMC | [5 empty] | 3.25 |  |  |  |  | Phase-I Almost Completed
| Park Karachi.Shifted to F.B.Area | [10 empty] | Phase-II, ……..do……..
| Block # 1, Karachi. |  | KYC | 23.289 | 0 | 0 | 3.25 | 9.483 | 0.411 | 1.289 | 10.772 | Phase-III, Plaster work in Progress | ***
0
2) 852/42 | CONSTRUCTION OF GOVT:
| DEGREE COLLEGE at F.B. Area. |  | KYC | 11.713 | 0 | 0 | 0 | 11.974 | 0 | 0.019 | 11.993 | Completed ready to Handedover | ***
5
3) 855/43 | ESTABLISHEMNT OF DEGREE COLLEGE | [10 empty] | Phase-I, Completed
| @Shaheed-e- Millat Azizabad | [10 empty] | Phase-II, Colouring in progress
| Federal ".B".Area Karachi. |  | KYC | 30.672 | 0 | 0 | 5 | 19.325 | 0.017 | 1.591 | 20.916 | Phase-III, Colouring in Progress | ***
1
4) 859/44 | ADDITION/ ALTERATION IN APWA
GOVT. COLLEGE FOR WOMEN
| Federal "B" AREA: |  | KYC | 3.93 | 0 | 0 | 1 | 3.998 | 0 | 0 | 3.998 | Completed & Handedover | 2004-11-03
|  | Total College |  | 69.604 | 0 | 0 | 9.25 | 44.78 | 0.428 | 2.899 | 47.679
DISTRICT OFFICER
EDUCATION WORKS-II KARACHI
CITY GOVERNMENT
MONTHLY PROGRESS REPORT IN RESPECT OF GULBERG TOWN PRIORITY PROGRAMME 1997-98
EDUCATION WORKS-II KARACHI CITY GOVERNMENT
FOR THE MONTH OF "SEPTEMBER- 2001"
| Category |  | Approved Sanctioned |  |  | Allocation | Released | E X P E N D I T U R E |  |  |  | Physical | Actual
ADP # |  | Name of Scheme/ | Taluka | Cost | Date | 2001-02 | 2001-02 | Upto | During the | During the | Total | Progress | Date of
2001-02 |  | Project / Location |  |  |  | Original |  | 6-2001. | Month | Year | Since | Remarks | Compl:
[6 empty] | Modified |  |  |  | 2001-02 | Comme:
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 18 | 19
GULBERG TOWN
1) 48 | ADDITION OF CLASS ROOM IN EXISTING
| SECONDARY SCHOOL IN U/AREA KARACHI | [5 empty] | 1.1
1 | GBSS | Allama Iqbal F.B.Area | Kyc | 1.16 | 0 | 0 | 0 | 0.263 | 0 | 0 | 0.263 | F/Floor Roof completed
( 4 Class Rooms)
2 | GBSS | New Method F.B.Area | Kyc | 1.16 | 0 | 0 | 0 | 0.687 | 0.023 | 0.023 | 0.71 | Roof slab Completed
( 4 Class Rooms)
3 | GBSS | Anglo Oriential Block-15, | Kyc | 1.45 | 0 | 0 | 0 | 0.944 | 0.103 | 0.103 | 1.047 | Roof slab Completed
F.B.Area Karachi.( 5 C/Room)
|  |  |  | 3.77 | 0 | 0 | 1.1 | 1.894 | 0.126 | 0.126 | 2.02
2) 49 | ESTABLISHMENT/ OPENING OF GOVT: DEGREE COLLEGE. | [10 empty] | Ph-I, Colouring in Progress
4 | North Karachi. |  | Kyc | 26.098 | 0 | 0 | 1.75 | 8 | 0.59 | 0.971 | 8.59 | Ph:II, upto plinth level.
3) 50 | ESTABLISHMENT/ OPENING OF GOVT: DEGREE COLLEGE. | [10 empty] | Phase-I Plaster in Progress
5 | North Nazimabad |  | Kyc | 26.098 | 0 | 0 | 2.5 | 4.4 | 1.465 | 1.947 | 5.865
4) 51 | ESTABLISHMENT OF MONOTECHIC INSTITUTE
AT DISTRICT CENTRAL KARACHI.
6 | F.B Area (Phase-I) |  | Kyc | 21.38 | 0 | 0 | 1.75 | 3.881 | 0.491 | 1.75 | 6.122 | Ph-I) Colouring Stage.
Ph-II) Plinth work in Progress
|  |  |  | 21.38 | 0 | 0 | 1.75 | 3.881 | 0.491 | 1.75 | 6.122
5) 55 | UP-GRADATION OF PRIMARY TO MIDDKE SCHOOL | [5 empty] | 0.75
7 | GBPS | Allama Iqbal Bl-16,F.B.Area | Kyc | 3.562 | 0 | 0 | 0 | 1.115 | 0 | 0 | 1.115 | S/S F/Floor roof Completed
8 | GGPS | Kamyab Bl-15,F.B.Area | Kyc | 3.562 | 0 | 0 | 0 | 1.742 | 0.226 | 0.387 | 2.129 | Plastering in Progress
|  |  |  | 7.124 | 0 | 0 | 0.75 | 2.857 | 0.226 | 0.387 | 3.244
|  | GRAND TOTAL |  | 84.47 | 0 | 0 | 7.85 | 21.032 | 2.898 | 5.181 | 25.841
MONTHLY PROGRESS REPORT IN RESPECT OF LIAQUATABAD TOWN A.D.P. SCHEMES 2001-02
EDUCATION WORKS-II KARACHI CITY GOVERNMENT
FOR THE MONTH OF SEPTEMBER-2001
<<Page1>>
| Category |  | Approved Sanctioned |  |  | Allocation | Released | E X P E N D I T U R E |  |  |  | Physical | Actual
ADP # |  | Name of Scheme/ | Taluka | Cost | Date | 2000-01 | 2001-02 | Upto | During the | During the | Total | Progress | Date of
2001-02 |  | Project / Location |  |  |  | Original |  | 6-2001. | Month | Year | Since | Remarks | Completion
[6 empty] | Modified |  |  |  | 2001-02 | Comme:
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 18 | 19
LIAQUATABAD TOWN
MIDDLE SCHOOL
1 | CONSTT:/RE-CONSTT: OF BUILDING FOR
630/ 90 | EXISTING MIDDLE SCHOOL ( 1990-91)
1 | GBLSS | Zia-ul-Uloom Firdous Col | Kyc | 1.014 | 0 | 0 | 0 | 0.727 | 0 | 0 | 0.727 | Under Litigation lying abandoned at roof Level
|  | Total |  | 1.014 | 0 | 0 | 0 | 0.727 | 0 | 0 | 0.727
|  | Total Middle School |  | 1.014 | 0 | 0 | 0 | 0.727 | 0 | 0 | 0.727 | due to non-availability of funds
|  | Grand Total Middle School |  | 1.014 | 0 | 0 | 0 | 0.727 | 0 | 0 | 0.727
DISTRICT OFFICER
EDUCATION WORKS-II KARACHI
CITY GOVERNMENT
<<Page2>>
| Category |  | Approved Sanctioned |  |  | Allocation | Released | E X P E N D I T U R E |  |  |  |  | Actual
ADP # |  | Name of Scheme/ | Taluka | Cost | Date | 2001-02 | 2001-02 | Upto | During the | During the | Total | Physical Progress | Date of
2000-01 |  | Project / Location |  |  |  | Original |  | 6-2001. | Month | Year | Since | Remarks | Completion
[6 empty] | Modified |  |  |  | 2001-02 | Comme:
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 18 | 19
LIAQUATABAD TOWN
SECONDARY EDUCATION
4 | UP-GRADATION OF MIDDLE SCHOOL
662/40 | TO HIGH SCHOOL(1991-92) |  |  |  |  | 0 | 0
1 | GBLSS | Major Zia Uddin Memorial | KYC | 3.278 | 0 | 0 | 0 | 3.539 | 0 | 0 | 3.539 | Completed & Handed Over | 2005-06-03
|  |  |  | 3.278 | 0 | 0 | 0 | 3.539 | 0 | 0 | 3.539
5 | CONSTT / RE-CONSTT: OF BUILDING
667/124 | FOR EXISTING HIGH SCHOOL (1988-89). | [5 empty] | 0
1 | GBSS | Green Land Premises | KYC | 2.28 | 0 | 0 | 0 | 2.241 | 0 | 0 | 2.241 | Completed & Handed Over | 08/05/91.
Happy Dale Nazim'd Kyc
2 | GGSS | Al Zohra Karachi. | KYC | 2.28 | 0 | 0 | 0 | 2.477 | 0 | 0 | 2.477 | Completed & Handed Over | 04/04/91.
|  |  |  | 4.56 | 0 | 0 | 0 | 4.718 | 0 | 0 | 4.718
7 | ADDITION OF C/ROOM IN EXIST:
675/142 | SCHOOL IN KARACHI (1991-92) | [5 empty] | 0
2 | SSHS | Liaquatabad No:3(3 C/R) | KYC | 0.729 | 0 | 0 | 0 | 0.586 | 0 | 0 | 0.586 | Completed & Handed Over | ***
3 | GBSS | Liaquatabad No:2(3 C/R) | KYC | 0.729 | 0 | 0 | 0 | 0.772 | 0 | 0 | 0.772 | Completed & Handed Over | ***
4 | GBSS | Liaquatabad No:3(3 C/R) | KYC | 0.729 | 0 | 0 | 0 | 0.8 | 0 | 0 | 0.8 | Completed & Handed Over | ***
5 | GGSS | Liaquatabad No:2(3C/R) | KYC | 0.729 | 0 | 0 | 0 | 0.759 | 0 | 0 | 0.759 | Completed & Handed Over | ***
|  |  |  | 2.916 | 0 | 0 | 0 | 2.917 | 0 | 0 | 2.917
8 | ADD C/R IN EXISTING SECONDARY
677/ 127 | SCHOOL IN KARACHI (1992-93) (2 C/R) | [5 empty] | 0.9
1 | GGSS | F.C Area Karachi. | KYC | 0.682 | 0 | 0 | 0 | 0.115 | 0.052 | 0.168 | 0.283 | Finishing in Progress
|  |  |  | 0.682 | 0 | 0 | 0.9 | 0.115 | 0.052 | 0.168 | 0.283
10 | INTRODUCTION / ADD: OF XI-XII CLASSES IN EXISTING
696/146 | HIGH SECONDARY SCHOOL IN SINDH ( 1991-92) | [5 empty] | 0
1 | GGSS | Liaquatabad No:4, | KYC | 3.97 | 0 | 0 | 0 | 3.055 | 0 | 0 | 3.055 | Ground Floor Completed
2 | GBSS | Liaquatabad No:4, | KYC | 3.97 | 0 | 0 | 0 | 1.371 | 0 | 0 | 1.371 | Work lying due to non availability of Funds
3 | GGSS | Ishat-ul-Quran Nazim'd | KYC | 3.97 | 0 | 0 | 0 | 2.937 | 0 | 0 | 2.937 | Work lying abondend at plaster Stage
|  |  |  | 11.91 | 0 | 0 | 0 | 7.363 | 0 | 0 | 7.363 | (PC-1 is Under Revision)
| Grand Total Secondary School |  |  | 23.346 | 0 | 0 | 0.9 | 18.652 | 0.052 | 0.168 | 18.82
<<Page3>>
| Category |  | Approved Sanctioned |  |  | Allocation | Released | E X P E N D I T U R E |  |  |  |  | Actual
ADP # |  | Name of Scheme/ | Taluka | Cost | Date | 2001-02 | 2001-02 | Upto | During the | During the | Total | Physical Progress | Date of
2001-02 |  | Project / Location |  |  |  | Original |  | 6-2001. | Month | Year | Since | Remarks | Completion
[6 empty] | Modified |  |  |  | 2001-02 | Comme:
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 18 | 19
LIAQUATABAD TOWN
COLLEGE EDUCATION.
0
5) 832/40 | IMPROVEMENT OF RAIZ GOVT:
| GIRLS COLLEGE @ Liaquatabad #10 |  | KYC | 8.701 | 0 | 0 | 0 | 8.314 | 0 | 0 | 8.314 | Completed & Handedover | 2001-04-03
|  | Total College |  | 8.701 | 0 | 0 | 0 | 8.314 | 0 | 0 | 8.314
|  | Grand Total |  | 33.061 | 0 | 0 | 0.9 | 27.693 | 0.052 | 0.168 | 27.861
DISTRICT OFFICER
EDUCATION WORKS-II KARACHI
CITY GOVERNMENT
MONTHLY PROGRESS REPORT IN RESPECT OF LIAQUATABAD TOWN PRIORITY PROGRAMME 1997-98
EDUCATION WORKS-II KARACHI CITY GOVERNMENT
FOR THE MONTH OF "SEPTEMBER- 2001"
| Category |  | Approved Sanctioned |  |  | Allocation | Released | E X P E N D I T U R E |  |  |  | Physical | Actual
ADP # |  | Name of Scheme/ | Taluka | Cost | Date | 2001-02 | 2001-02 | Upto | During the | During the | Total | Progress | Date of
2001-02 |  | Project / Location |  |  |  | Original |  | 6-2001. | Month | Year | Since | Remarks | Compl:
[6 empty] | Modified |  |  |  | 2001-02 | Comme:
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 18 | 19
LIAQUATABAD TOWN
1) 46 | ADDITION/ IMPROVEMENT OF DEGREE COLLEGE:
1 | Sir Syed Govt: Degree College |  | Kyc | 12.848 | 0 | 0 | 1.5 | 3.65 | 0.069 | 1.015 | 3.719 | Structure Completed
Nazimabad Karachi (Phase-I)
|  |  |  | 12.848 | 0 | 0 | 1.5 | 3.65 | 0.069 | 1.015 | 3.719
2) 47 | ADDITION OF COMPUTER CLASSES
1 | Sir Syed Government College Kyc: |  | Kyc | 2.394 | 0 | 0 | 0 | 1.416 | 0 | 0 | 1.416 | Completed
|  |  |  | 2.394 | 0 | 0 | 0 | 1.416 | 0 | 0 | 1.416
3) 48 | ADDITION OF CLASS ROOM IN EXISTING
| SECONDARY SCHOOL IN U/AREA KARACHI | [5 empty] | 1.1
1 | GGSS | Liaquatabad No:4 Karachi. | Kyc | 0.87 | 0 | 0 | 0 | 0.426 | 0.093 | 0.093 | 0.519 | Colouring Stage.
( 3 Class Rooms )
2 | GBSS | Liaquatbad No:4 Karachi. | Kyc | 1.16 | 0 | 0 | 0 | 1.099 | 0 | 0 | 1.099 | Completed & Handed
( 4 Class Rooms )
|  |  |  | 2.03 | 0 | 0 | 1.1 | 1.525 | 0.093 | 0.093 | 1.618
4) 55 | UP-GRADATION OF PRIMARY TO MIDDKE SCHOOL | [5 empty] | 0.75
1 | GBPS | Liaquatabad No 4 Karachi. | Kyc | 3.562 | 0 | 0 | 0 | 0.704 | 0 | 0 | 0.704 | Completed upto Lintel Level
|  |  |  | 3.562 | 0 | 0 | 0.75 | 0.704 | 0 | 0 | 0.704
|  | GRAND TOTAL |  | 20.834 | 0 | 0 | 3.35 | 7.295 | 0.162 | 1.108 | 7.457
DISTRICT OFFICER
EDUCATION WORKS-II KARACHI
CITY GOVERNMENT
MONTHLY PROGRESS REPORT IN RESPECT OF GULSHAN-E-IQBAL TOWN A.D.P. SCHEMES 2001-02
EDUCATION WORKS-II KARACHI CITY GOVERNMENT
FOR THE MONTH OF SEPTEMBER-2001
Rs. In Million
| Category |  | Approved Sanctioned |  |  | Allocation | Released | E X P E N D I T U R E |  |  |  | Physical | Actual
ADP # |  | Name of Scheme/ | Taluka | Cost | Date | 2000-01 | 2001-02 | Upto | During the | During the | Total | Progress | Date of
2001-02 |  | Project / Location |  |  |  | Original |  | 6-2001. | Month | Year | Since | Remarks | Completion
[6 empty] | Modified |  |  |  | 2001-02 | Comme:
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 18 | 19
GULSHAN-e-IQBAL TOWN
MIDDLE / SECONDARY EDUCATION
1) 634/ 138 | UP-GRADATION OF MIDDLE TO HIGH SCHOOL
IN RURAL AREA KARACHI
1 | GGMS | Leemo Gabol Goth |  | 1.286 | [7 empty] | Finishing in Progress
|  |  |  | 1.286 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2) 134 | ESTABLISHMENT OF SINGLE SECTION HIGH
SCHOOL IN SINDH ( 1994-95)
1 | GGHS | Schal Balouch Goth Shifted | [9 empty] | Lintel Level (tender Remaining)
|  | from GGHS Sukkur |  | 4.297
|  |  |  | 4.297 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3) 634 | UP-GRADATION OF PRIMARY TO MIDDLE
SCHOOL (Under Middle School Project)
1 | GBPS | Schal Goth Karachi. |  | 3.619 | [7 empty] | Completed & Handedover
|  |  |  | 3.619 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4) 617 | UP-GRADATION OF PRIMARY TO MIDDLE
IN RUBAN AREA ( 1990-91)
1 | GPS | Yar Muhammad Jokhio |  | 0.966 | [7 empty] | Finishing in Progress
|  |  |  | 0.966 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5) 90 | CONSTT: /RE-CONSTT: OF BUILDING FOR
EXISTING MIDDLE SCHOOL ( 1990-91)
1 | GBLSS | No:5, Drigh Colony Shifted to
|  | GGSS Gulshan-e-Iqbal |  | 1.014 | [7 empty] | Plastering in Progress
|  |  |  | 1.014 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6) 91 | UP-GRADATION OF PRIMARY TO MIDDLE
SCHOOL IN URBAN AREA ( 1991-92)
1 | GBPS | Gulshan-e-Iqbal Block-1 |  | 2.195 | [7 empty] | Completed & Handedover
|  |  |  | 2.195 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7) 127 | ADDITON OF CLASSROOM IN EXISTING
SECONDARY SCHOOL ( 1992-93)
1 | GGSS | Khatoon-e-Pakistan (2C/R) |  | 2.195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Tender under Process
|  |  |  | 2.195 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8) 140 | UP-GRADATION OF MIDDLE TO HIGH
SCHOOL IN SINDH URBAN AREA
1 | GBLSS | Leemo Gabol Gulshan-e-Iqbal |  | 3.719 | [7 empty] | Plinth in Progress
|  |  |  | 3.719 | 0 | 0 | 0 | 0 | 0 | 0 | 0
<<Page2>>
| Category |  | Approved Sanctioned |  |  | Allocation | Released | E X P E N D I T U R E |  |  |  | Physical | Actual
ADP # |  | Name of Scheme/ | Taluka | Cost | Date | 2000-01 | 2001-02 | Upto | During the | During the | Total | Progress | Date of
2001-02 |  | Project / Location |  |  |  | Original |  | 6-2001. | Month | Year | Since | Remarks | Completion
[6 empty] | Modified |  |  |  | 2001-02 | Comme:
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 18 | 19
GULSHAN-e-IQBAL TOWN
COLLEGE EDUCATION
1) 59 | OPENING OF GIRLS DEGREE COLLEGE
| @ Gulshan-e-Iqbal Karachi (91-92) |  |  | 17.507 | [7 empty] | Ph-I G/Floor Partly Roof complete
|  |  |  | 17.507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Ph-II Plinth beam level completed
2) 60 | ESTABLISHMENT OF DEGREE BOYS COLLEGE
@ Gulzair-e-Hijri Karachi
| Scheme # 33 Kyc: (91-92) |  |  | 17.507 | [7 empty] | Ph-I G/Floor completed
|  |  |  | 17.507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Ph-II, Internal Plaster Completed
Ph-III, Plaster completed
3) 63 | OPENING OF COMPOSITE DEGREE COLLEGE
| @ Gulshan-e-Iqbal (Phase-II) |  |  | 6.828 | [7 empty] | Completed & handedover
| ( 1991-92) |  |  | 6.828 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DISTRICT OFFICER
EDUCATION WORKS-II KARACHI
CITY GOVERNMENT
MONTHLY PROGRESS REPORT IN RESPECT OF GULSHAN-E-IQBAL TOWN PRIORITY PROGRAMME 1997-98
EDUCATION WORKS-II KARACHI CITY GOVERNMENT
FOR THE MONTH OF SEPTEMBER-2001
| Category |  | Approved Sanctioned |  |  | Allocation | Released | E X P E N D I T U R E |  |  |  | Physical | Actual
ADP # |  | Name of Scheme/ | Taluka | Cost | Date | 2000-01 | 2001-02 | Upto | During the | During the | Total | Progress | Date of
2001-02 |  | Project / Location |  |  |  | Original |  | 6-2001. | Month | Year | Since | Remarks | Completion
[6 empty] | Modified |  |  |  | 2001-02 | Comme:
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 18 | 19
GULSHAN-e-IQBAL TOWN
1) /69 | ADDITION OF COMPUTER CLASSES IN
COLLEGE OF KARACHI REGION
1 | Govt. Boys College Gulshan-e-Iqbal |  |  | 2.394 | [7 empty] | Plastering in Progress
|  |  |  | 2.394 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2) 70 | ESTABLISHMENT/ OPENING OF SINGLE | [10 empty] | Disput of plot Sattled find not
| SECTION HIGH SCHOOL IN URBAN AREA | [10 empty] | find not available to start the
1 | Gulshan-e-Johar scheme # 36 |  |  | 26.098 | [7 empty] | level.
|  |  |  | 26.098 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3) 73 | ESTABLISHMENT OF SINGLE SECTION | [10 empty] | G/Floor Structure Completed
| HIGH SCHOOL IN URBAN AREA KARACHI | [10 empty] | F/Floor Block Masonary upto
1 | Gulshan-e-Iqbal Karachi |  |  | 4.189 | [7 empty] | Lintel Level.
|  |  |  | 4.189 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4) 74 | IMPROVEMENT OF KHATOON-E-PAKISTAN
| GOVT. GIRLS COLLEGE KARACHI: |  |  | 4.146
I | Repair to College Main Building |  |  | 0 | [7 empty] | Carparking, A.C Sheet lying in roof
2 | Repair to Block-A |  |  | 0 | [7 empty] | Wood work in progress
3 | Repair to Blcok-B ( B.Sc Block) |  |  | 0 | [7 empty] | Completed & Handedover
4 | Addition of Computer Classes |  |  | 2.394 | [7 empty] | Rood in progress
|  |  |  | 6.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5) 76 | INTRODUCTION OF XI & XII CLASSES
| IN EXISTING SECONDARY SCHOOL | [10 empty] | Block Masonary upto Lintel
1 | GBLSS | Gulshan-e-Iqbal Karachi |  | 7 | [7 empty] | Level.
|  |  |  | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6) 79 | UP-GRADATION OF PRIMARY TO
MIDDLE SCHOOL IN URBAN AREA
1 | B & G | Govt. Jamshad Road School
|  | Ghosia Colony Karachi |  | 3.562 | [7 empty] | G/Floor roof in Progress
|  |  |  | 3.562 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7) 80 | UP-GRADATION OF PRIMARY TO MIDDLE
SCHOOL IN URBAN AREA KARACHI
1 | GGSS | Gulshan-e-Iqbal Block-6
|  | (10 Classroom) |  | 2.67 | [7 empty] | Roof laid completed
|  |  |  | 2.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0
<<Page4>>
| Category |  | Approved Sanctioned |  |  | Allocation | Released | E X P E N D I T U R E |  |  |  | Physical | Actual
ADP # |  | Name of Scheme/ | Taluka | Cost | Date | 2000-01 | 2001-02 | Upto | During the | During the | Total | Progress | Date of
2001-02 |  | Project / Location |  |  |  | Original |  | 6-2001. | Month | Year | Since | Remarks | Completion
[6 empty] | Modified |  |  |  | 2001-02 | Comme:
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 18 | 19
GULSHAN-e-IQBAL TOWN
8) 81 | ESTABLISHMENT / OPENING OF GOVT.
| DEGREE COLLEGE: | [10 empty] | Super Structure Block Masonary
| Gulistan-e-Jouhar Scheme # 36 |  |  | 26.098 | [7 empty] | in Progress.
|  |  |  | 26.098 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9) 82 | ADDITION OF CLASS ROOM IN EXITING
DEGREE COLLEGE KARACHI
1 | Rana Liaquat Ali Khan College Home-Economic
| ( 2 Classroom) |  |  | 1.133 | [7 empty] | Completed & Handedover
2 | Construction of Degree College Gulshan-e-Iqbal
| Karachi. |  |  | 1.133 | [7 empty] | Finishing in Progress
|  |  |  | 2.266 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DISTRICT OFFICER
EDUCATION WORKS-II KARACHI
CITY GOVERNMENT
MONTHLY PROGRESS REPORT IN RESPECT OF GADAP TOWN PRIORITY PROGRAMME 1997-98
EDUCATION WORKS-II KARACHI CITY GOVERNMENT
FOR THE MONTH OF SEPTEMBER-2001
| Category |  | Approved Sanctioned |  |  | Allocation | Released | E X P E N D I T U R E |  |  |  | Physical | Actual
ADP # |  | Name of Scheme/ | Taluka | Cost | Date | 2000-01 | 2001-02 | Upto | During the | During the | Total | Progress | Date of
2001-02 |  | Project / Location |  |  |  | Original |  | 6-2001. | Month | Year | Since | Remarks | Completion
[6 empty] | Modified |  |  |  | 2001-02 | Comme:
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
G A D A P TOWN
1) 86 | UP-GRADATION OF PRIMARY TO MIDDLE
SCHOOL IN RURAL AREA (91-92) PROG
1 | GBPS | Haji Dur Muhammad Goth | 1.11 |  |  |  |  | 1.094 | 0 | 0 | 1.094
2 | GBPS | Mazar Khan Jokhio | 1.141 |  |  |  |  | 0.776 | 0 | 0 | 0.776 | Completed 7 Handedover
3 | GBPS | Murrad Memon Goth | 1.361 |  |  |  |  | 1.062 | 0 | 0 | 1.062 | C.C. topping +W/Work
4 | GBPS | Hashim Gabol Goth | 1.11 |  |  |  |  | 0.672 | 0 | 0 | 0.672 | Completed 7 Handedover
5 | GGPS | Ali Muhammad Goth | 1.11 |  |  |  |  | 1.104 | 0 | 0 | 1.104 | C.C. topping +W/Work
6 | GBPS | Salah Muhammad Jumani | 1.476 |  |  |  |  | 1.11 | 0 | 0 | 1.11 | Completed 7 Handedover
7 | GBPS | Haji Hassan Chohar | 1.476 |  |  |  |  | 0.999 | 0 | 0 | 0.999 | Completed 7 Handedover
8 | GGPS | Haji Sheedi Village | 1.11 |  |  |  |  | 1.103 | 0 | 0 | 1.103 | Doors/Windows to be Fixed
9 | GGPS | Gadap Village | 1.472 |  |  |  |  | 1.047 | 0 | 0 | 1.047 | Completed 7 Handedover
10 | GGPS | Pahlwan Goth | 1.11 |  |  |  |  | 1.11 | 0 | 0 | 1.11 | Doors/Windows to be Fixed
11 | GPS | Sheeo Zakria | 1.446 |  |  |  |  | 1.101 | 0 | 0 | 1.101 | Completed 7 Handedover
12 | GBPS | KDA Filter Hashim Khash: | 1.11 |  |  |  |  | 1.098 | 0 | 0 | 1.098 | Colouring Stage
13 | GBPS | Hakoo Khan Brohi. | 1.11 |  |  |  |  | 1.75 | 0 | 0 | 1.75 | Completed 7 Handedover
Completed 7 Handedover
|  |  | 16.142 | 0 | 0 | 0 | 0 | 14.026 | 0 | 0 | 14.026
2) 89 | UP-GRADATION OF PRIMARY TO MIDDLE
SCHOOL INR/AREA ( 91-92 Programme)
1 | GBPS | Binjo Jokhio | 1.633 |  |  |  |  | 1.533 |  |  | 1.533 | Completed & Handedover
2 | GGPS | Kamal Khan Jokhio | 2.2 |  |  |  |  | 1.471 |  |  | 1.471 | Structure Competed
|  |  | 3.833 | 0 | 0 | 0 | 0 | 3.004 | 0 | 0 | 3.004
12) 87 | CONSTT: OF BUILDING FOR EXISTING SHELTERLESS
PRIMARY SCHOOL IN R/AREA KARACHI
<<Page2>>
| Category |  | Approved Sanctioned |  |  | Allocation | Released | E X P E N D I T U R E |  |  |  | Physical | Actual
ADP # |  | Name of Scheme/ | Taluka | Cost | Date | 2000-01 | 2001-02 | Upto | During the | During the | Total | Progress | Date of
2001-02 |  | Project / Location |  |  |  | Original |  | 6-2001. | Month | Year | Since | Remarks | Completion
[6 empty] | Modified |  |  |  | 2001-02 | Comme:
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 18 | 19
G A D A P TOWN
3) 643/86 | CONSTRUCTION OF BUILDING FOR SHELTERLESS | [10 empty] | Plinth Completed S/S in Progress
| EXISTING PRIMARY SCHOOL IN R/AREA (2000-01) | [10 empty] | upto Roof Level
1 | ** | Haji Waryal Bandijo | 0.895 | [8 empty] | Tender under Scrutiny
2 | GBPS | Main Wasyo Kanroo | 0.895 | [8 empty] | S/Structure in Progress
3 | GBPS | Qasim Gabol S / Highway | 0.895 | [8 empty] | work Order issue
4 | GBPS | Konkar | 0.895 | [8 empty] | Tender under Scrutiny
5 | GBPS | Haji Umaid Ali | 0.895 | [8 empty] | work Order issue
6 | GBPS | Islamia Konkar | 0.895 | [8 empty] | work Order issue
7 | GBPS | Faiz Muhammad Gabol | 0.895 | [8 empty] | S/Structure in Progress
8 | GBPS | Kamal Burro | 0.895 | [8 empty] | S/Structure in Progress
9 | GBPS | Haji Sher Muhammad Bandijo(Moidan) | 0.895 | [8 empty] | Tender under Scrutiny
10 | GBPS | Thohar Kana Moidan | 0.895 | [8 empty] | Tender under Scrutiny
11 | GBPS | Ali Muhammad Chutto | 0.895 | [8 empty] | Tender under Scrutiny
12 | GBPS | Haji Hamal Balouch | 0.895 | [8 empty] | work Order issue
13 | GBPS | Moehan Chutto | 0.895 | [8 empty] | work Order issue
14 | GBPS | Photo Gabol Kathore | 0.895 | [8 empty] | work Order issue
15 | GBPS | Bapera Mohalla Memon.G. | 0.895 | [8 empty] | Tender under Scrutiny
16 | GGMOHS | Kamal Bari Dumba Goth | 0.895 | [8 empty] | Tender under Scrutiny
17 | GGMOHS | Mazar Khan Jokhio | 0.895 | [8 empty] | work Order issue
18 | GBPS | Soofan Jokhio | 0.895 | [8 empty] | Tender under Scrutiny
19 | GBPS | Nabi Bux Gadap | 0.895 | [8 empty] | S/Structure in Progress
20 | GBPS | Ali Muhammad Godar | 0.895 | [8 empty] | work Order issue
21 | GBPS | Ali Dad Gabol | 0.895 | [8 empty] | work Order issue
22 | GBPS | Darya Khan Gabol | 0.859 | [8 empty] | work Order issue
23 | GBPS | Bakhrani Mohalla | 0.895 | [8 empty] | work Order issue
24 | GBPS | Khan Muhammad Jokhio | 0.895 | [8 empty] | work Order issue
25 | GBPS | Lal Bux Kachelo | 0.895 | [8 empty] | work Order issue
26 | GBPS | Hayat Goundar | 0.895 | [8 empty] | S/Structure in Progress
27 | GBPS | Siraj Ahmed Kathore | 0.895 | [8 empty] | Plinth Completed
|  |  | 24.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3) 643-C | CONSOLIDATION / IMPROVEMENT OF BUILDING
IN EXISTING MIDDLE SCHOOL (2000-01 PROG)
1 | GGLSS | Konkar | 2.608 | [8 empty] | Tender under Scrutiny
2 | GBLSS | Khamiso Jokhio | 2.608 | [8 empty] | Excavation Started
3 | GGLSS | Soomar Kandani | 2.608 | [8 empty] | Work order issued
4 | GGLSS | Radho Jokhio | 2.608 | [8 empty] | Excavation Started
|  |  | 10.432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
<<Page3>>
| Category |  | Approved Sanctioned |  |  | Allocation | Released | E X P E N D I T U R E |  |  |  | Physical | Actual
ADP # |  | Name of Scheme/ | Taluka | Cost | Date | 2000-01 | 2001-02 | Upto | During the | During the | Total | Progress | Date of
2001-02 |  | Project / Location |  |  |  | Original |  | 6-2001. | Month | Year | Since | Remarks | Completion
[6 empty] | Modified |  |  |  | 2001-02 | Comme:
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 18 | 19
G A D A P TOWN
5) 649/138 | UP-GRADATION OF MIDDLE SCHOOL TO HIGH
SCHOOL IN RURAL AREA KARACHI ( 1990-91)
1 |  | Faiz Muhammad Bikik | 1.286 |  |  |  |  | 1.286 | 0 | 0 | 1.286 | Completed & Handedover
2 |  | Dumlotti No: 3 | 1.284 |  |  |  |  | 1.284 | 0 | 0 | 1.284 | Completed & Handedover
|  |  | 2.57 | 0 | 0 | 0 | 0 | 2.57 | 0 | 0 | 2.57
6) 650/139 | UP-GRADATION OF MIDDLE TO HIGH SCHOOL
IN RURAL AREA ( 1991-92 PROGRAMME)
1 | GBLSS | Salah Muhammad | 3.088 |  |  |  |  | 1.57 | 0 | 0 | 1.57 | W/Work &Work Stoped by the Contractor
2 | GBLSS | Ali Khan | 3.088 |  |  |  |  | 0.332 | 0 | 0 | 0.332 | Work at plinth Level.
|  |  | 6.176 | 0 | 0 | 0 | 0 | 1.902 | 0 | 0 | 1.902
7) 666 / 123 | UP-GRADATION OF MIDDLE SCHOOLTO HIGH
SCHOOL IN SINDH R/AREA (1992-93 Prog:)
1 | GBLSS | Darsano Channo | 1.604 |  |  |  |  | 0.01 | 0 | 0 | 0.01 | Tender Re-invited
|  |  | 1.604 | 0 | 0 | 0 | 0 | 0.01 | 0 | 0 | 0.01
8) 130 | OPENING OF DOUBLE SECTION HIGH SCHOOL
( 1991-92 PROGRAMME)
1 | @ Mullah Essa Goth |  | 6.342 |  |  |  |  | 5.56 | 0 | 0 | 5.56 | Completed & Handedover
|  |  | 6.342 | 0 | 0 | 0 | 0 | 5.56 | 0 | 0 | 5.56
9) 686 / 143 | ADDITION OF XI-XII CLASSES IN EXISTING
SECONDARY SCHOOL ( 1988-89 PROG:)
1 | @ Kamal Khan Jokhio |  | 6.674 |  |  |  |  | 2.792 | 0 | 0 | 2.792 | Roof Level & W/Stoped by the Contractor
|  |  | 6.674 | 0 | 0 | 0 | 0 | 2.792 | 0 | 0 | 2.792
10) 689/144 | INTRODUCTION / ADDITION OF XI-XII CLASSES
IN EXISTING HIGH SCHOOL ( 1989-90 PROG:)
1 | GGSS | Murrad Memon Goth | 3.576 |  |  |  |  | 3.497 | 0 | 0 | 3.497 | Completed & Handedover
|  |  | 3.576 | 0 | 0 | 0 | 0 | 3.497 | 0 | 0 | 3.497
11) 699/134 | ESTABLISHMENT OF SINGLE SECTION HIGH
SCHOOL IN SINDH ( 5 Units) 1994-95 Prog:
1 | Schal Balouch Goth Shifted from GGHS Sukkur |  | Kyc | 4.297 | 1999-04-21 | 0 | 0 | 1.76 | 0 | 0 | 1.76 | Lintel Level tender reinvited
|  |  |  | 4.297 | *** | 0 | 0 | 1.76 | 0 | 0 | 1.76 | for remaining works
11) 147 | UP-GRADATION OF MIDDLE SCHOOL TO
HIGH SCHOOL ( 1989-90 PRG:)
1 | @ Noor Muhammad Burfat |  | 1.595 | [8 empty] | Tender Re-invited
|  |  | 1.595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Category |  | Approved Sanctioned |  |  | Allocation | Released | E X P E N D I T U R E |  |  |  | Physical | Actual
ADP # |  | Name of Scheme/ | Taluka | Cost | Date | 2000-01 | 2001-02 | Upto | During the | During the | Total | Progress | Date of
2001-02 |  | Project / Location |  |  |  | Original |  | 6-2001. | Month | Year | Since | Remarks | Completion
[6 empty] | Modified |  |  |  | 2001-02 | Comme:
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 18 | 19
G A D A P TOWN
12) 148 | ADDITION OF CLASS ROOM IN EXISTING
HIGH SCHOOL IN SINDH R/AREA( 1994-95 PRG:)
1 | GBSS | Murrad Memon Goth | 0.919 |  |  |  |  | 0.995 | 0 | 0 | 0.995 | Colouring in Progress
2 | GHS | Dumba Goth | 0.46 |  |  |  |  | 0 |  |  |  | Tender to be invited.
|  |  | 1.379 | 0 | 0 | 0 | 0 | 0.995 | 0 | 0 | 0.995
13) 25 | ESTABLISHMENT OF MONOTECHNIC INSTITUTE | [10 empty] | Block-A, Colouring in Progress
| @ Murrad Memon Goth |  | 10.87 |  |  |  |  | 9.226 | 0 | 0 | 9.226 | Block-B, Colouring in Progress
|  |  | 10.87 | 0 | 0 | 0 | 0 | 9.226 | 0 | 0 | 9.226 | W/Suuply in Prog. & C/Wall Completed
14) 32 | ESTABLISHMENT OF GOVT. COLLEGE | [10 empty] | Block-A , Structure Completed
| OF EDUCATION B.Ed. & M.Ed. | [10 empty] | Block-B, Partly roof Laid .
| @ Darsano Channo |  | 25.412 |  |  |  |  | 15.169 | 0 | 0 | 15.169 | Block-C, roof to be laid.
|  |  | 25.412 | 0 | 0 | 0 | 0 | 15.169 | 0 | 0 | 15.169
15) 33 | ESTABLISHMENT OF GOVT. GIRLS DEGREE | [10 empty] | Block-A & B Colouring in Progress
| @ Konkar |  | 17.33 |  |  |  |  | 9.448 | 0 | 0 | 9.448 | Block-C, in progress
|  |  | 17.33 | 0 | 0 | 0 | 0 | 9.448 | 0 | 0 | 9.448
TAMEER-E-SINDH PROGRAMME
16)…… | ESTABLISHMENT OF PUBLIC SCHOOL @ Gadap.
1 | Secondary School ( VI- X )
2 | Higher Secondary School |  | 11.485 |  |  |  |  | 9.977 | 0 | 0 | 9.977 | Colouring in Progress
3 | Hostel Block |  | 13.675 |  |  |  |  | 9.484 | 0 | 0 | 9.484 | Colouring in Progress
4 | Residential Block |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | Colouring in Progress
5 | Gymnasium Hall |  | 0 |  |  |  |  | 0.742 | 0 | 0 | 0.742 | Plinth Laid
6 | Over Head Tank |  | 1.4 |  |  |  |  | 1.435 | 0 | 0 | 1.435 | Pump room in Progress
7 | Compound Wall |  | 2.498 |  |  |  |  | 2.225 | 0 | 0 | 2.225 | Completed
|  |  | 29.058 | 0 | 0 | 0 | 0 | 23.863 | 0 | 0 | 23.863
<<Page5>>
| Category |  | Approved Sanctioned |  |  | Allocation | Released | E X P E N D I T U R E |  |  |  | Physical | Actual
ADP # |  | Name of Scheme/ | Taluka | Cost | Date | 2000-01 | 2001-02 | Upto | During the | During the | Total | Progress | Date of
2001-02 |  | Project / Location |  |  |  | Original |  | 6-2001. | Month | Year | Since | Remarks | Completion
[6 empty] | Modified |  |  |  | 2001-02 | Comme:
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 18 | 19
G A D A P TOWN
17) 66 | MIDDLE SCHOOL PROJECT (ADB Loan # 1278 P.K)
1 | GBPS | Haji A. Karim | 3.619 | [8 empty] | Completed & Handedover
2 | GGPS | Hashim Khaskhali | 2.332 | [8 empty] | Completed
3 | GGPS | Mazar Khan Jokhio | 2.332 | [8 empty] | Completed
4 | GGPS | Dumba Goth | 2.332 | [8 empty] | Completed
5 | GBPS | Jam Kando | 1.751 | [8 empty] | Completed
6 | GBPS | Haji Noor Muhammad | 1.751 | [8 empty] | Completed & Handedover
|  |  | 14.117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18) 86 | ESTABLISHMENT OF GOVT. BOYS DEGREE
| COLLEGE @ Surjani Town Karachi |  | 24.105 |  |  |  |  | 13.396 | 0 | 0 | 13.396 | Plaster in Progress
|  |  | 24.105 | 0 | 0 | 0 | 0 | 13.396 | 0 | 0 | 13.396
19 ) 89 | ESTABLISHMENT OF GOVT. DEGREE
| COLLEGE FOR MAN @ Ghopir |  | 26.77 |  |  |  |  | 11.139 | 0 | 0 | 11.139 | Plaster in Progress
|  |  | 26.77 | 0 | 0 | 0 | 0 | 11.139 | 0 | 0 | 11.139
[8 empty] | 3.823 | 0 | 0 | 3.823 | Colouring in Progress
|  |  |  | 0 | 0 | 0 | 0 | 3.823 | 0 | 0 | 3.823
21)….. | CONVERSION INTO GIRLS COMMUNITY
MODLE SCHOOL UNDER (GPEDP-II)
1 | Haji Sheedi Goth |  | 1.536 | [8 empty] | Completd & Handedover
2 | Ansoo Goth Kathoro |  | 1.536 | [8 empty] | Upto Plinth level Work Stop by PM (GGMSP)
3 | Haji Noor Muhammad Burgat Moidan |  | 1.536 | [8 empty] | Finishing in Progress
(GADAP)
|  |  | 4.608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DISTRICT OFFICER
EDUCATION WORKS-II KARACHI
CITY GOVERNMENT

## Sheet1 (3) (hidden)
STATEMENT SHOWING THE DETAIL OF THE INCOMPLETE/ ON-GOING / ABANDONED SCHEMES.
Education Works Division-II ( Karachi City Government)
NAME OF HEAD OF ACCOUTNS
A= Annual Development Programme (A.D.P)
B= Tameer-e-Watan Programme. (T.W.P)
C= Tameer-e- Sindh Programme (T.S.P)
D= Social Action Programme (S.A.P)
Rs. ( In Million)
Sr. No: | Name of Scheme With Location | Date of Approval |  | Approved Cost |  | Status of | Physical | Exxpend: | Alllocation | Incomplete | The Scheme which | Scheme which have | Scheme completed | Scheme which are | Scheme which are required uo
ADP No: |  | Original | Revised | Original | Revised | Scheme | Progress | Incurred | 2001-02 | abondoned Scheme | could be considered | been completedphysicaly | but PC-IV not | not required by the | be completed given priority |  |  |  | Funds
2001-02 | [6 empty] | % age | till date |  | reason for not | for discontinuing | but SNE not sanctioned | submitted | A.D. but can be | Phase-I | Phase-II | Phase-III | Remarks / Other | Required
[10 empty] | completing the | with reasons | (given priority of | approval | utilized by other |  |  |  | recommandation | to comple
[10 empty] | scheme within the |  | commissioning the scheme) |  | Departments |  |  |  |  | the Unit /
[10 empty] | planned period |  |  |  | rational to be given |  |  |  |  | Scheme
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
A.D.P. SCHEMES ( S.A.P)
MIDDLE SCHOOL
1) 643/86 | CONSTRUCTION OF BUILDING FOR SHELTERLESS
| EXISTING PRIMARY SCHOOL IN R/AREA (2000-01) | [10 empty] | EDO (Education ) |  | EDO (Education )
| 30 Units |  |  | 26.85 | 0 | On-going | 0 | 0 | 0 | Funds Not Available | N.A | may be referred | Not yet Complete | may be referred | Ist Priority |  |  | All in progress | 26.85
2) *** / 87 | CONSTRUCITON OF BUIDING FOR EXISTING Shelterless
| PRIMARY SCHOOL IN R/AREA KARACHI | [10 empty] | EDO (Education ) |  | EDO (Education )
| 11 Units |  |  | 21.087 | 0 | On-going | 0 | 0 | 0 | Funds Not Available | N.A | may be referred | Not yet Complete | may be referred | ….do…. |  |  | All in progress | 21.087
3) *** / 92 | CONSOLIDATION / IMPROVEMENT OF BUILDING
| IN EXISTING MIDDLE SCHOOL (2000-01 PROG) | [10 empty] | EDO (Education ) |  | EDO (Education )
| 9 Units |  |  | 23.472 | 0 | On-going | 0 | 0 | 0 | Funds Not Available | N.A | may be referred | Not yet Complete | may be referred | ….do…. |  |  | All in progress | 23.472
4) 617/ 88 | UP-GRADATION OF MIDDLE TO HIGH
| SCHOOL RURAL AREA KARACHI | [10 empty] | EDO (Education ) |  | EDO (Education ) |  |  |  | 5 No. In progress | 5.43
| 15 Units |  |  | #REF! | 0 | On-going | #REF! | #REF! | 0 | No Funds At all | N.A | may be referred | Not yet Complete | may be referred | ….do…. |  |  | 10 No Completed
5) 618/ 89 | UP-GRADATION OF PRIAMRY TO MIDDLE
| SCHOOL R/AREA KARACHI ( 1991-92) | [10 empty] | EDO (Education ) |  | EDO (Education ) |  |  |  | 1 No. In progress | 1.4
| 2 Units |  |  | #REF! | 0 | On-going | #REF! | #REF! | 0 | No Funds At all | N.A | may be referred | Not yet Complete | may be referred | ….do…. |  |  | 1 No Completed
6) 630/90 | CONSTRUCTION / RE-CONSTRUCTION OF
BUILDING FOR EXISTING MIDDLE SCHOOL
| (1990-91 PROGRAMME ) KCY: DIVISION | [8 empty] | Abandoned due to |  | EDO (Education ) |  | EDO (Education ) |  |  |  | 7 Nos. Completed | 0.95
| 8 Units |  |  | #REF! | 0 | On-going | #REF! | #REF! | 0 | Court Stay | N.A | may be referred | Not yet Complete | may be referred | ….do…. |  |  | 1 Under Litigsation
7) 638/91 | UP-GRADATION OF PRIMARY TO MIDDLE
| SCHOOL ( 1991-92 ) | [8 empty] | Abandoned due to |  | EDO (Education ) |  | EDO (Education ) |  |  |  | 3 Nos. In progress | 3.88
| 5 Units |  |  | #REF! | 0 | On-going | #REF! | #REF! | 0 | paucity of Funds | N.A | may be referred | Not yet Complete | may be referred | ….do…. |  |  | 2 Completed
| Total Middle School ( S.A.P ) |  |  | #REF! | *** | *** | *** | #REF! | *** | *** | *** | *** | *** | *** | *** | *** | *** | *** | 83.069
TECHNICAL EDUCATION:
8 )760/25 | ESTABLISHMENT OF MONOTECHNIC
| INSTITUTE @ Murrad Memon Goth Gadap | [10 empty] | EDO (Education ) |  | EDO (Education ) |  |  |  | 1 No Completed | 4
| 2 Units |  |  | #REF! | 0 | On going | #REF! | #REF! | 1 | paucity of Funds | N.A | may be referred | Not yet Complete | may be referred | Ist Priority |  |  | 1 No in Progress
| TOTAL Technical Education |  |  | #REF! | *** | *** | *** | #REF! | 1 | *** | *** | *** | *** | *** | *** | *** | *** | *** | 4
Rs. ( In Million)
Sr. No: | Name of Scheme With Location | Date of Approval |  | Approved Cost |  | Status of | Physical | Exxpend: | Alllocation | Incomplete | The Scheme which | Scheme which have | Scheme completed | Scheme which are | Scheme which are required uo
ADP No: |  | Original | Revised | Original | Revised | Scheme | Progress | Incurred | 2001-02 | abondoned Scheme | could be considered | been completedphysicaly | but PC-IV not | not required by the | be completed given priority |  |  |  | Funds
2001-02 | [6 empty] | % age | till date |  | reason for not | for discontinuing | but SNE not sanctioned | submitted | A.D. but can be | Phase-I | Phase-II | Phase-III | Remarks / Other | Required
[10 empty] | completing the | with reasons | (given priority of | approval | utilized by other |  |  |  | recommandation | to comple
[10 empty] | scheme within the |  | commissioning the scheme) |  | Departments |  |  |  |  | the Unit /
[10 empty] | planned period |  |  |  | rational to be given |  |  |  |  | Scheme
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
NON- S.A.P ( Secondary Education )
9) 708/ 80 | ESTABLISHMENT OF SINGLE SECTION
| HIGH SCHOOL | [10 empty] | EDO (Education ) |  | EDO (education ) |  |  |  | 1 Completed
| ( 1 UNIT ) | 0 | 0 | 10.862 | 0 | On going | #REF! | #REF! | 0 | Paucity of Funds | N.A | may be referred | Not yet Completed | may be referred | Ist Priority |  |  | 1No In progress | 4.184
10) 666/123 | UP-GRADATION OF MIDDLE SCHOOL
| TO HIGH SCHOOL IN SINDH KYC (1992-93) | [10 empty] | EDO (Education ) |  | EDO (education )
| 1 Unit | 0 | 0 | #REF! | 0 | On going | #REF! | 0 | 0 | No Funds at all | N.A | may be referred | Not yet Completed | may be referred | ….do…. |  |  | 1 No. In progress | 1.5
11) 667/124 | CONSTT / RE-CONSTT: OF BUILDING
| FOR EXISTING HIGH SCHOOL (1988-89). | [10 empty] | EDO (Education ) |  | EDO (education )
| 4 Units | 0 | 0 | 9.12 | 0 | On going | 107.2259 | 9.779 | 0 | No Funds at all | N.A | may be referred | Not yet Completed | may be referred | ….do…. |  |  | All units Completed | 0
12 ) 677/127 | ADDITIONAL CLASS ROOM IN EXISTING
| SEECONDARY SCHOOL IN SINDH (1992-93) | [10 empty] | EDO (Education ) | [5 empty] | 2 Nos. In progress
| 3 Units | 0 | 0 | #REF! | 0 | On going | #REF! | #REF! | 0.9 | Ongoing | N.A | may be referred | Not yet Completed | may be referred | ….do…. |  |  | 1 No Completed | 0.82
13) 680/130 | OPENING / ESTT: OF DOUBLE SECTION
| HIGH SCHOOL IN SINDH ( 1990-91 PROG:) | [10 empty] | EDO (Education )
| 3 Units | 0 | 0 | #REF! | 0 | On going | #REF! | #REF! | #REF! | Ongoing | N.A | may be referred | Not yet Completed | may be referred | ….do…. |  |  | 3 Nos Completed | 1
14 ) 699/134 | ESTABLISHMENT OF SINGLE SECITON HIGH
| SCHOOL IN SINDH. ( 1994-95) | [10 empty] | EDO (Education )
| 1 Unit | 0 | 0 | #REF! | 0 | On going | #REF! | #REF! | 0.2 | Paucity of Funds | N.A | may be referred | Not yet Completed | may be referred | ….do…. |  |  | 1 No in Progress | 2.9
15) 649/138 | UP-GRADATION OF MIDDLE SCHOOL
| TO HIGH SCHOOL IN SINDH KYC: (1990-91) | [10 empty] | EDO (Education ) |  | EDO (education ) |  |  |  | 1 Nos. In progress
| 3 Units | 0 | 0 | #REF! | 0 | On going | #REF! | #REF! | 0 | Paucity of Funds | N.A | may be referred | Not yet Completed | may be referred | ….do…. |  |  | 2 Completed | 0.777
16 ) 650/139 | UP-GRADATION TO MIDDLE TO HIGH IN
| RURAL AREA KARACHI( 1990-91 PROG:) | [10 empty] | EDO (Education ) |  | EDO (education )
| 2 Units | 0 | 0 | #REF! | 0 | On going | #REF! | 1.902 | 0 | No Funds at all | N.A | may be referred | Not yet Completed | may be referred | ….do…. |  |  | 2 Nos. In progress | 5.2
Not yet Completed
17 ) 662/140 | UP-GRADATION OF MIDDLE SCHOOL TO
| HIGH SCHOOL IN KARACHI ( 1991-92) | [10 empty] | EDO (Education ) |  | EDO (education ) |  |  |  | 2 Completed
| 3 Units | 0 | 0 | #REF! | 0 | On going | #REF! | #REF! | 0 | No Funds at all | N.A | may be referred | Not yet Completed | may be referred | ….do…. |  |  | 1 No. In progress | 4.59
18) 672/ 141 | CONSTT/ RE-CONST:OF BUILDING
| FOR EXISTING SCHOOL KCY. (1991-92) | [10 empty] | EDO (Education )
| 1 Units | 0 | 0 | 4.551 | 0 | On going | 98.6377 | 4.489 | #REF! | Ongoing | N.A | may be referred | Not yet Completed | may be referred | ….do…. |  |  | 3 Nos Completed | 0
19) 675/142 | ADDITION OF C/ROOM IN EXISTING SECONDARY
| SCHOOL IN KARACHI (1991-92) | [10 empty] | EDO (Education )
| 4 Units | 0 | 0 | 4.331 | 0 | On going | 95.9825 | 4.157 | #REF! | Ongoing | N.A | may be referred | Not yet Completed | may be referred | ….do…. |  |  | 3 Nos Completed | 0
20) 686/143 | ADDITION OF XI - XII CLASSES IN EXISTING
| SECONDARY SCHOOL (1988-89 PROGR:) | [10 empty] | EDO (Education )
| 1 Unit | 0 | 0 | #REF! | 0 | On going | #REF! | #REF! | 0 | No Funds at all | N.A | may be referred | Not yet Completed | may be referred | ….do…. |  |  | 1 No in Progress | 0
Rs. ( In Million)
Sr. No: | Name of Scheme With Location | Date of Approval |  | Approved Cost |  | Status of | Physical | Exxpend: | Alllocation | Incomplete | The Scheme which | Scheme which have | Scheme completed | Scheme which are | Scheme which are required uo
ADP No: |  | Original | Revised | Original | Revised | Scheme | Progress | Incurred | 2001-02 | abondoned Scheme | could be considered | been completedphysicaly | but PC-IV not | not required by the | be completed given priority |  |  |  | Funds
2001-02 | [6 empty] | % age | till date |  | reason for not | for discontinuing | but SNE not sanctioned | submitted | A.D. but can be | Phase-I | Phase-II | Phase-III | Remarks / Other | Required
[10 empty] | completing the | with reasons | (given priority of | approval | utilized by other |  |  |  | recommandation | to comple
[10 empty] | scheme within the |  | commissioning the scheme) |  | Departments |  |  |  |  | the Unit /
[10 empty] | planned period |  |  |  | rational to be given |  |  |  |  | Scheme
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
21) 689/144 | INTRODUCTION / ADDITION OF XI-XII CLASSES
| IN EXISTING HIGH SCHOOL ( 1989-90 PROG:) | [10 empty] | EDO (Education )
| 1 Unit | 0 | 0 | #REF! | 0 | On going | #REF! | #REF! | 0 | No Funds at all | N.A | EDO (Education ) | Not yet Completed | may be referred | Ist Priority |  |  | 1 No in Progress | 0
22) 696/146 | INTRODUCTION / ADDITION OF XI-XII
CLASSES IN EXISTING BOYS/ GIRLS SECOND:
| HIGH SCHOOL (1989-90 ) KARACHI Division | [8 empty] | Paucity of Funds and |  | EDO (Education )
| 3 Unuts | 0 | 0 | #REF! | 0 | Abandoned | #REF! | #REF! | 0 | Law & Order Situation | N.A | may be referred | Not yet Completed | may be referred | ….do…. |  |  | 3 Nos Abandoned | 6.33
23) 703/147 | UP-GRADATION OF MIDDLE SCHOOL TO
| HIGH SCHOOL IN R/ AREA ( 1994-95) | [10 empty] | EDO (Education ) | [5 empty] | 2 Completed
| 3 Units | 0 | 0 | #REF! | 0 | On going | #REF! | #REF! | 3 | On going | N.A | may be referred | Not yet Completed | may be referred | ….do…. |  |  | 1 No in Progress | 0
24)706/148 | ADDITION OF CLASS ROOM IN EXISITNG
| HIGH SCHOOL ( 1994-95) KARACHI | [10 empty] | EDO (Education ) | [5 empty] | 8 Nos Completed
| 18 Units | 0 | 0 | #REF! | 0 | On going | #REF! | #REF! | 0.45 | On going | N.A | may be referred | Not yet Completed | may be referred | ….do…. |  |  | 10 Nos in Progress | 1
| Total of Secondary Education | *** | *** | #REF! | *** | *** | #REF! | #REF! | #REF! | *** | *** | *** | *** | *** |  | *** |  | *** | 28.301
COLLEGE EDUCATION:
25) 843/32 | ESTABLISHMENT OF GOVT COLLEGE OF
EDUCATION B.ED AND M.ED AT DARSANO
| CHANNA MALIR KARACHI 1994-95 prog | [10 empty] | EDO (Education )
| 1 Unit | 0 | 0 | #REF! | 0 | On going | #REF! | #REF! | 0 | Funds Not available | N.A | may be referred | Not yet Completed | may be referred | Ist Priority |  |  | 1 No in Progress | 14
26) 845/33 | ESTABLISHMENT OF GOVT: GIRLS DEGREE
COLLEGE @ Kaunkar Karachi ( Phase-II)
| ( 1994-95 Programme ) | [10 empty] | EDO (Education )
| 1 Unit | 0 | 0 | #REF! | 0 | On going | #REF! | #REF! | 1.833 | Paucity of Funds | N.A | may be referred | Not yet Completed | may be referred | ….do…. |  |  | 1 No in Progress | 8.65
27) 802 / 37 | OPENING OF GOVT:DEGREE GIRLS COLLEGE
| GIRLS COLLEGE NEW KARACHI. | [10 empty] | EDO (Education )
| 1 Unit | 0 | 0 | #REF! | 0 | On going | #REF! | #REF! | #REF! | Paucity of Funds | N.A | may be referred | Not yet Completed | may be referred | ….do…. |  |  | 1 No in Progress | 0
28) 817 / 38 | OPENING OF DEGREE COLLEGE AT NEW
| KARACHI CENTRAL KARACHI 1991-92 | [10 empty] | EDO (Education )
| 1 Unit | 0 | 0 | #REF! | 0 | On going | #REF! | #REF! | 0.88 | Ongoing | N.A | may be referred | Not yet Completed | may be referred | ….do…. |  |  | 1 No in Progress
29) 819 / 39 | ESTABLISHMENT OF DEGREE COLLEGE AT
LIAQUATABAD BLOCK-5 NEAR K.M.C PARK
| CENTRAL KARACHI 1992-93 PROGRAMME. | [10 empty] | EDO (Education )
| 1 Unit | 0 | 0 | #REF! | 0 | On going | #REF! | #REF! | 3.25 | Ongoing | N.A | may be referred | Not yet Completed | may be referred | ….do…. |  |  | 1 No in Progress
30) 851 / 41 | CONSTT: OF GOVT DEGREE | [10 empty] | EDO (Education )
| COLLEGE @ Buffarzone N'Karachi. | 0 | 0 | 12.142 | 0 | On going | #REF! | #REF! | 0.1 | Ongoing | N.A | may be referred | Not yet Completed | may be referred | ….do…. |  |  | Unit Completed | 0
31) 852 / 42 | CONSTRUCTION OF GOVT: | [10 empty] | EDO (Education )
| DEGREE COLLEGE at F.B. Area. | 0 | 0 | 11.713 | 0 | On going | #REF! | #REF! | 0.2 | Ongoing | N.A | may be referred | Not yet Completed | may be referred | ….do…. |  |  | Unit Completed | 0
Rs. ( In Million)
Sr. No: | Name of Scheme With Location | Date of Approval |  | Approved Cost |  | Status of | Physical | Exxpend: | Alllocation | Incomplete | The Scheme which | Scheme which have | Scheme completed | Scheme which are | Scheme which are required uo
ADP No: |  | Original | Revised | Original | Revised | Scheme | Progress | Incurred | 2001-02 | abondoned Scheme | could be considered | been completedphysicaly | but PC-IV not | not required by the | be completed given priority |  |  |  | Funds
2001-02 | [6 empty] | % age | till date |  | reason for not | for discontinuing | but SNE not sanctioned | submitted | A.D. but can be | Phase-I | Phase-II | Phase-III | Remarks / Other | Required
[10 empty] | completing the | with reasons | (given priority of | approval | utilized by other |  |  |  | recommandation | to comple
[10 empty] | scheme within the |  | commissioning the scheme) |  | Departments |  |  |  |  | the Unit /
[10 empty] | planned period |  |  |  | rational to be given |  |  |  |  | Scheme
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
32) 855 / 43 | ESTABLISHMENT OF GOVERNMENT DEGREE
COLLEGE @ Shaheed-e-Millat at Azizabad
| F.B.AREA Central Karachi.(1995-96 Prog:) | [10 empty] | EDO (Education )
| 1 Unit | 0 | 0 | #REF! | 0 | On going | #REF! | #REF! | 5 | Ongoing | N.A | may be referred | Not yet Completed | may be referred | Ist Priority |  |  | 1 No in Progress | 9.39
33) 859 / 44 | ADDITION/ ALTERATION IN APWA GOVT.
| COLLEGE FOR WOMEN Federal "B" AREA. | [10 empty] | EDO (Education )
| 1 Unit | 0 | 0 | 3.93 | 0 | On going | #REF! | #REF! | 0 | Ongoing | N.A | may be referred | Not yet Completed | may be referred | ….do…. |  |  | Unit Completed | 0
34)792/ 59 | OPENING OF GIRLS DEGREE COLLEGE | [10 empty] | EDO (Education ) | [5 empty] | 1 No Completed | 11.01
| 1 Unit | 0 | 0 | #REF! | 0 | On going | #REF! | #REF! | 0 | No Funds at all | N.A | may be referred | Not yet Completed | may be referred | ….do…. |  |  | 1 No in Progress
35)796/60 | ESTABLISHMENT OF BOYS DEGREE COLLEGE
| @ Gulzar-e-Hijri Colony Karachi (1991-92) | [10 empty] | EDO (Education ) | [5 empty] | 1 No Completed | 7.16
| 1 Unit | 0 | 0 | #REF! | 0 | On going | #REF! | #REF! | 0 | No Funds at all | N.A | may be referred | Not yet Completed | may be referred | ….do…. |  |  | 1 No in Progress
36) 818/86 | ESTABLISHMENT OF GOVT: BOYS
| DEGREE COLLEGE @ Surjani Town | [10 empty] | EDO (Education )
| 1 Unit | 0 | 0 | #REF! | 0 | On going | #REF! | #REF! | 2.574 | Funds Not available | N.A | may be referred | Not yet Completed | may be referred | ….do…. |  |  | 1 No in Progress | 10.21
37) 853/89 | ESTABLISHMENT OF GOVT: DEGREE | [10 empty] | EDO (Education )
| COLELEGE @ Mangopir | 0 | 0 | #REF! | 0 | On going | #REF! | #REF! | 1.75 | Funds Not available | N.A | may be referred | Not yet Completed | may be referred | ….do…. |  |  | 1 No in Progress
| Total College Education | *** | *** | #REF! | *** | *** | *** | #REF! | #REF! | *** | *** | *** | *** | *** | *** | *** | *** | *** | 42.25
PRIORITY PROGRAMME
1) 46 | ADDITION/ IMPROVEMENT OF DEGREE COLLEGE: | [10 empty] | EDO (Education )
| 1 Unit |  |  | 12.848 |  | Incomplete | 36.3092 | 4.665 | 1.5 | Paucity of Fudns | N.A | may be referred | Not yet Completed | may be referred | Ist Priority |  |  | 1 No in Progress | 10.11
2) 47 | ADDITION OF COMPUTER CLASSES | [10 empty] | EDO (Education )
| 1 Unit |  |  | 4.788 |  | Incomplete | 39.599 | 1.896 | 1 | Paucity of Fudns | N.A | may be referred | Not yet Completed | may be referred | ….do…. |  |  | 1 No in Progress | 3.61
3) 48 | ADDITION OF CLASS ROOM IN EXISTING
| SECONDARY SCHOOL IN U/AREA KARACHI | [10 empty] | EDO (Education ) | [5 empty] | 4 No Completed | 6.395
| 30Units |  |  | 8.7 |  | Incomplete | 41.4943 | 3.61 | 1.1 | Paucity of Fudns | N.A | may be referred | Not yet Completed | may be referred | ….do…. |  |  | 26 Nos in Progress
4) 49 | ESTABLISHMENT/ OPENING OF GOVT: DEGREE COLLEGE. | [10 empty] | EDO (Education )
| 1 units |  |  | 26.098 |  | Incomplete | 21.4691 | 5.603 | 1.75 | Paucity of Fudns | N.A | may be referred | Not yet Completed | may be referred | ….do…. |  |  | 1 No in Progress | 26.4
5) 50 | ESTABLISHMENT/ OPENING OF GOVT: DEGREE COLLEGE. | [10 empty] | EDO (Education )
| 1 units |  |  | 26.098 |  | Incomplete | 32.6922 | 8.532 | 2.5 | Paucity of Fudns | N.A | may be referred | Not yet Completed | may be referred | ….do…. |  |  | 1 No in Progress | 21.48
6) 51 | ESTABLISHMENT OF MONOTECHIC INSTITUTE
| AT DISTRICT CENTRAL KARACHI. | [10 empty] | EDO (Education )
| 1 units |  |  | 21.38 |  | Incomplete | 26.3377 | 5.631 | 1.75 | Paucity of Fudns | N.A | may be referred | Not yet Completed | may be referred | ….do…. |  |  | 1 No in Progress | 18.95
7) 52 | ESTABLISHMENT OF SINGLE
| SECTION HIGH SCHOOL IN U/AREA | [10 empty] | EDO (Education )
| 1 units |  |  | 4.189 |  | Incomplete | 60.8737 | 2.55 | 0.2 | Paucity of Fudns | N.A | may be referred | Not yet Completed | may be referred | ….do…. |  |  | 1 No in Progress | 2.267
8) 53 | UP-GRADATION OF MIDDLE TO HIGH SCHOOL IN KYC | [10 empty] | EDO (Education )
| 1 units |  |  | 3.964 |  | Incomplete | 47.2755 | 1.874 | 1.5 | Paucity of Fudns | N.A | may be referred | Not yet Completed | may be referred | ….do…. |  |  | 1 No in Progress | 2.684
Rs. ( In Million)
Sr. No: | Name of Scheme With Location | Date of Approval |  | Approved Cost |  | Status of | Physical | Exxpend: | Alllocation | Incomplete | The Scheme which | Scheme which have | Scheme completed | Scheme which are | Scheme which are required uo
ADP No: |  | Original | Revised | Original | Revised | Scheme | Progress | Incurred | 2001-02 | abondoned Scheme | could be considered | been completedphysicaly | but PC-IV not | not required by the | be completed given priority |  |  |  | Funds
2001-02 | [6 empty] | % age | till date |  | reason for not | for discontinuing | but SNE not sanctioned | submitted | A.D. but can be | Phase-I | Phase-II | Phase-III | Remarks / Other | Required
[10 empty] | completing the | with reasons | (given priority of | approval | utilized by other |  |  |  | recommandation | to comple
[10 empty] | scheme within the |  | commissioning the scheme) |  | Departments |  |  |  |  | the Unit /
[10 empty] | planned period |  |  |  | rational to be given |  |  |  |  | Scheme
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
9) 54 | UP-GRADATION OF SAIFEE EIDEE ZAHABI INSTITUTE
| OF TECHNOLOGY TO B.TECH LEVEL CLASSES KYC | [10 empty] | EDO (Education )
| 1 units |  |  | 11.913 | 0 | Incomplete | 15.7307 | 1.874 | 1.5 | Paucity of Fudns | N.A | may be referred | Not yet Completed | may be referred | Ist Priority |  |  | 1 No in Progress | 11.825
10) 55 | UP-GRADATION OF PRIMARY TO MIDDLE SCHOOL | [10 empty] | EDO (Education )
| 5 Units |  |  | 17.81 | 0 | Incomplete | 41.6339 | 7.415 | 0.75 | Paucity of Fudns | N.A | may be referred | Not yet Completed | may be referred | ….do…. |  |  | 1 Nos in Progress | 13.06
1) 81 | ESTABLISHMENT / OPENING OF GOVT.
| DEGREE COLLEGE: | [10 empty] | EDO (Education )
| Gulistan-e-Jouhar Scheme # 36 |  |  | 26.098 | 0 | Incomplete | 0 | 0 | 0 | Paucity of Fudns | N.A | may be referred | Not yet Completed | may be referred | ….do…. |  |  | 1 Nos in Progress | 26.098
11) . | INTRODUCTION OF XI & XII IN CLASSES IN EXISTING
| (BOYS/GIRLS) SECONDARY SCHOOL IN U/AREA KYC: | [10 empty] | EDO (Education )
| 1 units |  |  | 7 |  | Non-ADP | 38.8143 | 2.717 | 0 | Funds not available | N.A | may be referred | Not yet Completed | may be referred | ….do…. |  |  | 1 No in Progress | 5.333
1) 69 | ADDITION OF COMPUTER CLASSES IN
| COLLEGE OF KARACHI REGION | [10 empty] | EDO (Education )
|  |  |  | 2.394 |  | Incomplete | 53.7176 | 1.286 | 0 | Funds not available | N.A | may be referred | Not yet Completed | may be referred | ….do…. |  |  | 1 No in Progress | 1.467
2) 70 | ESTABLISHMENT/ OPENING OF SINGLE
| SECTION HIGH SCHOOL IN URBAN AREA | [10 empty] | EDO (Education )
|  |  |  | 26.098 |  | Incomplete | 0 | 0 | 0 | Due to non-availablity | N.A | may be referred | Not yet Completed | may be referred | ….do…. |  |  | Plot not yet received | 0
3) 73 | ESTABLISHMENT OF SINGLE SECTION
| HIGH SCHOOL IN URBAN AREA KARACHI | [10 empty] | EDO (Education )
| 1 Unit |  |  | 4.189 |  | Incomplete | 53.3302 | 2.234 | 0 | Funds not available | N.A | may be referred | Not yet Completed | may be referred | ….do…. |  |  | 1 No in Progress | 2.583
4) 74 | IMPROVEMENT OF KHATOON-E-PAKISTAN
| GOVT. GIRLS COLLEGE KARACHI: | [10 empty] | EDO (Education ) | [5 empty] | 1 No Completed | 4.503
| 4 Units |  |  | 6.54 |  | Incomplete | 46.1468 | 3.018 | 0 | Funds not available | N.A | may be referred | Not yet Completed | may be referred | ….do…. |  |  | 3 No in Progress
5) 75 | INTRODUCTION OF XI & XII CLASSES
| IN EXISTING SECONDARY SCHOOL | [10 empty] | EDO (Education )
| 1 Unit |  |  | 7 |  | Incomplete | 27.8571 | 1.95 | 0 | Funds not available | N.A | may be referred | Not yet Completed | may be referred | ….do…. |  |  | 1 No in Progress | 6.1
6) 79 | UP-GRADATION OF PRIMARY TO
| MIDDLE SCHOOL IN URBAN AREA | [10 empty] | EDO (Education )
| 1 Unit |  |  | 3.562 |  | Incomplete | 24.7614 | 0.882 | 0 | Funds not available | N.A | may be referred | Not yet Completed | may be referred | ….do…. |  |  | 1 No in Progress | 3.214
7) . | ADDITION OF CLASS ROOM IN EXISTING
| SECONDARY SCHOOL IN U/AREA (50 C/ROOM) | [10 empty] | EDO (Education )
| 10 Units |  |  | 2.67 |  | Incomplete | 73.5955 | 1.965 | 0 | Funds not available | N.A | may be referred | Not yet Completed | may be referred | ….do…. |  |  | 10 Nos in Progress | 1.5
| Total Priority Programme | *** |  | 223.339 | *** | *** | *** | 57.702 | *** | *** | *** | *** | *** | *** | *** | *** | *** | *** | 167.579
| Grand Total | *** |  | #REF! | *** | *** | *** | #REF! | *** | *** | *** | *** | *** | *** | *** | *** | *** | *** | 325.199
DISTRICT OFFICER
EDUCATION WORKS-II KARACHI
CITY GOVERNMENT

## MPA Priority (hidden)
MONTHLY PROGRESS REPORT IN RESPECT OF MPA's PRIORITY PROGRAMME 2004-05
EDUCATION WORKS - II (WORKS & SERVICES DEPARTMENT) CITY DISTRICT GOVERNMENT KARACHI
FOR THE MONTH OF OCTOBER- 2004:
Rs. In Million
Sr. No: |  | Town | Approved Cost |  | E X P E N D I T U R E |  |  |  |  | Actual
| Name of Scheme/ |  |  | Allocation | Upto | During the | During the | Total Since | Physical Progress | Date of
| Project / Location |  |  | 2004-50 | 6-2004. | Month | Year | commence | Remarks | Completion
2004-05
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
1 | CONSTRUCTION OF COMPUTER LAB IN EXISTING |  |  | 0.943
SECONDARY SCHOOL BUILDING:
Sponsored By:
Mr. Syed Sardar Ahmed ( PS-98)
Mr. Qammar Mansoor (PS-99)
Mr. Muhammad Adil Siddiqui ( PS-100)
Mr. Asma Sherwani (Reserved Seat)
I | @ GBSS 5/D North Karachi | New Karachi | 1.36 |  | 1.098 | 0 | 0 | 1.098 | Colouring in Progress
II | @ GBSS 5/B New Karachi | New Karachi | 1.36 |  | 0.697 | 0 | 0 | 0.697 | Finishing in Progress
III | @ GGSS 11/E U.P Society. | New Karachi | 1.36 |  | 1.104 | 0.069 | 0.069 | 1.173 | Colouring in Progress |  | Balance
IV | @ GBSS APWA 5/E New Karachi. | New Karachi | 1.36 |  | 1.076 | 0.141 | 0.141 | 1.217 | Colouring in Progress |  | 0.733
| TOTAL >>>> |  | 5.44 | 0.943 | 3.975 | 0.21 | 0.21 | 4.185
2 | ADDITION OF (8) CLASSROOM IN EXISTING |  |  | 2.534
SECONDARY
Mr. Syed Sardar Ahmed ( PS-98)
Mr. Qammar Mansoor (PS-99)
Mr. Muhammad Adil Siddiqui ( PS-100)
Mr. Asma Sherwani (Reserved Seat)
I | @ GBSS 11/ C-3, North Karachi | New Karachi | 3.481 |  | 1.912 | 0.347 | 0.347 | 2.259 | Colouring in Progress
II | @ GBSS 11/E-1 North Karachi. | New Karachi | 3.481 |  | 1.823 | 0.522 | 0.522 | 2.345 | Colouring in Progress
| TOTAL >>>> |  | 6.962 | 2.534 | 3.735 | 0.869 | 0.869 | 4.604
3 | CONSTRUCTION OF ADDITIONAL (2) CLASSROOM
At Government Boys Lower
| Secondary School Block "L" | N'Nazimabad | 0.92 | 0.228 | 0.616 | 0 | 0 | 0.616 | Finishing in Progress
Arfat Town North Nazimabad Kyc:
Sponsored By
Ms. Bilquis Mukhtar (PS-101)
| TOTAL >>>> |  | 0.92 | 0.228 | 0.616 | 0 | 0 | 0.616
Sponsored By:
Miss: Farhina Ambreen (MPA)
4 | ADDOTION OF (3) ROOMS @ GGPS
STAFF WELFARE F.C. AREA
| Liaquatabad Town Karachi | Liaquatabad | 1.02 | 0 | 1.035 | 0 | 0 | 1.035 | Completed.
| TOTAL >>>> |  | 1.02 | 0 | 1.035 | 0 | 0 | 1.035
Sponsored By:
Mr. Sajid Jokhio (MPA)
5 | CONSTRUCTION OF (2) TWO ROOMED
PRIMARY SCHOOL I/C COMPOUND WALL
I | GPS Nido Buro UC Gadap | Gadap | 0.714 | 0 | 0.664 | 0 | 0 | 0.664 | Finishing in Progress
II | GPS Nandho Jokhio | Gadap | 0.714 | 0 | 0.668 | 0 | 0 | 0.668 | Colouring in Progress
(Deh Tahdo UC Darsano Channo)
III | GPS Jarro Khan Chooto | Gadap | 0.714 | 0 | 0.664 | 0 | 0 | 0.664 | Finishing in Progress
(Deh Almani UC Darsano Channa)
| TOTAL >>>> |  | 2.142 | 0 | 1.996 | 0 | 0 | 1.996
6 | ADDITION OF (3) CLASS ROOM IN |  |  | 0
PRIMARY SCHOOL:
| @ Haji Gul Hassan Kathori. | Gadap | 0.591 |  | 0.208 | 0 | 0 | 0.208 | roofing in progress
| TOTAL >>>> |  | 0.591 | 0 | 0.208 | 0 | 0 | 0.208
| GRAND TOTAL |  | 16.055 | 3.705 | 10.53 | 1.079 | 1.079 | 11.609
DISTRICT OFFICER
EDUCATION WORKS-II (W & S DEPTT)
CITY DISTRICT GOVT: KARACHI

## MP-Priority Programme-2 (hidden)
MONTHLY PROGRESS REPORT IN RESPECT OF PRIORITY PROGRAMME 1997-98
EDCATION WORKS-II (WORKS & SERVICES DEPARTMENT ) CITY DISTRICT GOVERNMENT KARACHI
FOR THE MONTH OF "NOVEMBER-2003"
Page-9 to 11
(Rs in Million )
Sr. No: | Category |  | Town | Approved Cost | Allocation | E X P E N D I T U R E |  |  |  | Physical | Actual
ADP # |  | Name of Scheme/ |  |  |  | Upto | During the | During the | Total | Progress | Date of
2001-02 |  | Project / Location |  |  | 2003-04 | 6-2003. | Month | Year | Since | Remarks | Completion
[8 empty] | 2003-04 | Comme:
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1) 81/ 172 | ADDITION/ IMPROVEMENT OF DEGREE COLLEGE: (P.Programme) | [8 empty] | Phase-I (8 C/R & 4 Lab Completed
1 | Sir Syed Govt: Degree College |  | Liaquatabad | 12.848 | 0.45 | 12.05 | 0 | 0 | 12.05 | Ph-II I) Common room plaster in progress
| Nazimabad Karachi (Phase-I) | [8 empty] | ii) Fitness room Roof Laid
III) Gymnasium Hall Ceiling completed
|  |  |  | 12.848 | 0.45 | 12.05 | 0 | 0 | 12.05
2) 82/ 173 | ADDITION OF COMPUTER CLASSES (P.Programme) |  |  |  | 0
2 | Mujeeb-un-Nisa Govt Girls College |  | New Karachi | 2.394 | 0 | 2.702 | 0 | 0 | 2.702 | Completed & Handedover
New Karachi Distt: Central
3 | Sir Syed Government College Kyc: |  | Liaquatabad | 2.394 | 0 | 1.998 | 0 | 0 | 1.998 | Completed & Handed over
|  |  |  | 4.788 | 0 | 4.7 | 0 | 0 | 4.7
3) 83 / 105 | ADDITION OF CLASS ROOM IN EXISTING |  |  |  | 0.5
SECONDARY SCHOOL IN U/AREA KARACHI (P.Programme)
4 | GBSS | Allama Iqbal F.B.Area ( 4 Class Rooms) | Gulberg | 1.16 | 0 | 0.869 | 0 | 0 | 0.869 | Completed
5 | GBSS | New Method F.B.Area ( 4 Class Rooms) | Gulberg | 1.16 | 0 | 0.969 | 0 | 0 | 0.969 | Completed
6 | GBSS | Anglo Oriential Block-15,F.B.Area (5 C/R) | Gulberg | 1.45 | 0 | 1.38 | 0 | 0 | 1.38 | Completed & Handed over
7 | GGSS | Hyderi North Karachi (5 Class/Room ) | New Karachi | 1.45 | 0 | 1.626 | 0 | 0 | 1.626 | Completed & Handed over
8 | GBSS | 5/A-3, New Karachi.(5 Class Room) | New Karachi | 1.45 | 0 | 1.469 | 0 | 0 | 1.469 | Completed & Handed over
9 | GGSS | Liaquatabad No:4 Karachi.(3 C/ Room) | Liaquatabad | 0.87 | 0 | 0.774 | 0 | 0 | 0.774 | Completed & Handed over
10 | GBSS | Liaquatbad No:4 Karachi.(4 C/ Rooms ) | Liaquatabad | 1.16 | 0 | 1.099 | 0 | 0 | 1.099 | Completed & Handed over
|  |  |  | 8.7 | 0.5 | 8.186 | 0 | 0 | 8.186
4) 84 / 174 | ESTABLISHMENT/ OPENING OF GOVT: DEGREE COLLEGE. (P.Programme) | [8 empty] | Phase- I Completed
11 | North Nazimabad |  | N'Nazim'd | 26.098 | 1.7 | 17.55 | 0 | 0 | 17.55 | Phase-II Completed
|  |  |  | 26.098 | 1.7 | 17.55 | 0 | 0 | 17.55 | Phase-III, Plaster & Flooring in Progress
5) 85 / 175 | ESTABLISHMENT/ OPENING OF GOVT: DEGREE COLLEGE. (P.Programme)
12 | North Karachi. |  | New Karachi | 26.098 | 1.3 | 23.5 | 0 | 0 | 23.5 | Nearing Completion
|  |  |  | 26.098 | 1.3 | 23.5 | 0 | 0 | 23.5
6) 86/ 136 | ESTABLISHMENT OF MONOTECHIC INSTITUTE
| AT DISTRICT CENTRAL KARACHI. (P.Programme) |  |  |  | 0
13 | F.B Area Karachi |  | Gulberg | 21.38 | 0 | 14.781 | 0 | 0 | 14.781 | Colouring Work in Progress
|  |  |  | 21.38 | 0 | 14.781 | 0 | 0 | 14.781
7) 87/ *** | ESTABLISHMENT OF SINGLE
| SECTION HIGH SCHOOL IN U/AREA (P.Programme) |  |  |  | 0
15 | Opening of Single Section High |  | N' Nazim'd | 4.189 | 0 | 5.1 | 0 | 0 | 5.1 | Completed
School @ Bufar Zone
|  |  |  | 4.189 | 0 | 5.1 | 0 | 0 | 5.1
8) 88/ *** | UP-GRADATION OF MIDDLE TO HIGH SCHOOL IN KYC (P.Programme) |  |  |  | 0
16 | GBLSS | 5/G Moon Light N'Karachi | New Karachi | 3.964 | 0 | 3.757 | 0 | 0 | 3.757 | Completed ready to Handedover
|  |  |  | 3.964 | 0 | 3.757 | 0 | 0 | 3.757
9) 89 / 137 | UP-GRADATION OF SAIFEE EIDEE ZAHABI INSTITUTE
| OF TECHNOLOGY TO B.TECH LEVEL CLASSES KYC (P.Programme) |  |  |  | 0 |  |  |  |  | Phase-I Finishing in Progress
17 | North Nazimabad Karachi |  | N' Nazim'd | 11.913 | 0 | 7.994 | 0 | 0 | 7.994 | Phase-II, Finishing in Progress
Phase-III, Plinth Completed
|  |  |  | 11.913 | 0 | 7.994 | 0 | 0 | 7.994
10) 90 / 69 | UP-GRADATION OF PRIMARY TO MIDDLE SCHOOL (P.Programme) |  |  |  | 1
18 | GBPS | Sector 5/C-2, N/K. | New Karachi | 3.562 | 0 | 2.454 | 0 | 0 | 2.454 | Colouring in Progress
19 | GBPS | 5/B-2, N' Karachi. | New Karachi | 3.562 | 0 | 3.173 | 0 | 0 | 3.173 | Completed & Handed Over
20 | GBPS | Allama Iqbal Bl-16,F.B.Area | Gulberg | 3.562 | 0 | 3.839 | 0 | 0 | 3.839 | Completed
21 | GGPS | Kamyab Block # 15, F.B.Area | Gulberg | 3.562 | 0 | 3.422 | 0 | 0 | 3.422 | Completed
22 | GBPS | Liaquatabad No 4 Karachi. | Liaquatabad | 3.562 | 0 | 2.599 | 0 | 0 | 2.599 | Finishing in Progress
|  |  |  | 17.81 | 1 | 15.487 | 0 | 0 | 15.487
11) 91/ 108 | INTRODUCTION OF XI & XII IN CLASSES IN EXISTING
| (BOYS/GIRLS) SECONDARY SCHOOL IN U/AREA KYC: (P.Programme) |  |  |  | 0.2
| GBSS | APWA 5/E New Karachi. | New Karachi | 7 | 0.2 | 7.916 | 0 | 0 | 7.916 | Completed
|  |  |  | 7 | 0.2 | 7.916 | 0 | 0 | 7.916
12) 92 / 173 | ADDITION OF COMPUTER CLASSES IN
| COLLEGE OF KARACHI REGION (P.Programme) |  |  |  | 0.75
1 | Govt. Boys College Gulshan-e-Iqbal |  | Gulshan'Iqbal | 2.394 | 0.75 | 2.614 | 0 | 0 | 2.614 | Completed
|  |  |  | 2.394 | 0.75 | 2.614 | 0 | 0 | 2.614
13) 93 / 177 | ESTABLISHMENT/ OPENING OF GOVT: DEGREE | [8 empty] | Phase-I Finishing in progress
| COLLEGE FOR BOYS (P.Programme) at |  |  |  | 2.95 |  |  |  |  | Phase-II, Plastering in Progress
1 | Gulistan-e-Johar scheme # 36 |  | Gulshan'Iqbal | 26.098 | 2.95 | 15.016 | 0 | 0 | 15.016 | Phase-III,Plastering in Progress
|  |  |  | 26.098 | 2.95 | 15.016 | 0 | 0 | 15.016
14) 94 / 178 | ESTABLISHMENT/ OPENING OF GOVT: DEGREE |  |  |  | 3.2 |  |  |  |  | Phase-I Plastering in Progress
| COLLEGE FOR GIRSL (P.Programme) AT |  | Gulshan'Iqbal | 26.098 | 3.2 | 9.427 | 0 | 0 | 9.427 | Phase-II Plastering in Progress
1 | Gulistan-e-Johar scheme # 36 |  |  | 26.098 | 3.2 | 9.427 | 0 | 0 | 9.427
3) 97 / *** | ESTABLISHMENT OF SINGLE SECTION
| HIGH SCHOOL IN URBAN AREA KARACHI (P.Programme) |  |  |  | 0
1 | Gulshan-e-Iqbal Karachi |  | Gulshan'Iqbal | 4.189 | 0 | 4.604 | 0 | 0 | 4.604 | Completed
|  |  |  | 4.189 | 0 | 4.604 | 0 | 0 | 4.604
4) 98 / *** | IMPROVEMENT OF KHATOON-E-PAKISTAN
| GOVT. GIRLS COLLEGE KARACHI: (P.Programme) |  |  |  | 0
I | Repair to College Main Building |  | Gulshan'Iqbal | 4.146 | 0 | 1.654 | 0 | 0 | 1.654 | Completed
2 | Repair to Block-A |  | Gulshan'Iqbal | 0 | 0 | 0.813 | 0 | 0 | 0.813 | Completed
3 | Repair to Block-B ( B.Sc Block) |  | Gulshan'Iqbal | 0 | 0 | 0.665 | 0 | 0 | 0.665 | Completed & Handedover
4 | Addition of Computer Classes |  | Gulshan'Iqbal | 2.394 | 0 | 4.066 | 0 | 0 | 4.066 | Completed
|  |  |  | 6.54 | 0 | 7.198 | 0 | 0 | 7.198
5) 99 / *** | INTRODUCTION OF XI & XII CLASSES
| IN EXISTING SECONDARY SCHOOL (P.Programme) |  |  |  | 0
1 | GBLSS | Gulshan-e-Iqbal Karachi | Gulshan'Iqbal | 7 | 0 | 7.75 | 0 | 0 | 7.75 | Completed
|  |  |  | 7 | 0 | 7.75 | 0 | 0 | 7.75
6) 103 / *** | UP-GRADATION OF PRIMARY TO
| MIDDLE SCHOOL IN URBAN AREA (P.Programme) |  |  |  | 0
1 | B & G | Govt. Jamshad Road School | Gulshan'Iqbal | 3.562 |  | 3.382 | 0 | 0 | 3.382 | Finishing in Progress
|  | Ghosia Colony Karachi |  | 3.562 | 0 | 3.382 | 0 | 0 | 3.382
7) NON | ADDITION OF CLASS ROOM IN EXISTING
ADP / 109 | SECONDARY SCHOOL IN U/AREA (50 C/ROOM) (P.Programme)
1 | GGSS | Gulshan-e-Iqbal Block-6 (10 C/Room) | Gulshan'Iqbal |  | 0
|  |  |  | 2.67 | 0 | 2.865 | 0 | 0 | 2.865 | Completed & Handedover
|  |  |  | 2.67 | 0 | 2.865 | 0 | 0 | 2.865
8) / . | ADDITION OF CLASS ROOM IN EXISTING
| COLLEGE BUILDING : (P.Programme) |  |  |  | 0
1 | Rana Liaquat Ali Khan Govt. College Homeconomic |  | Gulshan'Iqbal | 1.133 | 0 | 0.9782 | 0 | 0 | 0.9782 | Completed & Handedover
(2 Class room)
2 | Govt. Degree College Gulshan-e-Iqbal (2 C/Room) |  | Gulshan'Iqbal | 1.133 | 0 | 1.118 | 0 | 0 | 1.118 | Completed & Handedover
|  |  |  | 2.266 | 0 | 2.0962 | 0 | 0 | 2.0962
|  | GRAND TOTAL |  | 225.605 | 12.05 | 175.9732 | 0 | 0 | 175.9732
(Saeed Hussain Malik)
DISTRICT OFFICER
EDUCATION WORKS-II (W & S DEPTT)
CITY DISTRICTGOVERNMENT KARACHI

## DO-II Monthly Progress (hidden)
MONTHLY PROGRESS REPORT IN RESPECT OF A.D.P. SCHEMES 2003-04
EDUCATION WORKS - II (WORKS & SERVICES DEPARTMENT) CITY DISTRICT GOVERNMENT KARACHI
FOR THE MONTH OF JULY- 2004:
Rs. In Million
Sr. No: | Category |  | Town | Approved Cost | Allocation | E X P E N D I T U R E |  |  |  | Physical | Actual
ADP # |  | Name of Scheme/ |  |  | 2003-04 | Upto | During the | During the | Total Science | Progress | Date of
2003-04 |  | Project / Location |  |  |  | 6-2004. | Month | Year | commence | Remarks | Completion
2004-05
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
A | MIDDLE SCHOOL
ELEMENTARY EDUCATION
1 | CONSTRUCTION OF BUILDING FOR SHELTERLESS
14 / 56 | EXISTING PRIMARY SCHOOL IN R/AREA (2000-01) (2 units) |  |  |  | 0
1 | ** | Haji Waryal Bandijo | Gadap | 0.895 | 0 | 0.643 | 0 | 0 | 0.643 | Colouring in Progress
2 | GBPS | Main Wasyo Kanroo | Gadap | 0.895 | 0 | 0.924 | 0 | 0 | 0.924 | Completed
3 | GBPS | Qasim Gabol S / Highway | Gadap | 0.895 | 0 | 0.942 | 0 | 0 | 0.942 | Completed & Handed over
4 | GBPS | Konkar | Gadap | 0.895 | 0 | 0.9 | 0 | 0 | 0.9 | Completed
5 | GBPS | Haji Umaid Ali Gabol | Gadap | 0.895 | 0 | 0.803 | 0 | 0 | 0.803 | Completed & Handed over
6 | GBPS | Islamia Konkar | Gadap | 0.895 | 0 | 0.881 | 0 | 0 | 0.881 | Completed & Handed over
7 | GBPS | Faiz Muhammad Gabol | Gadap | 0.895 | 0 | 0.583 | 0 | 0 | 0.583 | Completed & Handed over
8 | GBPS | Kamal Burro | Gadap | 0.895 | 0 | 0.511 | 0 | 0 | 0.511 | Finishing in Progress
9 | GBPS | Haji Sher Muhammad Bandijo (Moidan) | Gadap | 0.895 | 0 | 0.788 | 0 | 0 | 0.788 | Colouring in Progress
10 | GBPS | Thohar Kana Moidan | Gadap | 0.895 | 0 | 1.109 | 0 | 0 | 1.109 | Completed
11 | GBPS | Ali Muhammad Chutto | Gadap | 0.895 | 0 | 0.191 | 0 | 0 | 0.191 | Roof Level
12 | GBPS | Haji Hamal Balouch | Gadap | 0.895 | 0 | 0.923 | 0 | 0 | 0.923 | colouring stage
13 | GBPS | Meehan Chutto | Gadap | 0.895 | 0 | 0.938 | 0 | 0 | 0.938 | Completed
14 | GBPS | Photo Gabol Kathore | Gadap | 0.895 | 0 | 0.975 | 0 | 0 | 0.975 | Colouring in Progress
15 | GBPS | Bapera Mohalla Memon.Gadap | Gadap | 0.895 | 0 | 1.076 | 0 | 0 | 1.076 | Completed & Handed over
16 | GGMOHS | Kamal Bari Dumba Goth | Gadap | 0.895 | 0 | 0.522 | 0 | 0 | 0.522 | Completed & Handed over
17 | GGMOHS | Mazar Khan Jokhio | Gadap | 0.895 | 0 | 1.072 | 0 | 0 | 1.072 | Completed & Handed over
18 | GBPS | Soofan Jokhio | Gadap | 0.895 | 0 | 0.877 | 0 | 0 | 0.877 | Completed & Handed over
19 | GBPS | Nabi Bux Gabol (Gadap) | Gadap | 0.895 | 0 | 0.674 | 0 | 0 | 0.674 | Completed & Handed over
20 | GBPS | Ali Muhammad Gounder | Gadap | 0.895 | 0 | 0.983 | 0 | 0 | 0.983 | Completed
21 | GBPS | Ali Dad Gabol | Gadap | 0.895 | 0 | 0.796 | 0 | 0 | 0.796 | Completed & Handed over
22 | GBPS | Darya Khan Gabol | Gadap | 0.895 | 0 | 0.82 | 0 | 0 | 0.82 | Completed & Handed over
23 | GBPS | Bakhrani Mohalla | Gadap | 0.895 | 0 | 0.959 | 0 | 0 | 0.959 | Completed & Handed over
24 | GBPS | Khan Muhammad Jokhio | Gadap | 0.895 | 0 | 0.906 | 0 | 0 | 0.906 | Completed & Handed over
25 | GBPS | Lal Bux Kachelo | Gadap | 0.895 | 0 | 0.909 | 0 | 0 | 0.909 | Completed & Handed over
26 | GBPS | Hayat Goundar | Gadap | 0.895 | 0 | 0.933 | 0 | 0 | 0.933 | completed
27 | GBPS | Siraj Ahmed Kathore | Gadap | 0.895 | 0 | 0.756 | 0 | 0 | 0.756 | Finishing in Progress
28 | GBPS | Muhammadi Goth Mangopir | Gadap | 0.895 | 0 | 1.565 | 0 | 0 | 1.565 | Completed & Handed over
29 | GBPMS | Abdul Ghaffar Burfat Songal | Gadap | 0.895 | 0 | 0.906 | 0 | 0 | 0.906 | Completed & Handed over
30 | GBPS | Qadir Bux Jokhio | Gadap | 0.895 | 0 | 0.947 | 0 | 0 | 0.947 | Completed & Handed over
|  | Total |  | 26.85 | 0 | 25.812 | 0 | 0 | 25.812
2 | CONSTT: OF BUILDING FOR EXISTING SHELTERLESS
15 / 57 | PRIMARY SCHOOL IN U/AREA KARACHI (2000-01) (5 ROOM) |  |  |  | 0
1 | GBPS | Full Bright B-16, Sohrab Goth F.B.Area | Gulberg | 1.917 | 0 | 1.8 | 0 | 0 | 1.8 | Completed & Handedover
2 | GBPS | Godra Muslim Anjumn 11/F New Karachi | New Karachi | 1.917 | 0 | 1.779 | 0 | 0 | 1.779 | Completed & Handedover
3 | GBPS | 15/ B Buffarzone North Karachi | North Naz'd | 1.917 | 0 | 1.742 | 0 | 0 | 1.742 | Completed & Handedover
4 | GBMSQS | Rehamani Sector No:4 North Karachi | New Karachi | 1.917 | 0 | 2.074 | 0 | 0 | 2.074 | Completed & Handedover
5 | GBMSQS | Siddique Sector 5/G New Karachi | New Karachi | 1.917 | 0 | 1.731 | 0 | 0 | 1.731 | Completed & Handedover
6 | GBMSQS | Siddique Sector 5/D New Karachi. | New Karachi | 1.917 | 0 | 2.172 | 0 | 0 | 2.172 | Completed & Handedover
7 | GBMSQS | Chishtia Sector 1/A-3, Khuwaja Ajmair | New Karachi | 1.917 | 0 | 1.791 | 0 | 0 | 1.791 | Completed & Handedover
Nagri North Karachi
8 | GBPS | New Era Dastagir No:9. F.B.Area Kyc: | Gulberg | 1.917 | 0 | 1.95 | 0 | 0 | 1.95 | Completed & Handedover
9 | GBPS | Sector 7/D-3 North Karachi. | New Karachi | 1.917 | 0 | 1.923 | 0 | 0 | 1.923 | Completed & Handedover
10 | GBPS | J/M Quba Block-22, Shafique Colony | Gulberg | 1.917 | 0 | 2.257 | 0 | 0 | 2.257 | Completed & Handedover
11 | GBMSQS | Bilal 5/G New Karachi | New Karachi | 1.917 | 0 | 2.011 | 0 | 0 | 2.011 | Completed
|  | Total |  | 21.087 | 0 | 21.23 | 0 | 0 | 21.23
3 | UP-GRADATION OF PRIMARY TO MIDDLE SCHOOL |  |  |  | 0
16 / 58 | IN R/AREA KARACHI DIVISION (1990-91)
1 | GBPS | Chutta Gabol Karachi | Gulberg | 0.966 | 0 | 0.989 | 0 | 0 | 0.989 | Completed & Handedover | 1998-10-03
2 | GBPS | Haji Dur Muhammad Goth | Gadap | 1.11 | 0 | 1.094 | 0 | 0 | 1.094 | Completed & Handedover
3 | GBPS | Mazar Khan Jokhio | Gadap | 1.141 | 0 | 1.194 | 0 | 0 | 1.194 | Finishing in Progress (Abondondand Unit)
4 | GBPS | Murrad Memon Goth | Gadap | 1.361 | 0 | 1.096 | 0 | 0 | 1.096 | Completed & Handedover
5 | GBPS | Hashim Gabol Goth | Gadap | 1.11 | 0 | 1.409 | 0 | 0 | 1.409 | Finishing in Progress
6 | GGPS | Ali Muhammad Goth | Gadap | 1.11 | 0 | 1.104 | 0 | 0 | 1.104 | Completed & Handedover
7 | GBPS | Salah Muhammad Jumani | Gadap | 1.476 | 0 | 1.11 | 0 | 0 | 1.11 | Completed & Handedover
8 | GBPS | Haji Hussain Chohar | Gadap | 1.476 | 0 | 1.46 | 0 | 0 | 1.46 | Completed & Handedover
9 | GGPS | Haji Sheedi Village | Gadap | 1.11 | 0 | 1.103 | 0 | 0 | 1.103 | Completed & Handedover
10 | GGPS | Gadap Village | Gadap | 1.472 | 0 | 1.408 | 0 | 0 | 1.408 | Completed
11 | GGPS | Pahalwan Goth | Gadap | 1.11 | 0 | 1.11 | 0 | 0 | 1.11 | Completed & Handedover
12 | GPS | Sheedo Zakria | Gadap | 1.446 | 0 | 1.552 | 0 | 0 | 1.552 | Completed & Handedover
13 | GBPS | KDA Filter Hashim Khashkhali | Gadap | 1.11 | 0 | 1.098 | 0 | 0 | 1.098 | Completed & Handedover
14 | GBPS | Hakoo Khan Brohi. | Gadap | 1.11 | 0 | 1.075 | 0 | 0 | 1.075 | Completed & Handedover
15 | GBPS | Bachal Goth | Gadap | 1.11 | 0 | 1.049 | 0 | 0 | 1.049 | Completed & Handedover
16 | GGPS | Yar Muhammad Jokhio | Gulshan-Iqbal | 0.966 | 0 | 1.127 | 0 | 0 | 1.127 | Completed & Handedover
|  | Total |  | 19.184 | 0 | 18.978 | 0 | 0 | 18.978
4 | UP-GRADATION OF PRIMARY TO MIDDLE
17 / 59 | SCHOOL IN R/AREA (1991-92 Programme) |  |  |  | 0
1 | GBPS | Binjo Jokhio | Gadap | 1.633 | 0 | 1.533 | 0 | 0 | 1.533 | Completed & Handedover
2 | GGPS | Kamal Khan Jokhio | Gadap | 2.2 | 0 | 2.953 | 0 | 0 | 2.953 | Finishing in Progress
|  | Total |  | 3.833 | 0 | 4.486 | 0 | 0 | 4.486
5 | CONSTT: / RECONSTRUCTION OF BUILDING FOR |  |  |  | 0
18 / 60 | EXISTING MIDDLE SCHOOL IN KARACHI (90-91 PROG) | [8 empty] | (Under litegaton) Lying Abandoned at roof level
| GBLSS | Zia-Ul-Uloom Firdous Colony Karachi | Liaquatabad | 1.296 |  | 0.727 | 0 | 0 | 0.727 | (PC1, revied )
|  | Total |  | 1.296 | 0 | 0.727 | 0 | 0 | 0.727
6 | CONSOLIDATION / IMPROVEMENT OF BUILDING |  |  |  | 0
20 / 62 | IN EXISTING MIDDLE SCHOOL (2000-01 PROG)
1 | GGLSS | Konkar | Gadap | 2.608 | 0 | 1.952 | 0 | 0 | 1.952 | Finishing in Progress
2 | GBLSS | Khamiso Jokhio | Gadap | 2.608 | 0 | 2.952 | 0 | 0 | 2.952 | Completed & Handedover
3 | GGLSS | Soomar Kandani | Gadap | 2.608 | 0 | 2.102 | 0 | 0 | 2.102 | Completed & Handedover
4 | GGLSS | Radho Jokhio | Gadap | 2.608 | 0 | 2.43 | 0 | 0 | 2.43 | Completed & Handedover
5 | GBLSS | Atta Truk F.B.Area Liaquatabad | Gulberg | 2.608 | 0 | 2.454 | 0 | 0 | 2.454 | Colouring in Progress
6 | GBLSS | Brighter Grammaer North Nazimabad | N'Nazimabad | 2.608 | 0 | 2.387 | 0 | 0 | 2.387 | Completed & Handedover
7 | GBLSS | Farzana 5/D New Karachi@5/A-3 N/Kyc: | N/Karachi | 2.608 | 0 | 2.546 | 0 | 0 | 2.546 | Completed & Handedover
8 | GBLSS | Little Angle 11/E UP Society Karachi | N/Karachi | 2.608 | 0 | 2.388 | 0 | 0 | 2.388 | Completed & Handedover
9 | GBLSS | My Ideal North Nazimabad Karachi | N'Nazimabad | 2.608 | 0 | 2.489 | 0 | 0 | 2.489 | Completed & Handedover
|  | Total |  | 23.472 | 0 | 21.7 | 0 | 0 | 21.7
7 | UP-GRADATION OF PRIMARY TO MIDDLE SCHOOL
22 / 63 | IN KARACHI CITY (8 Units) (2001-02 Programme) |  |  |  | 0
1 | GBPS | Moosa Colony No: 1 Karachi | Gulberg | 2.296 | 0 | 0 | 0 | 0 | 0 | Plot not yet received
2 | GGPS | Sector 5/G-2 New Karcahi | New Karachi | 2.296 | 0 | 2.099 | 0 | 0 | 2.099 | completed
3 | GGPS | Anjuman-e-Tarraqui | Gulshan' Iqbal | 2.296 | 0 | 2.301 | 0 | 0 | 2.301 | Main Building Completed & Ext: Deve: in Progress
|  | Total |  | 6.888 | 0 | 4.4 | 0 | 0 | 4.4
8 | UP-GRADATION OF PRIMARY TO MIDDLE |  |  |  | 0
24 / 64 | SCHOOL IN SINDH ( 2001-02 PROGRAMME)
1 | GBPS | Bhai Khan Goth Gadap | Gadap | 1.05 | 0 | 1.102 | 0 | 0 | 1.102 | Colouring in Progress
2 | GGPS | Community Centre Surjani Town Siddique Goth Karachi | Gadap | 1.05 | 0 | 0.836 | 0 | 0 | 0.836 | Plastering in Progress
3 | GBPS | Abdullah Palari Goth Zero Mall SuperHigh Way Karachi | Gulshan' Iqbal | 1.05 | 0 | 0.788 | 0 | 0 | 0.788 | Plastering in Progress
4 | GBPS | Sohrab Goth F.B.Area Block # 22 Kyc | Gulberg | 1.05 | 0 | 0.46 | 0 | 0 | 0.46 | Upto Lintel Level
5 | GBPS | Sector-2 New Karachi Town | N/Karachi | 1.05 | 0 | 1.117 | 0 | 0 | 1.117 | Finishing in Progress
6 | GGPS | Sector 11-J New Karachi Town | N/Karachi | 1.05 | 0 | 1.069 | 0 | 0 | 1.069 | Finishing in Progress
7 | GBPS | Block " Q " North Nazimabad Karachi | N'Nazimabad | 1.05 | 0 | 0.978 | 0 | 0 | 0.978 | Plastering in Progress
|  | Total |  | 7.35 | 0 | 6.35 | 0 | 0 | 6.35
9 | CONSTRUCTION OF BUILDING FOR EXISTING |  |  |  | 0
25 / 65 | PRIMARY SCHOOL IN SINDH (2001-02 PROG)
1 | GBPS | Murad Memon (Malir) GADAP Town | Gadap | 0.528 | 0 | 0.574 | 0 | 0 | 0.574 | Colouring in Progress
2 | GBPS | Manghopir GADAP Town | Gadap | 0.528 | 0 | 0.54 | 0 | 0 | 0.54 | Finishing in Progress
3 | GBPS | Babul Islam Gadap Town | Gadap | 0.528 | 0 | 0.219 | 0 | 0 | 0.219 | Roofing in Progress
4 | GBPS | J/M Khawaja 5/B New Karachi | N/Karachi | 1.312 | 0 | 1.169 | 0 | 0 | 1.169 | Finishing in Progress
5 | GBPS | J/M Khamisoo Goth 5/F New Karachi | N/Karachi | 1.312 | 0 | 1.191 | 0 | 0 | 1.191 | Finishing in Progress
6 | *** | Sector 11/D-2, No: 2 New Karachi | N/Karachi | 1.312 | 0 | 1.226 | 0 | 0 | 1.226 | Finishing in Progress
7 | GGPS | Gujjan Village | Gadap | 0.528 | 0 | 0.29 | 0 | 0 | 0.29 | Colouring in Progress
8 | GBPS | Hashim Gabol | Gadap | 0.528 | 0 | 0.35 | 0 | 0 | 0.35 | Finishing in Progress
9 | GBPS | Yousaf Goth | Gadap | 0.528 | 0 | 0.543 | 0 | 0 | 0.543 | Plastering in progress
10 | GBPS | Ayoub Goth | Gadap | 0.528 | 0 | 0.566 | 0 | 0 | 0.566 | Finishing in Progress
11 | GBPS | 7 Star Colony Gadap Town Karachi | Gadap | 0.528 | 0 | 0.132 | 0 | 0 | 0.132 | Plastering in progress
|  | Total |  | 8.16 | 0 | 6.8 | 0 | 0 | 6.8
10 | UP-GRADATION OF PRIMARY TO MIDDLE SCHOOL |  |  |  | 0
90 / 69 | IN URBAN AREA KARACHI 1987-88
1 | GBPS | Sector 5/C-2, North Karachi | New Karachi | 3.562 | 0 | 2.613 | 0 | 0 | 2.613 | Completed
2 | GBPS | 5/B-2, North Karachi. | New Karachi | 3.562 | 0 | 3.706 | 0 | 0 | 3.706 | Completed & Handed Over
3 | GBPS | Allama Iqbal Bl-16,F.B.Area | Gulberg | 3.562 | 0 | 3.976 | 0 | 0 | 3.976 | Completed & Handed Over
4 | GGPS | Kamyab Block # 15, F.B.Area | Gulberg | 3.562 | 0 | 3.422 | 0 | 0 | 3.422 | Completed & Handed Over
5 | GBPS | Liaquatabad No 4 Karachi. | Gulberg | 3.562 | 0 | 4.036 | 0 | 0 | 4.036 | Completed
6 | B & G | Govt. School Ghosia Colony Jamshad | Gulshan' Iqbal | 3.562 | 0 | 3.616 | 0 | 0 | 3.616 | Finishing in Progress
Road Karachi.
|  | Total |  | 21.372 | 0 | 21.369 | 0 | 0 | 21.369
11 | OPENING OF (5) ROOMED PRIMARY SCHOOL |  |  |  | 0
131 / 71 | AT Khuda Ki Basti |  | GADAP | 3.37 | 0 | 3.007 | 0 | 0 | 3.007 | Colouring in Progress
12 | UP-GRADATION OF MIDDLE TO HIGH SCHOOL
*** 72 | AT KARACHI DISTRICT (10 Units) |  |  |  | 0
1 |  | Haji Ramzan Gabol Goth Karachi | Gulshan' Iqbal | 4.868 | 0 | 1.229 | 0 | 0 | 1.229 | Plinth completed
2 | GGLSS | Surjani Town Karachi | Gadap | 4.868 | 0 | 0.673 | 0 | 0 | 0.673 | Footing in Progress
3 | GBLSS | Ibrahim Ali Bhai Block "I" N-Nazimabad | North Naz'd | 4.868 | 0 | 0 | 0 | 0 | 0 | Plinth in Progress
4 | GBLSS | Sector-2, North Karachi | New Karachi | 4.868 | 0 | 0.598 | 0 | 0 | 0.598 | Upto Lintel Level
5 | CDGK | Choudary Rehmat Illahi School | North Naz'd | 4.868 | 0 | 0 | 0 | 0 | 0 | Tender Under Process
|  | Total |  | 24.34 | 0 | 2.5 | 0 | 0 | 2.5
13 | ADDITION OF CLASS ROOM IN EXISTING
*** / 73 | ELEMENTARY SCHOOL (40 Units) |  |  |  | 0
1 | GGPS | Enclish Islamia Nazimabad No:2 (4 C/R) | Liaquatabad | 1.766 | 0 | 0.2 | 0 | 0 | 0.2 | Upto Lintel Level
2 | GGPS | APWA Gulbahar No: 2 Karachi ( 8 C/R) | Liaquatabad | 3.532 | 0 | 0 | 0 | 0 | 0 | Dismentling Work of Existing old Building in Progress
3 | GBPS | D.B Advani (Sachal Goth) (2 C/Room) | Gulshan' Iqbal | 0.883 | 0 | 0.204 | 0 | 0 | 0.204 | Tender Under Process
4 | GBPS | Sher Muhammad Goth (3 C/Room) | Gulshan' Iqbal | 1.3245 | 0 | 0 | 0 | 0 | 0 | Tender Under Process
5 | GBPS | Bhittaiabad Karachi (3 C/Room) | Gulshan' Iqbal | 1.3245 | 0 | 0.371 | 0 | 0 | 0.371 | Tender Under Process
6 | GBPS | Ayoob Goth (1 Classroom) | Gulshan' Iqbal | 0.442 | 0 | 0 | 0 | 0 | 0 | Tender Under Process
|  | Total |  | 9.272 | 0 | 0.775 | 0 | 0 | 0.775
14 | CONSTRUCTION / RE-CONSTRUCTION OF
*** / 74 | EXISTING MIDDLE SCHOOL (10 UNITS) |  |  |  | 0
1 | GBSS | Memon Goth Gadap | Gadap | 4.313 |  | 0.564 | 0 | 0 | 0.564 | Footing in Progress
2 | GGLSS | Rehri at Memon Goth Gadap | Gadap | 4.313 |  | 0.881 | 0 | 0 | 0.881 | Footing in Progress
3 | GGLSS | Sector 5/G Dhobi Ghat New Karachi | New Karachi | 4.313 |  | 1.006 | 0 | 0 | 1.006 | Upto Plinth Level
4 | GBMS | Peoples Own 11/F New Karachi | New Karachi | 4.313 |  | 0.025 | 0 | 0 | 0.025 | Dismentling Work of Existing old Building in Progress
5 | GBMS | Standared 5/D New Karachi | New Karachi | 4.313 |  | 0.024 | 0 | 0 | 0.024 | Dismentling Work of Existing old Building in Progress
|  | Total |  | 21.565 | 0 | 2.5 | 0 | 0 | 2.5
15 | UP-GRADATION OF PRIMARY TO MIDDLE
*** / 75 | SCHOOL (18 Units)
1 | GGPS | APWA Gulbahar Liaquatabad Kyc | Liaquatabad | 4.637 | 0 | 0 | 0 | 0 | 0 | Dismentling Work of Existing old Building in Progress
2 | Major Khalid Sultan Primary School North Nazimabad |  | North Naz'd | 4.637 |  | 0 | 0 | 0 | 0 | Tender Under Process
3 | GBPS | Al-Noor Block-19 F.B.Area Karachi | Gulberg | 4.637 |  | 0.251 | 0 | 0 | 0.251 | Plinth in Progress
4 | GGPS | Madhoo Goth Gulshan-e-Iqal | Gulshan' Iqbal | 4.637 |  | 0.25 | 0 | 0 | 0.25 | Plinth in Progress
5 | GGPS | Mughal Hazara Goth Gulshan'Iqbal | Gulshan' Iqbal | 4.637 |  | 0.049 | 0 | 0 | 0.049 | Plinth in Progress
6 | GGPS | Model Community UC-7, Gadap | Gadap | 4.637 |  | 0.25 | 0 | 0 | 0.25 | Footing in progress
|  | Total |  | 27.822 | 0 | 0.8 | 0 | 0 | 0.8
16 | CONSTRUCTION OF BUILDING FOR SHELTER
*** / 76 | LESS PRIMARY SCHOOL (20 UNITS) (2003-04) |  |  |  | 0 |  |  |  |  | Location not yet justified
1 | GBPS | Siddiqu-e-Akber-III 5/E North Karachi | New Karachi | 3.261 |  | 0 | 0 | 0 | 0
2 | GBPS | Raza Muhammad Brohi Goth | Gadap | 3.261 |  | 0 | 0 | 0 | 0
3 | GBLSS | Seta Nagar Gulshan-e-Iqbal | Gulshan' Iqbal | 3.261 |  | 0 | 0 | 0 | 0
4 | GGPS | Old Subzi Mandi | Gulshan' Iqbal | 3.261 |  | 0 | 0 | 0 | 0
5 | GBPS | Haji Bethai Goth Sector 7/A Sujani Town | Gadap | 3.261 |  | 0 | 0 | 0 | 0
6 | GBPS | Saif-ul-Marri Goth Sector 8 Sujani Tonw | Gadap | 3.261 |  | 0 | 0 | 0 | 0
7 |  | Sector 11/D-2, North Karachi | New Karachi | 3.261 |  | 0 | 0 | 0 | 0
8 | GBPS | J.M Kakki Sector 5/C North Karachi | New Karachi | 3.261 |  | 0 | 0 | 0 | 0
|  | Total |  | 26.088 | 0 | 0 | 0 | 0 | 0
17 | CONSTRUCTION OF THREE PRIMARY SCHOOL
*** / 77 | IN KARACHI DIVISION
1 | GGPS | Surjani Town Gadap | Gadap | 3.206 | 0 | 0.6 | 0 | 0 | 0.6 | Footing in Progress
|  | Total |  | 3.206 | 0 | 0.6 | 0 | 0 | 0.6
|  | Total Elementary Education |  | 255.155 | 0 | 142.034 | 0 | 0 | 142.034
|  | Total Middle School Project |  | 0 | 0 | #REF! | 0 | 0 | #REF!
|  | Sub-Total ( Elementary Education) " A " |  | 255.155 | 0 | #REF! | 0 | 0 | #REF!
B | SECONDARY EDUCATION
18 | UP-GRADATION OF MIDDLE SCHOOLTO HIGH |  |  |  | 0
26 / 78 | SCHOOL IN SINDH R/AREA (1992-93 Prog:)
1 | GBLSS | Darsano Channo | Gadap | 1.604 | 0 | 1.81 | 0 | 0 | 1.81 | Colouring in Progress
|  | Total |  | 1.604 | 0 | 1.81 | 0 | 0 | 1.81
19 | ADDITION C/R IN EXISTING
37 / 87 | HIGH SCHOOL IN SINDH(1994-95) |  |  |  | 0
1 | GGSS | Dastagir No:9 Federal "B" area (4 C/R) | Gulberg | 1.06 | 0 | 1.143 | 0 | 0 | 1.143 | Completed & Handedover
2 | GHSS | Ibrahim Ali Bhai Federal "B" area (4 C/R) | Gulberg | 1.06 | 0 | 1.114 | 0 | 0 | 1.114 | Completed & Handedover
3 | GBSS | Sitar-e-Hydri 11/D North Karachi ( 2C/R ) | New Karachi | 0.53 | 0 | 0.537 | 0 | 0 | 0.537 | Completed & Handedover | 2005-08-04
4 | GGSS | Allama Iqbal Bl # 16 F.B.Area Kyc (2 C/R) | Gulberg | 0.53 | 0 | 0.483 | 0 | 0 | 0.483 | Completed & Handedover | 2004-07-26
5 | GBSS | Murrad Memon ( 4 Classroom) | Gadap | 0.919 | 0 | 1.325 | 0 | 0 | 1.325 | Completed & Handedover
6 | GGMS | Dumba Goth ( 2 C/Room) | Gadap | 0.46 | 0 | 0.47 | 0 | 0 | 0.47 | Completed & Handedover
|  | Total |  | 4.559 | 0 | 5.072 | 0 | 0 | 5.072
20 | ESTABLISHMENT OF DOUBLE SECTION HIGH
131 / 93 | SCHOOL FOR BOYS/ GIRLS KARACHI CITY
| North Nazimabad |  | N'Nazimabad | 13.858 | 0 | 7.399 | 0 | 0 | 7.399 | Cement plaster, Tiles Flooring in Progress
|  | Total |  | 13.858 | 0 | 7.399 | 0 | 0 | 7.399
21 | CONSTRUCTION / RE-CONSTRUCTION OF
131 / 97 | BUILDING FOR EXISTING SECONDARY SCHOOL
| GBSS Nazimabad No:1 Karachi |  | Liaquatabad | 5.881 | 0 | 5.481 | 0 | 0 | 5.481 | Finishing in Progress, Ext: Dev Work completed
|  | Total |  | 5.881 | 0 | 5.481 | 0 | 0 | 5.481
22 | ADDITION OF CLASSROOM IN EXISTING
*** / 99 | SECODARY SCHOOLIN SINDH (1992-93 PROG: )
| GGSS | Khatoon-e-Pakistan | Gulshan' Iqbal | 0 | 0 | 0 | 0 | 0 | 0 | Unit Not yet Identify.
|  | Total |  | 0 | 0 | 0 | 0 | 0 | 0
23 | CONSTRUCTION / RE-CONSTRUCTION OF BUILDING
*** / 101 | FOR EXISTING SECONDARY SCHOOL KARACHI |  |  | 15.297 | 0 | 0 | 0 | 0 | 0 | Location not yet available
| DIVISION (1991-92 PROGRAMME) |  |  | 15.297 | 0 | 0 | 0 | 0 | 0
Total
24 | ADDITION OF CLASSROOM IN EXISTING SECON: |  |  | 0 | 0 | 0 | 0 | 0 | 0 | Location not yet available
*** / 102 | SCHOOL IN KARACHI ( 1991-92 PROGRAMME) |  |  | 0 | 0 | 0 | 0 | 0 | 0
Total
25 | ADDITION OF CLASS ROOM IN EXISTING |  |  |  | 0
83 / 105 | SECONDARY SCHOOL IN U/AREA KARACHI
1 | GBSS | Allama Iqbal F.B.Area ( 4 Class Rooms) | Gulberg | 1.16 | 0 | 0.869 | 0 | 0 | 0.869 | Completed & Handed over
2 | GBSS | New Method F.B.Area ( 4 Class Rooms) | Gulberg | 1.16 | 0 | 0.969 | 0 | 0 | 0.969 | Completed
3 | GBSS | Anglo Oriential Block-15,F.B.Area (5 C/R) | Gulberg | 1.45 | 0 | 1.514 | 0 | 0 | 1.514 | Completed & Handed over
4 | GGSS | Hyderi North Karachi (5 Class/Room ) | New Karachi | 1.45 | 0 | 1.626 | 0 | 0 | 1.626 | Completed & Handed over
5 | GBSS | 5/A-3, New Karachi.(5 Class Room) | New Karachi | 1.45 | 0 | 1.469 | 0 | 0 | 1.469 | Completed & Handed over
6 | GGSS | Liaquatabad No:4 Karachi.(3 C/ Room) | Liaquatabad | 0.87 | 0 | 0.774 | 0 | 0 | 0.774 | Completed & Handed over
7 | GBSS | Liaquatbad No:4 Karachi.(4 C/ Rooms ) | Liaquatabad | 1.16 | 0 | 1.099 | 0 | 0 | 1.099 | Completed & Handed over
|  | Total |  | 8.7 | 0 | 8.32 | 0 | 0 | 8.32
26 | INTRODUCTION OF XI & XII CLASSES IN EXISTING |  |  |  | 0
33 / 114 | SECONDARY SCHOOL IN KARACHI DIVISION
| GBGSS | Sharafabad Gulshan-e-Iqbal | Gulshan' Iqbal | 9.206 |  | 1.33 | 0 | 0 | 1.33 | Upto Plinth Level
|  | Total |  | 9.206 | 0 | 1.33 | 0 | 0 | 1.33
27 | CONSTRUCTION / RE-CONSTRUCTION OF
34 / 115 | EXISTING SECONDARY SCHOOL IN KARACHI |  |  |  | 0
| GGPS | APWA Gulbahar Laiquatabad Kyc | Liaquatabad | 7.84 |  | 0 | 0 | 0 | 0 | Dismentling Work of Existing Old Building in Progress
| GGSS | Sector 5/G New Karachi | New Karachi | 7.84 |  | 0 | 0 | 0 | 0 | Dismentling Work of Existing Old Building in Progress
|  | Total |  | 15.68 | 0 | 0 | 0 | 0 | 0
28 | ESTABLISHMENT OF DOUBLE SECTION HIGH
36 / 118 | SCHOOL IN SINDH ( 3 UNITS) |  |  |  | 0
1 | at North Karachi (Girls) |  | New Karachi | 9.184 |  | 1.02 | 0 | 0 | 1.02 | Upto Plinth Level
2 | at GSS Gulistan-e-Jouhar Bock-12 Karach |  | Gulshan' Iqbal | 9.184 |  | 0 | 0 | 0 | 0 | Tender Under Process
|  | Total |  | 18.368 | 0 | 1.02 | 0 | 0 | 1.02
29 | ESTABLISHMENT OF SINGLE SECTION HIGH
37 / 119 | SCHOOL KARACHI (5 UNITS) |  |  |  | 0
| GGPS | Farqulit Nazimabad Karachi | Liaquatabad | 7.456 |  | 0.82 | 0 | 0 | 0.82 | Upto Lintel Level
| GGPS | Maymarabad Surjani Town | Gadap | 7.456 |  | 1.08 | 0 | 0 | 1.08 | Footing in Progress
|  | Total |  | 14.912 | 0 | 1.9 | 0 | 0 | 1.9
30 | CONSTT: / RE-CONSTRUCTION OF BUILDING FOR
38 / 120 | EXISTING HIGH SCHOOL IN KARACHI ( 5 UNITS) |  |  |  | 0
1 | GBSS | Standered 5/F New Karachi | New Karachi | 10.653 |  | 0.025 | 0 | 0 | 0.025 | Dismentling Work of Existing Old Building in Progress
2 | GGSS | Nazia Square 5/E New Karachi | New Karachi | 10.653 |  | 2.975 | 0 | 0 | 2.975 | Upto Roof Level
3 | GGSS | Ibrahim Ali Bhai Block-6, F.B.Area | Gulberg | 10.653 |  | 0 | 0 | 0 | 0 | Tender Under scrutiny
|  | Total |  | 31.959 | 0 | 3 | 0 | 0 | 3
|  | Sub-Total ( Secondary Education) " B" |  | 140.024 | 0 | 35.332 | 0 | 0 | 35.332
C | TECHNICAL EDUCATION
31 | ESTABLISHMENT OF MONO TECHNIC INSTITUTE | [8 empty] | Block-A Finishing in Progress
42 / 122 | GADAP KARACHI 1994-95 PROGRAMME | [8 empty] | Block-B Finishing in progress
1 |  | @ Memon Goth. | Gadap | 21.199 | 0 | 20.776 | 0 | 0 | 20.776 | C/Wall completed , W/S & S/F i/c Ext Developmenet
|  | Total |  | 21.199 | 0 | 20.776 | 0 | 0 | 20.776
32 | UP-GRADATION OF SAIFEE EIDEE ZAHABI INSTITUTE
89 / 137 | OF TECHNOLOGY TO B.TECH LEVEL CLASSES KYC |  |  |  | 0 |  |  |  |  | Phase-I Finishing in Progress
| North Nazimabad Karachi |  | N' Nazim'd | 11.913 | 0 | 9.894 | 0 | 0 | 9.894 | Phase-II, Finishing in Progress
Phase-III, Finishing in Progress
|  | Total |  | 11.913 | 0 | 9.894 | 0 | 0 | 9.894
|  | Total :Technical Education >>>>> |  | 33.112 | 0 | 30.67 | 0 | 0 | 30.67
|  | TOTAL : Technical Education(ADB) |  | #REF! | 0 | #REF! | 0 | 0 | #REF!
| Sub Total ( Technical Education ) " C " |  |  | #REF! | 0 | #REF! | 0 | 0 | #REF!
D | COLLEGE EDUCATION
33 | ADDITION/ ALTERATION IN APWA GOVT. | [8 empty] | Phase-I, Finishing in Progress
63 / 148 | COLLEGE FOR WOMEN Federal "B" AREA. |  | Gulberg | 11.564 | 0 | 16.41 | 0 | 0 | 16.41 | Phase-II, Lab 1st Floor Stru: in Progress
|  | Total |  | 11.564 | 0 | 16.41 | 0 | 0 | 16.41 |  | 2004-11-03
34 | ESTABLISHMENT OF GOVT. DEGREE
73 / 157 | COLLEGE FOR MAN @ Mangopir |  | Gadap | 26.77 | 0 | 23.485 | 0 | 0 | 23.485 | Completed
|  | Total |  | 26.77 | 0 | 23.485 | 0 | 0 | 23.485
35 | CONSTRUCTION OF COMMERCE BLOCK FOR
131 / 169 | GOVERNMENT GIRLS COLLEGE NEW KARACHI |  | New Karachi | 9 | 0 | 7.149 | 0 | 0 | 7.149 | Finishing in Progress
|  | Total |  | 9 | 0 | 7.149 | 0 | 0 | 7.149
36 | ESTABLISHMENT OF GOVERNMENT DEGREE
131 / 170 | GIRLS COLLEGE NORTH KARACHI
| Sector 11/B North Karachi |  | New Karachi | 17.347 | 0 | 8.875 | 0 | 0 | 8.875 | G+F/Floor Finishing in Progress
|  | Total |  | 17.347 | 0 | 8.875 | 0 | 0 | 8.875
37 | CONSTRUCTION / ADDITION OF (2) CLASSROOM
131 / 171 | AUDITORIUM & COMPUTER LABS: IN GOVT:
| COLLEGE FOR WOMEN NORTH NAZIMABAD |  | N'Nazimabad | 12.657 | 0 | 9.338 | 0 | 0 | 9.338 | Finishing in Progress
BLOCK "M" KARACHI
|  | Total |  | 12.657 | 0 | 9.338 | 0 | 0 | 9.338
38 | ADDITION BLOCK & IMPROVEMENT OF GOVT: |  |  |  | 0
96 / 185 | GIRLS COLLEGE F.B.AREA BLOCK # 16 KYC: |  | Gulberg | 26.531 |  | 0 | 0 | 0 | 0 | Plot Not yet received
|  |  |  | 26.531 | 0 | 0 | 0 | 0 | 0
39 | EXPANSION AND ADDITION IN GOVT RIAZ |  |  |  | 0
*** / 188 | GIRLS COLLEGE AT LIAQUATABAD KARACHI |  | Liaquatabad | 17.454 |  | 2.7 | 0 | 0 | 2.7 | Block "B" 3rd Floor Roof Laid in Progress
|  |  |  | 17.454 | 0 | 2.7 | 0 | 0 | 2.7
72 | RE-CONSTRUCTION OF GOVERNMENT DEGREE
*** / 191 | FOR MEN NAZIMABAD KARACHI |  | Liaquatabad |  | 0 |  |  |  |  | Foundation in Progress
|  |  |  | 37.504 |  | 0.7 | 0 | 0 | 0.7
|  |  |  | 37.504 | 0 | 0.7 | 0 | 0 | 0.7
74 | ESTABLISHMENT OF GOVERNMENT CITY |  |  |  | 0
*** / 195 | DEGREE COLLEGE AT SHARIFABAD KARACHI |  | Liaquatabad | 41.235 |  | 0 | 0 | 0 | 0 | Tender Under Process
|  |  |  | 41.235 | 0 | 0 | 0 | 0 | 0
78 | ADDITION OF CLASSROOM IN EXISTING
*** / 201 | COLLEGES OF KARACHI ( 50 UNITS) |  |  |  | 0
1 | Sir Syed Govt. College for Women Nazimabad (4unit) |  | Liaquatabad | 2.52 |  | 0.158 | 0 | 0 | 0.158 | Roof Shuttering in Progress (First Floor)
2 | H.I. Usmania Govt. Girls College Nazimabad (4 Units) |  | Liaquatabad | 2.52 |  | 0 | 0 | 0 | 0 | Tender Under Process
3 | Govt College for Women 11/B North Karach (4 Units) |  | New Karachi | 2.52 |  | 0.542 | 0 | 0 | 0.542 | Upto Plinth Level
4 | Govt Boys & Girls College Stadium Road (4 Units) |  | Gulshan'Iqbal | 2.52 |  | 0 | 0 | 0 | 0 | Tender Under Process
5 | Govt. College for Women Block-16 F.B.Area (4 Unit) |  | Gulberg | 2.52 |  | 0 | 0 | 0 | 0 | Tender Under Process
6 | Govt Degree College for BOYS Buffarzone (4 Units) |  | North Nazim'd | 2.52 |  | 0.1 | 0 | 0 | 0.1 | Foundation in Progress
|  |  |  | 15.12 | 0 | 0.8 | 0 | 0 | 0.8
80 | IMPROVEMENT / ALTERATION OF STAFF RESIDENCE |  |  |  | 0
99 / 205 | OF RANA LIAQUAT ALI KHAN GOVERNMENT |  | Gulshan'Iqbal | 0.975 | 0 | 5.47 | 0 | 0 | 5.47 | Finishing in Progress
| COLLEGE OF HOME ECONOMIC KARACHI |  |  | 0.975 | 0 | 5.47 | 0 | 0 | 5.47
81 | ESTABLISHMENT OF GOVERNMENT DEGREE |  |  | 47.087 | 0
*** / 206 | COLLEGE AT 15/A BUFFARZONE KARACHI
|  |  | North Nazim'd | 47.087 | 0 | 1 | 0 | 0 | 1 | Upto Plinth Completed
| Sub Total (College Education) " D " |  |  | 263.244 | 0 | 75.927 | 0 | 0 | 75.927
E | EDUCATION LITERACY PROGRAMME
82 | REPAIR & RENOVATION OF (2) TWO ROOMED |  |  |  | 0
*** / 213 | FOR VOCATIONAL CENTRE IN SUPER MARKET | [8 empty] | completed
| LIAQUATABAD TOWN KARACHI (2003-04 PRG) |  | Liaquatabad | 0.2 |  | 0.103 | 0 | 0 | 0.103
|  |  |  | 0.2 | 0 | 0.103 | 0 | 0 | 0.103
84 | UP-GRADATION OF GOVERNMENT VOCATIONAL |  |  |  | 0
*** / 217 | SCHOOL (GIRLS) AT KARACHI DIVISION
1 | at Sachal Balouch Goth |  | Gulshan'Iqbal | 3.94 |  | 1.1 | 0 | 0 | 1.1 | Work Started
2 | at Buffarzone Karachi. |  | N'Nazimabad | 3.94 |  | 0 | 0 | 0 | 0 | Work Initial Stage
|  |  |  | 7.88 | 0 | 1.1 | 0 | 0 | 1.1
| Sub Total (Education Literacy Prog) " E " |  |  | 8.08 | 0 | 1.203 | 0 | 0 | 1.203
G | PROVINCIAL EDUCATION (TEACHER EDUCATION)
92 | ADDITIONAL / IMPROVEMENT OF GOVERNMENT
288 | ELEMENTARY COLLEGE (MEN) QASIMABAD |  | Liaquatabad | 5.214 | 0 | 3.8 | 0 | 0 | 3.8 | G+ F Floor : Plastering Completed
| LIAQUATABAD KARACHI |  |  | 5.214 | 0 | 3.8 | 0 | 0 | 3.8
|  | Total Prov: Education (Teacher Edu) |  | 5.214 | 0 | 3.8 | 0 | 0 | 3.8
MPA's PRIORITY PROGRAMME
(EDUCATION SECTOR)
1 |  | CONSTRUCTION OF COMPUTER LAB IN EXISTING |  |  | 5.1
SECONDARY SCHOOL BUILDING:
Sponsored By:
Mr. Syed Sardar Ahmed ( PS-98)
Mr. Qammar Mansoor (PS-99)
Mr. Muhammad Adil Siddiqui ( PS-100)
Mr. Asma Sherwani (Reserved Seat)
| I | @ GBSS 5/D North Karachi | New Karachi | 1.36 |  | 1.098 | 0 | 0 | 1.098 | Finishing in Progress
| II | @ GBSS 5/D-1 New Karachi | New Karachi | 1.36 |  | 0.697 | 0 | 0 | 0.697 | Finishing in Progress
| III | @ GGSS 11/E U.P Society. | New Karachi | 1.36 |  | 1.104 | 0 | 0 | 1.104 | Finishing in Progress |  | Balance
| IV | @ GBSS APWA 5/E New Karachi. | New Karachi | 1.36 |  | 1.076 | 0 | 0 | 1.076 | Finishing in Progress |  | 5.1
|  | TOTAL >>>> |  | 5.44 | 5.1 | 3.975 | 0 | 0 | 3.975
2 |  | ADDITION OF (8) CLASSROOM IN EXISTING |  |  | 6.22
SECONDARY
Mr. Syed Sardar Ahmed ( PS-98)
Mr. Qammar Mansoor (PS-99)
Mr. Muhammad Adil Siddiqui ( PS-100)
Mr. Asma Sherwani (Reserved Seat)
| I | @ GBSS 11/ C-3, North Karachi | New Karachi | 3.481 |  | 1.912 | 0 | 0 | 1.912 | Finishing in Progres
| II | @ GBSS 11/E-1 North Karachi. | New Karachi | 3.481 |  | 1.823 | 0 | 0 | 1.823 | Finishing in Progres
|  | TOTAL >>>> |  | 6.962 | 6.22 | 3.735 | 0 | 0 | 3.735
3 |  | CONSTRUCTION OF ADDITIONAL (2) CLASSROOM
At Government Boys Lower
|  | Secondary School Block "L" | N'Nazimabad | 0.92 | 0.845 | 0.616 | 0 | 0 | 0.616 | Super Structure Masonary Work in Progress
Arfat Town North Nazimabad Kyc:
Sponsored By
Ms. Bilquis Mukhtar (PS-101)
|  | TOTAL >>>> |  | 0.92 | 0.845 | 0.616 | 0 | 0 | 0.616
Sponsored By:
Miss: Farhina Ambreen (MPA)
4 |  | ADDOTION OF (3) ROOMS @ GGPS
STAFF WELFARE F.C. AREA
|  | Liaquatabad Town Karachi | Liaquatabad | 1.02 | 1.139 | 1.035 | 0 | 0 | 1.035 | Completed
|  | TOTAL >>>> |  | 1.02 | 1.139 | 1.035 | 0 | 0 | 1.035
Sponsored By:
Mr. Sajid Jokhio (MPA)
5 |  | CONSTRUCTION OF (2) TWO ROOMED
PRIMARY SCHOOL I/C COMPOUND WALL
| I | GPS Nido Buro UC Gadap | Gadap | 0.714 | 0.67 | 0.664 | 0 | 0 | 0.664 | Finishing in Progress
| II | GPS Nandho Jokhio | Gadap | 0.714 | 0.67 | 0.668 | 0 | 0 | 0.668 | Completed
(Deh Tahdo UC Darsano Channo)
| III | GPS Jarro Khan Chooto | Gadap | 0.714 | 0.67 | 0.664 | 0 | 0 | 0.664 | Finishing in Progress
(Deh Almani UC Darsano Channa)
|  | TOTAL >>>> |  | 2.142 | 2.01 | 1.996 | 0 | 0 | 1.996
6 |  | ADDITION OF (3) CLASS ROOM IN |  |  | 0.553
PRIMARY SCHOOL:
|  | @ Haji Gul Hassan Kathori. | Gadap | 0.591 |  | 0.208 | 0 | 0 | 0.208 | roof level completed
|  | TOTAL >>>> |  | 0.591 | 0.553 | 0.208 | 0 | 0 | 0.208
|  | GRAND TOTAL |  | 17.075 | 15.867 | 11.565 | 0 | 0 | 11.565
|  | Grand Total |  | #REF! | 15.867 | #REF! | 0 | 0 | #REF!
DISTRICT OFFICER
EDUCATION WORKS-II (W & S DEPTT)
CITY DISTRICT GOVT: KARACHI
NON- ADP SCHEME
1 | CONSTT:/RE-CONSTT: OF BUILDING FOR
18 / *** | EXISTING MIDDLE SCHOOL ( 1990-91) |  |  |  | 0
1 | GBLSS | Karachi Elemantry | N'Nazimabad | 1.014 | 0 | 1.183 | 0 | 0 | 1.183 | Completed & Handedover | 14/01/1996.
2 | GBLSS | Moon Ligh 5/G-1 N/K | New Karachi | 1.014 | 0 | 1.159 | 0 | 0 | 1.159 | Completed & Handedover | 21/08/1992.
3 | GBLSS | 5/A Buffarzone N/K | New Karachi | 1.014 | 0 | 0.975 | 0 | 0 | 0.975 | Completed & Handedover | 01/07/1992.
4 | GBLSS | 11/E U.P Society | New Karachi | 1.014 | 0 | 1.175 | 0 | 0 | 1.175 | Completed & Handedover | 13/04/2001.
5 | GBLSS | Bright Grammar N/Naz: | New Karachi | 1.014 | 0 | 1.111 | 0 | 0 | 1.111 | Completed & Handedover | 09/07/1999.
6 | GBLSS | Zia-ul-Uloom Firdous Col | Liaquatabad | 1.014 | 0 | 0.727 | 0 | 0 | 0.727 | Under Litigation lying abandoned at roof Level
7 | GBLSS | 5/G New Karachi. | New Karachi | 1.014 | 0 | 1.098 | 0 | 0 | 1.098 | Completed & Handedover | 30/03/2000.
8 | GBLSS | No:5 Drigh Colony Shifted to GGSS | Gulshan' Iqbal | 1.014 | 0 | 1.051 | 0 | 0 | 1.051 | Completed & Handedover
Gulshan-e-Iqbal Karachi.
|  | Total |  | 8.112 | 0 | 8.479 | 0 | 0 | 8.479
2 | UP-GRADATION OF PRIMARY TO MIDDLE |  |  |  | 0
19 / *** | IN SINDH ( 1991-92 PROGRAMME) |  |  |  | 0
1 | GBPS | 5/A-3, New Karachi | New Kyc |  | 0 | 2.007 | 0 | 0 | 2.007 | Completed & Handedover | 2005-04-14
2 | GBPS | 5/G-1, New Karachi | New Kyc | 2.195 | 0 | 0.814 | 0 | 0 | 0.814 | Completed | ***
3 | GBPS | 5/D-1,New Karachi. | New Kyc | 2.195 | 0 | 0.936 | 0 | 0 | 0.936 | Taken under Abandoned units | ***
4 | GBPS | 5/E-II, New Karachi. | New Kyc | 2.195 | 0 | 0.794 | 0 | 0 | 0.794 | Completed | ***
5 | GBPS | Block # 1, Gulshan-e-Iqbal Karachi | Gulshan' Iqbal | 2.195 | 0 | 2.665 | 0 | 0 | 2.665 | Completed & Handedover
|  | Total |  | 8.78 | 0 | 7.216 | 0 | 0 | 7.216
3 | ESTABLISHMENT OF SINGLE SECTION HIGH |  |  |  | 0
30 / *** | SCHOOL IN SINDH ( 5 Units) 1994-95 Prog:
1 | Schal Balouch Goth Shifted from GGHS Sukkur |  | Gulshan' Iqbal | 7.097 | 0 | 4.66 | 0 | 0 | 4.66 | Completed
|  |  |  | 7.097 | 0 | 4.66 | 0 | 0 | 4.66
4 | UP-GRADATION OF MIDDLE TO HIGH SCHOOL |  |  |  | 0
31 / *** | IN RURAL AREA KARACHI
1 | GGMS | Leemo Gabol Gulshan-e-Iqbal Karachi | Gulshan'Iqbal | 1.286 | 0 | 1.483 | 0 | 0 | 1.483 | Completed & Handedover
2 | GBMS | Faiz Muhammad Bikik | Gadap | 1.286 | 0 | 1.286 | 0 | 0 | 1.286 | Completed & Handedover
3 | GBMS | Dumlotti No: 3 | Gadap | 1.284 | 0 | 1.284 | 0 | 0 | 1.284 | Completed & Handedover
|  |  |  | 3.856 | 0 | 4.053 | 0 | 0 | 4.053
5 | UP-GRADATION OF MIDDLE TO HIGH SCHOOL |  |  |  | 0
32 / *** | IN RURAL AREA ( 1991-92 PROGRAMME)
1 | GBLSS | Aali Khan | Gadap | 3.088 | 0 | 3.432 | 0 | 0 | 3.432 | Completed | 2006-11-02
|  |  |  | 3.088 | 0 | 3.432 | 0 | 0 | 3.432
6 | UP-GRADATION OF MIDDLE TO
147 / *** | HIGH SCHOOL IN R/AREA (1994-95) |  |  |  | 0
1 | GBLSS | District Council 11/D N/K | New Karachi | 1.607 | 0 | 2.328 | 0 | 0 | 2.328 | Completed & Handover
2 | GBLSS | 11/E New Karachi. | New Karachi | 1.607 | 0 | 2.333 | 0 | 0 | 2.333 | Completed & Handover
3 | Haji Noor Muhammad Borfat Moiden |  | Gadap | 1.595 | 0 | 2.265 | 0 | 0 | 2.265 | Completed
|  |  |  | 4.809 | 0 | 6.926 | 0 | 0 | 6.926
7 | CONSTT / RE-CONSTT: OF BUILDING
40 / *** | FOR EXISTING HIGH SCHOOL (1988-89). |  |  |  | 0
1 | GBPS | Block # 9 F.B area Kyc: | Gulberg | 2.28 | 0 | 2.577 | 0 | 0 | 2.577 | Completed & Handed Over | 12/11/90.
2 | GBSS | Green Land Premises | Gulberg | 2.28 | 0 | 2.241 | 0 | 0 | 2.241 | Completed & Handed Over | 08/05/91.
Happy Dale Nazimabad Karachi
3 | GGSS | Al Zohra Karachi. | Gulberg | 2.28 | 0 | 2.477 | 0 | 0 | 2.477 | Completed & Handed Over | 04/04/91.
4 | GBPS | Technical Age F.B.Area (Shifted to | Gulberg | 2.28 | 0 | 2.484 | 0 | 0 | 2.484 | Completed & Handed Over | 27/4/97.
Ibrahim Ali Bhai B# 15 F.B.Area Kyc)
|  |  |  | 9.12 | 0 | 9.779 | 0 | 0 | 9.779
COLLEGE EDUCATION.
8 | ESTABLISHMENT OF GOVT. COLLEGE | [8 empty] | Block-A & C = Floor Completed
58 / *** | OF EDUCATION B.Ed. & M.Ed. | [8 empty] | Block-B = Partially Roof Laid,
| @ Darsano Channo |  | Gadap | 25.412 | 0 | 19.569 | 0 | 0 | 19.569 | but the Scheme Dropped from ADP Scheme
|  |  |  | 25.412 | 0 | 19.569 | 0 | 0 | 19.569
9 | OPENING OF GOVERNMENT DEGREE
38 / *** | COLLEGE IN ARTS & SCIENCE |  |  | 22.149 | 0 | 21.293 | 0 | 0 | 21.293 | Completed & Handedover | 2002-09-29
| Boys | @ New Karachi | New Karachi | 22.149 | 0 | 21.293 | 0 | 0 | 21.293
10 | IMPROVEMENT OF RAIZ GOVT: |  |  | 8.701 | 0 | 8.314 | 0 | 0 | 8.314
40/ *** | GIRLS COLLEGE @ Liaquatabad #10 |  | Liaquatabd | 8.701 | 0 | 8.314 | 0 | 0 | 8.314 | Completed & Handedover | 2001-04-03
11 | CONSTRUCTION OF GOVT DEGREE |  |  | 11.713 | 0 | 12.318 | 0 | 0 | 12.318 | Completed & Handedover
41 /*** | COLLEGE @ Buffarzone N'Karachi. |  | New Karachi | 11.713 | 0 | 12.318 | 0 | 0 | 12.318 |  | ***
12 | CONSTRUCTION OF GOVT: |  | Gulberg | 11.713 | 0 | 12.234 | 0 | 0 | 12.234 | Completed & Handedover
42 / *** | DEGREE COLLEGE at F.B. Area. |  |  | 11.713 | 0 | 12.234 | 0 | 0 | 12.234 |  | ***
13 | ESTABLISHEMNT OF DEGREE COLLEGE
43 / *** | @Shaheed-e- Millat Azizabad |  | Gulberg | 30.672 | 0 | 28.524 | 0 | 0 | 28.524 | Completed & Handedover
| Federal ".B".Area Karachi. |  |  | 30.672 | 0 | 28.524 | 0 | 0 | 28.524 |  | ***
14 | OPENING OF COMPOSITE DEGREE COLLEGE
63 / *** | @ Gulshan-e-Iqbal (Phase-II) ( 1991-92) |  | Gulshan' Iqbal | 6.828 | 0 | 7.631 | 0 | 0 | 7.631 | Completed & handedover
|  |  |  | 6.828 | 0 | 7.631 | 0 | 0 | 7.631
15 | ESTABLISHMENT OF GOVT. BOYS/GIRLS DEGREE
71/ *** | COLLEGE @ National Stadium Road Karachi. |  | Gulshan' Iqbal | 16.529 | 0 | 17.848 | 0 | 0 | 17.848 | Completed & handedover
|  |  |  | 16.529 | 0 | 17.848 | 0 | 0 | 17.848
17 | ADDITION / IMPROVEMENT OF GOVERNMENT |  | Liaquatabad | 0 | 0 | 0.5 | 0 | 0 | 0.5 | Initial Stage
131 / *** | BOYS / GIRLS PRIMARY SCHOOL (Atta Turk)
| F.C. Area Karachi ( Abandoned Unit) |  |  | 0 | 0 | 0.5 | 0 | 0 | 0.5
| Grand Total (Non-ADP Schemes) |  |  | 178.984 | 0 | 169.65 | 0 | 0 | 169.65
REPAIR WORK OF SCHOOL EDUCATION
1 | GBPS | Bukhar Goth | Gulshan'e'I |  |  |  | 88365 | 88365 | 88365
2 | GPS | Gulshan-e-Iqbal Block-I Karachi | Gulshan'e'I |  |  |  | 36524 | 36524 | 36524
3 | GGPS | Sector 5/D New Karachi | New Karachi |  |  |  | 10036 | 10036 | 10036
4 | GBPS | Sector 11/D New Karachi | New Karachi |  |  |  | 77977 | 77977 | 77977
5 | GBPS | Manik Nagar Karachi | GADAP |  |  |  | 53517 | 53517 | 53517
6 | GGPS | Manik Nagar Karachi | GADAP |  |  |  | 48976 | 48976 | 48976
7 | GGMSS | APWA Liaquatabad Karachi | Liaquatabad |  |  |  | 49974 | 49974 | 49974
8 | GBPS | DMS Gulshan-e-Iqbal Karachi | Gulshan'e'I |  |  |  | 37836 | 37836 | 37836
9 | GBPS | Green Land Nazimabad No: N'Naz: | N' Nazim'd |  |  |  | 256129 | 256129 | 256129
10 | GGPS | Gadap City Karachi | GADAP |  |  |  | 39149 | 39149 | 39149
11 | GPS | Mochi Para Gulshan-e-Iqbal | Gulshan'e'I |  |  |  | 109886 | 109886 | 109886
12 | GGHSS | APWA Liaquatabad Karachi | Liaquatabad |  |  |  | 47512 | 47512 | 47512
13 | GBSS | Sector 5/B New Karachi | New Karachi |  |  |  | 272611 | 272611 | 272611
14 | *** | Sector-2 North Karachi | New Karachi |  |  |  | 330032 | 330032 | 330032
15 | GBPS | APWA 5/E-III New Karachi | New Karachi |  |  |  | 149974 | 149974 | 149974
16 | GBPS | APWA 5/E-II New Karachi | New Karachi |  |  |  | 216925 | 216925 | 216925
17 | GBPS | APWA 5/E-I New Karachi | New Karachi |  |  |  | 236363 | 236363 | 236363
18 | GBPS | Ayoub Goth Gulshan-e-Iqbal kyc: | Gulshan'e'I |  |  |  | 168861 | 168861 | 168861
19 | GPS | GADAP City Gadap Town Karachi | GADAP |  |  |  | 96405 | 96405 | 96405
20 | GBPS | Wastania Nazimabad # 4 Karachi | Nazimabad |  |  |  | 151278 | 151278 | 151278
21 | GGPS | Bhatai Goth Gulshan-e-Iqbal | Gulshan'e'I |  |  |  | 152624 | 152624 | 152624
22 | GBPS | Sher Muhammad Goth | Gulshan'e'I |  |  |  | 115461 | 115461 | 115461
23 | GGPS | Safora Goth Gulshan-e-Iqbal | Gulshan'e'I |  |  |  | 130268 | 130268 | 130268
24 | GBPS | Bright Grammer 5/E New Karachi | New Karachi |  |  |  | 178270 | 178270 | 178270
25 | GBPS | Bhatai Goth Gulshan-e-Iqbal | Gulshan'e'I |  |  |  | 105491 | 105491 | 105491
26 | GGPS | Salah Muhammad Goth G'Iqbal | Gulshan'e'I |  |  |  | 84432 | 84432 | 84432
27 | GPS | Babul Islam Goth (Phase - II) | GADAP |  |  |  | 368926 | 368926 | 368926
28 | GGPS | Siddique Goth Karachi | New Karachi |  |  |  | 199202 | 199202 | 199202
29 | GBPS | Ali Muhamamd Khaskhali Gadap | GADAP |  |  |  | 162957 | 162957 | 162957
30 | GBPS | Abdul Rahim Goth Karachi | GADAP |  |  |  | 100000 | 100000 | 100000
31 | GBSS | Malir Cantt (Prayer Hall & Audit'm) | Gulshan'e'I |  |  |  | 40000 | 40000 | 40000
32 | GBPS | Dost Muhammad Khaskhali | GADAP |  |  |  | 101296 | 101296 | 101296
33 | GBPS | Asghar Alnoor Block-19 F.B.area | Gulberg |  |  |  | 39894 | 39894 | 39894
34 | GPS | Konkar Gadap Karachi | GADAP |  |  |  | 100000 | 100000 | 100000
35 | GPS | Ibrahim Ali Bhai Jalalabad Nazim'd | Liaquatabad |  |  |  | 65000 | 65000 | 65000
36 | GGPS | Liaquatabad # 2 Karachi | Liaquatabad |  |  |  | 100000 | 100000 | 100000
37 | GBPS | Liaquatabad # 2 Karachi | Liaquatabad |  |  |  | 200000 | 200000 | 200000
38 | GBPS | Siddiqui-e-Akber 5/E New Karachi | New Karachi |  |  |  | 75000 | 75000 | 75000
39 | GBPS | Sector 11 / F New Karachi | New Karachi |  |  |  | 100000 | 100000 | 100000
40 | GBPS | Maqbool 5/E New Karachi | New Karachi |  |  |  | 100000 | 100000 | 100000
41 | GBPS | Gulberg No: 1 ( Sindhi Hotal) | Liaquatabad |  |  |  | 200000 | 200000 | 200000
REPAIR WORK OF COLLEGE EDUCATION
1 |  | Government College of Physical | Gulshan'e'I |  |  |  | 571951 | 571951 | 571951
Education University Road Karachi
2 |  | Government Commercial Institute | Gulberg |  |  |  | 28741 | 28741 | 28741
Azizabad Karachi
3 |  | APWA Govt. Girls College F.B.Area | Gulberg |  |  |  | 110271 | 110271 | 110271
4 |  | Govt Girls College Rana Liaquat | Gulshan'e'I |  |  |  | 222175 | 222175 | 222175
Ali Khan
5 |  | Government College for Women | Liaquatabad |  |  |  | 245636 | 245636 | 245636
Nazimabad Karachi
6 |  | H.I.Usmania Government Girls | Liaquatabad |  |  |  | 72202 | 72202 | 72202
College Nazimabad Karachi
7 |  | Abdullah Government Girls College | Liaquatabad |  |  |  | 20000 | 20000 | 20000
for Women Nazimabad Karachi
[7 empty] | 6468127 | 6468127 | 6468127
ABANDONED SCHEMES
ADP-130
1 | OPENING OF (5) ROOMED PRIMARY SCHOOL
| IN SINDH KARACHI ( 1992-93 Programme) |  | New Karachi | 1.202 | 0 | 1.396 | 0 | 0 | 1.396 | Completed
| GGPS | Saudi Colony Mali Karachi
|  |  |  | 1.202 | 0 | 1.396 | 0 | 0 | 1.396
2 | CONSTRUCTION / RECONSTRUCTION OF (2)
| CLASS ROOMED PRY: SCHOOL (1994-95 PROG) |  |  | 0.2 | 0 | 0.199 | 0 | 0 | 0.199 | Completed
| @ Jafar Khan Murrad Memon |  | GADAP
|  |  |  | 0.2 | 0 | 0.199 | 0 | 0 | 0.199
3 | CONSTRUCTION / RECONSTRUCTION OF (2)
CLASS ROOMED PRY: SCHOOL (1995-96 PROG)
I | GPS | Adam Gabol | GADAP | 0.8 | 0 | 0.3 | 0 | 0 | 0.3 | Completed
II | GPS | Haji Murrad Balouch | GADAP | 0.3 | 0 | 0.7 | 0 | 0 | 0.7 | Completed
III | GPS | Dada Salar | GADAP | 0 | 0 | 0 | 0 | 0 | 0 | Completed
IV | GPS | Khalifa Jat Para | GADAP | 0 | 0 | 0 | 0 | 0 | 0 | Completed
|  |  |  | 1.1 | 0 | 1 | 0 | 0 | 1
4 | ADDITION OF (1) CLASSROOM PRIMARY
SCHOOL ( 1995-96 PROGRAMME)
I | GPS | Mario Faqer Kahore | GADAP | 0.04 | 0 | 0.039 | 0 | 0 | 0.039 | Completed
II | GPS | Jalab Goth | GADAP | 0.15 | 0 | 0.149 | 0 | 0 | 0.149 | Completed
III | GPS | Abdullah Hakeem Kathore | GADAP | 0.04 | 0 | 0.082 | 0 | 0 | 0.082 | Completed
|  |  |  | 0.23 | 0 | 0.27 | 0 | 0 | 0.27
5 | UP-GRADATION OF PRIMARY SCHOOL
TO MIDDLE SCHOOL (1991-92 PROGRAMME)
I | GBPS | 5/G-1, New Karachi | New Karachi | 1.805 | 0 | 1.956 | 0 | 0 | 1.956 | Completed
II | GBPS | 5/E-2, New Karachi | New Karachi | 1.827 | 0 | 0.934 | 0 | 0 | 0.934 | Completed
III | GBPS | 5/D-1, New Karachi | New Karachi | 1.685 | 0 | 1.268 | 0 | 0 | 1.268 | Completed
|  |  |  | 5.317 | 0 | 4.158 | 0 | 0 | 4.158
| GRAND TOTAL ABANDONED SCHEMES |  |  | 8.049 | 0 | 7.023 | 0 | 0 | 7.023
1- GADAP
2- GULBERG
3- GULSHAN
4- LIAQUATABAD
5- NEW KARACHI
6- NORTH NAZIMABAD
P.Programme
P.Programme
P.Programme

## Modified August M.P-ADP (hidden)
MONTHLY PROGRESS REPORT IN RESPECT OF A.D.P. SCHEMES 2003-04
EDUCATION WORKS - II (WORKS & SERVICES DEPARTMENT) CITY DISTRICT GOVERNMENT KARACHI
FOR THE MONTH OF AUGUST- 2004:
Rs. In Million
[5 empty] | Town | Approved Cost | Allocation | E X P E N D I T U R E |  |  |  | Physical | Actual
Sr. No: | ADP # | ADP # | Category | Name of Scheme/ |  |  | 2003-04 | Upto | During the | During the | Total Science | Progress | Date of
| 2003-04 | 2004-05 |  | Project / Location |  |  |  | 6-2004. | Month | Year | commence | Remarks | Completion
2004-05
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
|  | A | MIDDLE SCHOOL
ELEMENTARY EDUCATION
CONSTRUCTION OF BUILDING FOR SHELTERLESS
1 | 56 | 64 | EXISTING PRIMARY SCHOOL IN R/AREA (2000-01) (2 units) |  |  |  | 0
1 |  |  | ** | Haji Waryal Bandijo | Gadap | 0.895 | 0 | 0.643 | 0 | 0 | 0.643 | Colouring in Progress
2 |  |  | GBPS | Main Wasyo Kanroo | Gadap | 0.895 | 0 | 0.924 | 0 | 0 | 0.924 | Completed
3 |  |  | GBPS | Qasim Gabol S / Highway | Gadap | 0.895 | 0 | 0.942 | 0 | 0 | 0.942 | Completed & Handed over
4 |  |  | GBPS | Konkar | Gadap | 0.895 | 0 | 0.9 | 0 | 0 | 0.9 | Completed
5 |  |  | GBPS | Haji Umaid Ali Gabol | Gadap | 0.895 | 0 | 0.803 | 0 | 0 | 0.803 | Completed & Handed over
6 |  |  | GBPS | Islamia Konkar | Gadap | 0.895 | 0 | 0.881 | 0 | 0 | 0.881 | Completed & Handed over
7 |  |  | GBPS | Faiz Muhammad Gabol | Gadap | 0.895 | 0 | 0.583 | 0 | 0 | 0.583 | Completed & Handed over
8 |  |  | GBPS | Kamal Burro | Gadap | 0.895 | 0 | 0.511 | 0 | 0 | 0.511 | Finishing in Progress
9 |  |  | GBPS | Haji Sher Muhammad Bandijo (Moidan) | Gadap | 0.895 | 0 | 0.788 | 0 | 0 | 0.788 | Colouring in Progress
10 |  |  | GBPS | Thohar Kana Moidan | Gadap | 0.895 | 0 | 1.109 | 0 | 0 | 1.109 | Completed
11 |  |  | GBPS | Ali Muhammad Chutto | Gadap | 0.895 | 0 | 0.191 | 0 | 0 | 0.191 | Roof Level
12 |  |  | GBPS | Haji Hamal Balouch | Gadap | 0.895 | 0 | 0.923 | 0 | 0 | 0.923 | colouring stage
13 |  |  | GBPS | Meehan Chutto | Gadap | 0.895 | 0 | 0.938 | 0 | 0 | 0.938 | Completed
14 |  |  | GBPS | Photo Gabol Kathore | Gadap | 0.895 | 0 | 0.975 | 0 | 0 | 0.975 | Colouring in Progress
15 |  |  | GBPS | Bapera Mohalla Memon.Gadap | Gadap | 0.895 | 0 | 1.076 | 0 | 0 | 1.076 | Completed & Handed over
16 |  |  | GGMOHS | Kamal Bari Dumba Goth | Gadap | 0.895 | 0 | 0.522 | 0 | 0 | 0.522 | Completed & Handed over
17 |  |  | GGMOHS | Mazar Khan Jokhio | Gadap | 0.895 | 0 | 1.072 | 0 | 0 | 1.072 | Completed & Handed over
18 |  |  | GBPS | Soofan Jokhio | Gadap | 0.895 | 0 | 0.877 | 0 | 0 | 0.877 | Completed & Handed over
19 |  |  | GBPS | Nabi Bux Gabol (Gadap) | Gadap | 0.895 | 0 | 0.674 | 0 | 0 | 0.674 | Completed & Handed over
20 |  |  | GBPS | Ali Muhammad Gounder | Gadap | 0.895 | 0 | 0.983 | 0 | 0 | 0.983 | Completed
21 |  |  | GBPS | Ali Dad Gabol | Gadap | 0.895 | 0 | 0.796 | 0 | 0 | 0.796 | Completed & Handed over
22 |  |  | GBPS | Darya Khan Gabol | Gadap | 0.895 | 0 | 0.82 | 0 | 0 | 0.82 | Completed & Handed over
23 |  |  | GBPS | Bakhrani Mohalla | Gadap | 0.895 | 0 | 0.959 | 0 | 0 | 0.959 | Completed & Handed over
24 |  |  | GBPS | Khan Muhammad Jokhio | Gadap | 0.895 | 0 | 0.906 | 0 | 0 | 0.906 | Completed & Handed over
25 |  |  | GBPS | Lal Bux Kachelo | Gadap | 0.895 | 0 | 0.909 | 0 | 0 | 0.909 | Completed & Handed over
26 |  |  | GBPS | Hayat Goundar | Gadap | 0.895 | 0 | 0.933 | 0 | 0 | 0.933 | completed
27 |  |  | GBPS | Siraj Ahmed Kathore | Gadap | 0.895 | 0 | 0.756 | 0 | 0 | 0.756 | Finishing in Progress
28 |  |  | GBPS | Muhammadi Goth Mangopir | Gadap | 0.895 | 0 | 1.565 | 0 | 0 | 1.565 | Completed & Handed over
29 |  |  | GBPMS | Abdul Ghaffar Burfat Songal | Gadap | 0.895 | 0 | 0.906 | 0 | 0 | 0.906 | Completed & Handed over
30 |  |  | GBPS | Qadir Bux Jokhio | Gadap | 0.895 | 0 | 0.947 | 0 | 0 | 0.947 | Completed & Handed over
|  |  |  | Total |  | 26.85 | 0 | 25.812 | 0 | 0 | 25.812
CONSTT: OF BUILDING FOR EXISTING SHELTERLESS
2 | 57 | 65 | PRIMARY SCHOOL IN U/AREA KARACHI (2000-01) (5 ROOM) |  |  |  | 0
1 |  |  | GBPS | Full Bright B-16, Sohrab Goth F.B.Area | Gulberg | 1.917 | 0 | 1.8 | 0 | 0 | 1.8 | Completed & Handedover
2 |  |  | GBPS | Godra Muslim Anjumn 11/F New Karachi | New Karachi | 1.917 | 0 | 1.779 | 0 | 0 | 1.779 | Completed & Handedover
3 |  |  | GBPS | 15/ B Buffarzone North Karachi | North Naz'd | 1.917 | 0 | 1.742 | 0 | 0 | 1.742 | Completed & Handedover
4 |  |  | GBMSQS | Rehamani Sector No:4 North Karachi | New Karachi | 1.917 | 0 | 2.074 | 0 | 0 | 2.074 | Completed & Handedover
5 |  |  | GBMSQS | Siddique Sector 5/G New Karachi | New Karachi | 1.917 | 0 | 1.731 | 0 | 0 | 1.731 | Completed & Handedover
6 |  |  | GBMSQS | Siddique Sector 5/D New Karachi. | New Karachi | 1.917 | 0 | 2.172 | 0 | 0 | 2.172 | Completed & Handedover
7 |  |  | GBMSQS | Chishtia Sector 1/A-3, Khuwaja Ajmair | New Karachi | 1.917 | 0 | 1.791 | 0 | 0 | 1.791 | Completed & Handedover
Nagri North Karachi
8 |  |  | GBPS | New Era Dastagir No:9. F.B.Area Kyc: | Gulberg | 1.917 | 0 | 1.95 | 0 | 0 | 1.95 | Completed & Handedover
9 |  |  | GBPS | Sector 7/D-3 North Karachi. | New Karachi | 1.917 | 0 | 1.923 | 0 | 0 | 1.923 | Completed & Handedover
10 |  |  | GBPS | J/M Quba Block-22, Shafique Colony | Gulberg | 1.917 | 0 | 2.257 | 0 | 0 | 2.257 | Completed & Handedover
11 |  |  | GBMSQS | Bilal 5/G New Karachi | New Karachi | 1.917 | 0 | 2.011 | 0 | 0 | 2.011 | Completed
|  |  |  | Total |  | 21.087 | 0 | 21.23 | 0 | 0 | 21.23
|  |  | UP-GRADATION OF PRIMARY TO MIDDLE SCHOOL |  |  |  | 0
3 | 58 | 66 | IN R/AREA KARACHI DIVISION (1990-91)
1 |  |  | GBPS | Chutta Gabol Karachi | Gulberg | 0.966 | 0 | 0.989 | 0 | 0 | 0.989 | Completed & Handedover | 1998-10-03
2 |  |  | GBPS | Haji Dur Muhammad Goth | Gadap | 1.11 | 0 | 1.094 | 0 | 0 | 1.094 | Completed & Handedover
3 |  |  | GBPS | Mazar Khan Jokhio | Gadap | 1.141 | 0 | 1.194 | 0 | 0 | 1.194 | Finishing in Progress (Abondondand Unit)
4 |  |  | GBPS | Murrad Memon Goth | Gadap | 1.361 | 0 | 1.096 | 0 | 0 | 1.096 | Completed & Handedover
5 |  |  | GBPS | Hashim Gabol Goth | Gadap | 1.11 | 0 | 1.409 | 0 | 0 | 1.409 | Finishing in Progress
6 |  |  | GGPS | Ali Muhammad Goth | Gadap | 1.11 | 0 | 1.104 | 0 | 0 | 1.104 | Completed & Handedover
7 |  |  | GBPS | Salah Muhammad Jumani | Gadap | 1.476 | 0 | 1.11 | 0 | 0 | 1.11 | Completed & Handedover
8 |  |  | GBPS | Haji Hussain Chohar | Gadap | 1.476 | 0 | 1.46 | 0 | 0 | 1.46 | Completed & Handedover
9 |  |  | GGPS | Haji Sheedi Village | Gadap | 1.11 | 0 | 1.103 | 0 | 0 | 1.103 | Completed & Handedover
10 |  |  | GGPS | Gadap Village | Gadap | 1.472 | 0 | 1.408 | 0 | 0 | 1.408 | Completed
11 |  |  | GGPS | Pahalwan Goth | Gadap | 1.11 | 0 | 1.11 | 0 | 0 | 1.11 | Completed & Handedover
12 |  |  | GPS | Sheedo Zakria | Gadap | 1.446 | 0 | 1.552 | 0 | 0 | 1.552 | Completed & Handedover
13 |  |  | GBPS | KDA Filter Hashim Khashkhali | Gadap | 1.11 | 0 | 1.098 | 0 | 0 | 1.098 | Completed & Handedover
14 |  |  | GBPS | Hakoo Khan Brohi. | Gadap | 1.11 | 0 | 1.075 | 0 | 0 | 1.075 | Completed & Handedover
15 |  |  | GBPS | Bachal Goth | Gadap | 1.11 | 0 | 1.049 | 0 | 0 | 1.049 | Completed & Handedover
16 |  |  | GGPS | Yar Muhammad Jokhio | Gulshan-Iqbal | 0.966 | 0 | 1.127 | 0 | 0 | 1.127 | Completed & Handedover
|  |  |  | Total |  | 19.184 | 0 | 18.978 | 0 | 0 | 18.978
UP-GRADATION OF PRIMARY TO MIDDLE
4 | 59 | 67 | SCHOOL IN R/AREA (1991-92 Programme) |  |  |  | 0
1 |  |  | GBPS | Binjo Jokhio | Gadap | 1.633 | 0 | 1.533 | 0 | 0 | 1.533 | Completed & Handedover
2 |  |  | GGPS | Kamal Khan Jokhio | Gadap | 2.2 | 0 | 2.953 | 0 | 0 | 2.953 | Finishing in Progress
|  |  |  | Total |  | 3.833 | 0 | 4.486 | 0 | 0 | 4.486
|  |  | CONSTT: / RECONSTRUCTION OF BUILDING FOR |  |  |  | 0
5 | 60 | 68 | EXISTING MIDDLE SCHOOL IN KARACHI (90-91 PROG) | [8 empty] | (Under litegaton) Lying Abandoned
|  |  | GBLSS | Zia-Ul-Uloom Firdous Colony Karachi | Liaquatabad | 1.296 |  | 0.727 | 0 | 0 | 0.727 | at roof level (PC1, revied )
|  |  |  | Total |  | 1.296 | 0 | 0.727 | 0 | 0 | 0.727
|  |  | CONSOLIDATION / IMPROVEMENT OF BUILDING |  |  |  | 0
6 | 62 | 70 | IN EXISTING MIDDLE SCHOOL (2000-01 PROG)
1 |  |  | GGLSS | Konkar | Gadap | 2.608 | 0 | 1.952 | 0 | 0 | 1.952 | Finishing in Progress
2 |  |  | GBLSS | Khamiso Jokhio | Gadap | 2.608 | 0 | 2.952 | 0 | 0 | 2.952 | Completed & Handedover
3 |  |  | GGLSS | Soomar Kandani | Gadap | 2.608 | 0 | 2.102 | 0 | 0 | 2.102 | Completed & Handedover
4 |  |  | GGLSS | Radho Jokhio | Gadap | 2.608 | 0 | 2.43 | 0 | 0 | 2.43 | Completed & Handedover
5 |  |  | GBLSS | Atta Truk F.B.Area Liaquatabad | Gulberg | 2.608 | 0 | 2.454 | 0 | 0 | 2.454 | Colouring in Progress
6 |  |  | GBLSS | Brighter Grammaer North Nazimabad | N'Nazimabad | 2.608 | 0 | 2.387 | 0 | 0 | 2.387 | Completed & Handedover
7 |  |  | GBLSS | Farzana 5/D New Karachi@5/A-3 N/Kyc: | N/Karachi | 2.608 | 0 | 2.546 | 0 | 0 | 2.546 | Completed & Handedover
8 |  |  | GBLSS | Little Angle 11/E UP Society Karachi | N/Karachi | 2.608 | 0 | 2.388 | 0 | 0 | 2.388 | Completed & Handedover
9 |  |  | GBLSS | My Ideal North Nazimabad Karachi | N'Nazimabad | 2.608 | 0 | 2.489 | 0 | 0 | 2.489 | Completed & Handedover
|  |  |  | Total |  | 23.472 | 0 | 21.7 | 0 | 0 | 21.7
UP-GRADATION OF PRIMARY TO MIDDLE SCHOOL
7 | 63 | 71 | IN KARACHI CITY (8 Units) (2001-02 Programme) |  |  |  | 0
1 |  |  | GBPS | Moosa Colony No: 1 Karachi | Gulberg | 2.296 | 0 | 0 | 0 | 0 | 0 | Plot not yet received
2 |  |  | GGPS | Sector 5/G-2 New Karcahi | New Karachi | 2.296 | 0 | 2.099 | 0 | 0 | 2.099 | completed
3 |  |  | GGPS | Anjuman-e-Tarraqui | Gulshan' Iqbal | 2.296 | 0 | 2.301 | 0 | 0 | 2.301 | Main Building Completed & Ext: Deve: in Progress
|  |  |  | Total |  | 6.888 | 0 | 4.4 | 0 | 0 | 4.4
|  |  | UP-GRADATION OF PRIMARY TO MIDDLE |  |  |  | 0
8 | 64 | 72 | SCHOOL IN SINDH ( 2001-02 PROGRAMME)
1 |  |  | GBPS | Bhai Khan Goth Gadap | Gadap | 1.05 | 0 | 1.102 | 0 | 0 | 1.102 | Colouring in Progress
2 |  |  | GGPS | Community Centre Surjani Town Siddique Goth Karachi | Gadap | 1.05 | 0 | 0.836 | 0 | 0 | 0.836 | Plastering in Progress
3 |  |  | GBPS | Abdullah Palari Goth Zero Mall SuperHigh Way Karachi | Gulshan' Iqbal | 1.05 | 0 | 0.788 | 0 | 0 | 0.788 | Plastering in Progress
4 |  |  | GBPS | Sohrab Goth F.B.Area Block # 22 Kyc | Gulberg | 1.05 | 0 | 0.46 | 0 | 0 | 0.46 | Upto Lintel Level
5 |  |  | GBPS | Sector-2 New Karachi Town | N/Karachi | 1.05 | 0 | 1.117 | 0 | 0 | 1.117 | Finishing in Progress
6 |  |  | GGPS | Sector 11-J New Karachi Town | N/Karachi | 1.05 | 0 | 1.069 | 0 | 0 | 1.069 | Finishing in Progress
7 |  |  | GBPS | Block " Q " North Nazimabad Karachi | N'Nazimabad | 1.05 | 0 | 0.978 | 0 | 0 | 0.978 | Plastering in Progress
|  |  |  | Total |  | 7.35 | 0 | 6.35 | 0 | 0 | 6.35
|  |  | CONSTRUCTION OF BUILDING FOR EXISTING |  |  |  | 0
9 | 65 | 73 | PRIMARY SCHOOL IN SINDH (2001-02 PROG)
1 |  |  | GBPS | Murad Memon (Malir) GADAP Town | Gadap | 0.528 | 0 | 0.574 | 0 | 0 | 0.574 | Colouring in Progress
2 |  |  | GBPS | Manghopir GADAP Town | Gadap | 0.528 | 0 | 0.54 | 0 | 0 | 0.54 | Finishing in Progress
3 |  |  | GBPS | Babul Islam Gadap Town | Gadap | 0.528 | 0 | 0.219 | 0 | 0 | 0.219 | Roofing in Progress
4 |  |  | GBPS | J/M Khawaja 5/B New Karachi | N/Karachi | 1.312 | 0 | 1.169 | 0 | 0 | 1.169 | Finishing in Progress
5 |  |  | GBPS | J/M Khamisoo Goth 5/F New Karachi | N/Karachi | 1.312 | 0 | 1.191 | 0 | 0 | 1.191 | Finishing in Progress
6 |  |  | *** | Sector 11/D-2, No: 2 New Karachi | N/Karachi | 1.312 | 0 | 1.226 | 0 | 0 | 1.226 | Finishing in Progress
7 |  |  | GGPS | Gujjan Village | Gadap | 0.528 | 0 | 0.29 | 0 | 0 | 0.29 | Colouring in Progress
8 |  |  | GBPS | Hashim Gabol | Gadap | 0.528 | 0 | 0.35 | 0 | 0 | 0.35 | Finishing in Progress
9 |  |  | GBPS | Yousaf Goth | Gadap | 0.528 | 0 | 0.543 | 0 | 0 | 0.543 | Plastering in progress
10 |  |  | GBPS | Ayoub Goth | Gadap | 0.528 | 0 | 0.566 | 0 | 0 | 0.566 | Finishing in Progress
11 |  |  | GBPS | 7 Star Colony Gadap Town Karachi | Gadap | 0.528 | 0 | 0.132 | 0 | 0 | 0.132 | Plastering in progress
|  |  |  | Total |  | 8.16 | 0 | 6.8 | 0 | 0 | 6.8
|  |  | UP-GRADATION OF PRIMARY TO MIDDLE SCHOOL |  |  |  | 0
10 | 69 | 77 | IN URBAN AREA KARACHI 1987-88
1 |  |  | GBPS | Sector 5/C-2, North Karachi | New Karachi | 3.562 | 0 | 2.613 | 0 | 0 | 2.613 | Completed
2 |  |  | GBPS | 5/B-2, North Karachi. | New Karachi | 3.562 | 0 | 3.706 | 0 | 0 | 3.706 | Completed & Handed Over
3 |  |  | GBPS | Allama Iqbal Bl-16,F.B.Area | Gulberg | 3.562 | 0 | 3.976 | 0 | 0 | 3.976 | Completed & Handed Over
4 |  |  | GGPS | Kamyab Block # 15, F.B.Area | Gulberg | 3.562 | 0 | 3.422 | 0 | 0 | 3.422 | Completed & Handed Over
5 |  |  | GBPS | Liaquatabad No 4 Karachi. | Gulberg | 3.562 | 0 | 4.036 | 0 | 0 | 4.036 | Completed
6 |  |  | B & G | Govt. School Ghosia Colony Jamshad | Gulshan' Iqbal | 3.562 | 0 | 3.616 | 0 | 0 | 3.616 | Finishing in Progress
Road Karachi.
|  |  |  | Total |  | 21.372 | 0 | 21.369 | 0 | 0 | 21.369
|  |  | OPENING OF (5) ROOMED PRIMARY SCHOOL |  |  |  | 0
11 | 71 | 79 | AT Khuda Ki Basti |  | GADAP | 3.37 | 0 | 3.007 | 0 | 0 | 3.007 | Colouring in Progress
UP-GRADATION OF MIDDLE TO HIGH SCHOOL
12 | 72 | 80 | AT KARACHI DISTRICT (10 Units) |  |  |  | 0
1 |  |  |  | Haji Ramzan Gabol Goth Karachi | Gulshan' Iqbal | 4.868 | 0 | 1.229 | 0 | 0 | 1.229 | Plinth completed
2 |  |  | GGLSS | Surjani Town Karachi | Gadap | 4.868 | 0 | 0.673 | 0 | 0 | 0.673 | Footing in Progress
3 |  |  | GBLSS | Ibrahim Ali Bhai Block "I" N-Nazimabad | North Naz'd | 4.868 | 0 | 0 | 0 | 0 | 0 | Plinth in Progress
4 |  |  | GBLSS | Sector-2, North Karachi | New Karachi | 4.868 | 0 | 0.598 | 0 | 0 | 0.598 | Upto Lintel Level
5 |  |  | CDGK | Choudary Rehmat Illahi School | North Naz'd | 4.868 | 0 | 0 | 0 | 0 | 0 | Tender Under Process
|  |  |  | Total |  | 24.34 | 0 | 2.5 | 0 | 0 | 2.5
ADDITION OF CLASS ROOM IN EXISTING
13 | 73 | 81 | ELEMENTARY SCHOOL (40 Units) |  |  |  | 0
1 |  |  | GGPS | Enclish Islamia Nazimabad No:2 (4 C/R) | Liaquatabad | 1.766 | 0 | 0.2 | 0 | 0 | 0.2 | Upto Lintel Level
2 |  |  | GGPS | APWA Gulbahar No: 2 Karachi ( 8 C/R) | Liaquatabad | 3.532 | 0 | 0 | 0 | 0 | 0 | Dismentling Work of Existing old Building in Progress
3 |  |  | GBPS | D.B Advani (Sachal Goth) (2 C/Room) | Gulshan' Iqbal | 0.883 | 0 | 0.204 | 0 | 0 | 0.204 | Tender Under Process
4 |  |  | GBPS | Sher Muhammad Goth (3 C/Room) | Gulshan' Iqbal | 1.3245 | 0 | 0 | 0 | 0 | 0 | Tender Under Process
5 |  |  | GBPS | Bhittaiabad Karachi (3 C/Room) | Gulshan' Iqbal | 1.3245 | 0 | 0.371 | 0 | 0 | 0.371 | Tender Under Process
6 |  |  | GBPS | Ayoob Goth (1 Classroom) | Gulshan' Iqbal | 0.442 | 0 | 0 | 0 | 0 | 0 | Tender Under Process
|  |  |  | Total |  | 9.272 | 0 | 0.775 | 0 | 0 | 0.775
CONSTRUCTION / RE-CONSTRUCTION OF
14 | 74 | 82 | EXISTING MIDDLE SCHOOL (10 UNITS) |  |  |  | 0
1 |  |  | GBSS | Memon Goth Gadap | Gadap | 4.313 |  | 0.564 | 0 | 0 | 0.564 | Footing in Progress
2 |  |  | GGLSS | Rehri at Memon Goth Gadap | Gadap | 4.313 |  | 0.881 | 0 | 0 | 0.881 | Footing in Progress
3 |  |  | GGLSS | Sector 5/G Dhobi Ghat New Karachi | New Karachi | 4.313 |  | 1.006 | 0 | 0 | 1.006 | Upto Plinth Level
4 |  |  | GBMS | Peoples Own 11/F New Karachi | New Karachi | 4.313 |  | 0.025 | 0 | 0 | 0.025 | Dismentling Work of Existing old Building in Progress
5 |  |  | GBMS | Standared 5/D New Karachi | New Karachi | 4.313 |  | 0.024 | 0 | 0 | 0.024 | Dismentling Work of Existing old Building in Progress
|  |  |  | Total |  | 21.565 | 0 | 2.5 | 0 | 0 | 2.5
UP-GRADATION OF PRIMARY TO MIDDLE
15 | 75 | 83 | SCHOOL (18 Units)
1 |  |  | GGPS | APWA Gulbahar Liaquatabad Kyc | Liaquatabad | 4.637 | 0 | 0 | 0 | 0 | 0 | Dismentling Work of Existing old Building in Progress
2 |  |  | Major Khalid Sultan Primary School North Nazimabad |  | North Naz'd | 4.637 |  | 0 | 0 | 0 | 0 | Tender Under Process
3 |  |  | GBPS | Al-Noor Block-19 F.B.Area Karachi | Gulberg | 4.637 |  | 0.251 | 0 | 0 | 0.251 | Plinth in Progress
4 |  |  | GGPS | Madhoo Goth Gulshan-e-Iqal | Gulshan' Iqbal | 4.637 |  | 0.25 | 0 | 0 | 0.25 | Plinth in Progress
5 |  |  | GGPS | Mughal Hazara Goth Gulshan'Iqbal | Gulshan' Iqbal | 4.637 |  | 0.049 | 0 | 0 | 0.049 | Plinth in Progress
6 |  |  | GGPS | Model Community UC-7, Gadap | Gadap | 4.637 |  | 0.25 | 0 | 0 | 0.25 | Footing in progress
|  |  |  | Total |  | 27.822 | 0 | 0.8 | 0 | 0 | 0.8
CONSTRUCTION OF BUILDING FOR SHELTER
16 | 76 | 84 | LESS PRIMARY SCHOOL (20 UNITS) (2003-04) |  |  |  | 0 |  |  |  |  | Location not yet justified
1 |  |  | GBPS | Siddiqu-e-Akber-III 5/E North Karachi | New Karachi | 3.261 |  | 0 | 0 | 0 | 0
2 |  |  | GBPS | Raza Muhammad Brohi Goth | Gadap | 3.261 |  | 0 | 0 | 0 | 0
3 |  |  | GBLSS | Seta Nagar Gulshan-e-Iqbal | Gulshan' Iqbal | 3.261 |  | 0 | 0 | 0 | 0
4 |  |  | GGPS | Old Subzi Mandi | Gulshan' Iqbal | 3.261 |  | 0 | 0 | 0 | 0
5 |  |  | GBPS | Haji Bethai Goth Sector 7/A Sujani Town | Gadap | 3.261 |  | 0 | 0 | 0 | 0
6 |  |  | GBPS | Saif-ul-Marri Goth Sector 8 Sujani Tonw | Gadap | 3.261 |  | 0 | 0 | 0 | 0
7 |  |  |  | Sector 11/D-2, North Karachi | New Karachi | 3.261 |  | 0 | 0 | 0 | 0
8 |  |  | GBPS | J.M Kakki Sector 5/C North Karachi | New Karachi | 3.261 |  | 0 | 0 | 0 | 0
|  |  |  | Total |  | 26.088 | 0 | 0 | 0 | 0 | 0
CONSTRUCTION OF THREE PRIMARY SCHOOL
17 | 77 | 85 | IN KARACHI DIVISION
1 |  |  | GGPS | Surjani Town Gadap | Gadap | 3.206 | 0 | 0.6 | 0 | 0 | 0.6 | Footing in Progress
|  |  |  | Total |  | 3.206 | 0 | 0.6 | 0 | 0 | 0.6
|  |  | ADDITION / IMPROVEMENT OF GOVERNMENT |  | Liaquatabad | 2.782 | 0 | 1.89 | 0 | 0 | 1.89 | 1) Original work: Roof Laid
18 | 131 | 92 | BOYS / GIRLS PRIMARY SCHOOL (Atta Turk) | [8 empty] | 2) Repair work Finishing in Progress
|  |  | F.C. Area Karachi (Abandoned Unit) |  |  | 2.782 | 0 | 1.89 | 0 | 0 | 1.89
|  |  |  | Total Elementary Education |  | 255.155 | 0 | 142.034 | 0 | 0 | 142.034
|  |  |  | Total Middle School Project |  | 0 | 0 | #REF! | 0 | 0 | #REF!
|  |  |  | Sub-Total ( Elementary Education) " A " |  | 255.155 | 0 | #REF! | 0 | 0 | #REF!
|  | B | SECONDARY EDUCATION
|  |  | UP-GRADATION OF MIDDLE SCHOOLTO HIGH |  |  |  | 0
19 | 78 | 95 | SCHOOL IN SINDH R/AREA (1992-93 Prog:)
1 |  |  | GBLSS | Darsano Channo | Gadap | 1.604 | 0 | 1.81 | 0 | 0 | 1.81 | Colouring in Progress
|  |  |  | Total |  | 1.604 | 0 | 1.81 | 0 | 0 | 1.81
OPENING OF DOUBLE SECTION HIGH SCHOOL
20 | 80 | 97 | IN SINDH KARACHI DIVISION (1991-92) |  |  |  | 0
1 |  |  | Sector | 5/A North Karachi. | New Karachi | 6.342 | 0 | 5.983 | 0 | 0 | 5.983 | Completed & Handed Over | 1999-12-18
2 |  |  | Sector | 11/B North Karachi. | New Karachi | 6.342 | 0 | 10.44 | 0 | 0 | 10.44 | Completed & Handed Over | **
3 |  |  | GGHS | Mulla Essa Goth Shifted to Landhi # 2 | Gadap | 6.342 | 0 | 9.868 | 0 | 0 | 9.868 | M/Building Completed to ready Handed Over & Auditorium Colouring in Progress | 01/06/2001.
|  |  |  | Total |  | 19.026 | 0 | 26.291 | 0 | 0 | 26.291
UP-GRADATION OF MIDDLE SCHOOLTO HIGH
21 | 81 | 98 | R/AREA OF KARACHI ( 1990-91 PROGRAMME) |  |  |  | 0
|  |  | GBLSS | District Council 11/D New Karachi | New Karachi | 1.607 |  | 2.328 | 0 | 0 | 2.328 | Completed & Handed Over
|  |  | GBLSS | Sector 11/E UP Society New Karachi | New Karachi | 1.607 |  | 2.333 | 0 | 0 | 2.333 | Completed & Handed Over
[6 empty] | 3.214 | 0 | 4.661 | 0 | 0 | 4.661
UP-GRADATION OF MIDDLE SCHOOL
22 | 83 | 99 | TO HIGH SCHOOL(1991-92) |  |  |  | 0
1 |  |  | GGPS | Wazir Jehan Karachi. | Gulberg | 3.278 | 0 | 3.685 | 0 | 0 | 3.685 | Completed & Handed Over
2 |  |  | GBLSS | Major Zia Uddin Memorial | Liaquatabad | 3.278 | 0 | 3.539 | 0 | 0 | 3.539 | Completed & Handed Over
3 |  |  | GBLSS | Lemoo Gabol Gulshan-e-Iqbal | Gulshan'Iqbal | 4.825 | 0 | 4.76 | 0 | 0 | 4.76 | Completed & Handed Over
|  |  |  | Total |  | 11.381 | 0 | 11.984 | 0 | 0 | 11.984
|  |  | INTRODUCTION / ADD: OF XI-XII CLASSES IN EXISTING |  |  |  | 0
23 | 86 | 101 | HIGH SECONDARY SCHOOL IN SINDH ( 1991-92)
1 |  |  | GGSS | Liaquatabad No:4, | Liaquatabad | 5.995 | 0 | 6.655 | 0 | 0 | 6.655 | G/Floor Completed & Handedover & F/Floor Roof laid
2 |  |  | GBSS | Liaquatabad No:4, | Liaquatabad | 6.601 | 0 | 1.371 | 0 | 0 | 1.371 | First Floor Super Structrure completed
3 |  |  | GGSS | Ishat-ul-Quran Nazimabad Karachi | North Naz'd | 6.289 | 0 | 2.937 | 0 | 0 | 2.937 | (PC-1 Revised ) AA awaited.
|  |  |  | Total |  | 18.885 | 0 | 10.963 | 0 | 0 | 10.963
ADDITION C/R IN EXISTING
24 | 87 | 102 | HIGH SCHOOL IN SINDH(1994-95) |  |  |  | 0
1 |  |  | GGSS | Dastagir No:9 Federal "B" area (4 C/R) | Gulberg | 1.06 | 0 | 1.143 | 0 | 0 | 1.143 | Completed & Handedover
2 |  |  | GHSS | Ibrahim Ali Bhai Federal "B" area (4 C/R) | Gulberg | 1.06 | 0 | 1.114 | 0 | 0 | 1.114 | Completed & Handedover
3 |  |  | GBSS | Sitar-e-Hydri 11/D North Karachi ( 2C/R ) | New Karachi | 0.53 | 0 | 0.537 | 0 | 0 | 0.537 | Completed & Handedover | 2005-08-04
4 |  |  | GGSS | Allama Iqbal Bl # 16 F.B.Area Kyc (2 C/R) | Gulberg | 0.53 | 0 | 0.483 | 0 | 0 | 0.483 | Completed & Handedover | 2004-07-26
5 |  |  | GBSS | Murrad Memon ( 4 Classroom) | Gadap | 0.919 | 0 | 1.325 | 0 | 0 | 1.325 | Completed & Handedover
6 |  |  | GGMS | Dumba Goth ( 2 C/Room) | Gadap | 0.46 | 0 | 0.47 | 0 | 0 | 0.47 | Completed & Handedover
|  |  |  | Total |  | 4.559 | 0 | 5.072 | 0 | 0 | 5.072
|  |  | ESTABLISHMENT OF SINGLE SECTION |  |  |  | 0
25 | 88 | 103 | SECTION HIGH SCHOOL
1 |  |  | @ Yousaf Goth union Council Mangopir Karachi |  | Gadap | 5.431 | 0 | 4.557 | 0 | 0 | 4.557 | Completed & Handedover
2 |  |  | @ Angaroo Goth |  | Gadap | 5.431 | 0 | 4.462 | 0 | 0 | 4.462 | Completed & Handedover
|  |  |  | Total |  | 10.862 | 0 | 9.019 | 0 | 0 | 9.019
ESTABLISHMENT OF DOUBLE SECTION HIGH
26 | 93 | 107 | SCHOOL FOR BOYS/ GIRLS KARACHI CITY
|  |  | North Nazimabad |  | N'Nazimabad | 13.858 | 0 | 7.399 | 0 | 0 | 7.399 | Cement plaster, Tiles Flooring in Progress
|  |  |  | Total |  | 13.858 | 0 | 7.399 | 0 | 0 | 7.399
OPENING OF DOUBEL SECTION HIGH SCHOOL AT
27 | 94 | 108 | SINGLE SECTION HIGH SCHOOL SACHAL GOTH |  | Gulshan' Iqbal | 11 | 0 | 11.089 | 0 | 0 | 11.089 | Finishing in Progress
|  |  |  | Total |  | 11 | 0 | 11.089 | 0 | 0 | 11.089
CONSTRUCTION / RE-CONSTRUCTION OF
28 | 97 | 110 | BUILDING FOR EXISTING SECONDARY SCHOOL
|  |  | GBSS Nazimabad No:1 Karachi |  | Liaquatabad | 5.881 | 0 | 5.481 | 0 | 0 | 5.481 | Finishing in Progress, Ext: Dev Work completed
|  |  |  | Total |  | 5.881 | 0 | 5.481 | 0 | 0 | 5.481
ESTABLISHMENT OF GOVERNMENT BOYS
29 | 95 | 112 | SECONDARY SCHOOL GULSHAN-E-IQBAL
KARACHI (1991-92 PROGRAMME)
|  |  | GBSS | Gulshan-e-Iqbal (Tameer-e-Watan) | Gulshan'Iqbal | 5.847 | 0 | 2.5 | 0 | 0 | 2.5 | Finishing in Progress
|  |  |  | Total |  | 5.847 | 0 | 2.5 | 0 | 0 | 2.5
CONSTRUCTION / RE-CONSTRUCTION OF BUILDING
30 | 101 | 114 | FOR EXISTING SECONDARY SCHOOL KARACHI
|  |  | DIVISION (1991-92 PROGRAMME) |  |  | 15.297 | 0 | 0 | 0 | 0 | 0 | Location not yet available
|  |  |  | Total |  | 15.297 | 0 | 0 | 0 | 0 | 0
|  |  | INTRODUCTION OF XI & XII CLASSES IN EXISTING |  |  |  | 0
31 | 114 | 117 | SECONDARY SCHOOL IN KARACHI DIVISION
|  |  | GBGSS | Sharafabad Gulshan-e-Iqbal | Gulshan' Iqbal | 9.206 |  | 1.33 | 0 | 0 | 1.33 | Upto Plinth Level
|  |  |  | Total |  | 9.206 | 0 | 1.33 | 0 | 0 | 1.33
CONSTRUCTION / RE-CONSTRUCTION OF
32 | 115 | 118 | EXISTING SECONDARY SCHOOL IN KARACHI |  |  |  | 0
|  |  | GGPS | APWA Gulbahar Laiquatabad Kyc | Liaquatabad | 7.84 |  | 0 | 0 | 0 | 0 | Dismentling Work of Existing Old Building in Progress
|  |  | GGSS | Sector 5/G New Karachi | New Karachi | 7.84 |  | 0 | 0 | 0 | 0 | Dismentling Work of Existing Old Building in Progress
|  |  |  | Total |  | 15.68 | 0 | 0 | 0 | 0 | 0
ADDITIION OF CLASSROOMS (4) IN SECONDARY
33 | 116 | 119 | SCHOOL IN U/ AREA OF KARACHI DIVISION
1 |  |  | GBSS | Greenland Nazimabad No:4 Kyc (3 C/R) | Liaquatabad | 1.3245 | 0 | 0.424 | 0 | 0 | 0.424 | First Floor Roof laid
2 |  |  | GGSS | Ibrahim Ali Bhai Block-20 F.B.Area (3 " ) | Gulberg | 1.3245 |  | 0.15 | 0 | 0 | 0.15 | Plinth in Progress
3 |  |  | GGSS | University Campus (11 C/Room) | Gulshan' Iqbal | 4.8565 |  | 0.416 | 0 | 0 | 0.416 | Foundation in Progress
|  |  |  | Total |  | 7.5055 | 0 | 0.99 | 0 | 0 | 0.99
ESTABLISHMENT OF DOUBLE SECTION HIGH
34 | 118 | 121 | SCHOOL IN SINDH ( 3 UNITS) |  |  |  | 0
1 |  |  | at North Karachi (Girls) |  | New Karachi | 9.184 |  | 1.02 | 0 | 0 | 1.02 | Upto Plinth Level
2 |  |  | at GSS Gulistan-e-Jouhar Bock-12 Karach |  | Gulshan' Iqbal | 9.184 |  | 0 | 0 | 0 | 0 | Tender Under Process
|  |  |  | Total |  | 18.368 | 0 | 1.02 | 0 | 0 | 1.02
ESTABLISHMENT OF SINGLE SECTION HIGH
35 | 119 | 122 | SCHOOL KARACHI (5 UNITS) |  |  |  | 0
|  |  | GGPS | Farqulit Nazimabad Karachi | Liaquatabad | 7.456 |  | 0.82 | 0 | 0 | 0.82 | Upto Lintel Level
|  |  | GGPS | Maymarabad Surjani Town | Gadap | 7.456 |  | 1.08 | 0 | 0 | 1.08 | Footing in Progress
|  |  |  | Total |  | 14.912 | 0 | 1.9 | 0 | 0 | 1.9
CONSTT: / RE-CONSTRUCTION OF BUILDING FOR
36 | 120 | 123 | EXISTING HIGH SCHOOL IN KARACHI ( 5 UNITS) |  |  |  | 0
1 |  |  | GBSS | Standered 5/F New Karachi | New Karachi | 10.653 |  | 0.025 | 0 | 0 | 0.025 | Dismentling Work of Existing Old Building in Progress
2 |  |  | GGSS | Nazia Square 5/E New Karachi | New Karachi | 10.653 |  | 2.975 | 0 | 0 | 2.975 | Upto Roof Level
3 |  |  | GGSS | Ibrahim Ali Bhai Block-6, F.B.Area | Gulberg | 10.653 |  | 0 | 0 | 0 | 0 | Tender Under scrutiny
|  |  |  | Total |  | 31.959 | 0 | 3 | 0 | 0 | 3
|  |  | ADDITION OF CLASS ROOM IN EXISTING |  |  |  | 0
37 | 105 | 128 | SECONDARY SCHOOL IN U/AREA KARACHI
1 |  |  | GBSS | Allama Iqbal F.B.Area ( 4 Class Rooms) | Gulberg | 1.16 | 0 | 0.869 | 0 | 0 | 0.869 | Completed & Handed over
2 |  |  | GBSS | New Method F.B.Area ( 4 Class Rooms) | Gulberg | 1.16 | 0 | 0.969 | 0 | 0 | 0.969 | Completed
3 |  |  | GBSS | Anglo Oriential Block-15,F.B.Area (5 C/R) | Gulberg | 1.45 | 0 | 1.514 | 0 | 0 | 1.514 | Completed & Handed over
4 |  |  | GGSS | Hyderi North Karachi (5 Class/Room ) | New Karachi | 1.45 | 0 | 1.626 | 0 | 0 | 1.626 | Completed & Handed over
5 |  |  | GBSS | 5/A-3, New Karachi.(5 Class Room) | New Karachi | 1.45 | 0 | 1.469 | 0 | 0 | 1.469 | Completed & Handed over
6 |  |  | GGSS | Liaquatabad No:4 Karachi.(3 C/ Room) | Liaquatabad | 0.87 | 0 | 0.774 | 0 | 0 | 0.774 | Completed & Handed over
7 |  |  | GBSS | Liaquatbad No:4 Karachi.(4 C/ Rooms ) | Liaquatabad | 1.16 | 0 | 1.099 | 0 | 0 | 1.099 | Completed & Handed over
|  |  |  | Total |  | 8.7 | 0 | 8.32 | 0 | 0 | 8.32
INTRODUCTION OF XI & XII IN CLASSES IN EXISTING
38 | 108 | 131 | (BOYS/GIRLS) SECONDARY SCHOOL IN U/AREA KYC |  |  |  | 0
|  |  | GBSS | APWA 5/E New Karachi. | New Karachi | 7 |  | 8.116 | 0 | 0 | 8.116 | Completed & Handed over
|  |  |  | Total |  | 7 | 0 | 8.116 | 0 | 0 | 8.116
|  |  | INTRODUCTION OF XI & XII CLASSES IN EXISTING |  |  |  | 0
39 | 109 | 132 | SECONDARY SCHOOL IN U/AREA KYC: 1997-98.
|  |  | GBLSS | Gulshan-e-Iqbal Karachi Block # 6 Kyc | Gulshan' Iqbal | 7 |  | 7.75 | 0 | 0 | 7.75 | Completed & Handed over
|  |  |  | Total |  | 7 | 0 | 7.75 | 0 | 0 | 7.75
|  |  |  | Sub-Total ( Secondary Education) " B" |  | 249.0785 | 0 | 140.528 | 0 | 0 | 140.528
C |  |  | TECHNICAL EDUCATION
|  |  | ESTABLISHMENT OF MONO TECHNIC INSTITUTE | [8 empty] | Block-A Finishing in Progress
40 | 122 | 137 | GADAP KARACHI 1994-95 PROGRAMME | [8 empty] | Block-B Finishing in progress
1 |  |  |  | @ Memon Goth. | Gadap | 21.199 | 0 | 20.776 | 0 | 0 | 20.776 | C/Wall completed , W/S & S/F i/c Ext Developmenet
|  |  |  | Total |  | 21.199 | 0 | 20.776 | 0 | 0 | 20.776
ESTABLISHMENT OF MONO TECHNIC INSTITUTE
41 | 125 | 140 | DISTRICT CENTRAL KARACHI @ Sector 5/J NK |  | New Karachi | 9.58 | 0 | 8.916 | 0 | 0 | 8.916 | Completed & Handedover
|  |  |  | Total |  | 9.58 | 0 | 8.916 | 0 | 0 | 8.916
ESTABLISHMENT OF MONOTECHNIC INSTITUTE
42 | 132 | 147 | LIAQUATABAD (Shifted to Gulistan-e-Jouhar) |  | Gulshan' Iqbal | 33.874 | 0 | 13.499 | 0 | 0 | 13.499 | Finishing in Progress
|  |  |  | Total |  | 33.874 | 0 | 13.499 | 0 | 0 | 13.499
|  |  | Establishment of Government Commercial |  |  |  | 0
43 | 216 | 151 | Institute Malir GICE Azizabad Karachi
[5 empty] | Gulberg | 12.432 |  | 0 | 0 | 0 | 0 | Tender under Process
|  |  |  | Total |  | 12.432 | 0 | 0 | 0 | 0 | 0
|  |  | UP-GRADATION OF GOVERNMENT VOCATIONAL |  |  |  | 0
44 | 217 | 152 | SCHOOL (GIRLS) AT KARACHI DIVISION
1 |  |  | at Sachal Balouch Goth |  | Gulshan'Iqbal | 3.94 |  | 1.1 | 0 | 0 | 1.1 | Work Started
2 |  |  | at Buffarzone Karachi. |  | N'Nazimabad | 3.94 |  | 0 | 0 | 0 | 0 | Work Initial Stage
|  |  |  | Total |  | 7.88 | 0 | 1.1 | 0 | 0 | 1.1
ESTABLISHMENT OF MONOTECHIC INSTITUTE
45 | 136 | 159 | AT DISTRICT CENTRAL KARACHI |  |  |  | 0
|  |  | F.B Area Karachi |  | Gulberg | 33.874 | 0 | 16.631 | 0 | 0 | 16.631 | Main Building nearing Completed & Ext: Dev
Work in Progress
|  |  |  | Total |  | 33.874 | 0 | 16.631 | 0 | 0 | 16.631
UP-GRADATION OF SAIFEE EIDEE ZAHABI INSTITUTE
46 | 137 | 160 | OF TECHNOLOGY TO B.TECH LEVEL CLASSES KYC |  |  |  | 0 |  |  |  |  | Phase-I Finishing in Progress
|  |  | North Nazimabad Karachi |  | N' Nazim'd | 11.913 | 0 | 9.894 | 0 | 0 | 9.894 | Phase-II, Finishing in Progress
Phase-III, Finishing in Progress
|  |  |  | Total |  | 11.913 | 0 | 9.894 | 0 | 0 | 9.894
|  |  |  | Total :Technical Education >>>>> |  | 164.626 | 0 | 87.447 | 0 | 0 | 87.447
|  |  |  | TOTAL : Technical Education(ADB) |  | #REF! | 0 | #REF! | 0 | 0 | #REF!
|  |  | Sub Total ( Technical Education ) " C " |  |  | #REF! | 0 | #REF! | 0 | 0 | #REF!
D |  |  | COLLEGE EDUCATION
|  |  | ESTABLISHMENT OF GOVT. GIRLS DEGREE | [8 empty] | Block-A & B Colouring in Progress
47 | 144 | 166 | @ Konkar Village |  | Gadap | 23.601 | 0 | 24.173 | 0 | 0 | 24.173 | Block-C, Colouring in Progress
|  |  |  | Total |  | 23.601 | 0 | 24.173 | 0 | 0 | 24.173 | Block-D, Colouring in Progress
|  |  | ADDITION/ ALTERATION IN APWA GOVT. | [8 empty] | Phase-I, Finishing in Progress
48 | 148 | 170 | COLLEGE FOR WOMEN Federal "B" AREA. |  | Gulberg | 11.564 | 0 | 16.41 | 0 | 0 | 16.41 | Phase-II, Lab 1st Floor Stru: in Progress
|  |  |  | Total |  | 11.564 | 0 | 16.41 | 0 | 0 | 16.41 |  | 2004-11-03
CONSTRUCTION OF GOVERNMENT PREMIER
49 | 149 | 171 | COLLEGE NORTH NAZIMABAED KARACHI |  | N'Nazimbad | 23.106 | 0 | 0.8 | 0 | 0 | 0.8 | Super Structure work in Progress
|  |  |  | Total |  | 23.106 | 0 | 0.8 | 0 | 0 | 0.8 | (PC-1 Revised )
OPENING OF GIRLS DEGREE COLLEGE
50 | 150 | 172 | @ Gulshan-e-Iqbal Karachi (91-92) |  | Gulshan' Iqbal | 25.175 | 0 | 25.396 | 0 | 0 | 25.396 | Completed & Handedover
|  |  |  | Total |  | 25.175 | 0 | 25.396 | 0 | 0 | 25.396
ESTABLISHMENT OF DEGREE BOYS COLLEGE
51 | 151 | 173 | @ Gulzair-e-Hijri, Scheme # 33 Kyc: (91-92) |  | Gulshan' Iqbal | 23.301 | 0 | 23.634 | 0 | 0 | 23.634 | Completed
|  |  |  | Total |  | 23.301 | 0 | 23.634 | 0 | 0 | 23.634
|  |  | ESTABLISHMENT OF GOVT. BOYS DEGREE | [8 empty] | ( Rs. 2.496 M, were consumed for XEN
52 | 156 | 178 | COLLEGE @ Surjani Town Karachi |  | Gadap | 24.105 | 0 | 21.376 | 0 | 0 | 21.376 | (EWD Wet (Defunt) Karachi
|  |  |  | Total |  | 24.105 | 0 | 21.376 | 0 | 0 | 21.376 | Completed & Handedover
ESTABLISHMENT OF GOVT. DEGREE
53 | 157 | 179 | COLLEGE FOR MAN @ Mangopir |  | Gadap | 26.77 | 0 | 23.485 | 0 | 0 | 23.485 | Completed
|  |  |  | Total |  | 26.77 | 0 | 23.485 | 0 | 0 | 23.485
IMPROVEMENT OF GOVERNMENT DEGREE
54 | 168 | 189 | COLLEGE FOR WOMEN
|  |  | Premier College North Nazimabad Karachi |  | N'Nazimabad | 19 | 0 | 12.648 | 0 | 0 | 12.648 | Finishing in Progress
|  |  |  | Total |  | 19 | 0 | 12.648 | 0 | 0 | 12.648
CONSTRUCTION OF COMMERCE BLOCK FOR
55 | 169 | 190 | GOVERNMENT GIRLS COLLEGE NEW KARACHI |  | New Karachi | 9 | 0 | 7.149 | 0 | 0 | 7.149 | Finishing in Progress
|  |  |  | Total |  | 9 | 0 | 7.149 | 0 | 0 | 7.149
ESTABLISHMENT OF GOVERNMENT DEGREE
56 | 170 | 191 | GIRLS COLLEGE NORTH KARACHI
|  |  | Sector 11/B North Karachi |  | New Karachi | 17.347 | 0 | 8.875 | 0 | 0 | 8.875 | G+F/Floor Finishing in Progress
|  |  |  | Total |  | 17.347 | 0 | 8.875 | 0 | 0 | 8.875
CONSTRUCTION / ADDITION OF (2) CLASSROOM
57 | 171 | 192 | AUDITORIUM & COMPUTER LABS: IN GOVT:
|  |  | COLLEGE FOR WOMEN NORTH NAZIMABAD |  | N'Nazimabad | 12.657 | 0 | 9.338 | 0 | 0 | 9.338 | Finishing in Progress
BLOCK "M" KARACHI
|  |  |  | Total |  | 12.657 | 0 | 9.338 | 0 | 0 | 9.338
|  |  | ADDITION BLOCK & IMPROVEMENT OF GOVT: |  |  |  | 0
58 | 185 | 193 | GIRLS COLLEGE F.B.AREA BLOCK # 16 KYC: |  | Gulberg | 26.531 |  | 0 | 0 | 0 | 0 | Plot Not yet received
|  |  |  | Total |  | 26.531 | 0 | 0 | 0 | 0 | 0
ESTABLISHMENT OF GOVERNMENT DEGREE
59 | 186 | 194 | COLLEGE FOR WOMEN AT GULSHAN-E-MAYMAR |  |  |  | 0
|  |  | GADAP TOWN SUPER HIGHWAY KARACHI |  | Gadap | 41.235 |  | 3.5 | 0 | 0 | 3.5 | Footing in Progress
|  |  |  | Total |  | 41.235 | 0 | 3.5 | 0 | 0 | 3.5
|  |  | EXPANSION AND ADDITION IN GOVT RIAZ |  |  |  | 0
60 | 188 | 196 | GIRLS COLLEGE AT LIAQUATABAD KARACHI |  | Liaquatabad | 17.454 |  | 2.7 | 0 | 0 | 2.7 | Block "B" 3rd Floor Roof Laid in Progress
|  |  |  | Total |  | 17.454 | 0 | 2.7 | 0 | 0 | 2.7
|  |  | RE-CONSTRUCTION OF GOVERNMENT DEGREE |  |  |  | 0 |  |  |  |  | Foundation in Progress
61 | 191 | 199 | FOR MEN NAZIMABAD KARACHI |  | Liaquatabad | 37.504 |  | 0.7 | 0 | 0 | 0.7
|  |  |  | Total |  | 37.504 | 0 | 0.7 | 0 | 0 | 0.7
CONSTRUCTION OF AN AUITORIUM, (4) CLASS
62 | 192 | 200 | ROOMS. ( 1 ) COMMONROOM & EXTENSION
IN LIBRARY WITH LAVATORY, GYMNASIUM
|  |  | HALL & SEMINAR ROOM IN ABDULLAH GOVT |  | North Nazim'd |  | 0 |  |  |  |  | Main Building, Auditorium Hall plinth Completed
|  |  | COLLEGE FOR WOMEN NORTH NAZIMABAD |  |  | 35.556 |  | 3.6 | 0 | 0 | 3.6
|  |  |  | Total |  | 35.556 | 0 | 3.6 | 0 | 0 | 3.6
|  |  | ESTABLISHMENT OF GOVERNMENT CITY |  |  |  | 0
63 | 195 | 203 | DEGREE COLLEGE AT SHARIFABAD KARACHI |  | Liaquatabad | 41.235 |  | 0 | 0 | 0 | 0 | Tender Under Process
|  |  |  | Total |  | 41.235 | 0 | 0 | 0 | 0 | 0
|  |  | ESTABLISHMENT OF GOVERNMENT CITY |  |  |  | 0
64 | 197 | 205 | DEGREE COLLEGE AT SUJANI TOWN KARACHI |  | GADAP | 41.235 |  | 4.42 | 0 | 0 | 4.42 | Plinth level Completed.
|  |  |  | Total |  | 41.235 | 0 | 4.42 | 0 | 0 | 4.42
|  |  | ESTABLISHMENT OF GOVERNMENT DEGREE |  |  |  | 0
65 | 199 | 207 | GIRLS COLLEGE SAPHOORA GOTH KARACHI |  | Gulshan'Iqbal | 41.235 |  | 5 | 0 | 0 | 5 | Plinth Completed
|  |  |  | Total |  | 41.235 | 0 | 5 | 0 | 0 | 5
|  |  | ESTABLISHMENT OF GOVERNMENT DEGREE |  |  |  | 0
66 | 200 | 208 | GIRLS COLLEGE AT PLOT # ST-BLOCK "G" |  | North Nazim'd | 41.235 |  | 2 | 0 | 0 | 2 | Foundation in Progress
|  |  |  | Total |  | 41.235 | 0 | 2 | 0 | 0 | 2
ADDITION OF CLASSROOM IN EXISTING
67 | 201 | 209 | COLLEGES OF KARACHI ( 50 UNITS) |  |  |  | 0
1 |  |  | Sir Syed Govt. College for Women Nazimabad (4unit) |  | Liaquatabad | 2.52 |  | 0.158 | 0 | 0 | 0.158 | Roof Shuttering in Progress (First Floor)
2 |  |  | H.I. Usmania Govt. Girls College Nazimabad (4 Units) |  | Liaquatabad | 2.52 |  | 0 | 0 | 0 | 0 | Tender Under Process
3 |  |  | Govt College for Women 11/B North Karach (4 Units) |  | New Karachi | 2.52 |  | 0.542 | 0 | 0 | 0.542 | Upto Plinth Level
4 |  |  | Govt Boys & Girls College Stadium Road (4 Units) |  | Gulshan'Iqbal | 2.52 |  | 0 | 0 | 0 | 0 | Tender Under Process
5 |  |  | Govt. College for Women Block-16 F.B.Area (4 Unit) |  | Gulberg | 2.52 |  | 0 | 0 | 0 | 0 | Tender Under Process
6 |  |  | Govt Degree College for BOYS Buffarzone (4 Units) |  | North Nazim'd | 2.52 |  | 0.1 | 0 | 0 | 0.1 | Foundation in Progress
|  |  |  | Total |  | 15.12 | 0 | 0.8 | 0 | 0 | 0.8
CONSTRUCTION OF GOVT. DEGREE BOYS
68 | 202 | 210 | COLLEGE SCHEME # 33, UC-13, SUPER HIGHWAY |  | Gulshan'Iqbal |  | 0
|  |  | GULSHAN-E-IQBAL KARACHI |  |  | 41.389 |  | 3.5 | 0 | 0 | 3.5 | Upto Plinth Level
|  |  |  | Total |  | 41.389 | 0 | 3.5 | 0 | 0 | 3.5
|  |  | IMPROVEMENT / ALTERATION OF STAFF RESIDENCE |  |  |  | 0
69 | 205 | 213 | OF RANA LIAQUAT ALI KHAN GOVERNMENT |  | Gulshan'Iqbal | 0.975 | 0 | 5.47 | 0 | 0 | 5.47 | Finishing in Progress
|  |  | COLLEGE OF HOME ECONOMIC KARACHI |  |  | 0.975 | 0 | 5.47 | 0 | 0 | 5.47
|  |  | ESTABLISHMENT OF GOVERNMENT DEGREE |  |  | 47.087 | 0
70 | 206 | 214 | COLLEGE AT 15/A BUFFARZONE KARACHI
|  |  |  | Total | North Nazim'd | 47.087 | 0 | 1 | 0 | 0 | 1 | Upto Plinth Completed
IMPROVEMENT / ADDITION STAFF RESIDENCE "2"
71 | 262 | 221 | OF RANA LIQUAT ALI KHAN GOVERNMENT
|  |  | COLLEGE HOME ECONOMICE KARACHI |  | Gulshan'Iqbal | 0.975 | 0 | 1 | 0 | 0 | 1 | Foundation in Progress
|  |  |  | Total |  | 0.975 | 0 | 1 | 0 | 0 | 1
CONSTRUCTION OF AUDITORIUM HALL IN
72 | 262 | 222 | EXISTING DEGREE COLLEGE @ KMC PARK
|  |  | BLOCK# 5 LIAQUATABAD (Shifted to F.B.Area) |  | Gulberg | 7.657 | 0 | 2.5 | 0 | 0 | 2.5 | Plinth completed
|  |  |  | Total |  | 7.657 | 0 | 2.5 | 0 | 0 | 2.5
ADDITION/ IMPROVEMENT OF DEGREE COLLEGE
73 | 172 | 225 | Sir Syed Govt: Degree College |  | Liaquatabad | 12.848 | 0 | 14.4 | 0 | 0 | 14.4 | Completed & Handedover
Nazimabad Karachi (Phase-I)
|  |  |  | Total |  | 12.848 | 0 | 14.4 | 0 | 0 | 14.4
74 | 174 | 226 | ESTABLISHMENT/ OPENING OF GOVT: DEGREE COLLEGE | [8 empty] | Phase- I Completed
|  |  | North Nazimabad |  | N'Nazimabad | 26.098 | 0 | 24.45 | 0 | 0 | 24.45 | Phase-II Completed
|  |  |  | Total |  | 26.098 | 0 | 24.45 | 0 | 0 | 24.45 | Phase-III, Colouring in Progress
75 | 175 | 227 | ESTABLISHMENT/ OPENING OF GOVT: DEGREE COLLEGE
|  |  | North Karachi. |  | New Karachi | 26.098 | 0 | 28.3 | 0 | 0 | 28.3 | Completed & Handedover
|  |  |  | Total |  | 26.098 | 0 | 28.3 | 0 | 0 | 28.3
76 | 176 | 228 | ADDITION OF COMPUTER CLASSES IN
|  |  | COLLEGE OF KARACHI REGION (P.Programme) |  |  |  | 0
1 |  |  | Govt. Boys College Gulshan-e-Iqbal |  | Gulshan'Iqbal | 2.394 | 0 | 2.614 | 0 | 0 | 2.614 | Completed
|  |  |  | Total |  | 2.394 | 0 | 2.614 | 0 | 0 | 2.614
77 | 178 | 229 | ESTABLISHMENT/ OPENING OF GOVT: DEGREE |  |  |  | 0
|  |  | COLLEGE FOR GIRSL |  | Gulshan'Iqbal | 26.098 |  | 21.697 | 0 | 0 | 21.697 | Phase-I & II Finishing in Progress
|  |  | at Gulistan-e-Johar scheme # 36 |  |  | 26.098 | 0 | 21.697 | 0 | 0 | 21.697
78 | 177 | 230 | ESTABLISHMENT/ OPENING OF GOVT: DEGREE
|  |  | COLLEGE FOR BOYS |  |  |  | 0 |  |  |  |  | Phase-I Completed
|  |  | at Gulistan-e-Johar scheme # 36 |  | Gulshan'Iqbal | 26.098 |  | 23.766 | 0 | 0 | 23.766 | Phase-II Completed
|  |  |  | Total |  | 26.098 | 0 | 23.766 | 0 | 0 | 23.766 | Phase-III, Finishing in Progress
79 | 180 | 232 | IMPROVEMENT OF KHATOON-E-PAKISTAN
|  |  | GOVT. GIRLS COLLEGE KARACHI |  |  |  | 0
I |  |  | Main Building (Repair+Computer Labs) |  | Gulshan'Iqbal | 7.365 | 0 | 7.396 | 0 | 0 | 7.396 | Completed & Handedover
2 |  |  | Addition of (10) Classroom & (5) Labs |  | Gulshan'Iqbal | 15.802 | 0 | 2.901 | 0 | 0 | 2.901 | Foundation in Progress
3 |  |  | Auditorium Hall |  | Gulshan'Iqbal | 5.469 | 0 | 0 | 0 | 0 | 0 | Tender Under Process
|  |  |  | Total |  | 28.636 | 0 | 10.297 | 0 | 0 | 10.297
|  |  | Sub Total (College Education) " D " |  |  | 800.319 | 0 | 334.998 | 0 | 0 | 334.998
E |  |  | EDUCATION LITERACY PROGRAMME
80 | 213 | 246 | REPAIR & RENOVATION OF (2) TWO ROOMED |  |  |  | 0
|  |  | FOR VOCATIONAL CENTRE IN SUPER MARKET | [8 empty] | completed
|  |  | LIAQUATABAD TOWN KARACHI (2003-04 PRG) |  | Liaquatabad | 0.2 |  | 0.103 | 0 | 0 | 0.103
[6 empty] | 0.2 | 0 | 0.103 | 0 | 0 | 0.103
|  |  | Sub Total (Education Literacy Prog) " E " |  |  | 0.2 | 0 | 0.103 | 0 | 0 | 0.103
F |  |  | PROVINCIAL EDUCATION
81 | 288 | 404 | ADDITIONAL / IMPROVEMENT OF GOVERNMENT
|  |  | ELEMENTARY COLLEGE (MEN) QASIMABAD |  | Liaquatabad | 5.214 | 0 | 3.8 | 0 | 0 | 3.8 | G+ F Floor : Plastering Completed
|  |  | LIAQUATABAD KARACHI |  |  | 5.214 | 0 | 3.8 | 0 | 0 | 3.8
82 | 289 | 405 | ADDITIONAL / IMPROVEMENT OF GOVERNMENT
|  |  | COLLEGE OF EDUCATION BLOCK # 15 F.B.AREA |  | Gulberg | 30.548 | 0 | 3 | 0 | 0 | 3 | Foundation & Ext: Developmnet in Progress
|  |  | GULBERG TOWN KARACHI |  |  | 30.548 | 0 | 3 | 0 | 0 | 3
83 | 58 | 406 | ESTABLISHMENT OF GOVT. COLLEGE | [8 empty] | Block-A & C = Finishing in Progress
|  |  | OF EDUCATION B.Ed. & M.Ed. | [8 empty] | Block-B = Finishing in Progress
|  |  | @ Darsano Channo |  | Gadap | 25.412 | 0 | 22.569 | 0 | 0 | 22.569 | F/Floor roofing in Progress
[6 empty] | 25.412 | 0 | 22.569 | 0 | 0 | 22.569
84 | 298 | 422 | INTRODUCTION OF POST GRADUATE COURSES
|  |  | IN EXISTING COLLEGE IN KARACHI CITY |  |  |  | 0
1 |  |  | GGC | Shaheed-e-Millat Azizabad | Gulberg | 0 |  | 0 | 0 | 0 | 0 | A.A awaiated
2 |  |  | GGC | Mujeeb-un-Nisa New Karachi | New Karachi | 0 |  | 0 | 0 | 0 | 0 | A.A awaiated
3 |  |  | GGC | Premier College Nazimabad Karachi | Liaquatabad | 0 |  | 0 | 0 | 0 | 0 | A.A awaiated
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total Prov: Education (Teacher Edu) ( F ) |  | 61.174 | 0 | 29.369 | 0 | 0 | 29.369
|  | G | ABANDONED UNITS (Tameer-e-Watan Programme)
85 | *** | 223 | IMPROVEMENT OF RANA LIAQUAT ALI KHAN
GOVERNMENT COLLEGE HOME ECONOMICS
|  |  | KARACHI (FEDERAL GOVERNMENT) |  | Gulshan'Iqbal | 4.48 | 0 | 3.5 | 0 | 0 | 3.5 | Finishing in Progress
|  |  |  | Total |  | 4.48 | 0 | 3.5 | 0 | 0 | 3.5
|  |  |  | Sub-Total ( A+B+C+D+E+F+G) |  | #REF! | 0 | #REF! | 0 | 0 | #REF!
H |  |  | MPA's PRIORITY PROGRAMME (EDUCATION SECTOR)
1 |  |  |  | CONSTRUCTION OF COMPUTER LAB IN EXISTING |  |  | 5.1
SECONDARY SCHOOL BUILDING:
Sponsored By:
Mr. Syed Sardar Ahmed ( PS-98)
Mr. Qammar Mansoor (PS-99)
Mr. Muhammad Adil Siddiqui ( PS-100)
Mr. Asma Sherwani (Reserved Seat)
|  |  | I | @ GBSS 5/D North Karachi | New Karachi | 1.36 |  | 1.098 | 0 | 0 | 1.098 | Finishing in Progress
|  |  | II | @ GBSS 5/D-1 New Karachi | New Karachi | 1.36 |  | 0.697 | 0 | 0 | 0.697 | Finishing in Progress
|  |  | III | @ GGSS 11/E U.P Society. | New Karachi | 1.36 |  | 1.104 | 0 | 0 | 1.104 | Finishing in Progress |  | Balance
|  |  | IV | @ GBSS APWA 5/E New Karachi. | New Karachi | 1.36 |  | 1.076 | 0 | 0 | 1.076 | Finishing in Progress |  | 5.1
|  |  |  | TOTAL >>>> |  | 5.44 | 5.1 | 3.975 | 0 | 0 | 3.975
2 |  |  |  | ADDITION OF (8) CLASSROOM IN EXISTING |  |  | 6.22
SECONDARY
Mr. Syed Sardar Ahmed ( PS-98)
Mr. Qammar Mansoor (PS-99)
Mr. Muhammad Adil Siddiqui ( PS-100)
Mr. Asma Sherwani (Reserved Seat)
|  |  | I | @ GBSS 11/ C-3, North Karachi | New Karachi | 3.481 |  | 1.912 | 0 | 0 | 1.912 | Finishing in Progres
|  |  | II | @ GBSS 11/E-1 North Karachi. | New Karachi | 3.481 |  | 1.823 | 0 | 0 | 1.823 | Finishing in Progres
|  |  |  | TOTAL >>>> |  | 6.962 | 6.22 | 3.735 | 0 | 0 | 3.735
3 |  |  |  | CONSTRUCTION OF ADDITIONAL (2) CLASSROOM
At Government Boys Lower
|  |  |  | Secondary School Block "L" | N'Nazimabad | 0.92 | 0.845 | 0.616 | 0 | 0 | 0.616 | Super Structure Masonary Work in Progress
Arfat Town North Nazimabad Kyc:
Sponsored By
Ms. Bilquis Mukhtar (PS-101)
|  |  |  | TOTAL >>>> |  | 0.92 | 0.845 | 0.616 | 0 | 0 | 0.616
Sponsored By:
Miss: Farhina Ambreen (MPA)
4 |  |  |  | ADDOTION OF (3) ROOMS @ GGPS
STAFF WELFARE F.C. AREA
|  |  |  | Liaquatabad Town Karachi | Liaquatabad | 1.02 | 1.139 | 1.035 | 0 | 0 | 1.035 | Completed
|  |  |  | TOTAL >>>> |  | 1.02 | 1.139 | 1.035 | 0 | 0 | 1.035
Sponsored By:
Mr. Sajid Jokhio (MPA)
5 |  |  |  | CONSTRUCTION OF (2) TWO ROOMED
PRIMARY SCHOOL I/C COMPOUND WALL
|  |  | I | GPS Nido Buro UC Gadap | Gadap | 0.714 | 0.67 | 0.664 | 0 | 0 | 0.664 | Finishing in Progress
|  |  | II | GPS Nandho Jokhio | Gadap | 0.714 | 0.67 | 0.668 | 0 | 0 | 0.668 | Completed
(Deh Tahdo UC Darsano Channo)
|  |  | III | GPS Jarro Khan Chooto | Gadap | 0.714 | 0.67 | 0.664 | 0 | 0 | 0.664 | Finishing in Progress
(Deh Almani UC Darsano Channa)
|  |  |  | TOTAL >>>> |  | 2.142 | 2.01 | 1.996 | 0 | 0 | 1.996
6 |  |  |  | ADDITION OF (3) CLASS ROOM IN |  |  | 0.553
PRIMARY SCHOOL:
|  |  |  | @ Haji Gul Hassan Kathori. | Gadap | 0.591 |  | 0.208 | 0 | 0 | 0.208 | roof level completed
|  |  |  | TOTAL >>>> |  | 0.591 | 0.553 | 0.208 | 0 | 0 | 0.208
|  |  |  | GRAND TOTAL |  | 17.075 | 15.867 | 11.565 | 0 | 0 | 11.565
|  |  |  | Grand Total ( ADP + P-Programme) |  | #REF! | 15.867 | #REF! | 0 | 0 | #REF!
DISTRICT OFFICER
EDUCATION WORKS-II (W & S DEPTT)
CITY DISTRICT GOVT: KARACHI
SCHEME HAS BEEN DROPED IN 2004-05
ADDITION OF XI-XII CLASSES IN EXISTING
84 / 128 |  |  | SECONDARY SCHOOL ( 1988-89 PROG:) |  |  |  | 0
1 |  |  | @ Kamal Khan Jokhio |  | Gadap | 6.674 | 0 | 5.486 | 0 | 0 | 5.486 | Completed & Handedover
|  |  |  | Total |  | 6.674 | 0 | 5.486 | 0 | 0 | 5.486
|  |  | ADDITION/ALTERATION OF GOVERNMENT BOYS |  | Liaquatabad | 2.431 | 0 | 5.05 | 0 | 0 | 5.05 | completed
96 / *** |  |  | SECONDARY SCHOOL LIAQUATABAD No: 4 |  |  | 2.431 | 0 | 5.05 | 0 | 0 | 5.05
ADDITION OF CLASSROOM IN EXISTING
*** / 99 |  |  | SECODARY SCHOOLIN SINDH (1992-93 PROG: )
|  |  | GGSS | Khatoon-e-Pakistan | Gulshan' Iqbal | 0 | 0 | 0 | 0 | 0 | 0 | Unit Not yet Identify.
|  |  |  | Total |  | 0 | 0 | 0 | 0 | 0 | 0
PROVISION OF LACKING FACILITIES IN EXISTING
191 / 100 |  |  | SECONDARY SCHOOLS IN SINDH (1993-94 PROGRAMME) |  |  |  | 0
CONSTRUCTION OF COMPOUND WALLS IN
1 |  |  | Govt: Single Section High School Buffarzone |  | N'Nazimabad | 0.5 | 0 | 0.2 | 0 | 0 | 0.2 | Partly Completed / Partly Disputed
|  |  |  | Total |  | 0.5 | 0 | 0.2 | 0 | 0 | 0.2
|  |  | ADDITION OF CLASSROOM IN EXISTING SECON: |  |  | 0 | 0 | 0 | 0 | 0 | 0 | Location not yet available
*** / 102 |  |  | SCHOOL IN KARACHI ( 1991-92 PROGRAMME) |  |  | 0 | 0 | 0 | 0 | 0 | 0
Total
INTRODUCTION / ADDITION OF XI & XII CLASSES IN EXISTING
*** / 103 |  |  | SECONDARY SCHOOL IN SINDH KARACHI (1989-90 Prog)
1 |  |  | GGSS | Murrad Memon Goth | Gadap | 3.576 | 0 | 3.597 | 0 | 0 | 3.597 | Completed & Handed over
|  |  |  | Total |  | 3.576 | 0 | 3.597 | 0 | 0 | 3.597
ESTABLISHMENT GOVERNMENT DEGREE COLLEGE
62 / 147 |  |  | @ LIAQUATABAD NO: (5) Near KMC Park Karachi
|  |  | .Shifted to F.B.Area Block # 1, Karachi. |  | Gulberg | 23.289 | 0 | 18.435 | 0 | 0 | 18.435 | Completed & Handedover
|  |  |  | Total |  | 23.289 | 0 | 18.435 | 0 | 0 | 18.435 |  | ***
|  |  | ADDITION OF COMPUTER CLASSES |  |  |  | 0
82 / 173
1 |  |  | Mujeeb-un-Nisa Govt Girls College |  | New Karachi | 2.394 | 0 | 2.702 | 0 | 0 | 2.702 | Completed & Handedover
New Karachi Distt: Central
2 |  |  | Sir Syed Government College Kyc: |  | Liaquatabad | 2.394 | 0 | 1.998 | 0 | 0 | 1.998 | Completed & Handed over
|  |  |  | Total |  | 4.788 | 0 | 4.7 | 0 | 0 | 4.7
F |  |  | EDUCATION ADMINISTRATION
IMPROVEMENT OF EXISTING INSTITUTE BY
180 / *** |  |  | PROVISION NECESSARY LACKING FACILITIES:
1 |  |  | GBPS | Sector 5/D New Kyc:(Over Head Tank) | New Karachi | 0.05 | 0 | 0.048 | 0 | 0 | 0.048 | Completed & Handedover
2 |  |  | BOYS | G.Comprihensive High School (E/ Work) | F.B.Area | 0.26 | 0 | 0.279 | 0 | 0 | 0.279 | Completed & Handedover
3 |  |  | GBPS | APWA 5/E New Karachi: | New Karachi | 0.12 | 0 | 0.124 | 0 | 0 | 0.124 | Completed & Handedover
4 |  |  | GBPS | Sector 5/F New Karachi. | New Karachi | 0.05 | 0 | 0.0425 | 0 | 0 | 0.0425 | Completed & Handedover
5 |  |  | GBPS | Sector 5/F New Karachi. | New Karachi | 0.098 | 0 | 0.0505 | 0 | 0 | 0.0505 | Completed & Handedover
6 |  |  | GBPS | Sector 5/F New Karachi. | New Karachi | 0.068 | 0 | 0.05 | 0 | 0 | 0.05 | Completed & Handedover
7 |  |  | GIRLS | Govt: Comprihensive High North Karachi. | N'Nazimabad | 0.05 | 0 | 0.103 | 0 | 0 | 0.103 | Completed
8 |  |  | BOYS | Govt:Commercial Institute Azizabad Kyc | F.B.Area | 0.05 | 0 | 0.063 | 0 | 0 | 0.063 | Completed
9 |  |  | GBPS | Sector 5/F N' Karachi Town Committee | New Karachi | 0.05 | 0 | 0.05 | 0 | 0 | 0.05 | Completed
10 |  |  | GBPS | Sector 5/F New Karachi (O/Head Tank) | New Karachi | 0.05 | 0 | 0 | 0 | 0 | 0 | Not Required
11 |  |  | GBSS | Sector 5/D New Karachi (O/ Head Tank) | New Karachi | 0.05 | 0 | 0.051 | 0 | 0 | 0.051 | Completed
12 |  |  | GPS | Federal .B.Area Karachi. (Stair Case). | F.B.Area | 0.05 | 0 | 0 | 0 | 0 | 0 | Not Required
|  |  |  | Sub Total (Education Adminstration) " F " |  | 0.946 | 0 | 0.861 | 0 | 0 | 0.861
|  |  | 92 | EXTENSIVE REPAIR OF EXISTING GOVT; GIRLS
|  |  | *** / 262 | DEGREE COLLEGE 11/B NEW KARACHI |  | New Karachi | 3 | 0 | 2.26 | 0 | 0 | 2.26 | Completed
[7 empty] | 3 | 0 | 2.26 | 0 | 0 | 2.26
G |  |  | NON- ADP SCHEME
87 |  |  | UP-GRADATION OF MIDDLE TO HIGH SCHOOL
*** |  |  | IN RURAL AREA (1991-92 PROGRAMME)
|  |  | GBLSS | Aali Khan Gabol | Gadap | 1.433 | 0 | 0 | 0 | 0 | 0 | Main Building Completed & Audotirum Colouring
[6 empty] | 1.433 | 0 | 0 | 0 | 0 | 0 | in Progress
88 |  |  | INTRODUCTION / ADDITION OF XI & XII CLASSES
*** |  |  | IN EXISTING HIGH SCHOOL ( 1989-90 PROG:)
|  |  | GGSS | Murrad Memon Goth | Gadap | 0 | 0 | 0 | 0 | 0 | 0 | Tender under process
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0
ESTABLISHMENT OF PUBLIC SCHOOL GADAP
|  |  | MALIR KARACHI | [8 empty] | Detailed Sheet Seprately attached
|  |  |  | GRAND TOTAL ( NON-ADP) |  | 29.627 | 0 | 24.459 | 0 | 0 | 24.459
ABANDONED UNITS (Tameer-e-Watan Programme)
97 |  |  | ADDITION OF (1) C/ROOM PRIMARY SCHOOL
*** / |  |  | (1995-96 PROGRAMME) |  |  |  | 0
3 |  |  | GBPS | Ali Muhammad Khaskhely | Gadap | 0.352 |  | 0.159 | 0 | 0 | 0.159 | Colouring in Progress
|  |  |  | Total |  | 0.352 | 0 | 0.159 | 0 | 0 | 0.159
98 |  |  | CONSTRUCTION OF OF IV -V MOSQUE SCHOOL
*** / |  |  | (SPEDP) (1995-96)
1 |  |  | GMS | Bakharani Mohallah | Gadap | 0.258 | 0 | 0.126 | 0 | 0 | 0.126 | Colouring in Progress
|  |  |  | Total |  | 0.258 | 0 | 0.126 | 0 | 0 | 0.126
99 |  |  | CONSTRUCTION / RE-CONSTRUCTION OF (2)
*** / |  |  | ROOMED PRIMARY SCHOOL (1992-93)
1 |  |  | GPS | Hashim Bikik Moidan Gadap | Gadap | 0.74 | 0 | 0.339 | 0 | 0 | 0.339 | Finishing in Progress
2 |  |  | GPS | Mian Bikik Moidan Gadap | Gadap | 0.74 |  | 0.401 | 0 | 0 | 0.401 | Finishing in Progress
|  |  |  | Total |  | 1.48 | 0 | 0.74 | 0 | 0 | 0.74
100 |  |  | CONSTRUCTION / RE-CONSTRUCTION OF (2)
*** / |  |  | CLASS ROOM PRIMARY SCHOOL (1995-96) |  |  |  | 0
1 |  |  | GPS | Nabi Bux Gabol | Gadap | 0.848 | 0 | 0.282 | 0 | 0 | 0.282 | Finishing in Progress
2 |  |  | GBPS | Buxo Bandijo | Gadap | 0.75 | 0 | 0.696 | 0 | 0 | 0.696 | Colouring in Progress
|  |  |  | Total |  | 1.598 | 0 | 0.978 | 0 | 0 | 0.978
102 |  |  | UP-GRADATION OF PRIMARY TO MDDDLE
*** / |  |  | SCHOOL IN U/AREA ( 1990-91 PROG)
1 |  |  | GBPS | Mazar Khan Jokhio Gadap Town | Gadap | 1.141 | 0 | 0.365 | 0 | 0 | 0.365 | Colouring in Progress
|  |  |  | Total |  | 1.141 | 0 | 0.365 | 0 | 0 | 0.365
103 |  |  | OPENING OF (2) CLASSROOM PRIMARY SCHOOL
*** / |  |  | IN KARACHI SINDH ( 1994-95 PROGRAMME)
1 |  |  | GGPS | Yousaf Brohi Goth Karachi | Gadap | 0.75 | 0 | 0.45 | 0 | 0 | 0.45 | Colouring in Progress
|  |  |  | Total |  | 0.75 | 0 | 0.45 | 0 | 0 | 0.45
104 |  |  | CONSTRUCTION OF CLASSROOM IN EXISTING |  |  |  | 0
*** / |  |  | MOSQUE SCHOOL (SPEDP) IN SINDH
|  |  | GPS | Hashim Bikik Maidam | Gadap | 0 |  | 0 | 0 | 0 | 0 | Tender Under Process
|  |  | GPS | Mian Bikik Moidan | Gadap | 0 |  | 0 | 0 | 0 | 0 | Tender Under Process
|  |  |  | Total |  | 0 | 0 | 0.45 | 0 | 0 | 0.45
105 |  |  | ADDITION OF (1) CLASSROOM IN PRIMARY
*** / |  |  | SCHOOL (1995-96 PROGRAMME)
|  |  | GPS | Bakhar Goth | Gadap | 0.274 | 0 | 0.263 | 0 | 0 | 0.263 | Colouring in Progress
|  |  | GPS | Allah Warayo Chitto | Gadap | 0.274 |  | 0.301 | 0 | 0 | 0.301 | Finishing in Progress
|  |  |  | Total |  | 0.548 | 0 | 0.564 | 0 | 0 | 0.564
|  |  |  | TOTAL ( ABANDONED UNITS ) |  | 16.454 | 0 | 9.832 | 0 | 0 | 9.832
Note on H766: Faheem Uddin Siddiqui: Amount of Revised PC-1 correction from Liaq't Town Progress Report
Note on J441: Faheem Uddin Siddiqui: Expt: Less from 22.396 - - 18.896 ( Diff: 3.500 ) As per Naich Instruction.
1- GADAP
2- GULBERG
3- GULSHAN
4- LIAQUATABAD
5- NEW KARACHI
6- NORTH NAZIMABAD
P.Programme
P.Programme
P.Programme
P.Programme
P.Programme
P.Programme
P.Programme
P.Programme
P.Programme
P.Programme
P.Programme
P.Programme
P.Programme

## KKP-II-5 (hidden)
MONTHLY PROGRESS REPORT IN RESPECT KHUSHALL PAKISTAN PROGRAMME 2002-03
FOR THE MONTH OF SEPTEMBER - 2004
Education Works-II (Works & Services Department ) City District Government Karachi
Sr. No: | Category |  | Town | Approved Cost | Allocation | E X P E N D I T U R E |  |  |  | Physical | Actual
ADP # |  | Name of Scheme/ |  |  |  | Upto | During the | During the | Total | Progress | Date of
2001-02 |  | Project / Location |  |  | 2003-04 | 6-2003. | Month | Year | Since | Remarks | Completion
[8 empty] | 2003-04 | Comme:
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
0
1 |  | Repair to Govt. Boys Secondary School
|  | At Malir Cant't Karachi | Gulshan Town | 2.475 | 0 | 1.129 | 0 | 0 | 1.129 | Work in Progress
2 |  | Repair to Government Degree Science
|  | College At Malir Cant't Karachi | Gulshan Town | 3.142 | 0 | 0.857 | 0 | 0 | 0.857 | Work in Progress
3 |  | Construction of Compound Wall at
APWA Government College for Women
|  | F.B.Area Karachi | Gulberg Town | 1.279 | 0 | 0.814 | 0 | 0 | 0.814 | Completed
4 |  | Opening of (5) Classroom Primary
|  | School at Surjani Town GADAP | GADAP Town | 2.93 | 0 | 2.052 | 0 | 0 | 2.052 | Plaster in Progress
|  |  |  | 9.826 | 0 | 4.852 | 0 | 0 | 4.852
DISTRICT OFFICER
EDUCATION WORKS-II (W & S DEPTT)
CITY DISTRICT GOVERNMENT KARACHI

## Sheet1 (2) (hidden)
UTILIZATION OF FUNDS RELEASED UNDER M & R FOR NON-SAP SUB-SECTOR DURING 2000-01
Education Works Division Central Karachi
Rs. in Million
Name of Sub-Sector/ Location | Taluka | Authority Released # |  |  | Estimated | Actual Date | E X P E N D I T U R E | [8 empty] | Period of | Physical Progress | Actual Date of | Position of funds
|  | Authority | T/S No: | Date | Amount | of Start | Upto 30-06-2000 |  | During the Month |  | During 2000-01 |  | Total Expenditure |  | Total | completion | in % Age. | Completeion | agasint final Releases
[7 empty] | O/R | S/R | O/R | S/R | O/R | S/R | O/R | S/R |  | in the W/Order |  |  | Release | Requirement
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
[19 empty] | AOR -0.486 | Nil
SECONDARY SCHOOL EDUCATION | [18 empty] | SR- 0.414 | Nil
Total: 0.900
GBSS Happy Dale Nazim'd. | Central | PD ( Hyd) | 138 | 2004-04-29 | 0.55 | 18/5/00. | 0 | 0 | 0 | 0 | 0.134 | 0.11 | 0.134 | 0.11 | 0.244 | 4 Months | Completed | 18/5/01.
GBSS Jamia Tajia 15/A Buffar
zone Zone North Karachi. | Central | PD ( Hyd) | 212 | 2004-05-24 | 0.381 | 27/5/00. | 0 | 0 | 0 | 0 | 0.131 | 0.107 | 0.131 | 0.107 | 0.238 | 2 Months | Completed | ***
GBSS Happy Dale Nazimabad | Central | PD ( Hyd) | 133 | 2004-04-29 | 0.358 | 18/5/00. | 0.051 | 0.041 | 0 | 0 | 0.064 | 0.053 | 0.115 | 0.094 | 0.209 | 3 Months | Completed
Sir Syed Town 11/ C N'Kyc | Central | PD ( Hyd) | 205 | 2004-05-24 | 0.496 | 25/5/00. | 0.141 | 0.116 | 0 | 0 | 0.112 | 0.091 | 0.253 | 0.207 | 0.46 | 4 Months | Completed | ***
GBSS Karachi Elemantry | Central | SE(EWDC-I) | 723 | 2004-05-21 | 0.142 | 20/5/00. | 0 | 0 | 0 | 0 | 0.052 | 0.042 | 0.052 | 0.042 | 0.094 | 1 Months | Completed | 14/6/Y2K1
North Nazimabad Karachi
GBSS National Ideel 5/C-2, North Kyc: | Central | PD ( Hyd) | 203 | 2004-05-24 | 0.872 | 25/5/00. | 0.173 | 0.141 | 0 | 0 | 0.141 | 0.115 | 0.314 | 0.256 | 0.57 | 5 Months | Completed | 17/6/Y2k1
GGSS 5/D New Karachi. | Central | PD ( Hyd) | 204 | 2004-05-24 | 0.511 | 25/5/00. | 0.082 | 0.068 | 0 | 0 | 0.194 | 0.159 | 0.276 | 0.227 | 0.503 | 6 Months | Completed | ***
GGSS 5/B New Karachi | Central | PD ( Hyd) | 206 | 2004-05-24 | 0.317 | 25/5/00. | 0.132 | 0.108 | 0 | 0 | 0.043 | 0.036 | 0.175 | 0.144 | 0.319 | 3 Months | Completed | 24/6/Y2k1
GGSS Relax Cinema Nazim'd | Central | SE(EWDC-I) | 718 | 2004-05-19 | 0.237 | 28/5/00. | 0 | 0 | 0 | 0 | 0.123 | 0.102 | 0.123 | 0.102 | 0.225 | 2 Months | Completed | ***
Total Secondary School Education |  |  |  |  | 3.864 | **** | 0.579 | 0.474 | 0 | 0 | 0.994 | 0.815 | 1.573 | 1.289 | 2.862 | *** | *** | *** | 0.9 | Nil
Name of Sub-Sector/ Location | Taluka | Authority Released # |  |  | Estimated | Actual Date | E X P E N D I T U R E | [8 empty] | Period of | Physical Progress | Actual Date of | Position of funds
|  | Authority | T/S No: | Date | Amount | of Start | Upto 30-06-2000 |  | During the Month |  | During 2000-01 |  | Total Expenditure |  | Total | completion | in % Age. | Completeion | agasint final Released
[7 empty] | O/R | S/R | O/R | S/R | O/R | S/R | O/R | S/R |  | in the W/Order |  |  | Released | Required
1 | 2 | 3 | 4 | 5 | 6 | 78 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 20 | 21
COLLEGE EDUCATION
Government College For
Men Nazimabad Karachi | Central | PD ( Hyd) | 199 | 2004-05-24 | 0.397 | 28/5/00. | 0 | 0 | 0 | 0 | 0.192 | 0.158 | 0.192 | 0.158 | 0.35 | 4 Months | Completed | 22/3/01.
Govt. shipowner College North
Nazimabad Karachi. | Central | PD ( Hyd) | 211 | 2004-05-24 | 0.485 | 28/5/00. | 0.11 | 0.09 | 0 | 0 | 0.084 | 0.069 | 0.194 | 0.159 | 0.353 | 3 Months
[17 empty] | Completed | 12/3/01.
Govt. College For Women
Nazimabad Karachi. | Central | PD ( Hyd) | 198 | 2004-05-24 | 0.498 | 26/5/00. | 0 | 0 | 0 | 0 | 0.281 | 0.23 | 0.281 | 0.23 | 0.511 | 3 Months | Completed | 2/2/01.
….do..( W/S & S/I) | Central | SE(EWDC-I) | …do.. | ….do.. | 0.22 | 28/5/00. | 0 | 0 | 0 | 0 | 0.122 | 0.099 | 0.122 | 0.099 | 0.221 | 2 Months | Completed | 25/3/01.
…….do…. ( Gas Fitting ) | Central | SE(EWDC-I) | *** | *** | 0.226 | 04/7/00. | 0 | 0 | 0 | 0 | 0.125 | 0.102 | 0.125 | 0.102 | 0.227 | 2 Months | Completed | 2/6/01.
Govt. APWA College For
Women F.B.Ara Karachi. | Central | PD ( Hyd) | 101 | 2004-03-16 | 1.013 | 20/5/00. | 0.41 | 0.336 | 0 | 0 | 0.113 | 0.092 | 0.523 | 0.428 | 0.951 | 5 Months | Completed | ***
……..DO….(Barbad Wire) | Central | XEN(CENTRAL) | 103-A | 2004-04-04 | 0.07 | 17/05/00. | 0 | 0 | 0 | 0 | 0.037 | 0.03 | 0.037 | 0.03 | 0.067 | 2 Months | Completed | ***
Govt. College for Women New Kyc: | Central | PD ( Hyd) | 201 | 2004-05-24 | 0.61 | 25/5/00. | 0.223 | 0.182 | 0 | 0 | 0.078 | 0.064 | 0.301 | 0.246 | 0.547 | 4 Months | Completed | ***
Total College Edu: |  |  |  |  | 3.519 | *** | 0.743 | 0.608 | 0 | 0 | 1.032 | 0.844 | 1.775 | 1.452 | 3.227 | *** | *** | *** | 0 | ***
Grand Total Sec: + College |  |  |  |  | 7.383 | **** | 1.322 | 1.082 | 0 | 0 | 2.026 | 1.659 | 3.348 | 2.741 | 6.089 | *** | *** | *** | 0.9 | ***
Ordinary Repair | 2.1 | [5 empty] | EXECUTIVE ENGINEER
Special Repair | 1.73 | [5 empty] | EDUCATION WROKS DIVISION CENTRAL
Grand Total | 3.83 | [5 empty] | KARACHI
| Release | Reauirement
Ordinary Repair | 0.486 | Nil
Special Repair | 0.414 | Nil
Grand Total | 0.9 | Nil
UTILIZATION OF FUNDS RELEASED UNDER M & R FOR NON-SAP SUB-SECTOR DURING 2000-01
Education Works Division South Karachi
Rs. in Million
Name of Sub-Sector/ Location | Taluka | Authority Released # |  |  | Estimated | Actual Date | E X P E N D I T U R E | [8 empty] | Period of | Physical Progress | Actual Date of
|  | Authority | T/S No: | Date | Amount | of Start | Upto 30-06-2000 |  | During the Month |  | During 2000-01 |  | Total Expenditure |  | Total | completion | in % Age. | Completeion
[7 empty] | O/R | S/R | O/R | S/R | O/R | S/R | O/R | S/R |  | in the W/Order
1 | 2 | 3 | 4 | 5 | 6 | 78 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
SECONDARY EDUCATION
GBLSS G.H. AQSIM | Karachi | SE(EWCK-I) |  | 2004-06-01 | 0.1765 | 2004-06-05 | 0.104 | 0.045 | 0 | 0 | 0.026 | 0.01 | 0.13 | 0.055 | 0.185 |  | Completed & H/Over
GBSS Pak National | …do… | SE(EWCK-I) |  | 2004-06-01 | 0.14 | 06/06/00. | 0.074 | 0.032 | 0 | 0 | 0.028 | 0.012 | 0.102 | 0.044 | 0.146 |  | Completed & H/Over
GBSS Izzat Khan Gharib Shah | …do… | SE(EWCK-I) |  | 2004-06-01 | 0.1735 | 05/06/00. | 0.049 | 0.02 | 0 | 0 | 0.069 | 0.03 | 0.118 | 0.05 | 0.168 |  | Completed & H/Over
GBSS Metropolice (Urdu Bazar) | …do… | SE(EWCK-I) |  | 2004-06-01 | 0.22 | 06/06/00. | 0.087 | 0.037 | 0 | 0 | 0.07 | 0.03 | 0.157 | 0.067 | 0.224 |  | Completed & H/Over
GGSS Balouch E.K.M.K. Road | …do… | PD ( Office) |  | 2004-05-31 | 0.467 | 05/06/00. | 0.169 | 0.072 | 0 | 0 | 0.175 | 0.074 | 0.344 | 0.146 | 0.49 |  | Completed & H/Over
GSA W. Muhammad H.Yaqoob. | …do… | SE(EWCK-I) |  | 2004-06-01 | 0.099 | 06/06/00. | 0.046 | 0.0198 | 0 | 0 | 0.025 | 0.0107 | 0.071 | 0.0305 | 0.1015 |  | Completed & H/Over
GGSS Madressah T.Binnat | …do… | SE(EWCK-I) |  | 2004-06-01 | 0.157 | 03/06/00. | 0.0723 | 0.031 | 0 | 0 | 0.038 | 0.017 | 0.1103 | 0.048 | 0.1583 |  | Completed & H/Over
GGSS Ghribabad M.A.Alvi A.U.Gr. | …do… | PD ( Office) |  | 2004-05-31 | 0.93 | 07/06/00. | 0.538 | 0.23 | 0 | 0 | 0.143 | 0.061 | 0.681 | 0.291 | 0.972 |  | Completed & H/Over
GGSS P & T Colony (Lav: Block) | …do… | PD ( Office) |  | 2004-05-18 | 0.25 | 02/06/00. | 0.175 | 0.075 | 0 | 0 | 0.021 | 0.009 | 0.196 | 0.084 | 0.28 |  | Completed & H/Over
GGSS Ghulam Rasool Balouch | …do… | SE(EWCK-I) |  | 2004-06-01 | 0.136 | 06/06/00. | 0.074 | 0.032 | 0 | 0 | 0.026 | 0.011 | 0.1 | 0.043 | 0.143 |  | Completed & H/Over
GGHSS NJV Sindhi Medium | …do… | PD ( Office) |  | 2004-07-01 | 0.451 | 05/06/00. | 0.161 | 0.069 | 0 | 0 | 0.17 | 0.071 | 0.331 | 0.14 | 0.471 |  | Completed & H/Over
Irranian Technical High School | …do… | SE(EWCK-I) |  | 31/06/00 | 0.08 | 06/06/00. | 0.045 | 0.019 | 0 | 0 | 0.014 | 0.006 | 0.059 | 0.025 | 0.084 |  | Completed & H/Over
GGHSS Green Balt Mehmoodabad | …do… | SE(EWCK-I) |  | 31/06/00 | 0.25 | 05/06/00. | 0.162 | 0.07 | 0 | 0 | 0.197 | 0.085 | 0.359 | 0.155 | 0.514 |  | Completed & H/Over
GBSS Gulistan Colony. | …do… | XEN(EWDSK) |  | 2005-03-09 | 0.05 | 28/03/01. | 0.022 | 0.009 | 0 | 0 | 0.003 | 0.001 | 0.025 | 0.01 | 0.035 |  | Completed & H/Over
KAECHS ( Balouch Colony)Mahm'd | …do… | SE(EWCK-I) |  | 2005-03-09 | 0.13 | 04/04/01. | 0 | 0 | 0 | 0 | 0.056 | 0.024 | 0.056 | 0.024 | 0.08 |  | Completed
GGSS 1 & 3 | …do… | XEN(EWDSK) |  | 2005-03-17 | 0.05 | 30/03/01. | 0 | 0 | 0 | 0 | 0.021 | 0.009 | 0.021 | 0.009 | 0.03 |  | Completed & H/Over
GBLSS Green Belt Mehmoodabad | …do… | PD ( Office) |  | 2005-02-13 | 0.3 | 03/04/01. | 0 | 0 | 0 | 0 | 0.007 | 0.002 | 0.007 | 0.002 | 0.009 |  | work in Progress
Rehabilitation of NJV High School | …do… | PD ( Office) |  | 2005-03-09 | 1.8 |  | 0 | 0 | 0 | 0 | 0.524 | 0.224 | 0.524 | 0.224 | 0.748 |  | Send Blasting, Karbing
Repair to NJV School (W/S & S/I ) |  | PD ( Office) |  | *** | 0.615 | *** | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | fixation of grill completed
Bathroom. | [16 empty] | Plantation & Other work in
progress. Funds are
required to meet
contractor Liabilities
GGSS Mir Ayoub Lyari | …do… | PD ( Office) |  | *** | 0.25 | *** | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Inter W/S & S/I work
in advance stage
GBLSS Main Gizri (W/S & S/I) I/c | …do… | XEN(EWDSK) |  | *** | 0.035 | *** | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drinking water tank.
GGLSS Gizri (Sindhi Medium) | …do… | PD ( Office) |  | *** | 0.196 | *** | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | *** | *** | 6.956 | *** | 1.7783 | 0.7608 | 0 | 0 | 1.613 | 0.6867 | 3.3913 | 1.4475 | 4.8388
Name of Sub-Sector/ Location | Taluka | Authority Released # |  |  | Estimated | Actual Date | E X P E N D I T U R E | [8 empty] | Period of | Physical Progress | Actual Date of
|  | Authority | T/S No: | Date | Amount | of Start | Upto 30-06-2000 |  | During the Month |  | During 2000-01 |  | Total Expenditure |  | Total | completion | in % Age. | Completeion
[7 empty] | O/R | S/R | O/R | S/R | O/R | S/R | O/R | S/R |  | in the W/Order
1 | 2 | 3 | 4 | 5 | 6 | 78 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
COLLEGE EDUCATION
Govt.Girls Inter science College | Karachi | SE(EWCK-I) |  | 2004-06-01 | 0.031 | 2004-06-06 | 0.097 | 0.042 | 0 | 0 | 0.073 | 0.031 | 0.17 | 0.073 | 0.243 |  | Completed & H/Over
Moosa Lane Karachi south
Govt Degree Science & Commerence | …do… | SE(EWCK-I) |  | 2004-06-01 | 0.237 | 2004-06-07 | 0.118 | 0.05 | 0 | 0 | 0.049 | 0.021 | 0.167 | 0.071 | 0.238 |  | Completed & H/Over
Lyari Karachi south
Karachi College for Women C.E. | …do… | SE(EWCK-I) |  | 2004-06-01 | 0.153 | 2004-06-06 | 0.1 | 0.043 | 0 | 0 | 0.046 | 0.02 | 0.146 | 0.063 | 0.209 |  | Completed & H/Over
Govt. Commerce Boys/Girls College | …do… | SE(EWCK-I) |  | 2004-06-01 | 0.163 | 2004-06-06 | 0.09 | 0.039 | 0 | 0 | 0.024 | 0.011 | 0.114 | 0.05 | 0.164 |  | Completed & H/Over
at P.I.D.C. Karachi south
Govt. College for Women Ferer Road | …do… | SE(EWCK-I) |  | 2004-06-01 | 0.229 | 2004-06-06 | 0.09 | 0.039 | 0 | 0 | 0.029 | 0.013 | 0.119 | 0.052 | 0.171 |  | Completed & H/Over
Govt. DJ Science College Pak: Chowk | …do… | SE(EWCK-I) |  | 2004-06-01 | 0.239 | 2004-06-06 | 0.087 | 0.037 | 0 | 0 | 0.095 | 0.04 | 0.182 | 0.077 | 0.259 |  | Completed & H/Over
Govt. SMB Fatima Jinnah College | …do… | SE(EWCK-I) |  | 2004-06-01 | 0.221 | 2004-06-07 | 0.11 | 0.048 | 0 | 0 | 0.015 | 0.006 | 0.125 | 0.054 | 0.179 |  | Completed & H/Over
Repair to Govt. Ronaq-e-Islam Lyari | …do… | PD ( Office) |  | 2005-03-09 | 0.365 | 2005-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Work is likely to be
started in few days
Repair to D.J. Science College | …do… | PD ( Office) |  | 2005-03-10 | 0.315 | 2005-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Flooring of F/Floor of
Chemistry lab Plastering
of G/F Chemistry Lab
room No:18, & Colour
of Administration Block
and room No:18 Complete
Repair to Govt. Girls College | …do… | PD ( Office) |  | *** | 0.72 | *** | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Work in Progress
Moosa Lane Lyari.
Repair to Office Building XEN(EWDSK) | …do… | SE(EWCK-I) |  | 2005-06-01 | 0.21 | 2005-06-06 | 0.148 | 0.063 | 0 | 0 | 0.022 | 0.009 | 0.17 | 0.072 | 0.242 |  | Completed & H/Over
Advertisement Charges. | *** | *** | *** | *** | *** | 2005-03-24 | 0.045 | 0.019 | 0 | 0 | 0.01 | 0.004 | 0.055 | 0.023 | 0.078 |  | Paid all dues to Information
Department GOS Kyc
Total College Educaiton |  | *** | *** | *** | 2.883 | *** | 0.885 | 0.38 | 0 | 0 | 0.363 | 0.155 | 1.248 | 0.535 | 1.783
Grant Total Secondary + College |  | *** | *** | *** | 9.839 | *** | 2.6633 | 1.1408 | 0 | 0 | 1.976 | 0.8417 | 4.6393 | 1.9825 | 6.6218
EXECUTIVE ENGINEER
EDUCATION WROKS DIVISION SOUTH
KARACHI