## Procurement Plan
Guidelines/ Regulations For Procurement of Works. | [9 empty] | (Annexure A-I)
PROCUREMENT PLAN (Development/Captial)
OFFICE OF THE EXECUTIVE ENGINEER ROHRI DIVISION KANDIARO
FOR THE YEAR OF 2015 -16
P. No/ ADP No. | Name of Scheme & Estimated Cost | Allocated Funds | Cost of ongoing works (Expenditure already incurred) | Funds earmarked for ongoing works | Cost of New Works | Funds for New Works (c-e) | Nature of Procurement | Method of Procurement | Anticipated/ Actual Date of Advertisement | Anticipated/ Actual Date of Start | Anticipated/ Actual Date of Completion
a | b | c | d | e | f | g | h | i | j | k | l
P# (1) | Constructing Stone Pitching, Stone Apron and Earth Work along SM Bund Mile 4/0 to 4/2 (Sagyoon Site) | 59.145 | -- | -- | -- | -- | NCB | Single Stage one envelope method | 15.04.2016 | 12.05.2016 | 11.08.2016 (03 Months)
EXECUTIVE ENGINEER
Rohri Division Kandiaro