## Procurement Plan
Guidelines/ Regulations For Procurement of Works. | [9 empty] | (Annexure A-I)
PROCUREMENT PLAN (Development/Captial)
OFFICE OF THE EXECUTIVE ENGINEER ROHRI DIVISION KANDIARO
FOR THE YEAR OF 2015 -16
P. No/ ADP No. | Name of Scheme & Estimated Cost | Allocated Funds | Cost of ongoing works (Expenditure already incurred) | Funds earmarked for ongoing works | Cost of New Works | Funds for New Works (c-e) | Nature of Procurement | Method of Procurement | Anticipated/ Actual Date of Advertisement | Anticipated/ Actual Date of Start | Anticipated/ Actual Date of Completion
a | b | c | d | e | f | g | h | i | j | k | l
REVAMPING / REHABILITATION IRRIGATION DRAINAGE IN SINDH (RRIDS)
P# (1) | Constructing Groyance along Naulakhi Branch from RD-6+00 to 72+00 B/S in different Reaches under Revamping/Rehabilitation programme in Rohri Division Kandiaro. | 5.141 | -- | -- | -- | -- | NCB | Single Stage one envelope method | 18.04.2016 | 18.05.2016 | 18.11.2016 (06 Months)
P# (2) | Repair/Extension of Outlets Sehra branch under Revamping/ Rehabilitation Programme in Rohri Division kandiaro | 11.845 | -- | -- | -- | -- | NCB | Single Stage one envelope method | 18.04.2016 | 18.05.2016 | 18.11.2016 (06 Months) | National contract Bill
P# (3) | Repair of Naulakhi Head Regulator & Extension of its Existing bridge over Gadeji & Hingorja Minors Ex: Rohri Main canal @ RD-205 under scheme of Revamping/Rehabilitation of Irrigation & Drainage System Sindh. | 7.026 | -- | -- | -- | -- | NCB | Single Stage one envelope method | 18.04.2016 | 18.05.2016 | 18.11.2016 (06 Months)
P# (4) | Repair of Khanwahan X-Regulator @RD-75+800 of Naulkhi Branch & Remodeling of VRB @ RD-57+0 along Naulakhi under scheme of Revamping/Rehabilitation of Irrigation & Drainage System in Sindh | 9.24 | -- | -- | -- | -- | NCB | Single Stage one envelope method | 18.04.2016 | 18.05.2016 | 18.11.2016 (06 Months)
P# (5) | Repair to VRB along Siyal Distry @ RD-25+0 Khanwahan Minor @ RD-12+0 & Longrji Minor @ RD 3+0 under scheme of Revamping/ Rehabilitation of Irrigation & Drainage System in Sidh. | 2.558 | -- | -- | -- | -- | NCB | Single Stage one envelope method | 18.04.2016 | 18.05.2016 | 18.11.2016 (06 Months)
P# (6) | Earthwork along Godhu Distry RD 0 to 29 B/S. | 9.579 | -- | -- | -- | -- | NCB | Single Stage one envelope method | 18.04.2016 | 18.05.2016 | 18.11.2016 (06 Months)
P# (7) | Earthwork along Langerji from RD- 0 to 19+280 | 6.274 | -- | -- | -- | -- | NCB | Single Stage one envelope method | 18.04.2016 | 18.05.2016 | 18.11.2016 (06 Months)
P# (8) | Constructing Pre-Stressed Road Bridge along Rohri Main canal @ RD 235-36 Connect Hingorja & Deparja | 88.3 | -- | -- | -- | -- | NCB | Single Stage one envelope method | 18.04.2016 | 18.05.2016 | 18.05.2019 (36 Months)
EXECUTIVE ENGINEER
Rohri Division Kandiaro