## P.Plan 2015-16
REVISED PROCUREMENT PLAN 2015-2016 (HIGHWAYS DIVISION KAMBER-SHAHDADKOT)
CONSTRUCTION/RECONDITIONING OF ROADS & MASONARY STRUCTURES DISTRICT KAMBER-SHAHDADKOT.
S.No. | Description of Procurement | Quantity (Where applicable) | Estimated unit cost (where applicable) (in Million) | Estimated total cost | Funds allocated (in Million) | Source of funds (ADPs/Non ADPs) | Proposed Procurement metohd | Timing of Procurement |  |  |  | Remarks
[8 empty] | 1st Qtr: | 2nd Qtr: | 3rd Qtr: | 4th Qtr:
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1 | Reconditioning of link road from Qubo Saeed Khan via Lundi Shakh to Saifullah shakh U/C Qubo Saeed Khan Taluka Qubo Saeed Khan Mile 0/0-3/1 (5.0 KMs). | 5 | 26.135 | 26.135 | 185.844 (Block) | Provincial ADP-1129 | Single Stage One Envelope Method | 6.5338 | 6.5338 | 6.5338 | 6.5338
2 | Reconditioning of link road from Qubo Saeed Khan RD-97000 Pull U/C Bago Daro Taluka Qubo Saeed Khan mile 0/0-3/6 (6.0 KMs). | 6 | 31.591 | 31.591 | -do- | Provincial ADP-1129 | Single Stage One Envelope Method | 7.8978 | 7.8978 | 7.8978 | 7.8978
3 | Construction of link road from Sultan Ahmed Khuhawar Pump to Koto Moto Chowk mile 0/0-0/5 (1.0 KMs). | 1 | 19.856 | 19.856 | -do- | Provincial ADP-1129 | Single Stage One Envelope Method | 4.964 | 4.964 | 4.964 | 4.964
4 | Construction of link road from Hasrani Pump via Sijawal Phatak to Bus Stand U/c Shahdadkot-III mile 0/0-1/4+330' (2.50 KMs). | 2.5 | 50.881 | 50.881 | -do- | Provincial ADP-1129 | Single Stage One Envelope Method | 12.7203 | 12.7203 | 12.7203 | 12.7203
5 | Construction of link road from Mir Noorullah Khan Magsi Bungalow to village Faiz Muhammad Brohi U/C Shahdadkot-I mile 0/0-0/5 (1.0 KM). | 1 | 20.349 | 20.349 | -do- | Provincial ADP-1129 | Single Stage One Envelope Method | 5.0873 | 5.0873 | 5.0873 | 5.0873
6 | Construction of link road from Shaheed Nawab Saifullah Khan Library U/C Shahdadkot-I mile 0/0-0/3 (0.60 KMs). | 0.6 | 3.84 | 3.84 | -do- | Provincial ADP-1129 | Single Stage One Envelope Method | 0.96 | 0.96 | 0.96 | 0.96
7 | Construction of link road from Koto Moto Chowk to Station road U/c Shahdadkot Taluka Shahdadkot Mile 0/0-1/7 (3.0 KMs). | 3 | 57.742 | 57.742 | -do- | Provincial ADP-1129 | Single Stage One Envelope Method | 14.4355 | 14.4355 | 14.4355 | 14.4355
8 | Construction of link road from Single Section High School road to Kala Makan U/C Shahdadkot Taluka Shahdadkot Mile 0/0-0/5+330' (1.10 KMs). | 1.1 | 6.767 | 6.767 | -do- | Provincial ADP-1129 | Single Stage One Envelope Method | 1.6918 | 1.6918 | 1.6918 | 1.6918
9 | Construction of link road from Green Star Hotel via Lakh Pati road U/C Shahdadkot-I Mile 0/0-0/7+330' (1.50 KMs). | 1.5 | 28.868 | 28.868 | -do- | Provincial ADP-1129 | Single Stage One Envelope Method | 7.217 | 7.217 | 7.217 | 7.217
10 | Construction of link road from Public Health Office to Civil Hospital U/C Shahdadkot-I Taluka Shahdadkot mile 0/0-0/5 (1.0 KM). | 1 | 19.208 | 19.208 | -do- | Provincial ADP-1129 | Single Stage One Envelope Method | 4.802 | 4.802 | 4.802 | 4.802
11 | Reconditioning of link road from Katchi Pull to Chukhi U/C Bago Daro Taluka Qubo Saeed Khan Mile 0/0-2/4 (4.0 KMs). | 4 | 21.154 | 21.154 | -do- | Provincial ADP-1129 | Single Stage One Envelope Method | 5.2885 | 5.2885 | 5.2885 | 5.2885
12 | Construction of link road from Imam Bux Jamali road to village Nadirabad via Yousifabad U/c Aitbar Khan Chandio Taluka Shahdadkot mile 0/0-3/1 (5.0 KMs). | 5 | 37.647 | 37.647 | -do- | Provincial ADP-1129 | Single Stage One Envelope Method | 9.4117 | 9.4117 | 9.4117 | 9.4117
13 | Construction/Reconditioning of road from Grid Station Kamber via Sain Hussain Shah Dargah to Muhammad Hussain Magsi Shop to Bhutta Hotel U/C Kamber Taluka Kamber mile 0/0-1/6 (2.82 KMs). | 2.82 | 57.208 | 57.208 | -do- | Provincial ADP-1129 | Single Stage One Envelope Method | 14.302 | 14.302 | 14.302 | 14.302
14 | Construction of link road to village Lal Khan Magsi mile 0/0-1/0 Taluka Qubo Saeed Khan. | 1.6 | 11.961 | 11.961 | -do- | Provincial ADP-1129 | Single Stage One Envelope Method | 2.9903 | 2.9903 | 2.9903 | 2.9903
15 | Construction of link road to village Haji Ali Khan Magsi mile 0/0-0/5 Taluka Qubo Saeed Khan. | 1 | 8.019 | 8.019 | -do- | Provincial ADP-1129 | Single Stage One Envelope Method | 2.0048 | 2.0048 | 2.0048 | 2.0048
16 | Construction of link road to village Haji Kamber Magsi mile 0/0-0/5 Taluka Qubo Saeed Khan. | 1 | 7.911 | 7.911 | -do- | Provincial ADP-1129 | Single Stage One Envelope Method | 1.9777 | 1.9777 | 1.9777 | 1.9777
17 | Construction of link road from Wagan Chowk to By Pass imam Bargah to SP Chowk mile 0/0-0/6 Taluka Kamber. | 1.2 | 14.746 | 14.746 | -do- | Provincial ADP-1129 | Single Stage One Envelope Method | 3.6865 | 3.6865 | 3.6865 | 3.6865
18 | Construction of link road to Ghulam Shabir Chandio mile0/0-1/2 Taluka Shahdadkot. | 2 | 15.121 | 15.121 | -do- | Provincial ADP-1129 | Single Stage One Envelope Method | 3.7803 | 3.7803 | 3.7803 | 3.7803
19 | Construction of link road to village Arzi Markhand mile0/0-1/2 Taluka Shahdadkot. | 2 | 15.621 | 15.621 | -do- | Provincial ADP-1129 | Single Stage One Envelope Method | 3.9053 | 3.9053 | 3.9053 | 3.9053
20 | Reconditioning of road from Darya Khan Mastoi via Chakiyani to Dr Mehboob Shah village mile 0/0-3/0 Taluka Shahdadkot. | 4.7 | 23.889 | 23.889 | -do- | Provincial ADP-1129 | Single Stage One Envelope Method | 5.9722 | 5.9722 | 5.9722 | 5.9722
21 | Construction/Reconditioning road to village Umaid Ali Junejo Station road to Pir Mir Muhammad Shah mile 0/0-1/2 Taluka Shahdadkot. | 2 | 13.41 | 13.41 | -do- | Provincial ADP-1129 | Single Stage One Envelope Method | 3.3525 | 3.3525 | 3.3525 | 3.3525
22 | Construction of link road from Motorway to Dholyo Khoso mile 0/0-1/7 Taluka Qubo Saeed Khan. | 3.1 | 22.856 | 22.856 | -do- | Provincial ADP-1129 | Single Stage One Envelope Method | 5.714 | 5.714 | 5.714 | 5.714
23 | Construction of link road to Hakim Shah Shori Shakh Pasha Shah Muhammad Khuhro to village Ali Gohar Khoso mile 0/0-1/3 Taluka Miro Khan. | 2.2 | 17.887 | 17.887 | -do- | Provincial ADP-1129 | Single Stage One Envelope Method | 4.4718 | 4.4718 | 4.4718 | 4.4718
24 | Construction of link road to village Rais Ali Dost Aadmani mile 0/0-0/5 Taluka Shahdadkot. | 1 | 7.287 | 7.287 | -do- | Provincial ADP-1129 | Single Stage One Envelope Method | 1.8217 | 1.8217 | 1.8217 | 1.8217
25 | Construction of link road to village Ali Hassan Brohi Qalandrani mile 0/0-0/5 Taluka Qubo Saeed Khan. | 1 | 7.897 | 7.897 | -do- | Provincial ADP-1129 | Single Stage One Envelope Method | 1.9743 | 1.9743 | 1.9743 | 1.9743
26 | Construction of link road from Hayat Gopang to Tilan Jatoi road @ Point 0/5 to village Tilan Jatoi (Missing Length) mile 0/5-2/7 Taluka Sijawal. | 3.6 | 27.04 | 27.04 | -do- | Provincial ADP-1129 | Single Stage One Envelope Method | 6.76 | 6.76 | 6.76 | 6.76
27 | Construction of link road from Sirrai wah via village Luqman Siyal to village Ustad Ghulam Rasool Leghari mile 0/0-2/0 Taluka Shahdadkot. | 3.2 | 22.924 | 22.924 | -do- | Provincial ADP-1129 | Single Stage One Envelope Method | 5.731 | 5.731 | 5.731 | 5.731
28 | Reconditioning of road to village Baharo Gurgage mile 0/0-4/3 Taluka Shahdadkot. | 7 | 38.852 | 38.852 | -do- | Provincial ADP-1129 | Single Stage One Envelope Method | 9.713 | 9.713 | 9.713 | 9.713
29 | Construction of link road from Ghulam Mustafa Jarwar to Saifullah Magsi Branch mile 0/0-1/0 Taluka Qubo Saeed Khan. | 1.6 | 11.539 | 11.539 | -do- | Provincial ADP-1129 | Single Stage One Envelope Method | 2.8847 | 2.8847 | 2.8847 | 2.8847
30 | Construction of link road to village Mir Hassan Magsi Dahalkhani mile 0/5-1/2 Taluka Qubo Saeed Khan. | 1 | 7.844 | 7.844 | -do- | Provincial ADP-1129 | Single Stage One Envelope Method | 1.961 | 1.961 | 1.961 | 1.961
31 | Reconditioning of road from Imam Bux Jamali to Kot Chattu mile 0/0-2/4 Taluka Qubo Saeed Khan. | 4 | 20.462 | 20.462 | -do- | Provincial ADP-1129 | Single Stage One Envelope Method | 5.1155 | 5.1155 | 5.1155 | 5.1155
32 | Construction of link road from Abad Jani Bund road to village Thariri Hajiran, mile 1/5-2/1 (Remaining work) Taluka Warah. | 0.8 | 8.169 | 16.73 | 4 | ADP 111 | Single Stage One Envelope Method | 2.0423 | 2.0423 | 2.0423 | 2.0423
33 | Construction of link road from Miran Machi road to Qaim Khan Hasrani with Sim Shakh @ Meenhal Shakh mile 0/0-0/5 (Masonary Structure) Taluka Miro Khan. | 1 | 1.662 | 10 | 1.662 | ADP 153 | Single Stage One Envelope Method | 0.4155 | 0.4155 | 0.4155 | 0.4155
34 | Construction of link road from Shah Beg Shakh to Dayo-Jo-Goth, Kandio, Noorullah Khan, Choudhry Ramzan, Sobidar village and Zulifqar Karozie Goth mile 0/5-1/2 (Remaining work) Taluka Shahdadkot. | 1 | 7.5 | 15 | 0.05 | ADP 290 | Single Stage One Envelope Method | 1.875 | 1.875 | 1.875 | 1.875
35 | Construction of road from Shahdadkot Qubo Saeed Khan to village Mustafaabad with Tanwari Shakh via Khadim Hussain Langah via Shah Muhammad Seelro via Deepar village via Allah Dino Magsi mile 0/0-0/5 (Remaining work) Taluka Shahdadkot | 1 | 8.5 | 15 | 4.8 | ADP 309 | Single Stage One Envelope Method | 2.125 | 2.125 | 2.125 | 2.125
36 | Construction of Retaining Wall at link road from Dhing Allah Bux Leghari to Wasand-Ji-Wandh mile 0/0-1/0 Taluka Shahdadkot. | 1.6 | 1.5 | 7.5 | 3 | ADP 329 | Single Stage One Envelope Method | 0.375 | 0.375 | 0.375 | 0.375
37 | Construction of link road from Lohi Pull Shahdadkot road to village Chakar Sultan Rid mile 0/0-1/2 (Remaining work) Taluka Miro Khan. | 2 | 5 | 10.353 | 0.05 | ADP 339 | Single Stage One Envelope Method | 1.25 | 1.25 | 1.25 | 1.25
38 | Construction of link road from Lohi Pull Shahdadkot road to village Balouch Khan Mastoi mile 0/0-1/2 (Remaining work) Taluka Miro Khan. | 2 | 5 | 9.646 | 0.05 | ADP 340 | Single Stage One Envelope Method | 1.25 | 1.25 | 1.25 | 1.25
39 | Construction of link road from Gharhi Khairo road to Abdul Qadir Magsi, mile 0/5-1/2 (Remaining work) Taluka Shahdadkot. | 1 | 5.3 | 10.393 | 1.071 | ADP 388 | Single Stage One Envelope Method | 1.325 | 1.325 | 1.325 | 1.325
40 | Construction of Bridge at road from Motorway Zareen Petrol Pump to village Gul Hassan Brohi upto Sobho Kariro mile 0/0-0/5 (Bridge) Taluka Shahdadkot. | 1 | 1 | 5.284 | 1 | ADP 390 | Single Stage One Envelope Method | 0.25 | 0.25 | 0.25 | 0.25
41 | Construction of link road from Kamber Shahdadkot road to village Roshan Ali Khoso mile 0/3-0/5 (Remaining work) Taluka Miro Khan. | 1 | 4.5 | 3.7 | 0.05 | ADP 398 | Single Stage One Envelope Method | 1.125 | 1.125 | 1.125 | 1.125
42 | Construction of link road from Ayo Phulpoto road to village Ghulam Nabi Phulpoto mile 0/0-1/1 (Remaining work) Taluka Nasirabad. | 3 | 12.088 | 15 | 1 | ADP 380 | Single Stage One Envelope Method | 3.022 | 3.022 | 3.022 | 3.022
43 | Construction of link road from Ali Bux Panhwar to village Koreja mile 0/5-0/7 (Remaining work) Taluka Kamber. | 0.4 | 2.942 | 4.572 | 0.799 | ADP 391 | Single Stage One Envelope Method | 0.7355 | 0.7355 | 0.7355 | 0.7355
44 | Construction of Retaining Wall (540'Rft) at link road from Miro Khan road to Hasulla Shakh to Ibrahim Magsi village to Sher Ali Mugheri mile 0/0-0/6 (Retaining Wall 540'Rft) Taluka Kamber. | 1.2 | 2.478 | 7.044 | 2.2 | ADP 371 | Single Stage One Envelope Method | 0.6195 | 0.6195 | 0.6195 | 0.6195
45 | Construction of link road from Miro Khan Kot Lahori road to village Mukhtiar Ali Magsi mile 0/0-1/4 Taluka Miro Khan. | 2.4 | 27 | 0 | 0 | Non-ADP | Single Stage One Envelope Method | 6.75 | 6.75 | 6.75 | 6.75
46 | Construction of link road from Tanwari Shakh to village Haji Ashaque Ali Khan Mugheri mile 0/0-0/2 Taluka Shahdadkot. | 0.4 | 4.8 | 0 | 0 | Non-ADP | Single Stage One Envelope Method | 1.2 | 1.2 | 1.2 | 1.2
47 | Construction of link road from Miro Khan Mehmoodabad road to village Ghulam Umer Jatoi via Ali Nawaz Jagirani to connect Arzi Bhutto mile 0/0-1/4 Taluka Miro Khan. | 2.4 | 20 | 0 | 0 | Non-ADP | Single Stage One Envelope Method | 5 | 5 | 5 | 5
48 | Reconditioining of road from Kamber Ghaibi Dero road to village Phall Qaim Khan Shaikh mile 0/0-1/2 Taluka Kamber. | 2 | 10.872 | 0 | 0 | Non-ADP | Single Stage One Envelope Method | 2.718 | 2.718 | 2.718 | 2.718
49 | Construction of link road from Imam Bux road to village Abdul Wahab Khoso mile 0/0-0/2 Taluka Shahdadkot. | 0.4 | 3.789 | 0 | 0 | Non-ADP | Single Stage One Envelope Method | 0.94725 | 0.94725 | 0.94725 | 0.94725
50 | Construction of Bridge along Kamber Shahdadkot road to village Mir Niaz Ali Khoso near 5LA Sim Drain Taluka Miro Khan. | 0 | 1 | 0 | 0 | Non-ADP | Single Stage One Envelope Method | 0.25 | 0.25 | 0.25 | 0.25
51 | Construction of link road at village Abdul Wahab Khoso mile 400'ft Taluka Shahdadkot. | 0.1 | 1 | 0 | 0 | Non-ADP | Single Stage One Envelope Method | 0.25 | 0.25 | 0.25 | 0.25
52 | Construction of link road from Miro Khan Behram road to village Meharullah Brohi mile 0/0-0/1+200'. | 0.26 | 2 | 2 | 2 | ADP No.55 | Single Stage One Envelope Method | 0.5 | 0.5 | 0.5 | 0.5
53 | Construction of link road from Miro Khan Behram road to village Lal Bux Leghari mile 0/0-0/1+330'. | 0.3 | 2.5 | 2.5 | 2.5 | ADP No.55 | Single Stage One Envelope Method | 0.625 | 0.625 | 0.625 | 0.625
54 | Construction of damaged Bridges/Retaining Walls along Construction of Retaining Wall (340'Rft) along Kamber Miro Khan road to village Hasulla via Kot Ghulam Shah. | - | 2.144 | 2.144 | 1.4 | ADP No.23 | Single Stage One Envelope Method | 0.536 | 0.536 | 0.536 | 0.536
55 | Construction of link road from Warah Khandoo road to village Noorabad Jakhar Union Council Khandoo Taluka Warah mile 0/0-1/2 (ADP Program 2015-2016). | 2 | 19.7 | 20 | 5 | ADP Program | Single Stage One Envelope Method | 4.925 | 4.925 | 4.925 | 4.925
56 | Reconditioning/Raising portion of road from Qubo Main chowk Imam Bux via Muhammad Baqar Brohi (City portion) mile 0/0-0/5 i/c Masonry Structure (ADP Program 2015-2016). | 1 | 19.973 | 20 | 5 | ADP Program | Single Stage One Envelope Method | 4.9932 | 4.9932 | 4.9932 | 4.9932
57 | Reconditioning of link road from Thorhi Bijar road to Khair Muhammad Kartio mile 0/0-1/2 (but actual length upto village Khairo Muhammad Kartio mile 0/0-3/4) (ADP Program 2015-2016). | 2 | 10 | 10 | 2.5 | ADP Program | Single Stage One Envelope Method | 2.5 | 2.5 | 2.5 | 2.5
58 | Widening/Reconditioning of road from Phatak to Shell Petrol Pump Asphalt road (total length 0/0-0/5 = 1.0 KM) mile 0/0-0/1+340' = 1000'ft) (ADP Program 2015-2016). | 0.3 | 5 | 5 | 1.25 | ADP Program | Single Stage One Envelope Method | 1.25 | 1.25 | 1.25 | 1.25
59 | Construction of link road from Sijawal Miro Khan to village Muhammad Hassan Magsi, mile 0/0-0/2 (ADP No.188). | 0.4 | 3.639 | 4 | 0.05 | ADP No.188 | Single Stage One Envelope Method | 0.90975 | 0.90975 | 0.90975 | 0.90975
60 | Construction of Mettaled road from for a Lakha Bridge to village Gopang on the Top of Nasir Branch via Sahel Mugheri village mile 0/0-0/2+330’ (ADP No.450). | 0.5 | 4.489 | 4 | 0.05 | ADP No.450 | Single Stage One Envelope Method | 1.1222 | 1.1222 | 1.1222 | 1.1222
61 | Construction of link road from Bakho Khuhawar to 7th mile road to Badwani Khuhawar i/c Masonry Structure mile 0/0-0/2+330' (ADP No.22). | 0.4 | 6.308 | 6.35 | 0.5 | ADP No.22 | Single Stage One Envelope Method | 1.577 | 1.577 | 1.577 | 1.577
62 | Construction of Retainng Wall (270'Rft) along Reconditioning of road from Dost Ali road to villaege Walildad Mugheri mile 0/0-0/5. | - | 1.7 | 1.7 | 1.5 | ADP No.253 | Single Stage One Envelope Method | 0.425 | 0.425 | 0.425 | 0.425
62 | Construction of Damaged Bridges/Culverts and Retaining Walls in District Kamber-Shahdadkot (Construction of Retaining Wall 300'rft along Haji Allahyar Mastoi road @ mile 1/0). | - | 1.613 | 10 | 1.4 | ADP No.23 | Single Stage One Envelope Method | 0.40325 | 0.40325 | 0.40325 | 0.40325
63 | Construction of Damaged Bridges/Culverts and Retaining Walls in District Kamber-Shahdadkot (Construction of Bridge at Qubo Shakh @ Ahmed Nawaz Khuahwar Tangra Ahmed Nawaz Khuhawar Taluka Qubo Saeed Khan). | - | 0.873 | 10 | 1.4 | ADP No.23 | Single Stage One Envelope Method | 0.21825 | 0.21825 | 0.21825 | 0.21825
Executive Engineer
Highways Division
Kamber-Shahdadkot