## G Abstract for revised
GENERAL ABSTRACT
NAME OF WORK:- CONSTRUCTION OF CATAGARY -II BUNGLALOWS FOR GRADE 18 & 19 @ B&R COLONY DISTRICT T.M.KHAN (BUNGLALOW 01 NO) ( EXT: DEVELOPMENT).
REVISED ESTIMATE
S.No. | Name of Components | As per Technical Saction |  | As Per Work Done |  | Work To Be Done
1 | Part-A "Main Bldg" Total Amount | 4488818.2 | /= | 4333995.9295 | /= | 1656354.4267 | /=
2 | Part-B "W/S & S/F" | 98965.064 | /= | 106370.5612 | /= | 100004.3857 | /=
3 | Part-C "External Drainage" | 97016.192 | /= | 114348.6053 | /= | 213211.283 | /=
4 | Part-D " Non-Schedule Items" | 144553 | /= | 144556 | /= | 0 | /=
| Total | 4829352.456 | /= | 4317552.78 | /= | 1969570.0954 | /=
|  |  |  | G.Total |  | 6287122.8754 | /=
| SUB-ENGINEER | ASSISSTANT ENGINEER |  |  | EXECUTIVE ENGINEER
| BUILDINGS SUB-DIVISION | BUILDINGS SUB-DIVISION |  |  | BUILDINGS DIVISION
| TANDO MOHAMMAD KHAN | TANDO MOHAMMAD KHAN |  |  | TANDO MOHAMMAD KHAN

## Part A Sheet
NAME OF WORK:-. CONSTRUCTION OF CATAGARY -II BANGLOWS FOR GRADE 18 & 19 @ B & R COLONY DISTRICT T.M.KHAN (EXT: DEVELOPMENT).
PART-A "MAIN BUILDING (CIVIL WORK)"
S. No. | Name of Items | As per Technical Sanction |  |  |  |  | As Per Site Work Done |  |  |  |  | Work To Be Done |  |  |  |  | Remarks
|  | Qty | Rate | Unit | Amount |  | Qty | Rate | Unit | Amount |  | Qty | Rate | Unit | Amount
01 | 02 | 03 | 04 | 05 | 06 |  | 07 | 08 | 09 | 10 |  | 11 | 12 | 13 | 14 |  | 16
PART (A-i) CIVIL WORKS "MAIN BUILDINGS"
01. | Excavation in foundation.. | 3495 | 3176.25 | %OCft | 11101 |  | 4224 | 3176.25 | %OCft | 13416.48 |  | 0 | 3176.25 | %OCft | 0
02. | C.C.Brick/Stone (1:4:8)… | 874 | 9416.28 | %Cft | 82298 |  | 1057 | 9416.28 | %Cft | 99530.0796 |  | 0 | 9416.28 | %Cft | 0
03. | P.B.Work (1:6) in foundation… | 962 | 11948.36 | %Cft | 114943 |  | 1132 | 11948.36 | %Cft | 135255.4352 |  | 0 | 11948.36 | %Cft | 0
04. | C.C.Plain (1:3:6)… | 1643 | 5001.7 | %Cft | 82178 |  | 2076 | 5001.7 | %Cft | 103835.292 |  | 0 | 12595 | %Cft | 157637
05. | Erection and removing… | 2969 | 1610 | %Sft | 47823 |  | 2901 | 1610 | %Sft | 46706.1 |  | 0 | 7000 | %Sft | 156363.9
06. | Filling Surplus earth… | 2327 | 1512.5 | %OCft | 3520 |  | 2507 | 1512.5 | %OCft | 3791.8375 |  | 0 | 1512.5 | %OCft | 0
07. | Filling new earth… | 2412 | 3630 | %OCft | 8756 |  | 3126 | 3630 | %OCft | 11347.38 |  | - | 3630 | - | -
08. | S/F Sand under floor & plugging….. | 804 | 1141.25 | %OCft | 917 |  | 0 | 1141.25 | %OCft | 0 |  |  | 1141.25
09. | R.C.C (1:2:4)… | 1764 | 337 | P.Cft | 594468 |  | 2293.65 | 337 | P.Cft | 772960.05 |  | 97.3125 | 337 | P.Cft | 32794.3125
10. | Feb:of mild steel… | 89.7 | 5001.7 | P.Cwt | 448652 |  | 94.5 | 5001.7 | P.Cwt | 472660.65 |  | 3.7624 | 5001.7 | P.Cwt | 18818.2599
11. | C.C.Brick/Stone (1:5:10).. | 133 | 8694.95 | %Cft | 11564 |  | 583 | 8694.95 | %Cft | 50691.5585 |  | 0 | 8694.95 | %Cft | 0
12. | P.B.Work (1:6) G/Floor… | 3922 | 12674.36 | %Cft | 497088 |  | 4101 | 12674.36 | %Cft | 519775.5036 |  | - | 12674.36 | - | -
13. | P/F G.I. Frame Chowkatha Door… | 314 | 228.9 | P.Rft | 71874.6 |  | 255.5 | 228.9 | P.Rft | 58483.95 |  | - | 228.9 | - | -
14. | P/F G.I. Frame Chowkatha Windows… | 444.63 | 240.5 | P.Rft | 106933.52 |  | 523 | 240.5 | P.Rft | 125781.5 |  | - | 240.5 | - | -
15. | White Marble Flooring 3/4" thick | 1390 | 567.48 | P.Sft | 788797 |  | 1549 | 567.48 | P.Sft | 879026.52 |  | 0 | 567.48 | P.Sft | 0
16. | P/F 3/8" Marble tiles… | 206 | 186.04 | P.Sft | 38324 |  | 296 | 186.04 | P.Sft | 55067.84 |  | 0 | 186.04 | P.Sft | 0
17. | L/F of approved Glazed Tile…. | 294 | 27678.86 | %Sft | 81376 |  | 280 | 27678.86 | %Sft | 77500.808 |  | - | 27678.86 | - | -
18. | White Glazed tile dado…. | 591 | 28253.61 | %Sft | 166978 |  | 587 | 28253.61 | %Sft | 165848.6907 |  | 0 | 28253.61 | %Sft | 0
19. | C.Plaster 1/2"thick ratio(1:6) | 7548 | 2206.6 | %Sft | 166554 |  | 9810 | 2206.6 | %Sft | 216467.46 |  | - | 2206.6 | - | -
20. | C.Plaster 3/8" thick ratio(1:4)… | 5864 | 2197.52 | %Sft | 128862 |  | 7612 | 2197.52 | %Sft | 167275.2224 |  | 2080.31 | 2197.52 | %Sft | 45715.2283
21. | Cement Pointing Struck jointing…. | 2903 | 1287.44 | %Sft | 38533 |  | 0 | 1287.44 | %Sft | 0 |  |  | 1287.44
22. | 1st class deodar wood wire gauze 3/4" | 228 | 454.19 | P.Sft | 103555 |  | 228 | 454.19 | P.Sft | 41154 |  | 111 | 454.19 | P.Sft | 50415.09
23. | 1st class deodar wood wire gauze 1-1/2" | 49 | 562.98 | P.Sft | 27586 |  | 49 | 562.98 | P.Sft | 27586.02 |  | 24.5 | 562.98 | P.Sft | 13793.01
24. | 1st class deodar wood wrought,joinery… | 756 | 1131.11 | P.Sft | 855119.16 |  | 587 | 1131.11 | P.Sft | 663961.57 |  | 0 | 1273.76 | P.Sft | 0
| 1st Calass deodar wooden wardrobe…. |  | 2364.63 | P.Sft |  |  |  | 2364.63 | P.Sft |  |  | 110.5447 | 2364.63 | P.Sft | 261397.314
| Colour glazed tiles… | 0 | 30509.77 | %Sft |  |  |  | 30509.77 | %Sft |  |  | 169.2975 | 30509.77 | %Sft | 51652.2779
25. | Primary coat of chalk under distm: | 7548 | 442.75 | %Sft | 33419 |  | 0 | 442.75 | %Sft | 0 |  | 11736.81 | 442.75 | %Sft | 51964.7263
26. | White washing three coats…. | 501 | 829.95 | %Sft | 4158 |  | 0 | 829.95 | %Sft | 0 |  | 2594.5942 | 829.95 | %Sft | 21533.8346
27. | Distempering 2 coats with 1st coat.. | 7548 | 1043.9 | %Sft | 78794 |  | 0 | 1043.9 | %Sft | 0 |  | 11736.81 | 1043.9 | %Sft | 122520.5596
28. | Painting doors & windows any type 3.. | 1513 | 1489.68 | %Sft | 22539 |  | 0 | 1489.68 | %Sft | 0 |  | 1174 | 1489.68 | %Sft | 17488.8432
29. | P/L 2" thick C.C.topping… | 1189 | 3275.5 | %Sft | 38946 |  | 1547 | 3275.5 | %Sft | 50671.985 |  | 1943.4014 | 3275.5 | %Sft | 63656.1129
30. | Two coats of bitumen laid hot 34 lbs/squire inch… | 0 | 1887.4 | %Sft | 0 |  | 0 | 1887.4 | %Sft | 0 |  | 3361 | 1887.4 | %Sft | 63435.514
31. | P/F iron steel grills using solid square bars.. | 228 | 180.5 | P.Sft | 41154 |  | 0 | 180.5 | P.Sft | 0 |  | 339 | 180.5 | P.Sft | 61189.5
32. | RCC Spouts including fixing…. | 6 | 161.45 | Each | 969 |  | 6 | 161.45 | Each | 968.7 |  |  | 261.25
33. | S/F Window printed blinds…. | 156 | 91.11 | P.Sft | 14213 |  | 0 | 91.11 | P.Sft | 0 |  |  | 91.11
| Total |  |  |  | 4711968 | /= |  |  |  | 4759764.6325 | /= |  |  |  | 1190375.483 | /=
| Add Amount of Cartage |  |  |  | 212425 | /=
| Deduct 20% Below (-) |  |  |  | 942394 | /= | Deduct 16.00% (-) |  |  | 761562.3412 | /= | Deduct 16.00% (-) |  |  | 190460.0773 | /=
| Add 3% Contigency |  |  |  | 75391 | /=
| Total Amount |  |  |  | 4057390 | /= |  |  |  | 3998202.2913 | /= |  |  |  | 999915.4057 | /=
[7 empty] | Grand Total |  | 4998117.697
PART (A-ii) CIVIL WORKS "COURT YARD WALL"
01. | Excavation in foundation.. | 856 | 3176.25 | %OCft | 2719 |  | 1043 | 3176.25 | %OCft | 3312.8288 |  | 792 | 3176.25 | %OCft | 2515.59
02. | C.C.Brick/Stone (1:4:8)… | 285 | 9416.28 | %Cft | 26836 |  | 261 | 9416.28 | %Cft | 24576.4908 |  | 740.29 | 9416.28 | %Cft | 69707.7792
03. | P.B.Work (1:6) in foundation… | 302 | 11948.36 | %Cft | 36084 |  | 391 | 11948.36 | %Cft | 46718.0876 |  | 223.74 | 11948.36 | %Cft | 26733.2607
04. | C.C.Plain (1:3:6)… | 401 | 5001.7 | %Cft | 20057 |  | 386 | 5001.7 | %Cft | 19306.562 |  | 297 | 12595 | %Cft | 66717.288
05. | Erection and removing… | 1069 | 1610 | %Sft | 17211 |  | 1031 | 1610 | %Sft | 16599.1 |  | 792 | 7000 | %Sft | 111010.9
06. | P.B.Work other than buildings (1:6) … | 486 | 12346.65 | %Cft | 60005 |  | 554 | 12346.65 | %Cft | 68400.441 |  | 512.82 | 12346.65 | %Cft | 63316.0905
07. | M/F Steel grated door… | 60 | 594.57 | P.Sft | 35674 |  | 0 | 594.57 | P.Sft | 0 |  | 84.5 | 594.57 | P.Sft | 50241.165
08. | C.Plaster 1/2"thick ratio(1:6) | 903 | 2206.6 | %Sft | 19925 |  | 1120 | 2206.6 | %Sft | 24713.92 |  | 5255.4651 | 2206.6 | %Sft | 115967.0929
09. | C.Plaster 3/4" thick ratio(1:4)… | 903 | 2590.5 | %Sft | 23392 |  | 1120 | 2590.5 | %Sft | 29013.6 |  | 5255.4651 | 2590.5 | %Sft | 136142.8234
10. | Cement Pointing Struck jointing…. | 903 | 1287.44 | %Sft | 5827 |  | 0 | 1287.44 | %Sft | 0 |  | 0 | 1287.44 | %Sft | 0
11. | C.C.Topping 2" thick |  | 3275.5 | %Sft |  |  |  | 3275.5 | %Sft |  |  | 1084.58 | 3275.5 | %Sft | 35525.4179
12. | Colour Washing two coats… | 903 | 859.9 | %OCft | 7765 |  | 0 | 859.9 | %OCft | 0 |  | 6303.5222 | 859.9 | %Sft | 54203.9874
13. | Painting guard bars…. | 120 | 584.54 | P.Sft | 701 |  | 0 | 584.54 | P.Sft | 0 |  | 84.5 | 584.54 | P.Sft | 49393.63
| Total |  |  |  | 256196 | /= |  |  |  | 232641.0301 | /= |  |  |  | 781475.025 | /=
| Add Amount of Cartage |  |  |  | 408052 | /=
| Deduct 20% Below (-) |  |  |  | 51239 | /= | Deduct 16.00% (-) |  |  | 37222.5648 | /= | Deduct 16.00% (-) |  |  | 125036.004 | /=
| Total Amount |  |  |  | 245808 | /= |  |  |  | 195418.4653 | /= |  |  |  | 656439.021 | /=
[7 empty] | Grand Total |  | 851857.4863
PART (A-iii) CIVIL WORKS "PAVED COURT YARD"
01. | S/F Filling sand under floor…. | 242 | 1141.25 | %OCft | 276 |  | 241 | 1141.25 | %OCft | 275.0412 |  | 0 | 3176.25 | %OCft | 0
02. | C.C.Brick/Stone (1:4:8)… | 203 | 9416.28 | %Cft | 19115 |  | 241 | 9416.28 | %Cft | 22693.2348 |  | 0 | 9416.28 | %Cft | 0
03. | P/L C.C Topping 2" thick…. | 505 | 3275.5 | %Cft | 16541 |  | 657 | 3275.5 | %Cft | 21520.035 |  | 0 | 3275.5 | %Cft | 0
| Total |  |  |  | 35932 | /= |  |  |  | 44488.311 | /= |  |  |  | 0 | /=
| Add Amount of Cartage |  |  |  | 10739 | /=
| Deduct 20% Below (-) |  |  |  | 7186 | /= | Deduct 16.00% (-) |  |  | 7118.1298 | /= | Deduct 16.00% (-) |  |  | 0 | /=
| Total Amount |  |  |  | 39485 | /= |  |  |  | 37370.1813 | /= |  |  |  | 0 | /=
[7 empty] | Grand Total |  | 37370.1813
PART (A-iv) CIVIL WORKS "UNDER GROUND TANK"
01. | Excavation in foundation.. | 840 | 3176.25 | %OCft | 2668.05 |  | 0 | 3176.25 | %OCft | 0 |  | 0 | 3176.25 | %OCft | 0
02. | C.C.Brick/Stone (1:4:8)… | 63 | 9416.28 | %Cft | 5932.25 |  | 0 | 9416.28 | %Cft | 0 |  | 0 | 9416.28 | %Cft | 0
03. | R.C.C (1:2:4)… | 311 | 337 | P.Cft | 104807 |  | 356.28 | 337 | P.Cft | 120066.36 |  | 0 | 337 | P.Cft | 0
04. | Feb:of mild steel… | 12.45 | 5001.7 | P.Cwt | 62271.16 |  | 0 | 5001.7 | P.Cwt | 0 |  | 0 | 5001.7 | P.Cwt | 0
05. | P/L C.C Topping 2" thick…. | 50 | 3275.5 | %Cft | 1637.75 |  | 60 | 3275.5 | %Cft | 1965.3 |  | 0 | 3275.5 | %Cft | 0
06. | C.Plaster 3/8" thick ratio(1:4)… | 300 | 2197.52 | %Sft | 6592.56 |  | 27 | 2197.52 | %Sft | 593.33 |  | 0 | 2197.52 | %Sft | 0
| Total |  |  |  | 182669 | /= |  |  |  | 122624.99 | /= |  |  |  | 0 | /=
| Add Amount of Cartage |  |  |  | 0 | /=
| Deduct 20% Below (-) |  |  |  | 36533.8 | /= | Deduct 16.00% (-) |  |  | 19619.9984 | /= | Deduct 16.00% (-) |  |  | 0 | /=
| Total Amount |  |  |  | 146135.2 | /= |  |  |  | 103004.9916 | /= |  |  |  | 0 | /=
[7 empty] | Grand Total |  | 103004.9916
[9 empty] | Technical Sanction |  |  | Work Done |  | Work To Be Done
|  | PART (A-i) CIVIL WORK "MAIN BUILDING" | [7 empty] | 4057390 | /= | 3998202.2913 |  | 999915.4057 |  | /=
|  | PART (A-ii) CIVIL WORK "COURT YARD WALL" | [7 empty] | 245808 | /= | 195418.4653 |  | 656439.021 |  | /=
|  | PART (A-iii) CIVIL WORK "PAVED COURT YARD" | [7 empty] | 39485 | /= | 37370.1813 |  | 0 |  | /=
|  | PART (A-iv) CIVIL WORK "UNDER GROUND TANK" | [7 empty] | 146135.2 | /= | 103004.9916 |  | 0 |  | /=
|  | TOTAL AMOUNT OF PART A | [7 empty] | 4488818.2 | /= | 4333995.9295 |  | 1656354.4267 |  | /=
| SUB-ENGINEER |  |  |  | ASSISSTANT ENGINEER | [6 empty] | EXECUTIVE ENGINEER
| BUILDINGS SUB-DIVISION |  |  |  | BUILDINGS SUB-DIVISION | [6 empty] | BUILDINGS DIVISION
| TANDO MOHAMMAD KHAN |  |  |  | TANDO MOHAMMAD KHAN | [6 empty] | TANDO MOHAMAD KHAN

## Part B Sheet
NAME OF WORK:-. REVISED ESTIMATE OF CONSTRUCTION OF CATAGARY-II BANGLOWS FOR GRADE 18 & 19 @ B & R COLONY DISTRICT T.M.KHAN
PART-B "WATER SUPPLY & SANATERY FITTING"
S. No. | Name of Items | As per Technical Sanction |  |  |  |  | As Per Site Work Done |  |  |  |  | Work To Be Done
|  | Qty | Rate | Unit | Amount |  | Qty | Rate | Unit | Amount |  | Qty | Rate | Unit | Amount
01. | P/F Orisa type W.C….. | 3 | 12003.2 | Each | 36009.6 |  | 3 | 12003.2 | Each | 36009.6 |  | 0 | 12003.2 | Each | 0
02. | P/F Europeon type W.C…. | 1 | 2594.9 | Each | 2594.9 |  | 1 | 2594.9 | Each | 2594.9 |  | 0 | 11477.4 | Each | 8882.5
03. | P/F Lavatory Wash basin…. | 3 | 2229.15 | Each | 6687.45 |  | 4 | 2229.15 | Each | 8916.6 |  | 0 | 4253.9 | Each | 8099
04. | Add Extra for labour for wash basin…. | 3 | 1131.55 | Each | 3394.65 |  | 4 | 1131.55 | Each | 4526.2 |  | 0 | 938.47 | Each | -772.32
05. | P/F Steel Sink stainless…. | 1 | 1561.45 | Each | 1561.45 |  | 1 | 1561.45 | Each | 1561.45 |  | 0 | 5162.3 | Each | 3600.85
06. | P/F Nyloon Connection…. | 6 | 447.15 | Each | 2682.9 |  | 6 | 447.15 | Each | 2682.9 |  | 0 | 447.15 | Each | 0
07. | P/F M.S clamps…. | 18 | 72.16 | Each | 1298.88 |  | 18 | 72.16 | Each | 1298.88 |  | 0 | 72.16 | Each | 0
08. | P/F 6" x 4" C.C. Gully Trap….. | 4 | 316.7 | Each | 1266.8 |  | 4 | 316.7 | Each | 1266.8 |  | 0 | 1259.5 | Each | 3771.2
09. | G.I. Pipe…
| (a) 1/2" dia pipe | 250 | 73.21 | P.Rft | 18302.5 |  | 325 | 73.21 | P.Rft | 23793.25 |  | 0 | 73.21 | Rft | 0
| (b) 3/4" dia pipe | 300 | 34.4 | P.Rft | 10320 |  | 390 | 34.4 | P.Rft | 13416 |  | 0 | 95.79 | P.Rft | 23942.1
| (c) 1" dia pipe | 150 | 46.5 | P.Rft | 6975 |  | 195 | 46.5 | P.Rft | 9067.5 |  | 0 | 128.55 | P.Rft | 15999.75
10. | Add Extra labour for concealed G.I pipe..
| (a) 1/2" dia pipe | 250 | 3.6 | P.Rft | 900 |  | 325 | 3.6 | P.Rft | 1170 |  | 0 | 7.82 | P.Rft | 1371.5
| (b) 3/4" dia pipe | 300 | 8.85 | P.Rft | 2655 |  | 390 | 8.85 | P.Rft | 3451.5 |  | 0 | 8.45 | P.Rft | -156
| (c) 1" dia pipe | 150 | 4.3 | P.Rft | 645 |  | 195 | 4.3 | P.Rft | 838.5 |  | 0 | 9.96 | P.Rft | 1103.7
11. | P/F handle valves…
| (a) 1/2" dia pipe | 4 | 75.45 | Each | 301.8 |  | 4 | 75.45 | Each | 301.8 |  | 0 | 200.42 | Each | 499.88
| (b) 3/4" dia pipe | 2 | 102.95 | Each | 205.9 |  | 2 | 102.95 | Each | 205.9 |  | 0 | 271.92 | Each | 337.94
| (c) 1" dia pipe | 2 | 146.95 | Each | 293.9 |  | 2 | 146.95 | Each | 293.9 |  | 0 | 365.42 | Each | 436.94
12. | S/F Concealed Stop Cock of 1/2" dia… | 12 | 252.1 | Each | 3025.2 |  | 12 | 252.1 | Each | 3025.2 |  | 0 | 509.74 | Each | 3091.68
13. | S/F Long bib cock 1/2" dia…. | 10 | 1384.24 | Each | 13842.4 |  | 10 | 1384.24 | Each | 13842.4 |  | 0 | 1384.24 | Each | 0
14. | S/F Jet Shower with rod 1/2" dia…. | 4 | 197.1 | Each | 788.4 |  | 4 | 197.1 | Each | 788.4 |  | 0 | 1142.24 | Each | 3780.56
15. | S/F Bath room accessories (7-pieces)… | 3 | 2578.2 | Each | 7734.6 |  | 3 | 2578.2 | Each | 7734.6 |  | 0 | 10322.4 | Each | 23232.6
16. | S/F Concealed tee stop cock 1/2" dia… | 10 | 222 | Each | 2220 |  | 10 | 222 | Each | 2220 |  | 0 | 889.46 | Each | 6674.6
17 | P/F Water pump 1 H.P….. | 0 | 22691.35 | Each | 0 |  | 0 | 22691.35 | Each | 0 |  | 1 | 22691.35 | Each | 22691.35
| Total |  |  |  | 123706.33 | /= |  |  |  | 134646.28 | /= |  |  |  | 126587.83 | /=
| Deduct 20% below |  |  |  | 24741.266 | /= | Deduct 21% below |  |  | 28275.7188 | /= | Deduct 21% below |  |  | 26583.4443 | /=
| Total Amount |  |  |  | 98965.064 | /= | Total Amount |  |  | 106370.5612 | /= |  |  |  | 100004.3857 | /=
NON-SCHEDULE ITEMS
01. | P/F UPV floor trap…. | 8 | 1155 | Each | 9240 |  | 8 | 1155 | Each | 9240 |  | 0 | 1155 | Each | 0
02. | P/F 4"x4" UPV branch… | 8 | 2174 | Each | 17392 |  | 8 | 2174 | Each | 17392 |  | 0 | 2174 | Each | 0
03 | P/F UPV 4"x4" plain branch…. | 8 | 2623 | Each | 20984 |  | 8 | 2623 | Each | 20984 |  | 0 | 2623 | Each | 0
04. | P/F UPV Plug bend… | 8 | 2558 | Each | 20464 |  | 8 | 2558 | Each | 20464 |  | 0 | 2558 | Each | 0
05. | P/F UPV Plain bend…. | 8 | 2182 | Each | 17456 |  | 8 | 2182 | Each | 17456 |  | 0 | 2182 | Each | 0
06. | P/F UPV pipe 4" dia…. | 130 | 454 | Each | 59020 |  | 130 | 454 | Each | 59020 |  | 0 | 454 | Each | 0
| Total Amount |  |  |  | 144553 | /= |  |  |  | 144556 | /= |  |  |  | 0 | /=
Part-D External Drainage & Water Supply
01. | Excavation for pipe… | 1080 | 2032.8 | %Cft | 21954.24 |  | 624 | 2032.8 | %Cft | 12684.672 |  | 1200 | 2032.8 | %Cft | 24393.6
| Boring….. | 0 | 91.85 | %Cft | 0 |  | 0 | 91.85 | %Cft | 0 |  | 90 | 91.85 | %Cft | 8266.5
02. | Providing R.C.C pipe with Collar (B)… | [10 empty] | - | - | - | -
| (a) 6" dia RCC pipe | 70 | 72.4 | P.Rft | 5068 |  | 91 | 72.4 | P.Rft | 6588.4 |  | 0 | 163 | P.Rft | 8244.6
| (b) 9" dia RCC pipe | 50 | 115.2 | P.Rft | 5760 |  | 65 | 115.2 | P.Rft | 7488 |  | 300 | 163 | P.Rft | 52007
03. | Construction of main hole…. | 6 | 14748 | Each | 88488 |  | 8 | 14748 | Each | 117984 |  | 12 | 14748 | Each | 176976
| Total |  |  |  | 121270.24 | /= |  |  |  | 144745.07 | /= |  |  |  | 269887.7 | /=
| Deduct 20% below |  |  |  | 24254.048 | /= | Deduct 21% below |  |  | 30396.4647 | /= | Deduct 21% below |  |  | 56676.417 | /=
| Total Amount |  |  |  | 97016.192 | /= | Total Amount |  |  | 114348.6053 | /= |  |  |  | 213211.283 | /=
|  | PART-B | [7 empty] | 106370.5612 | /= |  |  |  | 100004.3857 | /=
|  | NON-SCHEDULE ITEMS | [7 empty] | 144556 | /= |  |  |  | 0 | /=
|  | Part-C | [7 empty] | 114348.6053 | /= |  |  |  | 213211.283 | /=
[7 empty] | Total Amount |  |  | 365275.1665 | /= | Total Amount |  |  | 313215.6687 | /=
[7 empty] | GRAND TOTAL AMOUNT |  |  |  |  | 678490.8352
| SUB-ENGINEER |  |  |  | ASSISSTANT ENGINEER | [6 empty] | EXECUTIVE ENGINEER
| BUILDINGS SUB-DIVISION |  |  |  | BUILDINGS SUB-DIVISION | [6 empty] | BUILDINGS DIVISION
| TANDO MOHAMMAD KHAN |  |  |  | TANDO MOHAMMAD KHAN | [6 empty] | TANDO MOHAMAD KHAN

## (R)Abstract Sheet
SCHEDULE "B"
NAME OF WORK:- CONSTRUCTION OF CATAGARY -II BUNGLALOWS FOR GRADE 18 & 19 @ B&R COLONY DISTRICT T.M.KHAN (BUNGLALOW 01 NO) ( EXT: DEVELOPMENT).
S.No. | Name of Items | Quantity |  | Rate (Rs.) | Unit | Amount (Rs.)
PART-A "MAIN BUILDINGS"
01 | RCC work 1:2:4 i/c all labour and material except the cost of steel reinf: & its labour for bending & binding which will be paid separately. This rate also i/cs all kinds of forms moulds lifting shuttering curing rendering and finishing the exposed surface (i/c screening & washing of shingle) (a) RCC work in roof slabs beams, coloumns, rafts lintels and other structural members laid in situ or precast laid in position complete in all respects.(SI No:6(a) P-18/19) | 97 | Cft | 337 | P.Cft | 32689
02 | Cement plaster 1:4 upto 20'ft: height 3/8" thick.(S.I.No:11(a)/P-58) | 2080 | Sft. | 2197.52 | %Sft. | 45708.416
03 | C.C plain i/c placing compacting finishing & curing complete (i/c screening & washing of stone aggregate without shuttering) ratio 1:3:6 (SI No:5(h)/P-15) | 2076 | Cft | 12595 | %Cft | 261472.2
04 | Ist: class deodar wood wrought, joinery work in wire gauze doors & windows with 22-SWG.Galvanized wire gauze 144-mesh per square inch iron fittings complete. (b) 1-1/2" thick deodar wood framming i/c wire gauze with spring hinges.(S.I.No:14(b) /P-58) | 25 | Sft. | 562.98 | P.Sft. | 14074.5
05 | P/F Deodar wooden wardrobe i/c boxing with backe sheleves, shaters, drawers, & brass fittings such as hendles locking arrangement henger rode, shoe rode and mirror measuring 2' x 1' complete as per approved design (S.I.No. 24/ P.No. 60). | 111 | Sft. | 2364.63 | P.Sft. | 262473.93
06 | Primary coat of chalk under distemper. (S.I.No:23/P-59) | 9839 | Sft. | 442.75 | %Sft. | 43562.1725
07 | White washing three coats (S.I.No.26 (c) /P-53) | 2595 | Sft. | 829.95 | %Sft. | 21537.2025
08 | Distempering two coats with 1st coat over primary coat 3 coats (S.I.No.24 a+b /P-60) | 9839 | Sft. | 1043.9 | %Sft. | 102709.321
09 | PNS & Painting of doors & windows any type (i/c edges) 3-coats (SI No:76(c) P.77) | 1174 | Sft. | 2116.41 | %Sft. | 24846.6534
10 | Providing & laying 1" thick topping cement concrete (1:2:4) i/c surface finishing & dividing into panels. (S.I.No:16/P-47).
| 2" thick | 1895 | Sft. | 3275.5 | %Sft. | 62070.725
11 | Two coats of bitumen laid hot using 34-lbs: for %sft. Over roof and blinded with sand at one Cft per %sft. (SI No:13/P-34) | 3361 | Sft | 1887.4 | %Sft. | 63435.514
|  | Total Amount |  |  |  | 934579.6344 | /=
PART "B"
01 | Fabrication of mild steel reinforcement for cement concrete i/c cutting bending laying in position making of joints and fastenings i/c cost of binding wire (also i/cs removal of rust from bars)[(a)Mild bars.(S.I.No:7(ii)(a)/P-20){(b)Tor bars.(S.I.No:7(ii)(b)/P-20)}] | 3.76 | Cwt | 5001.7 | P.Cwt | 18806.392
02 | P/F in position iron steel grill of 3/4" x 1/4" size flate iron of approved design i/c painting 3 coats etc complete (weight not to be less than 3.7 Lbs./square foot of finished grill).(S.I.No.26/P-92) | 339 | Sft | 180.5 | P.Sft | 61189.5
|  | Total Amount |  |  |  | 79995.892 | /=
PART-C "
01 | Providing & laying tiles glazed 6"x6"x1/4" on floor or walls facing in required colour and pattern of STILE specification jointed in white cement and pigment over a base of 1:2 grey cement mortar 3/4" thick i/c washing and filling of joints with slurry of white cement and pigment in desired shape with finishing cleaning and cost of wax polish etc, complete i/c cutting tiles to proper profile. (SI No:60 P-46) | 169 | Sft. | 30509.77 | %Sft. | 51561.5113
|  | Total Amount |  |  |  | 51561.5113 | /=
PART-D "COURT YARD WALL"
01. | Excavation in foundation of Bldg: bridges & other structures i/c dagbelling dressing refilling around str:with excavated earth watering & ramming lead upto 5 ft in ordanary siol (S.I.No.18(b)/P-5) | 792 | Cft | 3176.25 | %OCft | 2515.59
02 | C.C Brick or stone ballast 1-1/2" to 2" gauge Ratio 1:4:8 (S.I. No:4(b)/P-17) | 740.29 | Cft. | 9416.28 | %Cft | 69680
03. | P.B.Work in foundation & Plinth C.Sand Mortar 1:6 (S.I.No.4-e/P-19) | 223.74 |  | 11948.36 | %Cft | 26764
04. | C.C plain i/c placing compacting finishing & curing complete (i/c screening & washing of stone aggregate without shuttering) ratio 1:3:6 (SI No:5(h) P-18) | 297 | Cft. | 12595 | %Cft | 37407
05. | Erection and removal of centering for R.C.C or plain cement concrete works of Deodar wood (2nd class) (ii) vertical. (S.I No: 18(b)(ii) P. 21) for partial wood. | 792 | Sft. | 3127.41 | %Sft. | 24769.0872
06. | Pacca brick work other than buildings i/c stricking of joints upto 20'ft: height in cement sand mortar ratio 1:6 (S.I.No:7(I.e)/P-21) | 512.82 |  | 12346.65 | %Cft | 63338
07. | Cement plaster 1:6 upto 20'ft: height 1/2" thick.(S.I.No:11(a)/P-58) | 5255.4651 | Sft. | 2206.6 | %Sft. | 115956
08. | Cement plaster 1:4 upto 20'ft: height 3/8" thick.(S.I.No:11(a)/P-58) | 5255.4651 | Sft. | 2197.52 | %Sft. | 115480
09. | Providing & laying 1" thick topping cement concrete (1:2:4) i/c surfce finishing & dividing into panels. (SI No:16/P-51).
| (a) 2" thick | 1084.58 | Sft. | 3275.5 | %Sft. | 35539
10 | Colour Washing two coats.(S.I.No:11(a)/P-58) | 6303.5222 | Sft. | 859.9 | %Sft. | 54208
11 | Painting guard bars.(S.I.No:11(a)/P-58) | 84.5 | Sft. | 896.39 | P.Sft. | 76193
|  | Total amount Part "D" at Par |  |  |  | 621849.6772 | /=
PART "E"
01 | M/F steel grated doors with 1/16" thick sheeting i/c angle iron frame 2"x2"x3/8" and 3/4" square bars 4" centre to centre with locking arrangement. (S.I No:24/P-91) | 84.5 | Sft | 726.72 | P.Sft | 61771
|  | Total amount |  |  |  | 61771 | /=
GENERAL ABSTRACT
| PART "A" | 937455 | /=
| PART "B" | 88279 | /=
| PART "C" | 108344 | /=
| PART "D" | 621849.6772 | /=
| PART "E" | 67948 | /=
| G.TOTAL | 1823875.6772 | /=
NOTE: -
Any error or ommission in the Schedul "B" will be governed by the schedul of rates.
No. premium will be allowed on Non-Schedule items.
Cartage will not be paid for any meterials.
Mat: use in the work of finished product can be got tested from any approved lab: at the discreation of the XEN or his representitive & all expanses in conn: with such testing should be born by the cont exclusivaly without any re-imburament or cleim against the Government on his account.
CONTRACTOR
EXECUTIVE ENGINEER
BUILDINGS DIVISION
T.M.KHAN

## Measurement Sheet 1
MEASUREMENT SHEET
NAME OF WORK:- CONSTRUCTION OF CATAGARY -II BUNGLALOWS FOR GRADE 18 & 19 @ B&R COLONY DISTRICT T.M.KHAN (BUNGLALOW 01 NO) ( EXT: DEVELOPMENT).
S.No. | Description | Measurement | [11 empty] | Quantity
|  | No. |  |  | Length |  | Width |  |  | Height/Depth
PART-A "MAIN BUILDINGS"
01. | RCC work (1:2:4) i/c all labour…...
| Footing | 2 | × | 3.00 | × | 3.00 | × | 1.00 |  |  |  |  | ═ | 18 | Cft
| Column | 2 | × | 1.50 | × | 1.50 | × | 10.00 |  |  |  |  | ═ | 45 | Cft
| Servant/ bath plinth beam | 1 | × | 18.75 | × | 0.75 | × | 0.75 |  |  |  |  | ═ | 10.5469 | Cft
| " " " " " " " " " " " " " " " " " | 1 | × | 11.50 | × | 0.75 | × | 0.75 |  |  |  |  | ═ | 6.4688 | Cft
| Bath | 1 | × | 6.75 | × | 0.75 | × | 0.75 |  |  |  |  | ═ | 3.7969 | Cft
| Servant/ bath plinth beam | 2 | × | 10.00 | × | 0.75 | × | 0.75 |  |  |  |  | ═ | 11.25 | Cft
| Bath | 1 | × | 4.00 | × | 0.75 | × | 0.75 |  |  |  |  | ═ | 2.25 | Cft
[12 empty] | Total | ═ | 97.3125 | Cft
02. | Fabrication of mild steel reinforcement for cement concrete i/c cutting……
| Servant R P/Beam M/B 1/2" dia | 1 | ×( | 2 | + | 2 | )× | 18.75 | × | 0.667 |  |  | ═ | 50.025 | Lbs
| " " " " " " " " " " R/B 3/8" dia | 1 | × | 37 | × | 2.67 | × | 0.375 |  |  |  |  | ═ | 37.0463 | Lbs
| Servant R P/Beam M/B 1/2" dia | 1 | ×( | 2 | + | 2 | )× | 12.00 | × | 0.667 |  |  | ═ | 32.016 | Lbs
| " " " " " " " " " " R/B 3/8" dia | 1 | × | 23 | × | 2.67 | × | 0.375 |  |  |  |  | ═ | 23.0287 | Lbs
| Bath P/Beam M/B 1/2" dia | 1 | ×( | 2 | + | 2 | )× | 7.00 | × | 0.667 |  |  | ═ | 18.676 | Lbs
| " " " " " " " " " " R/B 3/8" dia | 1 | × | 9 | × | 2.67 | × | 0.375 |  |  |  |  | ═ | 9.0113 | Lbs
| Servant R P/Beam M/B 1/2" dia | 2 | ×( | 2 | + | 2 | )× | 10.50 | × | 0.667 |  |  | ═ | 56.028 | Lbs
| " " " " " " " " " " R/B 3/8" dia | 2 | × | 20 | × | 2.67 | × | 0.375 |  |  |  |  | ═ | 40.05 | Lbs
| Bath P/Beam M/B 1/2" dia | 1 | ×( | 2 | + | 2 | )× | 4.50 | × | 0.667 |  |  | ═ | 12.006 | Lbs
| " " " " " " " " " " R/B 3/8" dia | 1 | × | 8 | × | 2.67 | × | 0.375 |  |  |  |  | ═ | 8.01 | Lbs
| M/G Footing M/B 1/2" dia | 1 | × | 2 | × | 4.00 | × | 4.00 | × | 0.667 |  |  | ═ | 21.344 | Lbs
| M/G Footing D/B 1/2" dia | 1 | × | 2 | × | 4.00 | × | 4.00 | × | 0.667 |  |  | ═ | 21.344 | Lbs
| M/G Columns M/B 1/2" dia | 1 | ×( | 3 | + | 3 | )× | 11.50 | × | 0.667 |  |  | ═ | 46.023 | Lbs
| M/G Columns R/B 3/8" dia | 1 | × | 22 | × | 5.67 | × | 0.375 |  |  |  |  | ═ | 46.7775 | Lbs
[13 empty] | ═ | 421.3857 | Lbs
|  |  |  | 421.3857 | ÷ | 112 | [6 empty] | ═ | 3.7624 | Cwt
03 | Cement Plaster 1:4 upto 20'ft: height 3/8" thick…...
(a) Outside
| Drawing/Kitchen L/Side | 1 | × | 31.75 | × | 11.50 | [6 empty] | ═ | 365.125 | Sft
| Kitchen b/side | 1 | × | 12.17 | × | 11.50 | [6 empty] | ═ | 139.955 | Sft
| Bath l/side | 1 | × | 7.92 | × | 11.50 | [6 empty] | ═ | 91.08 | Sft
| Bath b/side | 1 | × | 8.75 | × | 11.50 | [6 empty] | ═ | 100.625 | Sft
| Bath / Bed / Bath b/side | 1 | × | 17.17 | × | 11.50 | [6 empty] | ═ | 197.455 | Sft
| Bath b/side | 1 | × | 10.17 | × | 11.50 | [6 empty] | ═ | 116.955 | Sft
| Bed b/side | 1 | × | 13.50 | × | 11.50 | [6 empty] | ═ | 155.25 | Sft
| Drawing room | 2 | × | 25.42 | × | 2.50 | [6 empty] | ═ | 127.1 | Sft
| Drawing room | 2 | × | 18.18 | × | 2.50 | [6 empty] | ═ | 90.9 | Sft
| Servant Room Bath R/side | 1 | × | 5.50 | × | 11.50 | [6 empty] | ═ | 63.25 | Sft
| " " " " " " " " " " Bath F/side | 1 | × | 6.92 | × | 11.50 | [6 empty] | ═ | 79.58 | Sft
| " " " " " " " " " " Bath R/side | 1 | × | 6.00 | × | 11.50 | [6 empty] | ═ | 69 | Sft
| " " " " " " " " " " Bath F/side | 1 | × | 11.67 | × | 11.50 | [6 empty] | ═ | 134.205 | Sft
| " " " " " " " " " " Bath L/side | 1 | × | 11.92 | × | 11.50 | [6 empty] | ═ | 137.08 | Sft
| " " " " " " " " " " Bath B/side | 1 | × | 18.50 | × | 11.50 | [6 empty] | ═ | 212.75 | Sft
[12 empty] | Total | ═ | 2080.31 | Sft
04 | 1st Class deodar Wood W/J in D/W wire gauze ……
Entire Measurement
| W | 7 | × | 6.00 | × | 4.00 | [6 empty] | ═ | 168 | Sft
| W-2 | 3 | × | 3.00 | × | 4.00 | [6 empty] | ═ | 36 | Sft
| W-3 | 6 | × | 3.00 | × | 6.00 | [6 empty] | ═ | 108 | Sft
| HW | 1 | × | 6.00 | × | 1.50 | [6 empty] | ═ | 9 | Sft
| HW | 4 | × | 3.00 | × | 1.50 | [6 empty] | ═ | 18 | Sft
[12 empty] | Total | ═ | 339 | Sft
|  |  |  | Work to be done | [5 empty] | Work done paid Qty: |  |  | ═ | 228 | Sft
[7 empty] | ( | 339 | - | 228 | ) |  | ═ | 111 | Sft
05 | 1st Class deodar Wood (a) 1-1/2" thick deodar wood framing of door wire gauze ……
| Doors | 3 | × | 3.50 | × | 7.00 | [5 empty] | Total | ═ | 73.5 | Sft
|  |  |  | Work to be done | [5 empty] | Work done paid Qty: |  |  | ═ | 49 | Sft
[7 empty] | ( | 73.5 | - | 49 | ) |  | ═ | 24.5 | Sft
06 | P/F deodar wooden wardrobe …….
| Bed room Cup board | 2 | × | 5.58 | × | 5.92 | [6 empty] | ═ | 66.0672 | Sft
| Drawing room Cup board | 1 | × | 6.17 | × | 5.75 | [6 empty] | ═ | 35.4775 | Sft
| Kitchen cup board | 1 | × | 6.00 | × | 1.50 | [6 empty] | ═ | 9 | Sft
[12 empty] | Total | ═ | 110.5447 | Sft
07 | Laying colour glazed tiles……
| Sarvent Room | 1 | × | 10.00 | × | 10.00 | [6 empty] | ═ | 100 | Sft
| Kitchen slab | 1 | × | 11.25 | × | 1.75 | [6 empty] | ═ | 19.6875 | Sft
| " " | 1 | × | 6.92 | × | 1.75 | [6 empty] | ═ | 12.11 | Sft
| Kitchen wall | 1 | × | 1.50 | × | 2.00 | [6 empty] | ═ | 3 | Sft
|  | 1 | × | 11.25 | × | 2.00 | [6 empty] | ═ | 22.5 | Sft
|  | 1 | × | 5.25 | × | 2.00 | [6 empty] | ═ | 10.5 | Sft
|  | 1 | × | 3.00 | × | 0.50 | [6 empty] | ═ | 1.5 | Sft
[12 empty] | Total | ═ | 169.2975 | Sft
08. | Primary coat of chalk under distemper……
Inside
| L / Bed Room | 1 | × | 2 | ×( | 12.00 | + | 16.00 | )× | 11.00 |  |  | ═ | 616 | Sft
| L / Barh Room | 1 | × | 2 | ×( | 8.50 | + | 6.50 | )× | 11.00 |  |  | ═ | 330 | Sft
| R / Bed Room | 1 | × | 2 | ×( | 16.00 | + | 12.00 | )× | 11.00 |  |  | ═ | 616 | Sft
| R / Bath Room | 1 | × | 2 | ×( | 7.08 | + | 7.08 | )× | 11.00 |  |  | ═ | 311.52 | Sft
| Store | 1 | × | 2 | ×( | 7.67 | + | 7.00 | )× | 11.00 |  |  | ═ | 322.74 | Sft
| Kitchen | 1 | × | 2 | ×( | 11.42 | + | 12.67 | )× | 11.00 |  |  | ═ | 529.98 | Sft
| Passage | 1 | ×( | 12.50 | + | 12.50 | + | 3.58 | )× | 11.00 |  |  | ═ | 2211 | Sft
| Lounge | 1 | × | 2 | ×( | 24.50 | + | 12.00 | )× | 11.00 |  |  | ═ | 803 | Sft
| Drawing / Dinning | 1 | × | 2 | ×( | 23.92 | + | 15.92 | )× | 13.50 |  |  | ═ | 1075.68 | Sft
| Guest | 1 | × | 2 | ×( | 12.00 | + | 15.00 | )× | 11.00 |  |  | ═ | 594 | Sft
| Bath | 1 | × | 2 | ×( | 6.08 | + | 10.00 | )× | 11.00 |  |  | ═ | 353.76 | Sft
| Lobby | 1 | × | 2 | ×( | 6.08 | + | 4.50 | )× | 11.00 |  |  | ═ | 232.76 | Sft
| Servant Room | 1 | × | 2 | ×( | 10.00 | + | 10.00 | )× | 11.00 |  |  | ═ | 440 | Sft
| Servant Bath | 1 | × | 2 | ×( | 6.00 | + | 4.00 | )× | 11.00 |  |  | ═ | 220 | Sft
Out side
| Bed / Lounge / R/Side | 1 | × | 31.17 | × | 11.50 | [6 empty] | ═ | 358.455 | Sft
| Lounge / F/Side | 1 | × | 25.58 | × | 11.50 | [6 empty] | ═ | 294.17 | Sft
| Drawing / Lobby / Bath | 1 | × | 25.37 | × | 11.50 | [6 empty] | ═ | 291.755 | Sft
| Guest / Bath F/Side | 1 | × | 20.67 | × | 11.50 | [6 empty] | ═ | 237.705 | Sft
| " " " " " " " " " L/Side | 1 | × | 15.83 | × | 11.50 | [6 empty] | ═ | 182.045 | Sft
| Drawing F/Side | 1 | × | 5.83 | × | 11.50 | [6 empty] | ═ | 67.045 | Sft
| " " " " " " Kitchen L/Side | 1 | × | 31.75 | × | 11.50 | [6 empty] | ═ | 365.125 | Sft
| Kitchen B/Side | 1 | × | 12.17 | × | 11.50 | [6 empty] | ═ | 139.955 | Sft
| Bath L/Side | 1 | × | 7.92 | × | 11.50 | [6 empty] | ═ | 91.08 | Sft
| Bath B/Side | 1 | × | 8.75 | × | 11.50 | [6 empty] | ═ | 100.625 | Sft
| Bath / Bed B/side | 1 | × | 17.17 | × | 11.50 | [6 empty] | ═ | 197.455 | Sft
| " " " " B/Side | 1 | × | 10.17 | × | 11.50 | [6 empty] | ═ | 116.955 | Sft
| Bath R/Side | 1 | × | 3.83 | × | 11.50 | [6 empty] | ═ | 44.045 | Sft
| Bed " " " " " | 1 | × | 13.50 | × | 11.50 | [6 empty] | ═ | 155.25 | Sft
| Drawing Room | 2 | × | 25.42 | × | 2.50 | [6 empty] | ═ | 127.1 | Sft
| " " " " " " " " " " | 2 | × | 18.18 | × | 2.50 | [6 empty] | ═ | 90.9 | Sft
| Servant Room Bath R/Side | 1 | × | 5.50 | × | 11.50 | [6 empty] | ═ | 63.25 | Sft
| " " " " " " " " " " " " " " F/Side | 1 | × | 6.92 | × | 11.50 | [6 empty] | ═ | 79.58 | Sft
| " " " " " " " " " " " " " " R/Side | 1 | × | 6.00 | × | 11.50 | [6 empty] | ═ | 69 | Sft
| " " " " " " " " " " " " " " F/Side | 1 | × | 11.67 | × | 11.50 | [6 empty] | ═ | 134.205 | Sft
| " " " " " " " " " " " " " " L/Side | 1 | × | 11.92 | × | 11.50 | [6 empty] | ═ | 137.08 | Sft
| " " " " " " " " " " " " " " B/Side | 1 | × | 18.50 | × | 11.50 | [6 empty] | ═ | 212.75 | Sft
| Column C/Yard | 2 | × | 4.42 | × | 13.50 | [6 empty] | ═ | 119.34 | Sft
[12 empty] | Total | ═ | 12331.31 | Sft
Deduction:
| D-1 | 5 | × | 3.50 | × | 7.00 | [6 empty] | ═ | 122.5 | Sft
| D-2 | 3 | × | 3.00 | × | 7.00 | [6 empty] | ═ | 63 | Sft
| D-3 | 4 | × | 2.50 | × | 7.00 | [6 empty] | ═ | 70 | Sft
| W | 7 | × | 6.00 | × | 4.00 | [6 empty] | ═ | 168 | Sft
| W-2 | 3 | × | 3.00 | × | 4.00 | [6 empty] | ═ | 36 | Sft
| W-3 | 6 | × | 3.00 | × | 6.00 | [6 empty] | ═ | 108 | Sft
| HW | 1 | × | 6.00 | × | 1.50 | [6 empty] | ═ | 9 | Sft
| HW | 4 | × | 3.00 | × | 1.50 | [6 empty] | ═ | 18 | Sft
[12 empty] | Total | ═ | 594.5 | Sft
|  |  | NET QTY: |  | ( | 12331.31 | ─ | 594.5 | ) |  |  | Total | ═ | 11736.81 | Cft
09. | White Washing three coats…..
Roof ceilling
| R / Bed Room | 1 | × | 12.00 | × | 16.00 | [6 empty] | ═ | 192 | Sft
| R / Bath Room | 1 | × | 8.50 | × | 6.60 | [6 empty] | ═ | 56.1 | Sft
| L / Bed Room | 1 | × | 16.00 | × | 12.00 | [6 empty] | ═ | 192 | Sft
| L / Bath Room | 1 | × | 7.08 | × | 7.08 | [6 empty] | ═ | 50.1264 | Sft
| Store | 1 | × | 7.67 | × | 7.00 | [6 empty] | ═ | 53.69 | Sft
| Kitchen | 1 | × | 11.42 | × | 12.67 | [6 empty] | ═ | 144.6914 | Sft
| Passage | 1 | × | 12.50 | × | 3.58 | [6 empty] | ═ | 44.75 | Sft
| Lounge | 1 | × | 24.50 | × | 12.00 | [6 empty] | ═ | 294 | Sft
| Drawing / Dinning | 1 | × | 23.92 | × | 15.92 | [6 empty] | ═ | 380.8064 | Sft
| Guest Room | 1 | × | 12.00 | × | 15.00 | [6 empty] | ═ | 180 | Sft
| Bath | 1 | × | 6.08 | × | 10.00 | [6 empty] | ═ | 60.8 | Sft
| Lobby | 1 | × | 6.08 | × | 4.50 | [6 empty] | ═ | 27.36 | Sft
| Open Terrace | 1 | × | 25.63 | × | 6.00 | [6 empty] | ═ | 153.78 | Sft
| " " " " " " " " " " | 1 | × | 3.00 | × | 4.00 | [6 empty] | ═ | 12 | Sft
| " " " " " " " " " " | 1 | × | 16.75 | × | 2.00 | [6 empty] | ═ | 33.5 | Sft
| Terrace | 1 | × | 20.28 | × | 8.00 | [6 empty] | ═ | 162.24 | Sft
| Porch | 1 | × | 11.00 | × | 23.75 | [6 empty] | ═ | 261.25 | Sft
| Chajja W | 3 | × | 7.50 | × | 3.00 | [6 empty] | ═ | 67.5 | Sft
| " " " " " " | 1 | × | 7.50 | × | 3.00 | [6 empty] | ═ | 22.5 | Sft
| D-2,W-2,W-3 Chajja | 1 | × | 25.50 | × | 3.00 | [6 empty] | ═ | 76.5 | Sft
| HW Chajja | 1 | × | 7.50 | × | 3.00 | [6 empty] | ═ | 22.5 | Sft
| HW Chajja | 2 | × | 4.50 | × | 3.00 | [6 empty] | ═ | 27 | Sft
| Servant Chajja D-1,D-3,W-1,W-2 | 1 | × | 22.00 | × | 3.00 | [6 empty] | ═ | 66 | Sft
| " " " " " " " " " " HW | 1 | × | 4.50 | × | 3.00 | [6 empty] | ═ | 13.5 | Sft
[12 empty] | Total | ═ | 2594.5942 | Sft
10. | Distempering two coats with 1st coat over primary coat 3 coats….
|  | Same Qty as Item No.08 | [9 empty] | Total | ═ | 11736.81 | Sft
11. | Painting new surface doors & windows any type 3 coats….
| Double the Qty as Item No.10 |  |  |  |  | 587 | × | 2 |  |  |  | Total | ═ | 1174 | Sft
12. | P/L C.C. Topping 2" thick (1:2:4)…
| Guest/bed/bath/lobby | 1 | × | 9.25 | × | 6.0 | [6 empty] | ═ | 55.5 | Sft
| Lounge/Bed room | 1 | × | 37.83 | × | 26.33 | [6 empty] | ═ | 996.0639 | Sft
| Passage / bed | 1 | × | 26.00 | × | 14.37 | [6 empty] | ═ | 373.62 | Sft
| Bath | 1 | × | 6.50 | × | 5.50 | [6 empty] | ═ | 35.75 | Sft
| Bath | 1 | × | 8.92 | × | 6.75 | [6 empty] | ═ | 60.21 | Sft
| Bath / Store | 1 | × | 14.75 | × | 14.67 | [6 empty] | ═ | 216.3825 | Sft
| Servant Room | 1 | × | 11.50 | × | 13.50 | [6 empty] | ═ | 155.25 | Sft
| " " " " " " Bath | 1 | × | 6.75 | × | 7.50 | [6 empty] | ═ | 50.625 | Sft
[12 empty] | Total | ═ | 1943.4014 | Sft
13. | Two coats of bitumen laid hot using 34-lbs: for %sft. Over roof and …..
| Guest/bed/bath/lobby | 1 | × | 32.33 | × | 21.58 | [6 empty] | ═ | 697.6814 | Sft
| " " " " " " " " " " " " " | 1 | × | 3.00 | × | 2.25 | [6 empty] | ═ | 6.75 | Sft
| Lounge/Bed room | 1 | × | 37.83 | × | 26.33 | [6 empty] | ═ | 996.0639 | Sft
| Bath | 1 | × | 11.83 | × | 3.75 | [6 empty] | ═ | 44.3625 | Sft
| Passage / bed | 1 | × | 26.00 | × | 14.37 | [6 empty] | ═ | 373.62 | Sft
| " " " " " " " " " | 1 | × | 9.37 | × | 9.00 | [6 empty] | ═ | 84.33 | Sft
| Bath | 1 | × | 6.50 | × | 5.50 | [6 empty] | ═ | 35.75 | Sft
| Kitchen /Store | 1 | × | 29.42 | × | 21.75 | [6 empty] | ═ | 639.885 | Sft
| Bath | 1 | × | 8.92 | × | 6.75 | [6 empty] | ═ | 60.21 | Sft
| Bath / Store | 1 | × | 14.75 | × | 14.67 | [6 empty] | ═ | 216.3825 | Sft
| Servant Room | 1 | × | 11.50 | × | 13.50 | [6 empty] | ═ | 155.25 | Sft
| " " " " " " Bath | 1 | × | 6.75 | × | 7.50 | [6 empty] | ═ | 50.625 | Sft
[12 empty] | Total | ═ | 3360.9103 | Sft
14. | P/F iron steel grill using solid square bars……
Entire Measurement
| W | 7 | × | 6.00 | × | 4.00 | [6 empty] | ═ | 168 | Sft
| W-2 | 3 | × | 3.00 | × | 4.00 | [6 empty] | ═ | 36 | Sft
| W-3 | 6 | × | 3.00 | × | 6.00 | [6 empty] | ═ | 108 | Sft
| HW | 1 | × | 6.00 | × | 1.50 | [6 empty] | ═ | 9 | Sft
| HW | 4 | × | 3.00 | × | 1.50 | [6 empty] | ═ | 18 | Sft
[12 empty] | Total | ═ | 339 | Sft
PART-A "COURT YARD WALL"
01. | Excavation ….
| DHO C/Wall east side | 1 | × | 99.00 | × | 2.00 | × | 2.00 |  |  |  |  | ═ | 396 | Cft
| DHO C/Wall back side | 1 | × | 99.00 | × | 2.00 | × | 2.00 |  |  |  |  | ═ | 396 | Cft
[12 empty] | Total | ═ | 792 | Cft
02. | 1:4:8…
| DHO C/Wall east side | 1 | × | 99.00 | × | 2.00 | × | 0.50 |  |  |  |  | ═ | 99 | Cft
| DHO C/Wall back side | 1 | × | 99.00 | × | 2.00 | × | 0.50 |  |  |  |  | ═ | 99 | Cft
| Right Side Main Bldg | 1 | × | 46.39 | × | 4.50 | × | 0.50 |  |  |  |  | ═ | 104.3775 | Cft
| Back Side Main Bldg | 1 | × | 51.98 | × | 4.75 | × | 0.50 |  |  |  |  | ═ | 123.4525 | Cft
| Left Side Main Bldg | 1 | × | 31.98 | × | 4.00 | × | 0.50 |  |  |  |  | ═ | 63.96 | Cft
| Porch Main Bldg | 1 | × | 21.75 | × | 12.00 | × | 0.50 |  |  |  |  | ═ | 130.5 | Cft
| Porch Main Bldg | 1 | × | 20.00 | × | 12.00 | × | 0.50 |  |  |  |  | ═ | 120 | Cft
[12 empty] | Total | ═ | 740.29 | Cft
03. | P.B.W.Foundation…
| DHO C/Wall east side | 1 | × | 99.00 | × | 1.13 | × | 1.00 |  |  |  |  | ═ | 111.87 | Cft
| DHO C/Wall back side | 1 | × | 99.00 | × | 1.13 | × | 1.00 |  |  |  |  | ═ | 111.87 | Cft
[12 empty] | Total | ═ | 223.74 | Cft
04. | 1:3:6…
| DHO C/Wall east side | 1 | × | 99.00 | × | 0.75 | × | 2.00 |  |  |  |  | ═ | 148.5 | Cft
| DHO C/Wall back side | 1 | × | 99.00 | × | 0.75 | × | 2.00 |  |  |  |  | ═ | 148.5 | Cft
[12 empty] | Total | ═ | 297 | Cft
05. | Errectio & Removal….
| DHO C/Wall east side | 1 | × | 2 | × | 99.00 | × | 2.00 |  |  |  |  | ═ | 396 | Sft
| DHO C/Wall back side | 1 | × | 2 | × | 99.00 | × | 2.00 |  |  |  |  | ═ | 396 | Sft
[12 empty] | Total | ═ | 792 | Sft
06. | P.B.W.other than buildings …..
| DHO C/Wall east side | 1 | × | 99.00 | × | 0.37 | × | 7.00 |  |  |  |  | ═ | 256.41 | Cft
| DHO C/Wall back side | 1 | × | 99.00 | × | 0.37 | × | 7.00 |  |  |  |  | ═ | 256.41 | Cft
[12 empty] | Total | ═ | 512.82 | Cft
07. | Cement Plaster 1:6 upto 20'ft: height 1/2" thick…...
Inside
| DHO C/Wall east side | 1 | × | 99.00 | × | 7.00 | [6 empty] | ═ | 693 | Cft
| DHO C/Wall back side | 1 | × | 99.00 | × | 7.00 | [6 empty] | ═ | 693 | Cft
| L / Side | 1 | × | 56.17 | × | 5.83 | [6 empty] | ═ | 327.4711 | Sft
| L / Side | 1 | × | 22.67 | × | 12.00 | [6 empty] | ═ | 272.04 | Sft
Outside
| DHO C/Wall east side | 1 | × | 99.00 | × | 7.37 | [6 empty] | ═ | 729.63 | Sft
| DHO C/Wall back side | 1 | × | 99.00 | × | 7.37 | [6 empty] | ═ | 729.63 | Sft
| F / Side | 1 | × | 60.00 | × | 6.20 | [6 empty] | ═ | 372 | Sft
| B / Side | 1 | × | 42.00 | × | 6.20 | [6 empty] | ═ | 260.4 | Sft
| R / Side | 1 | × | 90.00 | × | 6.20 | [6 empty] | ═ | 558 | Sft
| L / Side | 1 | × | 56.17 | × | 6.20 | [6 empty] | ═ | 348.254 | Sft
| L / Side | 1 | × | 22.67 | × | 12.00 | [6 empty] | ═ | 272.04 | Sft
[12 empty] | Total | ═ | 5255.4651 | Sft
08. | Cement Plaster 1:4 upto 20'ft: height 3/4" thick…...
Inside
| DHO C/Wall east side | 1 | × | 99.00 | × | 7.00 | [6 empty] | ═ | 693 | Sft
| DHO C/Wall back side | 1 | × | 99.00 | × | 7.00 | [6 empty] | ═ | 693 | Sft
| L / Side | 1 | × | 56.17 | × | 5.83 | [6 empty] | ═ | 327.4711 | Sft
| L / Side | 1 | × | 22.67 | × | 12.00 | [6 empty] | ═ | 272.04 | Sft
Outside
| DHO C/Wall east side | 1 | × | 99.00 | × | 7.37 | [6 empty] | ═ | 729.63 | Sft
| DHO C/Wall back side | 1 | × | 99.00 | × | 7.37 | [6 empty] | ═ | 729.63 | Sft
| F / Side | 1 | × | 60.00 | × | 6.20 | [6 empty] | ═ | 372 | Sft
| B / Side | 1 | × | 42.00 | × | 6.20 | [6 empty] | ═ | 260.4 | Sft
| R / Side | 1 | × | 90.00 | × | 6.20 | [6 empty] | ═ | 558 | Sft
| L / Side | 1 | × | 56.17 | × | 6.20 | [6 empty] | ═ | 348.254 | Sft
| L / Side | 1 | × | 22.67 | × | 12.00 | [6 empty] | ═ | 272.04 | Sft
[12 empty] | Total | ═ | 5255.4651 | Sft
09. | Steel grated door …..
| Main gate | 1 | × | 10.00 | × | 6.00 | [6 empty] | ═ | 60 | Sft
| Side gate | 1 | × | 3.50 | × | 7.00 | [6 empty] | ═ | 24.5 | Sft
[12 empty] | Total | ═ | 84.5 | Sft
10 | C.C Topping 2" thick
| Right Side Main Bldg | 1 | × | 46.39 | × | 4.50 | [6 empty] | ═ | 208.755 | Sft
| Back Side Main Bldg | 1 | × | 51.98 | × | 4.75 | [6 empty] | ═ | 246.905 | Sft
| Left Side Main Bldg | 1 | × | 31.98 | × | 4.00 | [6 empty] | ═ | 127.92 | Sft
| Porch Main Bldg | 1 | × | 21.75 | × | 12.00 | [6 empty] | ═ | 261 | Sft
| Porch Main Bldg | 1 | × | 20.00 | × | 12.00 | [6 empty] | ═ | 240 | Sft
[12 empty] | Total | ═ | 1084.58 | Sft
11 | Colour Washing two coats…..
| DHO C/Wall east side b/plinth | 2 | × | 99.00 | × | 1.50 | [6 empty] | ═ | 297 | Sft
| DHO C/Wall back side b/plinth | 2 | × | 99.00 | × | 1.50 | [6 empty] | ═ | 297 | Sft
| F / Side below Plinth | 2 | × | 60.00 | × | 1.50 | [6 empty] | ═ | 180 | Sft
| B / Side below Plinth | 2 | × | 42.00 | × | 1.50 | [6 empty] | ═ | 126 | Sft
| R / Side below Plinth | 2 | × | 90.00 | × | 1.50 | [6 empty] | ═ | 270 | Sft
| L / Side below Plinth | 2 | × | 56.17 | × | 1.50 | [6 empty] | ═ | 168.51 | Sft
| L / Side below Plinth | 2 | × | 22.67 | × | 1.50 | [6 empty] | ═ | 68.01 | Sft
| DHO C/Wall east side | 1 | × | 99.00 | × | 7.37 | [6 empty] | ═ | 729.63 | Sft
| DHO C/Wall back side | 1 | × | 99.00 | × | 7.37 | [6 empty] | ═ | 729.63 | Sft
| F / Side | 2 | × | 60.00 | × | 5.83 | [6 empty] | ═ | 699.6 | Sft
| B / Side | 2 | × | 42.00 | × | 5.83 | [6 empty] | ═ | 489.72 | Sft
| R / Side | 2 | × | 90.00 | × | 5.83 | [6 empty] | ═ | 1049.4 | Sft
| L / Side | 2 | × | 56.17 | × | 5.83 | [6 empty] | ═ | 654.9422 | Sft
| L / Side | 2 | × | 22.67 | × | 12.00 | [6 empty] | ═ | 544.08 | Sft
[12 empty] | Total | ═ | 6303.5222 | Sft
12 | Painting guard bars….
| Main Gate | 1 | × | 10.00 | × | 6.00 | [6 empty] | ═ | 60 | Sft
| Side gate | 1 | × | 3.50 | × | 7.00 | [6 empty] | ═ | 24.5 | Sft
[12 empty] | Total | ═ | 84.5 | Sft
SUB-ENGINEER |  |  |  |  | ASSISSTANT ENGINEER | [6 empty] | EXECUTIVE ENGINEER
BUILDINGS SUB-DIVISION |  |  |  |  | BUILDINGS SUB-DIVISION | [6 empty] | BUILDINGS DIVISION
TANDO MOHAMMAD KHAN |  |  |  |  | TANDO MOHAMMAD KHAN | [6 empty] | TANDO MOHAMMAD KHAN

## WS Abstract to be done
ABSTRACT SHEET
NAME OF WORK:- CONSTRUCTION OF CATAGARY -II BUNGLALOWS FOR GRADE 18 & 19 @ B&R COLONY DISTRICT T.M.KHAN (BUNGLALOW 01 NO) ( EXT: DEVELOPMENT).
PART-B "WORK TO BE DONE OF W/S & S/F"
S.No. | Name of Items | Quantity |  | Rate (Rs.) | Unit | Amount (Rs.)
PART-B (WORK TO BE DONE)
01 | P/F Water pumping set with seimen Motor & jawed Pump of 1-HP, 1400 RPM single phase 440-Volts 2"x1-1/2" suction and delivery 150'ft: head i/c base plate and also making C.C 1:3:6 plateform of required size and fixing with nuts and bolts complete in all respects. (S.I No:4 P-29) | 1 | Nos. | 22691.35 | Each | 22691.35
|  | Total Amount |  |  |  | 22691.35 | /=
|  | Deduct 21% below |  |  | (-) | 4765.1835 | /=
|  | Part-B Total Amount |  |  |  | 17926.1665 | /=
Part-C External Drainage & Water Supply (WORK TO BE DONE)
01. | Excavtion for pipe line in trenches and pits in soft soils i/c trimming & dressing sides to true alignment and shape levelling of beds of trenches to correct level and grade, cutting joint holes and disposal of surplus earth within a one chin as directed by engineer incharge providing fence guards lights flags and temporary crossings for non vehicular traffic where ever required lift upto 5'ft: (1.52mm and lead upto one chain (30.5mm) (SI No:1 P-46)P.H.E | 1200 | Cft | 2032.8 | %Cft | 24393.6
02. | Boring for truble well in all water bearing soils from ground levee upto 100 ft or 30.50 mortar depthy I/c making and with drening of casing pipe 800mm 3" Dia (S.I.No. 1 (a) P/36). | 90 | Rft | 91.85 | P.Rft | 8266.5
03 | Providing RCC pipes & collars of Class (B) & fixing in trenches i/c cutting fitting & jointing with maxphalt composition and cement mortar 1:1 i/c testing with water to a head of 22.50 metter or 75'ft: (Ch.No.II, S.I.No:A-2/P-15 P.H.E)
| (c) 9" dia RCC pipe | 300 | Rft | 163 | P.Rft | 48900
04 | Constructing of Man hole or inspection chamber for the required dia of circular sewer and 3'-6" depth with wall of B.B in cement mortar 1:3 cement plastered 1:3 1/2" thick inside of walls & 1" thick over benching and channel i/c fixing man hole cover with frame of clear opening 1-1/2'x1-1/2' if 1.75 Cwt: (88.90Kg:) embedded in plain C.C 1:2:4 and fixing 1" dia M.S steps 6" wide projecting 4" from the face of wall at 12" C/C duly painted etc complete as per specification & drawing No:D.P/1 of Public Health Circle Southern Zone (4"x12" dia 2'x2'x3'-6") (Ch.No.II, S.I.No:P (a)/46 P.H.E) | 12 | Nos | 14748 | Each | 176976
|  | Total Amount |  |  |  | 258536.1 | /=
|  | Deduct 21% below |  |  | (-) | 54292.581 | /=
|  | Part-C Total Amount |  |  |  | 204243.519 | /=
|  | PART-B |  |  |  | 17926.1665 | /=
|  | PART-C |  |  |  | 204243.519 | /=
|  | GRAND TOTAL AMOUNT |  |  |  | 222169.6855 | /=
| SUB-ENGINEER ASSISSTANT ENGINEER |  |  | EXECUTIVE ENGINEER
| BUILDINGS SUB-DIVISION BUILDINGS SUB-DIVISION |  |  | BUILDINGS DIVISION
| TANDO MOHAMMAD KHAN TANDO MOHAMMAD KHAN |  |  | TANDO MOHAMMAD KHAN

## MB Abstract Sheet
ABSTRACT SHEET
0
PART-A "SITE WORK DONE AS PER M.B OF MAIN BUILDING (CIVIL WORK)"
S.No. | Name of Items | Quantity |  | Rate (Rs.) | Unit | Amount (Rs.)
01. | Excavation in foundation of Bldg: bridges & other structures i/c dagbelling dressing refilling around str:with excavated earth watering & ramming lead upto 5 ft in ordanary siol (S.I.No.18(b)/P-5) | 0 | Cft | 1306.8 | %OCft | 0
02. | Fabrication of mild steel reinforcement for cement concrete i/c cutting bending laying in position making of joints and fastenings i/c cost of binding wire (also i/cs removal of rust from bars)[(a)Mild bars.(S.I.No:7(ii)(a)/P-20){(b)Tor bars.(S.I.No:7(ii)(b)/P-20)}] | 256.37 | Cwt | 2772.55 | P.Cwt | 710798.6435
03 | RCC work 1:2:4 i/c all labour and material except the cost of steel reinf: & its labour for bending & binding which will be paid separately. This rate also i/cs all kinds of forms moulds lifting shuttering curing rendering and finishing the exposed surface (i/c screening & washing of shingle) (a) RCC work in roof slabs beams, coloumns, rafts lintels and other structural members laid in situ or precast laid in position complete in all respects.(SI No:6(a) P-18/19) | #REF! | Cft | 114 | P.Cft | #REF!
04. | Erection and removal of centering for R.C.C or plain cement concrete works of Deodar wood (2nd class). (ii) vertical. (S.I No: 18(b)(ii) P. 21) | #REF! | Sft. | 1405.75 | %Sft. | #REF!
05. | Filling, watering and ramming earth in floor with surplus earth from foundation lead upto one chain & lift upto 5'ft: (S.I. No:21/P-5) | #REF! | Cft | 641.3 | %0Cft | #REF!
06. | Filling, watering and ramming earth under floor with new earth (excavated from outside) lead upto one chain & lift upto 5'ft: (Add: extra 3-miles lead) (R.A.Approved) (SI No:22 P-5) | 5927 | Cft | 5602.1 | %0Cft | 33203.6467
07. | C.C plain i/c placing compacting finishing & curing complete (i/c screening & washing of stone aggregate without shuttering) ratio 1:3:6 (SI No:5(h) P-18) | #REF! | Cft. | 5001.7 | %Cft | #REF!
08. | C.C Brick or stone ballast 1-1/2" to 2" gauge Ratio 1:4:8 (S.I. No:4(b)/P-17) | #REF! | Cft. | 3584.1 | %Cft | #REF!
09. | C.C Brick or stone ballast 1-1/2" to 2" gauge Ratio 1:5:10 (S.I. No:4(c)/P-17) | #REF! | Cft. | 3213.95 | %Cft | #REF!
10. | Pacca brick work in ground floor in cement sand mortar ratio 1:6 (S.I.No:5(1-e)/P-25) | 3372 | Cft. | 4246.3 | %Cft | 143185.236
11. | Providing & laying tiles glazed 6"x6"x1/4" on floor or walls facing in required colour and pattern of STILE specification jointed in white cement and pigment over a base of 1:2 grey cement mortar 3/4" thick i/c washing and filling of joints with slurry of white cement and pigment in desired shape with finishing cleaning and cost of wax polish etc, complete i/c cutting tiles to proper profile. (SI No:60 P-53) | 2329 | Sft | 13663.35 | %Sft | 318219.4215
12. | Cement plaster 1:6 upto 20'ft: height 1/2" thick.(S.I.No:13(b)/P-58) | 9784 | Sft. | 531.41 | %Sft. | 51993.1544
13. | P/F G.I frames / chowkats of size 7"x2" or 4-1/2"x3" for doors & windows using 20 gauge G.I sheet i/c welded hinges and fixing at site with necessary hold fasts, filling with cement sand slurry of ratio 1:6 and repairing the jambs. The cost also i/c all carriage, tools and plants used in making and fixing (SI No:28 & 29 P-98)
| A) Doors frames | 156.54 | Rft | 113.37 | P.Rft | 17746.9398
14. | Ist: class deodar wood wrought, joinery work in doors & windows etc, fixed in position i/c chowkats hold fasts, hinges iron tower bolts chocks, cleats, handles and cords with hooks etc. (Deodar panelled or panelled and glazed or fully glazed) (b) 1-3/4" thick (S.I.No:7(b)/P-65) | 85 | Sft | 228.38 | P.Sft | 19412.3
15. | S/F in position Aluminium channels framing for hinged doors or Alcop made with 5mm thick tinted glass glazing (Belgium) and Alpha (Japan) locks i/c handles, stoppers etc (b) Deluxe model (Bronze) (S.I.No:83(b)/P-114) | #REF! | Sft | 601.62 | P.Sft | #REF!
16. | P/F in position doors & windows and ventilators of first class deodar wood frames and 1-3/4" thick commercial ply, venler shutters of first commercial ply wood ( 3 ply both side ) .(S.I No:9 P-65) I/c hold fasts, hinges iron tower bolts handle & cleats with cord & one metric lacks and hooks( S.I No. 9 /P -66) ( without Chowkats ). | 97.75 | Sft | 236.41 | P.Sft | 23109.0775
17. | Providing & laying 1" thick topping cement concrete (1:2:4) i/c surface finishing & dividing into panels. (S.I.No:16/P-47).
| 2" thick | #REF! | Sft. | 1396.67 | %Sft. | #REF!
18. | S/F in position Aluminium channels framing for sliding windows & ventilators of Alcop made with 5mm thick tinted glass glazing (Belgium) & Aluminium fly screen i/c handles stoppers & locking arrangement etc complete (b) Duluxe model (Bronze) (S.I.No:84(b)/P-114) | 546 | Sft | 652.35 | P.Sft | 356183.1
19. | S/F False ceiling of plaster of pairs, in pannels, i/c making frame, work of deodar wood i/c painting with Soligia paint. (SI No:52 P-72) | #REF! | Sft. | 10630.26 | %Sft. | #REF!
20. | Providing & fixing plaster or paris ceiling border of 8" - 10" with of specified design & thickness i/c fixing besides ceiling with nails / screws with getties. (SI No:44 P.45) | 1195 | Rft | 44.8 | P.Rft | 53536
21. | Providing & fixing plaster of paris centre pieces of 2'-0" dia i/c fixing in ceiling with nails / screws. (SI No:45 P-45). | 12 | Nos: | 152.96 | Each | 1835.52
22. | Laying White Marble flooring fine dressed in the surface without wining set in laying mortar 1:2 i/c rubbing and polishing 1" thick flooring (S.I.No.28(a)/P-49) | #REF! | P.Sft | 148.06 | P.Sft | #REF!
23. | Cement plaster 1:4 upto 20'ft: height 3/8" thick.(S.I.No:11(a)/P-58) | 2061 | Sft. | 536.14 | %Sft. | 11049.8454
24. | Laying floor of approved coloured glazed tiles 1/4" thick laid in white cement and pigment on a bed of 3/4" thick cement mortar 1:2 complete. (SI No:25 P-49) | 128 | Sft. | 10443.84 | %Sft. | 13368.1152
25. | P/F iron steel grill using solid square bars of size 1/2"x1/2" placed at 4" i/c and frame of flate iron patti of 1" x 3/8" i/c circle shape fitted with screws or pins i/c paiting 3 coats with 1st of red oxide paint etc(Refer R.A.No.01) | #REF! | Sft | 348.99 | P.Sft | #REF!
26. | Glazed tile 1/4" thick dado laid in pigment over 1:2 cement sand mortar 3/4" thick i/c finishing. | #REF! | Sft. | 10719.22 | %Sft. | #REF!
|  | Total Amount |  |  |  | 3103189.57 | /=
|  | Add 25.20% Premium |  |  |  | 782003.7716 | /=
|  | Total Amount |  |  |  | 3885193.3416 | /=
Add Difference Cost of Cement
|  | 1266 | @ 195 | P/Bag |  | 246870 | /=
Add Difference Cost of Steel
|  | 12.381 | @ 23000 | P/Ton |  | 284763 | /=
|  | 2.5715 | @ 32000 | P/Ton |  | 82288 | /=
Add Difference Cost of Brick
|  | 16605 | @ 3300 | P/1000 Nos. |  | 54796.5 | /=
|  | Grand Total |  |  |  | 4553910.8416 | /=
| SUB-ENGINEER ASSISSTANT ENGINEER |  |  | EXECUTIVE ENGINEER
| BUILDINGS SUB-DIVISION BUILDINGS SUB-DIVISION |  |  | BUILDINGS DIVISION
| TANDO MOHAMMAD KHAN TANDO MOHAMMAD KHAN |  |  | TANDO MOHAMMAD KHAN

## Ext Devlp Abstract
ABSTRACT SHEET
NAME OF WORK:- CONSTRUCTION OF CATAGARY -II BUNGLALOWS FOR GRADE 18 & 19 @ B&R COLONY DISTRICT T.M.KHAN (BUNGLALOW 01 NO) ( EXT: DEVELOPMENT).
PART-D "EXTERNAL DEVELOPMENT"
S.No. | Name of Items | Quantity |  | Rate (Rs.) | Unit | Amount (Rs.)
01. | Filling, watering and ramming earth under floor with new earth (excavated from outside) lead upto one chain & lift upto 5'ft:(S.I.No:22/P-5) | 15563 | Cft | 1488.3 | %0Cft | 23162.4129
02. | Extra lead of 3 miles | 15563 | Cft | 5794.1 | %0Cft | 90173.5783
03. | Excavation in foundation of Bldg: bridges & other structures i/c dagbelling dressing refilling around str:with excavated earth watering & ramming lead upto 5 ft in ordanary siol (S.I.No.18(b)/P-5) | 812 | Cft | 1306.8 | %OCft | 1061.1216
04. | P.B.Work in foundation & Plinth C.Sand Mortar 1:6 (S.I.No.4/P-25) | 669.64 | Cft | 3865.15 | %Cft | 25896
05. | Cement plaster 1:6 upto 20'ft: height 1/2" thick.(S.I.No:13(b)/P-58) | 1284 | Sft. | 531.41 | %Sft. | 6823.3044
06. | Cement plaster 1:4 upto 20'ft: height 3/8" thick.(S.I.No:11(a)/P-58) | 1284 | Sft. | 536.14 | %Sft. | 6884.0376
07. | C.C Brick or stone ballast 1-1/2" to 2" gauge Ratio 1:4:8 (S.I. No:4(b)/P-17) | 1126.75 | Cft. | 3584.1 | %Cft | 40393
08. | Providing & laying topping cement concrete (1:2:4) i/c surface finishing & dividing into panels. (S.I.No:16/P-47).
| (a)3" thick | 1847.5 | Sft. | 1820.23 | %Sft. | 33639
09. | M/F steel grated doors with 1/16" thick sheeting i/c angle iron frame 2"x2"x3/8" and 3/4" square bars 4" centre to centre with locking arrangement. (S.I No:24 P.97) | 76 | Sft | 385.76 | P.Sft | 29317.76
10. | S/F in position iron steel grill of 3/4"x1/4" size flate iron of approved design i/c painting 3-coats etc complete (weight not to be less than 3.7 Lbs: / square foot of finished grill) (SI No. 26 P.97) | 57 | Sft | 115.47 | P.Sft | 6581.79
|  | Total Amount |  |  |  | 173758.4265 | /=
|  | Add Amount of Cartage |  |  |  | 60082.2391 | /=
|  | Add 20% Premium (Except Item No.02) |  |  |  | 46768.1331 | /=
|  |  | Total |  |  | 370782.377 | /=
Diff:of cement
|  | 227 | @ 205 | P/Bag |  | 46535 | /=
Diff:of Bricks
|  | 9040 | @3800 | P/1000 |  | 34352 | /=
|  | Grand Total |  |  |  | 451669.377 | /=
| SUB-ENGINEER ASSISSTANT ENGINEER |  |  | EXECUTIVE ENGINEER
| BUILDINGS SUB-DIVISION BUILDINGS SUB-DIVISION |  |  | BUILDINGS DIVISION
| TANDO MOHAMMAD KHAN TANDO MOHAMMAD KHAN |  |  | TANDO MOHAMMAD KHAN

## Rate Analysis (R.A.A)
(Rate Analysis)
NAME OF WORK:- CONSTRUCTION OF CATAGARY -II BUNGLALOWS FOR GRADE 18 & 19 @ B&R COLONY DISTRICT T.M.KHAN (BUNGLALOW 01 NO) ( EXT: DEVELOPMENT).
PART-D "EXTERNAL DEVELOPMENT"
Cartage of Hill Sand from Bolahri Quarry to Site of work
[6 empty] | M | F |  | 1 Mile = 8 Furlog
| 01. From Quarry to N.H.Way. |  |  |  |  | 3 | 0 |  | 1Furlong = 660 foot
| 02. From Quarry to 113/0 122/0 of N.H.Way. |  |  |  |  | 9 | 0
| 03. From 0/0 4/4 of Hyd: Ring Road. |  |  |  |  | 4 | 4
| 04. From 2/0 21/4 of Hyd:T.M.Khan. |  |  |  |  | 19 | 4
| 05. From 0/0 0/0 T.M.Khan to Site. |  |  |  |  | 0 | 0
[5 empty] | Total | 35 | 8 | 1
[5 empty] | Say total | 36 |  | 36
Lead
| 01. Carriage of 1st 6 miles |  |  |  | Rs:- | 771.96
| 02. Remaining |  | 30 | miles
|  | @Rs. | 32.56 | per %cft | Rs:- | 976.8
[5 empty] | Total | 1748.76 |  |  |  | 1748.76
Cartage of Stone Metal from Onger to Site of work
[6 empty] | M | F
| 01. From Quarry to N.H.way. |  |  |  |  | 3 | 0
| 02. From Quarry to 103/0 122/0 of N.H.Way. |  |  |  |  | 19 | 0
| 03. From 0/0 4/4 of Hyd: Ring Road. |  |  |  |  | 4 | 4
| 04. From 2/0 21/4 of Hyd:T.M.Khan. |  |  |  |  | 19 | 4
| 05. From 0/0 0/0 T.M.Khan to Site. |  |  |  |  | 0 | 0
[5 empty] | Total | 45 | 8 | 1
[5 empty] | Say total | 46 |  | 46
Lead
| 01. Carriage of 1st 6 miles |  |  |  | Rs:- | 771.96
| 02. Remaining |  | 40 | miles
|  | @Rs. | 32.56 | per %Cft | Rs:- | 1302.4
[5 empty] | Total | 2074.36 |  |  |  | 2074.36
Cartage of Bajri from T.M.Khan to Site of work
[6 empty] | M | F
| 01. From Quarry to 14/0 of N.H.way. |  |  |  |  | 14 | 0
| 02. From Quarry 110/40 to 122/0 of N.H.Way. |  |  |  |  | 11 | 4
| 03. From 0/0 4/4 of Hyd: Ring Road. |  |  |  |  | 4 | 4
| 04. From 2/0 21/4 of Hyd:T.M.Khan. |  |  |  |  | 19 | 4
| 05. From 0/0 0/0 T.M.Khan to Site. |  |  |  |  | 0 | 0
[5 empty] | Total | 48 | 12 | 2
[5 empty] | Say total | 50 |  | 50
Lead
| 01. Carriage of 1st 6 miles |  |  |  | Rs:- | 771.96
| 02. Remaining |  | 44 | miles
|  | @Rs. | 32.56 | per %cft | Rs:- | 1432.64
[5 empty] | Total | 2204.6 |  |  |  | 2204.6
Cartage of Cement from Zeal Pak Factory to Site of work
[6 empty] | M | F
| 01. From 2/0 21/4 of Hyd:T.M.Khan. |  |  |  |  | 17 | 4
| 02. From 0/0 0/0 T.M.Khan to Site. |  |  |  |  | 0 | 0
[5 empty] | Total | 17 | 4 | 1
[5 empty] | Say total | 18 |  | 18
Lead
| 01. Carriage of 1st 3 miles |  |  |  | Rs:- | 7.53
| 02. Remaining |  | 15 | miles
|  | @Rs. | 0.6 | per bag | Rs:- | 9
[5 empty] | Total | 16.53 |  |  |  | 16.53
Cartage of Brick from Kilen to Site of work
[6 empty] | M | F
| 01. From Brick Kilen 0/0 5/0 of Tando Fazal Sery Road |  |  |  |  | 5 | 6
| 02. From Sery Road 13/4 to 21/4 of Hyd:T.M.Khan. |  |  |  |  | 8 | 0
| 03. From 0/0 0/0 T.M.Khan to Site. |  |  |  |  | 0 | 0
[5 empty] | Total | 13 | 6 | FALSE
[5 empty] | Say total | 14 |  | 13
Lead
| 01. Carriage of 1st 6 miles |  |  |  | Rs:- | 617.54
| 02. Remaining |  | 8 | miles
|  | @Rs. | 26.05 | per O% Nos. | Rs:- | 208.4
[5 empty] | Total | 825.94 |  |  |  | 825.94
Cartage of Steel from Hyd. City to Site of work
[6 empty] | M | F
| 01. From 2/0 21/4 of Hyd:T.M.Khan. |  |  |  |  | 19 | 4
| 02. From 0/0 25/0 T.M.Khan to Site. |  |  |  |  | 0 | 0
[5 empty] | Total | 19 | 4 | 1
[5 empty] | Say total | 20 |  | 20
Lead
| 01. Carriage of 1st 6 miles |  |  |  | Rs:- | 771.96
| 02. Remaining |  | 14 | miles
|  | @Rs. | 32.56 | per Ton | Rs:- | 455.84
[5 empty] | Total | 1227.8 |  |  |  | 1227.8
SUB-ENGINEER |  |  |  | ASSISTANT ENGINEER |  | EXECUTIVE ENGINEER
BUILDINGS SUB-DIVISION |  |  |  | BUILDINGS SUB DIVISION |  | BUILDINGS DIVISION
TANDO MOHAMMAD KHAN |  |  |  | TANDO MUHAMMAD KHAN |  | TANDO MUHAMMAD KHAN

## Cartage
Material Cartage Satement
NAME OF WORK:- CONSTRUCTION OF CATAGARY -II BUNGLALOWS FOR GRADE 18 & 19 @ B&R COLONY DISTRICT T.M.KHAN (BUNGLALOW 01 NO) ( EXT: DEVELOPMENT).
Sr.# | Description | Qty: | Cement |  | Hill Sand |  | Stone Metal |  | Stone Bajri |  | Steel |  | Bricks
01. | C.C S/Ballast (1:4:8) | 1126.75 | 9.6 | 108.168 | 47.38 | 533.8542 | 96 | 1081.68 | - | - | - | - | - | -
02. | P.B.Work (1:6) in foundation | 669.64 | 3.44 | 23.0356 | 25.7 | 172.0975 | - | - | - | - | - | - | 1350 | 9040.14
03. | C.Plaster (1:6) 1/2" Thick | 1284 | 0.53 | 6.8052 | 4 | 51.36 | - | - | - | - | - | - | - | -
04. | C.Plaster (1:4) 3/8" Thick | 1284 | 0.57 | 7.3188 | 3 | 38.52 | - | - | - | - | - | - | - | -
05. | P/L C.Ctoping 3" thick | 1847.5 | 4.4 | 81.29 | 11 | 203.225 | - | - | 22 | 406.45 | - | - | - | -
06. |  | - | - | - | - | - | - | - | - | - | - | - | - | -
07. |  | - | - | - | - | - | - | - | - | - | - | - | - | -
| Total Quantity: | - | - | 226.6176 | - | 999.0566 | - | 1081.68 | - | 406.45 | - | 0 | - | 9040.14
| Rate as per R.A.A |  |  | 16.53 |  | 1748.76 |  | 2074.36 |  | 2204.6 |  | 1227.8 |  | 825.94
| Amount |  |  | 3745.9892 |  | 17471.1027 |  | 22437.9372 |  | 8960.5967 |  | 0 |  | 7466.6132
| Total Rs |  |  | 60082.2391 |  | /=
SUB-ENGINEER |  |  |  | ASSISSTANT ENGINEER | [6 empty] | EXECUTIVE ENGINEER
BUILDINGS SUB-DIVISION |  |  |  | BUILDINGS SUB-DIVISION | [6 empty] | BUILDINGS DIVISION
TANDO MOHAMMAD KHAN |  |  |  | TANDO MOHAMMAD KHAN | [6 empty] | TANDO MOHAMMAD KHAN

## Ext Devlp
MEASUREMENT SHEET
NAME OF WORK:- CONSTRUCTION OF CATAGARY -II BUNGLALOWS FOR GRADE 18 & 19 @ B&R COLONY DISTRICT T.M.KHAN (BUNGLALOW 01 NO) ( EXT: DEVELOPMENT).
PART-D "EXTERNAL DEVELOPMENT"
S.No. | Description | Measurement | [10 empty] | Quantity
|  | No. |  |  | Length |  | Width |  |  | Height/Depth
01. | Filling, watering and ramming new earth (excavated from outside) & lift upto 5'ft:
|  | 1 | × | 41.00 | × | 9.50 | × | 2.00 |  |  |  | ═ | 779 | Cft
|  | 1 | × | 44.00 | × | 96.00 | × | 3.50 |  |  |  | ═ | 14784 | Cft
[11 empty] | Total | ═ | 15563 | Cft
02. | Excavation in foundation of Bldg: bridges & other structures…..
|  | 1 | × | 2 | × | 96.00 | × | 2.00 | × | 2.00 |  | ═ | 768 | Cft
|  | 1 | × | 1 | × | 11.00 | × | 2.00 | × | 2.00 |  | ═ | 44 | Cft
[11 empty] | Total | ═ | 812 | Cft
03. | P.B.Work in foundation & Plinth 1:6
| For Passage 1st Step | 1 | × | 2 | × | 96.00 | × | 1.50 | × | 0.50 |  | ═ | 144 | Cft
|  | 1 | × | 1 | × | 11.00 | × | 1.50 | × | 0.50 |  | ═ | 8.25 | Cft
| 2nd Step | 1 | × | 2 | × | 96.00 | × | 1.13 | × | 1.00 |  | ═ | 216.96 | Cft
|  | 1 | × | 1 | × | 11.00 | × | 1.13 | × | 1.00 |  | ═ | 12.43 | Cft
| 3rd Step | 1 | × | 2 | × | 96.00 | × | 0.75 | × | 2.00 |  | ═ | 288 | Cft
|  | 1 | × | 1 | × | 11.00 | × | 0.75 | × | 2.00 |  | ═ | 16.5 | Cft
[11 empty] | Total | ═ | 669.64 | Cft
04. | C.C.Plaster 1/2" (1:6) upto 20"….
|  | 2 | × | 2 | × | 96.00 | × | 3.00 |  |  |  | ═ | 1152 | Sft
|  | 2 | × | 2 | × | 11.00 | × | 3.00 |  |  |  | ═ | 132 | Sft
[11 empty] | Total | ═ | 1284 | Sft
05. | C.C.Plaster 3/8" (1:4) upto 20"….
Same Qty as Item No. 04. | [10 empty] | Total | ═ | 1284 | Sft
06. | C.C Brick or stone ballast 1-1/2" to 2" gauge Ratio (1:4:8)…..
|  | 1 | × | 52.00 | × | 9.50 | × | 0.50 |  |  |  | ═ | 247 | Cft
|  | 1 | × | 96.00 | × | 12.00 | × | 0.50 |  |  |  | ═ | 576 | Cft
|  | 1 | × | 6.50 | × | 31.00 | × | 0.50 |  |  |  | ═ | 100.75 | Cft
|  | 1 | × | 11.00 | × | 2.00 | × | 0.50 |  |  |  | ═ | 11 | Cft
|  | 2 | × | 96.00 | × | 2.00 | × | 0.50 |  |  |  | ═ | 192 | Cft
[11 empty] | Total | ═ | 1126.75 | Cft
07. | P/L C.C. Topping 3" thick (1:2:4)….
|  | 1 | × | 52.00 | × | 9.50 | [5 empty] | ═ | 494 | Sft
|  | 1 | × | 96.00 | × | 12.00 | [5 empty] | ═ | 1152 | Sft
|  | 1 | × | 6.50 | × | 31.00 | [5 empty] | ═ | 201.5 | Sft
[11 empty] | Total | ═ | 1847.5 | Sft
08. | Steel Grated Doors…..
| D | 1 | × | 9.50 | × | 8.00 | [5 empty] | ═ | 76 | Sft
09. | S/F in position iron steel grill…..
|  | 1 | × | 9.50 | × | 6.00 | [5 empty] | ═ | 57 | Sft
SUB-ENGINEER |  |  |  |  | ASSISSTANT ENGINEER | [5 empty] | EXECUTIVE ENGINEER
BUILDINGS SUB-DIVISION |  |  |  |  | BUILDINGS SUB-DIVISION | [5 empty] | BUILDINGS DIVISION
TANDO MOHAMMAD KHAN |  |  |  |  | TANDO MOHAMMAD KHAN | [5 empty] | TANDO MOHAMMAD KHAN

## EXT DRAINAGE
NAME OF WORK:- CONSTRUCTION OF CATAGARY -II BUNGLALOWS FOR GRADE 18 & 19 @ B&R COLONY DISTRICT T.M.KHAN (BUNGLALOW 01 NO) ( EXT: DEVELOPMENT).
PART-E "EXTERNAL DRAINAGE"
SR: No: | ITEM OF WORK | QUANTITY |  | RATE | UNIT | AMOUNT
1/- | Providing RCC pipes & collars of Class (B) & fixing in trenches i/c cutting fitting & jointing with maxphalt composition and cement mortar 1:1 i/c testing with water to a head of 22.50 metter or 75'ft: (PHSI No:2 P-17)
| (a) 9" dia RCC pipe | 300 | Rft | 123.4 | P.Rft | 37020
2/- | Constructing of Man hole or inspection chamber for the required dia of circular sewer and 3'-6" depth with wall of B.B in cement mortar 1:3 cement plastered 1:3 1/2" thick inside of walls & 1" thick over benching and channel i/c fixing man hole cover with frame of clear opening 1-1/2'x1-1/2' if 1.75 Cwt: (88.90Kg:) embedded in plain C.C 1:2:4 and fixing 1" dia M.S steps 6" wide projecting 4" from the face of wall at 12" C/C duly painted etc complete as per specification & drawing No:D.P/1 of Public Health Circle Southern Zone (4"x12" dia 2'x2'x3'-6") (PHSI No:1 P-39) (With out cover) | 6 | Nos: | 2368.58 | Each | 14211.48
3 | Manufacturing and supplying R.C.C man hole cover cast in 1:2:4: concrete ratio 3 inch depth at centre. Reinforced with 3/8" dia for steel bars at 4" c/c welded to 1/8" thick 2.5 inch deep M.S plate i/c carriage stacking and transportation with in 10 miles (a) 30 inch dia. ( S.I No: 16 P- 27) | 6 | Nos: | 662.3 | Each | 3973.8
4/- | Excavtion for pipe line in trenches and pits in soft soils i/c trimming & dressing sides to true alignment and shape levelling of beds of trenches to correct level and grade, cutting joint holes and disposal of surplus earth within a one chin as directed by engineer incharge providing fence guards lights flags and temporary crossings for non vehicular traffic where ever required lift upto 5'ft: (1.52mm and lead upto one chain (30.5mm) (SI No:1 P-46) | 1200 | Cft | 1742.4 | %0Cft | 2090.88
|  |  | Total |  |  | 57296.16 | /=
|  | Add 20% Above |  |  |  | 11459.232 | /=
|  | Grand Total |  |  |  | 68755.392 | /=
|  |  | SAY TOTAL |  |  | 68800 | /=
| SUB-ENGINEER ASSISSTANT ENGINEER |  |  | EXECUTIVE ENGINEER
| BUILDINGS SUB-DIVISION BUILDINGS SUB-DIVISION |  |  | BUILDINGS DIVISION
| TANDO MOHAMMAD KHAN TANDO MOHAMMAD KHAN |  |  | TANDO MOHAMMAD KHAN

## Part E
NAME OF WORK:-. CONSTRUCTION OF SAYED MIRAN MOHAMMAD SHAH LIBARARY AT DISTRICT T.M.KHAN
PART-E "EXTERNAL DRAINAGE"
S. No. | Name of Items | As per Technical Sanction |  |  |  | As Per Site Work Done |  |  |  | Work To Be Done
|  | Qty | Rate | Unit | Amount | Qty | Rate | Unit | Amount | Qty | Rate | Unit | Amount
01. | R.C.C Pipe 9" | [8 empty] | 300 | 123.4 | P.Rft | 37020
02. | Construction of Main Hole or Inspection Chamber | [8 empty] | 6 | 2368.58 | Each | 14211.48
03. | Main Hole Cover | [8 empty] | 6 | 662.3 | Each | 3973.8
04. | Excavation for pipe in treanches | [8 empty] | 900 | 1742.4 | %Ocft | 1568.16
| Total | [11 empty] | 56773.44 | /=
| Add 20% Premium | [8 empty] | Add 20% Above |  |  | 11354.688 | /=
| Total Amount | [10 empty] | 68128.128 |  | /=
[6 empty] | Grand Total |  | 68128.128 |  |  |  | /=