## G.Abstract (hidden)
NAME OF WORK:- Constt: of Catg: -II Bunglow for BPS-18 to BPS-19 at B&R Colony T.M.Khan (Bunglow No-3) (01 No).
GENERAL ABSTRACT
| PART "A" | #REF! | /=
| PART "B" | #REF! | /=
| PART "C" | #REF! | /=
| G.TOTAL | #REF! | /=
| SAY | 49,98,000 | /=

## Part A Abstract Sheet
SCHEDULE "B"
NAME OF WORK:- Constt: of Catg: -II Bunglow for BPS-18 to BPS-19 at B&R Colony T.M.Khan (Bunglow No-3) (01 No).
S.No. | Name of Items | Quantity |  | Rate (Rs.) | Unit | Amount (Rs.)
PART-A MAIN BUILDING
01. | Excavation in foundation of Bldg: bridges & other structures i/c dagbelling dressing refilling around str:with excavated earth watering & ramming lead upto 5 ft in ordanary siol (S.I.No.18(b)/P-4) | 3494.58 | Cft | 3176.25 | %OCft | 11099.6597
02. | C.C Brick or stone ballast 1-1/2" to 2" gauge Ratio 1:4:8 (S.I. No:4(b)/P-14) | 873.645 | Cft. | 9416.28 | %Cft | 82298
03. | P.B.Work in foundation & Plinth C.Sand Mortar 1:6 (S.I.No.4-I (e)/P-20). | 962 | Cft | 11948.36 | %Cft | 114943.2232
04. | C.C plain i/c placing compacting finishing & curing complete (i/c screening & washing of stone aggregate without shuttering) ratio 1:3:6 (SI No:5(h) P-18) | 1643 | Cft. | 12595 | %Cft | 206994
05. | Erection and removal of centering for R.C.C or plain cement concrete works of Deodar wood (2nd class). (ii) vertical. (S.I No: 19(b) P. 17) | 2969.26 | Sft. | 3127.41 | %Sft. | 92853
06. | Filling, watering and ramming earth in floor with surplus earth from foundation lead upto one chain & lift upto 5'ft: (S.I. No:21/P-4) | 2327.3903 | Cft | 1512.5 | %0Cft | 3520.1778
07. | Filling, watering and ramming earth under floor with new earth (excavated from outside) lead upto one chain & lift upto 5'ft: (S.I.No:22/P-4) | 2412.3285 | Cft | 3630 | %0Cft | 8756.7525
08. | Supplying & filling sand under floor and plugging in walls. (SI No:29, P-31) | 804.1095 | Cft. | 1141.25 | %0Cft | 9175
09 | RCC work 1:2:4 i/c all labour and material except the cost of steel reinf: & its labour for bending & binding which will be paid separately. This rate also i/cs all kinds of forms moulds lifting shuttering curing rendering and finishing the exposed surface (i/c screening & washing of shingle) (a) RCC work in roof slabs beams, coloumns, rafts lintels and other structural members laid in situ or precast laid in position complete in all respects.(SI No:6(a) P-16) | 1764 | Cft | 337 | P.Cft | 594468
10 | Pacca brick work in ground floor in cement sand mortar ratio 1:6 (S.I.No:5(1-e)/P-20) | 3922.2903 | Cft. | 12674.36 | %Cft | 497088
11 | Ist: class deodar wood wrought, joinery work in doors & windows etc, fixed in position i/c chowkats hold fasts, hinges iron tower bolts chocks, cleats, handles and cords with hooks etc. (Deodar panelled or panelled and glazed or fully glazed) (b) 1-3/4" thick (S.I.No:07 /P-57) | 756.4775 | Sft | 1273.76 | P.Sft | 962963
12 | P/F G.I frames / chowkats of size 7"x2" or 4-1/2"x3" for doors & windows using 20 gauge G.I sheet i/c welded hinges and fixing at site with necessary hold fasts, filling with cement sand slurry of ratio 1:6 and repairing the jambs. The cost also i/c all carriage, tools and plants used in making and fixing (SI No:28 & 29 P-92)
| (a)Door | 314.275 | Rft | 228.9 | P.Rft | 71874
13 | P/F G.I frames / chowkats of size 7"x2" or 4-1/2"x3" for doors & windows using 20 gauge G.I sheet i/c welded hinges and fixing at site with necessary hold fasts, filling with cement sand slurry of ratio 1:6 and repairing the jambs. The cost also i/c all carriage, tools and plants used in making and fixing (SI No:28 & 29 P-92)
| (b)Window | 444.63 | Rft | 240.5 | P.Rft | 106933.515
14 | C.C Brick or stone ballast 1-1/2" to 2" gauge Ratio 1:5:10 (S.I. No:4(c)/P-14) | 132.6781 | Cft. | 8694.95 | %Cft | 11564
15 | Cement plaster 1:6 upto 12'ft: height 1/2" thick.(S.I.No:13(b)/P-51) | 7547.58 | Sft. | 2206.6 | %Sft. | 166554
16 | Cement pointing struck joints on walls ratio 1:2 (S.I No:19(a) P-52) | 2903 | Sft. | 1287.44 | %Sft. | 37374.3832
17 | Providing & laying 1" thick topping cement concrete (1:2:4) i/c surface finishing & dividing into panels. (S.I.No:16/P-41).
| (b)2" thick | 1189.24 | Sft. | 3275.5 | %Sft. | 38946
18 | Cement plaster 1:4 upto 20'ft: height 3/8" thick.(S.I.No:11(a)/P-51) | 7547.58 | Sft. | 2197.52 | %Sft. | 165859.58
19 | White washing three coats. (S.I.No:26(c) /P-53) | 1683.375 | Sft. | 829.95 | %Sft. | 13968
20 | Primary coat of chalk distemper. (S.I.No:23 /P-53) | 7547.58 | Sft. | 442.75 | %Sft. | 33416.9104
21 | Distempering two coats. (S.I.No:24(b)/P-53) | 7547.58 | Sft. | 1043.9 | %Sft. | 78793
22 | RCC spouts including fixing in position 2-1/2"×6"×5"(SI No:14 P-17) | 6 | Nos: | 261.25 | Each | 1567.5
23 | PNS & Painting of doors & windows any type (i/c edges) 3-coats (S.I.No:5(c) /P-69) | 1512.955 | Sft. | 1489.68 | %Sft. | 22538.188
24 | Supplying & fixing window printed blinds (Horizontal /Vertical) with plain design and of approved color i/c fixing in windows with necessary accessories.(S.I No: 71 P No: 66). | 156 | Sft | 91.11 | P.Sft | 14213.16
|  | Total Amount |  |  |  | 3347769.0499 | /=
PART-B MAIN BUILDING
01. | Fabrication of mild steel reinforcement for cement concrete i/c cutting bending laying in position making of joints and fastenings i/c cost of binding wire (also i/cs removal of rust from bars)[(a)Mild bars.(S.I.No:8 (a)/P-16){(b)Tor bars.(S.I.No:8 (b)/P-16)}]
| Tor | 90 | Cwt | 5001.7 | P.Cwt | 450153
02. | S/F in position iron steel grill of 3/4"x1/4" size flate iron of approved design i/c painting 3-coats etc complete (weight not to be less than 3.7 Lbs: / square foot of finished grill) (S.I.No.26/P-92) | 228 | Sft | 180.5 | P.Sft | 41154
|  | Total Amount |  |  |  | 491307 | /=
PART-C MAIN BUILDING
01 | Ist: class deodar wood wrought joinery work in wire gauze door & windows with 22-SWG. Galvanized wire gauze 144-mesh per square inch iron fittings complete.(b) 1-1/2" thick deodar wood framming i/c wire gauze with spring hinges. (SI No:14(b) P-58) | 49 | Sft | 562.98 | P.Sft | 27586.02
02 | Laying white marble 3/4" thick flooring fine dressed in the surface without winging set in lime mortar 1:2 i/c rubbing and polishing of the joints.(SI No:28/ P-42) | 1389.5625 | Sft | 567.48 | P.Sft | 788797
|  | Total |  |  |  | 816383.02 | /=
| GENERAL | ABSTRACT
| PART "A" | 3347769.0499
| PART "B" | 491307
| PART "C" | 816383.02
| G.TOTAL | 4655459.0699
NOTE: -
Any error or ommission in the Schedul "B" will be governed by the schedul of rates.
No. premium will be allowed on Non-Schedule items.
Cartage will not be paid for any meterials.
Mat: use in the work of finished product can be got tested from any approved lab: at the discreation of the XEN or his representitive & all expanses in conn: with such testing should be born by the cont exclusivaly without any re-imburament or cleim against the Government on his account.
CONTRACTOR
EXECUTIVE ENGINEER
BUILDINGS DIVISION
T.M.KHAN

## Measurement Sheet (hidden)
MEASUREMENT SHEET
NAME OF WORK:- Constt: of Catg: -II Bunglow for BPS-18 to BPS-19 at B&R Colony T.M.Khan (Bunglow No-3) (01 No).
S.No. | Description | Measurement | [15 empty] | Quantity
|  | No. |  |  | Length |  | Width |  |  | Height/Depth
PART-A CIVIL WORK (i) Main Buildings
01. | Excavation of foundation of building bridges and other structure
Horizetal Walls 13-1/2" thick
| Guest/bath wall | 1 | × | 22.00 | × | 3.00 | × | 3.00 | [8 empty] | ═ | 198 | Cft
| Drawing room | 1 | × | 33.75 | × | 3.00 | × | 3.00 | [8 empty] | ═ | 303.75 | Cft
| Drawing room | 1 | × | 23.25 | × | 3.00 | × | 3.00 | [8 empty] | ═ | 209.25 | Cft
| Loung | 1 | × | 24.19 | × | 3.00 | × | 3.00 | [8 empty] | ═ | 217.71 | Cft
| Bed | 1 | × | 40.18 | × | 3.00 | × | 3.00 | [8 empty] | ═ | 361.62 | Cft
| Bed Room | 1 | × | 19.25 | × | 3.00 | × | 3.00 | [8 empty] | ═ | 173.25 | Cft
| Bed Room | 1 | × | 13.19 | × | 3.00 | × | 3.00 | [8 empty] | ═ | 118.71 | Cft
| Loung v/w | 1 | × | 10.13 | × | 3.00 | × | 3.00 | [8 empty] | ═ | 91.17 | Cft
| Bed Room V/w | 1 | × | 14.13 | × | 3.00 | × | 3.00 | [8 empty] | ═ | 127.17 | Cft
Vertical Walls 9" thick
| Guest/bath wall | 3 | × | 12.13 | × | 2.50 | × | 3.00 | [8 empty] | ═ | 272.925 | Cft
| D/Room | 2 | × | 14.13 | × | 2.50 | × | 3.00 | [8 empty] | ═ | 211.95 | Cft
| Store/Kit:/H/W | 1 | × | 17.25 | × | 2.50 | × | 3.00 | [8 empty] | ═ | 129.375 | Cft
| Store/Kit:/H/W | 2 | × | 10.94 | × | 2.50 | × | 3.00 | [8 empty] | ═ | 164.1 | Cft
|  | 1 | × | 13.57 | × | 2.50 | × | 3.00 | [8 empty] | ═ | 101.775 | Cft
| Bed H/W | 1 | × | 17.82 | × | 2.50 | × | 3.00 | [8 empty] | ═ | 133.65 | Cft
| Bed/bath/V/W | 1 | × | 11.75 | × | 2.50 | × | 3.00 | [8 empty] | ═ | 88.125 | Cft
| Bath/H/W | 1 | × | 4.69 | × | 2.50 | × | 3.00 | [8 empty] | ═ | 35.175 | Cft
| Bath/V/W | 1 | × | 10.25 | × | 2.50 | × | 3.00 | [8 empty] | ═ | 76.875 | Cft
| Servant room H/W | 1 | × | 5.25 | × | 2.50 | × | 3.00 | [8 empty] | ═ | 39.375 | Cft
| Servant room V/W | 2 | × | 13.25 | × | 2.50 | × | 3.00 | [8 empty] | ═ | 198.75 | Cft
| Bath V/W | 2 | × | 8.25 | × | 2.50 | × | 3.00 | [8 empty] | ═ | 123.75 | Cft
| Bath H/W | 1 | × | 7.25 | × | 2.50 | × | 3.00 | [8 empty] | ═ | 54.375 | Cft
| Bath H/W | 2 | × | 4.25 | × | 2.50 | × | 3.00 | [8 empty] | ═ | 63.75 | Cft
[16 empty] | Total | ═ | 3494.58 | Cft
02. | C.C brick or stone ballast 1.1/2" to 2" gauge ratio 1:4:8
| Same Qty as Item No. 01 |  |  |  |  | 3494.58 | × | 0.75 | ÷ | 3.00 | [6 empty] | ═ | 873.645 | Cft
03. | P.B.Work in foundation & Plinth 1:6 …….
1st Step
Horizental 13-1/2" thick wall
| Guest/bath room | 1 | × | 21.37 | × | 2.25 | × | 0.50 | [8 empty] | ═ | 24.0413 | Cft
| D/room | 1 | × | 33.17 | × | 2.25 | × | 0.50 | [8 empty] | ═ | 37.3163 | Cft
| D/room | 1 | × | 22.62 | × | 2.25 | × | 0.50 | [8 empty] | ═ | 25.4475 | Cft
| Lounge | 1 | × | 24.13 | × | 2.25 | × | 0.50 | [8 empty] | ═ | 27.1462 | Cft
| Lounge V/W | 1 | × | 10.87 | × | 2.25 | × | 0.50 | [8 empty] | ═ | 12.2287 | Cft
| Bed/Store room | 1 | × | 37.63 | × | 2.25 | × | 0.50 | [8 empty] | ═ | 42.3338 | Cft
| Bed room | 1 | × | 14.87 | × | 2.25 | × | 0.50 | [8 empty] | ═ | 16.7287 | Cft
| Bed room | 1 | × | 13.13 | × | 2.25 | × | 0.50 | [8 empty] | ═ | 14.7713 | Cft
| Bed room | 1 | × | 14.87 | × | 2.25 | × | 0.50 | [8 empty] | ═ | 16.7287 | Cft
Vertical wall 9" thick
| Guest/bath wall | 3 | × | 12.87 | × | 1.87 | × | 0.50 | [8 empty] | ═ | 36.1003 | Cft
| D/room | 2 | × | 14.87 | × | 1.87 | × | 0.50 | [8 empty] | ═ | 27.8069 | Cft
| Store/Kit: | 2 | × | 11.62 | × | 1.87 | × | 0.50 | [8 empty] | ═ | 21.7294 | Cft
| Store/Kit:/H/W | 1 | × | 10.25 | × | 1.87 | × | 0.50 | [8 empty] | ═ | 9.5838 | Cft
| Bed/Bath | 1 | × | 14.50 | × | 1.87 | × | 0.50 | [8 empty] | ═ | 13.5575 | Cft
| Bed/Bath | 1 | × | 18.50 | × | 1.87 | × | 0.50 | [8 empty] | ═ | 17.2975 | Cft
| Bath H/W | 1 | × | 11.12 | × | 1.87 | × | 0.50 | [8 empty] | ═ | 10.3972 | Cft
| Bath V/W | 1 | × | 5.37 | × | 1.87 | × | 0.50 | [8 empty] | ═ | 5.021 | Cft
| Bath V/W | 1 | × | 9.62 | × | 1.87 | × | 0.50 | [8 empty] | ═ | 8.9947 | Cft
| Bath V/W | 1 | × | 5.87 | × | 1.87 | × | 0.50 | [8 empty] | ═ | 5.4885 | Cft
| Servant room | 2 | × | 12.62 | × | 1.87 | × | 0.50 | [8 empty] | ═ | 23.5994 | Cft
| Servant room | 2 | × | 8.87 | × | 1.87 | × | 0.50 | [8 empty] | ═ | 16.5869 | Cft
| Bath V/W | 2 | × | 4.87 | × | 1.87 | × | 0.50 | [8 empty] | ═ | 9.1069 | Cft
| Bath V/W | 1 | × | 6.62 | × | 1.87 | × | 0.50 | [8 empty] | ═ | 6.1897 | Cft
2nd Step
Horizental Walls
| Guest/bath wall | 1 | × | 21.00 | × | 1.87 | × | 0.75 | [8 empty] | ═ | 29.4525 | Cft
| D/room | 1 | × | 32.75 | × | 1.87 | × | 0.75 | [8 empty] | ═ | 45.9319 | Cft
| D/room H/W | 1 | × | 22.25 | × | 1.87 | × | 0.75 | [8 empty] | ═ | 31.2056 | Cft
| Lounge H/W | 1 | × | 24.13 | × | 1.87 | × | 0.75 | [8 empty] | ═ | 33.8423 | Cft
| Lounge H/W | 1 | × | 11.25 | × | 1.87 | × | 0.75 | [8 empty] | ═ | 15.7781 | Cft
| Bed/Store room | 1 | × | 37.63 | × | 1.87 | × | 0.75 | [8 empty] | ═ | 52.7761 | Cft
| Bed room H/W | 1 | × | 15.25 | × | 1.87 | × | 0.75 | [8 empty] | ═ | 21.3881 | Cft
| Bed h/W | 1 | × | 12.94 | × | 1.87 | × | 0.75 | [8 empty] | ═ | 18.1484 | Cft
| Bed Room V/W | 1 | × | 15.25 | × | 1.87 | × | 0.75 | [8 empty] | ═ | 21.3881 | Cft
Vertical Walls
| Guest/bath | 3 | × | 13.25 | × | 1.50 | × | 0.75 | [8 empty] | ═ | 44.7188 | Cft
| D/Room | 2 | × | 15.25 | × | 1.50 | × | 0.75 | [8 empty] | ═ | 34.3125 | Cft
| Kit:/Store/V/W | 2 | × | 12.00 | × | 1.50 | × | 0.75 | [8 empty] | ═ | 27 | Cft
| Kit:/Store H/W | 1 | × | 17.25 | × | 1.50 | × | 0.75 | [8 empty] | ═ | 19.4062 | Cft
| Bed/Bath V/W | 1 | × | 14.63 | × | 1.50 | × | 0.75 | [8 empty] | ═ | 16.4588 | Cft
| Bath V/W | 1 | × | 6.25 | × | 1.50 | × | 0.75 | [8 empty] | ═ | 7.0312 | Cft
| Bath H/W | 1 | × | 9.25 | × | 1.50 | × | 0.75 | [8 empty] | ═ | 10.4062 | Cft
| Bed Bath | 1 | × | 18.87 | × | 1.50 | × | 0.75 | [8 empty] | ═ | 21.2287 | Cft
| Bath H/W | 1 | × | 10.75 | × | 1.50 | × | 0.75 | [8 empty] | ═ | 12.0938 | Cft
| Bath V/W | 1 | × | 5.56 | × | 1.50 | × | 0.75 | [8 empty] | ═ | 6.255 | Cft
| Servant room | 2 | × | 12.25 | × | 1.50 | × | 0.75 | [8 empty] | ═ | 27.5625 | Cft
| Servant room V/W | 2 | × | 9.25 | × | 1.50 | × | 0.75 | [8 empty] | ═ | 20.8125 | Cft
| Bath V/W | 1 | × | 6.25 | × | 1.50 | × | 0.75 | [8 empty] | ═ | 7.0312 | Cft
| Bath H/W | 2 | × | 5.25 | × | 1.50 | × | 0.75 | [8 empty] | ═ | 11.8125 | Cft
[16 empty] | Total | ═ | 964.2432 | Cft
04. | CC Plain 1:3:6…..
Horizental Walls
| Guest room | 1 | × | 20.50 | × | 1.25 | × | 3.50 | [8 empty] | ═ | 89.6875 | Cft
| D/Room | 1 | × | 32.25 | × | 1.25 | × | 3.50 | [8 empty] | ═ | 141.0938 | Cft
| D/Room | 1 | × | 21.75 | × | 1.25 | × | 3.50 | [8 empty] | ═ | 95.1562 | Cft
| Lounge | 1 | × | 24.08 | × | 1.25 | × | 3.50 | [8 empty] | ═ | 105.35 | Cft
| Lounge V/W | 1 | × | 11.87 | × | 1.25 | × | 3.50 | [8 empty] | ═ | 51.9312 | Cft
| Bed room/Store | 1 | × | 26.58 | × | 1.25 | × | 3.50 | [8 empty] | ═ | 116.2875 | Cft
| Bed room | 1 | × | 15.75 | × | 1.25 | × | 3.50 | [8 empty] | ═ | 68.9062 | Cft
| Bed room H/W | 1 | × | 12.87 | × | 1.25 | × | 3.50 | [8 empty] | ═ | 56.3062 | Cft
| Bed Room V/w | 1 | × | 15.87 | × | 1.25 | × | 3.50 | [8 empty] | ═ | 69.4312 | Cft
Vertical Walls
| Guest/bath | 3 | × | 13.87 | × | 1.00 | × | 3.50 | [8 empty] | ═ | 145.635 | Cft
| D/Room | 2 | × | 15.87 | × | 1.00 | × | 3.50 | [8 empty] | ═ | 111.09 | Cft
| Kit:/Store/V/W | 2 | × | 12.56 | × | 1.00 | × | 3.50 | [8 empty] | ═ | 87.92 | Cft
| Kit:/Store H/W | 1 | × | 17.25 | × | 1.00 | × | 3.50 | [8 empty] | ═ | 60.375 | Cft
| Bed V/W | 1 | × | 15.19 | × | 1.00 | × | 3.50 | [8 empty] | ═ | 53.165 | Cft
| Bath | 1 | × | 6.75 | × | 1.00 | × | 3.50 | [8 empty] | ═ | 23.625 | Cft
| Bath V/W | 1 | × | 8.75 | × | 1.00 | × | 3.50 | [8 empty] | ═ | 30.625 | Cft
| Bath H/W | 1 | × | 19.44 | × | 1.00 | × | 3.50 | [8 empty] | ═ | 68.04 | Cft
| Bath H/W | 1 | × | 10.25 | × | 1.00 | × | 3.50 | [8 empty] | ═ | 35.875 | Cft
| Bath V/W | 1 | × | 6.31 | × | 1.00 | × | 3.50 | [8 empty] | ═ | 22.085 | Cft
| Servant Room | 2 | × | 11.75 | × | 1.00 | × | 3.50 | [8 empty] | ═ | 82.25 | Cft
| Servant room V/W | 2 | × | 9.75 | × | 1.00 | × | 3.50 | [8 empty] | ═ | 68.25 | Cft
| Bath V/W | 2 | × | 5.75 | × | 1.00 | × | 3.50 | [8 empty] | ═ | 40.25 | Cft
| Bath H/W | 1 | × | 5.75 | × | 1.00 | × | 3.50 | [8 empty] | ═ | 20.125 | Cft
[16 empty] | Total | ═ | 1643.46 | Cft
05. | Erection & Removal of centering…..
Horizental Walls
| Guest room | 1 | × | 2.00 | × | 20.50 | × | 3.50 | [8 empty] | ═ | 143.5 | Cft
| D/Room | 1 | × | 2.00 | × | 32.25 | × | 3.50 | [8 empty] | ═ | 225.75 | Cft
| D/Room | 1 | × | 2.00 | × | 21.75 | × | 3.50 | [8 empty] | ═ | 152.25 | Cft
| Lounge | 1 | × | 2.00 | × | 24.08 | × | 3.50 | [8 empty] | ═ | 168.56 | Cft
| Lounge V/W | 1 | × | 2.00 | × | 11.87 | × | 3.50 | [8 empty] | ═ | 83.09 | Cft
| Bed Room | 1 | × | 2.00 | × | 26.58 | × | 3.50 | [8 empty] | ═ | 186.06 | Cft
| Bed Room | 1 | × | 2.00 | × | 15.75 | × | 3.50 | [8 empty] | ═ | 110.25 | Cft
| Bed room H/W | 1 | × | 2.00 | × | 12.87 | × | 3.50 | [8 empty] | ═ | 90.09 | Cft
| Bed Room V/W | 1 | × | 2.00 | × | 15.87 | × | 3.50 | [8 empty] | ═ | 111.09 | Cft
Vertical Walls
| Guest | 3 | × | 2.00 | × | 13.87 | × | 3.50 | [8 empty] | ═ | 291.27 | Cft
| D/Room | 2 | × | 2.00 | × | 15.87 | × | 3.50 | [8 empty] | ═ | 222.18 | Cft
| Kit:/Store | 2 | × | 2.00 | × | 12.56 | × | 3.50 | [8 empty] | ═ | 175.84 | Cft
| Kit:/Store H/W | 1 | × | 2.00 | × | 17.25 | × | 3.50 | [8 empty] | ═ | 120.75 | Cft
| Bed V/W | 1 | × | 2.00 | × | 15.19 | × | 3.50 | [8 empty] | ═ | 106.33 | Cft
| Bath V/W | 1 | × | 2.00 | × | 6.75 | × | 3.50 | [8 empty] | ═ | 47.25 | Cft
| Bath H/W | 1 | × | 2.00 | × | 8.75 | × | 3.50 | [8 empty] | ═ | 61.25 | Cft
| Bath H/W | 1 | × | 2.00 | × | 19.44 | × | 3.50 | [8 empty] | ═ | 136.08 | Cft
| Bath V/W | 1 | × | 2.00 | × | 10.25 | × | 3.50 | [8 empty] | ═ | 71.75 | Cft
| Bath V/W | 1 | × | 2.00 | × | 6.31 | × | 3.50 | [8 empty] | ═ | 44.17 | Cft
| Servant room | 2 | × | 2.00 | × | 11.75 | × | 3.50 | [8 empty] | ═ | 164.5 | Cft
| Servant room | 2 | × | 2.00 | × | 9.75 | × | 3.50 | [8 empty] | ═ | 136.5 | Cft
| Bath H/W | 2 | × | 2.00 | × | 5.75 | × | 3.50 | [8 empty] | ═ | 80.5 | Cft
| Bath V/W | 1 | × | 2.00 | × | 5.75 |  | 3.50 | [8 empty] | ═ | 40.25 | Cft
[16 empty] | Total | ═ | 2969.26 | Cft
06. | Filling, watering and ramming surplus earth from foundation & lift upto 5'ft….
| Same Qty as Item No. 01 |  |  |  |  | 3494.58 | × | 2/3 | [7 empty] | Total | ═ | 2327.3903 | Cft
07. | Filling, watering and ramming new earth (excavated from outside) & lift upto 5'ft:…….
| Guest room | 1 | × | 11.63 | × | 13.63 | × | 1.50 | [8 empty] | ═ | 237.7754 | Cft
| Bath | 1 | × | 5.63 | × | 13.63 | × | 1.50 | [8 empty] | ═ | 115.1054 | Cft
| Drawing room | 1 | × | 22.63 | × | 15.63 | × | 1.50 | [8 empty] | ═ | 530.5603 | Cft
| Lounge | 1 | × | 22.63 | × | 11.63 | × | 1.50 | [8 empty] | ═ | 394.7803 | Cft
| Kit: | 1 | × | 8.37 | × | 12.37 | × | 1.50 | [8 empty] | ═ | 155.3053 | Cft
| Store | 1 | × | 6.63 | × | 12.37 | × | 1.50 | [8 empty] | ═ | 123.0196 | Cft
| Bed Room | 1 | × | 15.63 | × | 11.63 | × | 1.50 | [8 empty] | ═ | 272.6653 | Cft
| Bed Room | 1 | × | 11.63 | × | 15.63 | × | 1.50 | [8 empty] | ═ | 272.6653 | Cft
| Bath | 1 | × | 6.63 | × | 6.63 | × | 1.50 | [8 empty] | ═ | 65.9353 | Cft
| Bath | 1 | × | 8.13 | × | 6.13 | × | 1.50 | [8 empty] | ═ | 74.7554 | Cft
| Servant Room | 1 | × | 9.63 | × | 9.63 | × | 1.50 | [8 empty] | ═ | 139.1054 | Cft
| Bath | 1 | × | 5.63 | × | 3.63 | × | 1.50 | [8 empty] | ═ | 30.6553 | Cft
[16 empty] | Total | ═ | 2412.3285 | Cft
08. | S/F Sand under floor……
| Same Qty as Item No. 07 |  |  |  |  | 2412.3285 | × | 0.5 | ÷ | 1.50 | [5 empty] | Total | ═ | 804.1095 | Cft
09. | Extra lead for 3 miles….
| Same Qty as Item No. 07 + 08 |  |  |  |  | 2412.3285 | + | 804.1095 | [7 empty] | Total | ═ | 3216.438 | Cft
10. | R.C.C work (1:2:4) i/c all labour………..
(A) Plinth Beam
| Same Qty as Item No. 04 |  |  |  |  | 1643.46 | × | 0.5 | ÷ | 3.50 | [5 empty] | Total | ═ | 234.78 | Cft
(B) Lintels
| Bath Room | 1 | × | 10.00 | × | 0.75 | × | 0.75 | [8 empty] | ═ | 5.625 | Cft
| Bath Room | 1 | × | 3.25 | × | 0.75 | × | 0.75 | [8 empty] | ═ | 1.8281 | Cft
| Bed | 2 | × | 13.37 | × | 0.75 | × | 0.75 | [8 empty] | ═ | 15.0412 | Cft
| Door | 1 | × | 3.50 | × | 0.75 | × | 0.75 | [8 empty] | ═ | 1.9688 | Cft
| Door | 1 | × | 16.00 | × | 1.13 | × | 0.75 | [8 empty] | ═ | 13.56 | Cft
| Door | 1 | × | 16.50 | × | 1.13 | × | 0.75 | [8 empty] | ═ | 13.9838 | Cft
| Bed Room s/s | 2 | × | 16.00 | × | 1.13 | × | 0.75 | [8 empty] | ═ | 27.12 | Cft
| S/Wall | 1 | × | 13.50 | × | 0.75 | × | 0.75 | [8 empty] | ═ | 7.5938 | Cft
| Store /Bath | 2 | × | 8.50 | × | 0.75 | × | 0.75 | [8 empty] | ═ | 9.5625 | Cft
| Kitchen b/s | 1 | × | 9.50 | × | 0.75 | × | 0.75 | [8 empty] | ═ | 5.3438 | Cft
| s/wall | 1 | × | 13.50 | × | 0.75 | × | 0.75 | [8 empty] | ═ | 7.5938 | Cft
| Lounge f/s | 1 | × | 24.00 | × | 1.13 | × | 0.75 | [8 empty] | ═ | 20.34 | Cft
| s/wall | 2 | × | 12.70 | × | 0.75 | × | 0.75 | [8 empty] | ═ | 14.2875 | Cft
| D/B Hall E/S | 1 | × | 14.75 | × | 1.13 | × | 0.75 | [8 empty] | ═ | 12.5006 | Cft
| S/Wall | 1 | × | 16.00 | × | 0.75 | × | 0.75 | [8 empty] | ═ | 9 | Cft
| f/s | 2 | × | 5.00 | × | 0.75 | × | 0.75 | [8 empty] | ═ | 5.625 | Cft
| Guest | 1 | × | 13.50 | × | 0.75 | × | 0.75 | [8 empty] | ═ | 7.5938 | Cft
| B/Side | 1 | × | 14.75 | × | 0.75 | × | 0.75 | [8 empty] | ═ | 8.2969 | Cft
| S/Wall | 1 | × | 15.50 | × | 0.75 | × | 0.75 | [8 empty] | ═ | 8.7188 | Cft
| Bath Lobby | 2 | × | 6.75 | × | 0.75 | × | 0.75 | [8 empty] | ═ | 7.5938 | Cft
| S/Wall | 2 | × | 12.50 | × | 0.75 | × | 0.75 | [8 empty] | ═ | 14.0625 | Cft
| Porch F/s | 2 | × | 11.50 | × | 0.75 | × | 0.75 | [8 empty] | ═ | 12.9375 | Cft
| Porch F/s | 1 | × | 10.00 | × | 0.75 | × | 0.75 | [8 empty] | ═ | 5.625 | Cft
| Porch F/s | 1 | × | 7.50 | × | 0.75 | × | 0.75 | [8 empty] | ═ | 4.2188 | Cft
[16 empty] | Total | ═ | 240.0206 | Cft
(C) Chajja Shelves
| W1 | 1 | × | 5.00 | × | 1.50 | × | 0.25 | [8 empty] | ═ | 1.875 | Cft
| " " | 1 | × | 5.00 | × | 0.50 | × | 0.25 | [8 empty] | ═ | 0.625 | Cft
| " " | 1 | × | 9.50 | × | 2.00 | × | 0.25 | [8 empty] | ═ | 4.75 | Cft
| " " | 1 | × | 1.25 | × | 2.50 | × | 0.25 | [8 empty] | ═ | 0.78125 | Cft
| Door 3 | 4 | × | 4.00 | × | 1.50 | × | 0.25 | [8 empty] | ═ | 6 | Cft
| " " | 1 | × | 7.00 | × | 0.50 | × | 0.25 | [8 empty] | ═ | 0.875 | Cft
| W1 | 4 | × | 4.00 | × | 1.50 | × | 0.25 | [8 empty] | ═ | 6 | Cft
| " " | 4 | × | 4.00 | × | 0.50 | × | 0.25 | [8 empty] | ═ | 2 | Cft
| " " | 1 | × | 23.00 | × | 1.50 | × | 0.25 | [8 empty] | ═ | 8.625 | Cft
| " " | 1 | × | 23.00 | × | 1.25 | × | 0.25 | [8 empty] | ═ | 7.1875 | Cft
| " " | 1 | × | 7.00 | × | 0.75 | × | 0.25 | [8 empty] | ═ | 1.3125 | Cft
| " " | 1 | × | 7.00 | × | 0.50 | × | 0.25 | [8 empty] | ═ | 0.875 | Cft
| " " | 1 | × | 7.00 | × | 0.50 | × | 0.25 | [8 empty] | ═ | 0.875 | Cft
| " " | 3 | × | 3.75 | × | 2.50 | × | 0.25 | [8 empty] | ═ | 7.0312 | Cft
| " " | 2 | × | 6.13 | × | 2.50 | × | 0.25 | [8 empty] | ═ | 7.6625 | Cft
| " " | 1 | × | 9.50 | × | 2.25 | × | 0.25 | [8 empty] | ═ | 5.3438 | Cft
| " " | 1 | × | 6.00 | × | 2.25 | × | 0.25 | [8 empty] | ═ | 3.375 | Cft
| " " | 10 | × | 1.00 | × | 0.25 | × | 7.00 | [8 empty] | ═ | 17.5 | Cft
[16 empty] | Total | ═ | 82.6937 | Cft
(D) One Way Slab
| Bath | 1 | × | 10.00 | × | 8.37 | × | 0.33 | [8 empty] | ═ | 27.621 | Cft
| Bed Room | 1 | × | 14.12 | × | 15.12 | × | 0.50 | [8 empty] | ═ | 106.7472 | Cft
| Bed Room | 1 | × | 18.25 | × | 14.12 | × | 0.50 | [8 empty] | ═ | 128.845 | Cft
| Bath | 1 | × | 18.50 | × | 8.50 | × | 0.33 | [8 empty] | ═ | 51.8925 | Cft
| Store | 1 | × | 8.50 | × | 8.75 | × | 0.33 | [8 empty] | ═ | 24.5438 | Cft
| Guest room | 1 | × | 13.50 | × | 16.25 | × | 0.50 | [8 empty] | ═ | 109.6875 | Cft
| Bath/toilet | 1 | × | 7.50 | × | 15.88 | × | 0.33 | [8 empty] | ═ | 39.303 | Cft
| Porch | 1 | × | 12.50 | × | 25.10 | × | 0.42 | [8 empty] | ═ | 131.775 | Cft
| Servant quarter | 1 | × | 13.50 | × | 16.00 | × | 0.42 | [8 empty] | ═ | 90.72 | Cft
| Servant quarter | 2 | × | 13.50 | × | 0.50 | × | 0.25 | [8 empty] | ═ | 3.375 | Cft
[16 empty] | Total | ═ | 714.51 | Cft
(E) Two Way Slab
|  | 1 | × | 18.25 | × | 14.39 | × | 0.50 | [8 empty] | ═ | 131.3088 | Cft
|  | 1 | × | 23.38 | × | 12.94 | × | 0.50 | [8 empty] | ═ | 151.2686 | Cft
|  | 1 | × | 27.00 | × | 15.50 | × | 0.50 | [8 empty] | ═ | 209.25 | Cft
[16 empty] | Total | ═ | 491.8274 | Cft
[10 empty] | G.Total:A+B+C+D+E | [6 empty] | ═ | 1763.8317 | Cft
11. | Pacca brick work in ground floor 1:6….
| Guest/bath/H/W | 1 | × | 20.25 | × | 1.13 | × | 11.00 | [8 empty] | ═ | 251.7075 | Cft
| D/Room H/W | 1 | × | 32.00 | × | 1.13 | × | 11.00 | [8 empty] | ═ | 397.76 | Cft
| D/Room H/W | 1 | × | 25.50 | × | 1.13 | × | 13.50 | [8 empty] | ═ | 389.0025 | Cft
| Lounge | 1 | × | 24.13 | × | 1.13 | × | 11.00 | [8 empty] | ═ | 299.9359 | Cft
| Bed Room H/W | 1 | × | 36.50 | × | 1.13 | × | 11.00 | [8 empty] | ═ | 453.695 | Cft
| Bed Room H/W | 1 | × | 12.00 | × | 1.13 | × | 11.00 | [8 empty] | ═ | 149.16 | Cft
| Bed Room H/W | 1 | × | 16.00 | × | 1.13 | × | 11.00 | [8 empty] | ═ | 198.88 | Cft
| Bath H/W | 1 | × | 10.00 | × | 0.75 | × | 11.00 | [8 empty] | ═ | 82.5 | Cft
| Bath H/W | 1 | × | 8.50 | × | 0.75 | × | 11.00 | [8 empty] | ═ | 70.125 | Cft
| Kit:/Store H/W | 1 | × | 17.25 | × | 0.75 | × | 11.00 | [8 empty] | ═ | 142.3125 | Cft
| Guest /Bath | 3 | × | 14.00 | × | 0.75 | × | 11.00 | [8 empty] | ═ | 346.5 | Cft
| Porch | 1 | × | 20.13 | × | 0.75 | × | 9.00 | [8 empty] | ═ | 135.8775 | Cft
| D/Room V/W | 2 | × | 16.00 | × | 0.75 | × | 13.50 | [8 empty] | ═ | 324 | Cft
| D/Room | 1 | × | 21.50 | × | 1.13 | × | 2.50 | [8 empty] | ═ | 60.7375 | Cft
| Bed/ Lounge V/W | 1 | × | 30.25 | × | 1.13 | × | 11.00 | [8 empty] | ═ | 376.0075 | Cft
| Bed/Bath V/W | 1 | × | 19.63 | × | 0.75 | × | 11.00 | [8 empty] | ═ | 161.9475 | Cft
| Bath V/W | 1 | × | 6.50 | × | 0.75 | × | 11.00 | [8 empty] | ═ | 53.625 | Cft
| Store / Bath V/W | 1 | × | 15.37 | × | 0.75 | × | 11.00 | [8 empty] | ═ | 126.8025 | Cft
| Bath V/W | 1 | × | 7.00 | × | 0.75 | × | 11.00 | [8 empty] | ═ | 57.75 | Cft
| Kit: V/W | 2 | × | 12.75 | × | 0.75 | × | 11.00 | [8 empty] | ═ | 210.375 | Cft
| Servant room | 2 | × | 11.50 | × | 0.75 | × | 11.00 | [8 empty] | ═ | 189.75 | Cft
| Servant Room V/W | 2 | × | 10.00 | × | 0.75 | × | 11.00 | [8 empty] | ═ | 165 | Cft
| Bath | 2 | × | 6.75 | × | 0.75 | × | 11.00 | [8 empty] | ═ | 111.375 | Cft
| Bath V/W | 1 | × | 4.00 | × | 0.75 | × | 11.00 | [8 empty] | ═ | 33 | Cft
[16 empty] | Total | ═ | 4787.8259 | Cft
Deduction:
| (A) | Same Qty as Item No. 10 (B) | [13 empty] | Total | ═ | 240.0206 | Cft
(B)
| D1 | 5 | × | 3.50 | × | 1.13 | × | 7.00 | [8 empty] | ═ | 138.425 | Cft
| D1 | 1 | × | 3.50 | × | 0.75 | × | 7.00 | [8 empty] | ═ | 18.375 | Cft
| D2 | 4 | × | 3.00 | × | 0.75 | × | 7.00 | [8 empty] | ═ | 63 | Cft
| D3 | 3 | × | 2.50 | × | 0.75 | × | 7.00 | [8 empty] | ═ | 39.375 | Cft
| D3 | 1 | × | 2.50 | × | 0.37 | × | 7.00 | [8 empty] | ═ | 6.475 | Cft
| W | 5 | × | 6.00 | × | 1.13 | × | 4.00 | [8 empty] | ═ | 135.6 | Cft
| W | 2 | × | 6.00 | × | 0.75 | × | 4.00 | [8 empty] | ═ | 36 | Cft
| W1 | 2 | × | 4.50 | × | 0.75 | × | 4.00 | [8 empty] | ═ | 27 | Cft
| W2 | 2 | × | 3.00 | × | 1.13 | × | 4.00 | [8 empty] | ═ | 27.12 | Cft
| W3 | 3 | × | 3.00 | × | 0.75 | × | 6.00 | [8 empty] | ═ | 40.5 | Cft
| W2 | 1 | × | 3.00 | × | 0.75 | × | 4.00 | [8 empty] | ═ | 9 | Cft
| W3 | 3 | × | 3.00 | × | 1.13 | × | 6.00 | [8 empty] | ═ | 61.02 | Cft
| HW | 1 | × | 6.00 | × | 0.75 | × | 1.50 | [8 empty] | ═ | 6.75 | Cft
| HW1 | 5 | × | 3.00 | × | 0.75 | × | 1.50 | [8 empty] | ═ | 16.875 | Cft
[16 empty] | Total | ═ | 625.515 | Cft
[12 empty] | Total of Deduction (A+B) |  |  |  |  | ═ | 865.5356 | Cft
|  |  | NET QTY: |  | ( | 4787.8259 | ─ | 865.5356 | ) | [6 empty] | Total | ═ | 3922.2903 | Cft
12 | 1st Class Deodar wood (Shutters)…
Doors
| D | 1 | × | 4.00 | × | 7.00 | [10 empty] | ═ | 28 | Sft
| D1 | 4 | × | 3.50 | × | 7.00 | [10 empty] | ═ | 98 | Sft
| D2 | 3 | × | 3.00 | × | 7.00 | [10 empty] | ═ | 63 | Sft
| D3 | 7 | × | 2.50 | × | 7.00 | [10 empty] | ═ | 122.5 | Sft
| D4 | 1 | × | 4.00 | × | 6.50 | [10 empty] | ═ | 26 | Sft
| D5 | 1 | × | 3.50 | × | 5.25 | [10 empty] | ═ | 18.375 | Sft
| D4 | 1 | × | 3.14 | × | 2.00 | [10 empty] | ═ | 3.14 | Sft
2
1.57
| D5 | 1 | × | 3.14 | × | 1.75 | [10 empty] | ═ | 2.7475 | Sft
2
1.57
Windows
| W | 5 | × | 6.00 | × | 4.00 | [10 empty] | ═ | 120 | Sft
| W1 | 2 | × | 4.50 | × | 4.00 | [10 empty] | ═ | 36 | Sft
| W2 | 6 | × | 3.00 | × | 4.00 | [10 empty] | ═ | 72 | Sft
| W3 | 1 | × | 2.00 | × | 4.00 | [10 empty] | ═ | 8 | Sft
| W4 | 3 | × | 3.14 | ×( | 1.50 | × | 2.00 | × | 5.50 | ) | [5 empty] | ═ | 77.715 | Sft
2
1.57
| H.W | 1 | × | 6.00 | × | 1.50 | [10 empty] | ═ | 9 | Sft
| HE.1 | 6 | × | 3.00 | × | 1.50 | [10 empty] | ═ | 27 | Sft
| Servant room D | 1 | × | 3.00 | × | 7.00 | [10 empty] | ═ | 21 | Sft
| W | 2 | × | 3.00 | × | 4.00 | [10 empty] | ═ | 24 | Sft
[16 empty] | Total | ═ | 756.4775 | Sft
13 | P/F G.I Frame/Chowkats for Doors….
| D | 1 | ×( | 4.00 | + | 7.00 | + | 7.00 | ) | [7 empty] | ═ | 18 | Rft
| D1 | 4 | ×( | 3.50 | + | 7.00 | + | 7.00 | ) | [7 empty] | ═ | 70 | Rft
| D2 | 4 | ×( | 3.00 | + | 7.00 | + | 7.00 | ) | [7 empty] | ═ | 68 | Rft
| D3 | 7 | ×( | 2.50 | + | 7.00 | + | 7.00 | ) | [7 empty] | ═ | 115.5 | Rft
| D4 | 1 | ×( | 4.00 | + | 6.50 | + | 6.50 | ) | [7 empty] | ═ | 17 | Rft
| D5 | 1 | × | 3.14 | × | 4.00 | [10 empty] | ═ | 6.28 | Rft
2
|  |  |  | 1.57 | [14 empty] | Rft
|  | 1 | × | 14 | [12 empty] | ═ | 14 | Rft
|  | 1 | × | 3.14 | × | 3.50 | [10 empty] | ═ | 5.495 | Rft
2
|  |  |  | 1.57 | [14 empty] | Rft
[16 empty] | Total | ═ | 314.275 | Rft
14 | P/F G.I Frame/Chowkats for windows….
| W | 5 | ×( | 2 | × | 6 | )+( | 2 | × | 4 | )+( | 3 | × | 3.5 | ) |  | ═ | 152.5 | Rft
[5 empty] | 12 |  |  |  | 8 |  |  |  | 10.5
| W1 | 2 | ×( | 2 | × | 4.5 | )+( | 2 | × | 4 | )+( | 2 | × | 3.5 | ) |  | ═ | 48 | Rft
[5 empty] | 9 |  |  |  | 8 |  |  |  | 7
| W2 | 8 | ×( | 2 | × | 3 | )+( | 2 | × | 4 | )+( | 1 | × | 3.5 | ) |  | ═ | 140 | Rft
[5 empty] | 6 |  |  |  | 8 |  |  |  | 3.5
| W3 | 1 | ×( | 2 | × | 2 | )+( | 2 | × | 4 | ) | [5 empty] | ═ | 12 | Rft
[5 empty] | 4 |  |  |  | 8
| W4 | 3 | × | 3.14 | × | 3.00 | [10 empty] | ═ | 14.13 | Rft
2
1.57
| HW | 1 | ×( | 2 | × | 6 | )+( | 2 | × | 1.5 | )+( | 3 | × | 1 | ) |  | ═ | 18 | Rft
[5 empty] | 12 |  |  |  | 3 |  |  |  | 3
| HW1 | 6 | ×( | 2 | × | 3 | )+( | 2 | × | 1.5 | )+( | 1 | × | 1 | ) |  | ═ | 60 | Rft
[5 empty] | 6 |  |  |  | 3 |  |  |  | 1
[16 empty] | Total | ═ | 444.63 | Rft
15 | C.C Brick or stone ballast 1-1/2" to 2" gauge Ratio 1:5:10
| Same Qty as Item No. 08 |  |  |  |  | 804.1095 | × | 0.33 | ÷ | 2.00 | [5 empty] | Total | ═ | 132.6781 | Cft
16 | C.C.Plaster 1/2" (1:6) upto 20"….
| Bath room | 1 | × | 2.00 | ×( | 8.50 | + | 6.50 | )× | 8.50 | [6 empty] | ═ | 255 | Sft
| Bed room | 2 | × | 2.00 | ×( | 12.00 | + | 16.00 | )× | 12.00 | [6 empty] | ═ | 1344 | Sft
| Bath room | 1 | × | 2.00 | ×( | 7.00 | + | 7.00 | )× | 8.50 | [6 empty] | ═ | 238 | Sft
| Store | 1 | × | 2.00 | ×( | 7.00 | + | 7.63 | )× | 12.00 | [6 empty] | ═ | 351.12 | Sft
| Kitchen | 1 | × | 2.00 | ×( | 8.75 | + | 12.75 | )×( | 13 | + | 11 | ) |  |  |  | ═ | 795.5 | Sft
2
18.5
| Passage | 1 | × | 2.00 | ×( | 13.75 | + | 4.00 | )× | 12.00 | [6 empty] | ═ | 426 | Sft
| Drawing room | 1 | × | 2.00 | ×( | 23.00 | + | 16.00 | )× | 14.00 | [6 empty] | ═ | 1092 | Sft
| Lounge | 1 | × | 2.00 | ×( | 23.00 | + | 12.00 | )×( | 14 | + | 10 | ) |  |  |  | ═ | 1330 | Sft
2
19
| Guest Room | 1 | × | 2.00 | ×( | 12.00 | + | 14.00 | )× | 12.00 | [6 empty] | ═ | 624 | Sft
| Bath room | 1 | × | 2.00 | ×( | 6.00 | + | 9.13 | )× | 8.50 | [6 empty] | ═ | 257.21 | Sft
| Lobby | 1 | × | 2.00 | ×( | 6.00 | + | 4.50 | )× | 8.50 | [6 empty] | ═ | 178.5 | Sft
| Porch | 1 | × | 11.00 | × | 10.00 | × | 1.00 | [8 empty] | ═ | 110 | Sft
| Porch | 1 | × | 5.00 | × | 10.00 | × | 1.00 | [8 empty] | ═ | 50 | Sft
| Servant Room | 2 | × | 14.75 | × | 10.00 | × | 1.00 | [8 empty] | ═ | 295 | Sft
| Servant Room | 1 | × | 2.00 | ×( | 10.00 | + | 10.00 | )× | 10.00 | [6 empty] | ═ | 400 | Sft
| Bath Room | 1 | × | 2.00 | ×( | 6.00 | + | 4.00 | )× | 8.50 | [6 empty] | ═ | 170 | Sft
[16 empty] | Total | ═ | 7916.33 | Sft
Deduction:
| D1 | 1 | × | 4.00 | × | 7.00 | [10 empty] | ═ | 28 | Sft
| D2 | 3 | × | 3.50 | × | 7.00 | [10 empty] | ═ | 73.5 | Sft
| D3 | 3 | × | 2.50 | × | 7.00 | [10 empty] | ═ | 52.5 | Sft
| W2 | 6 | × | 4.00 | × | 4.50 | [10 empty] | ═ | 108 | Sft
| W3 | 2 | × | 3.00 | × | 4.00 | [10 empty] | ═ | 24 | Sft
| C.B | 1 | × | 2.00 | × | 4.00 | [10 empty] | ═ | 8 | Sft
| W.R | 2 | × | 5.75 | × | 6.50 | [10 empty] | ═ | 74.75 | Sft
[16 empty] | Total | ═ | 368.75 | Sft
|  |  | NET QTY: |  | ( | 7916.33 | ─ | 368.75 | ) | [6 empty] | Total | ═ | 7547.58 | Sft
17 | Cement pointing struck joints on walls….
| Bath | 1 | × | 2.50 | × | 8.50 | [10 empty] | ═ | 21.25 | Sft
| S/W | 1 | × | 7.25 | × | 8.50 | [10 empty] | ═ | 61.625 | Sft
| S/W | 1 | × | 10.00 | × | 13.50 | [10 empty] | ═ | 135 | Sft
| B/R | 2 | × | 13.37 | × | 13.50 | [10 empty] | ═ | 360.99 | Sft
| Bed R/W | 1 | × | 7.75 | × | 13.50 | [10 empty] | ═ | 104.625 | Sft
| Bed C/W | 1 | × | 9.42 | × | 8.50 | [10 empty] | ═ | 80.07 | Sft
| Kit:B/W | 1 | × | 17.87 | × | 13.50 | [10 empty] | ═ | 241.245 | Sft
| R/S Kit: | 1 | × | 8.75 | × | 8.50 | [10 empty] | ═ | 74.375 | Sft
| B/S L.S | 1 | × | 9.00 | × | 8.50 | [10 empty] | ═ | 76.5 | Sft
| Guest Room | 1 | × | 9.50 | × | 12.00 | [10 empty] | ═ | 114 | Sft
| Bath R/S | 1 | × | 13.50 | × | 11.00 | [10 empty] | ═ | 148.5 | Sft
| Lobby W.S | 1 | × | 18.25 | × | 11.00 | [10 empty] | ═ | 200.75 | Sft
| Lounge W.W | 1 | × | 13.50 | × | 12.00 | [10 empty] | ═ | 162 | Sft
| Lounge R.S | 1 | × | 6.75 | × | 8.50 | [10 empty] | ═ | 57.375 | Sft
| Servant Quarters | 1 | × | 15.87 | × | 11.00 | [10 empty] | ═ | 174.57 | Sft
| Bath B.S | 1 | × | 13.13 | ×( | 14.00 | + | 10.50 | ) | [7 empty] | ═ | 252.7525 | Sft
2
19.25
| Servant Quarters | 1 | × | 24.87 | × | 11.00 | [10 empty] | ═ | 273.57 | Sft
| Bath S.W | 1 | × | 13.00 | × | 8.00 | [10 empty] | ═ | 104 | Sft
| G.Red S/Side wall | 1 | × | 6.75 | × | 8.50 | [10 empty] | ═ | 57.375 | Sft
| " " | 1 | × | 11.00 | × | 9.00 | [10 empty] | ═ | 99 | Sft
| " " | 1 | × | 6.00 | × | 11.00 | [10 empty] | ═ | 66 | Sft
| " " | 1 | × | 11.00 | × | 4.25 | [10 empty] | ═ | 46.75 | Sft
| " " | 1 | × | 15.13 | × | 12.00 | [10 empty] | ═ | 181.56 | Sft
| " " | 1 | × | 9.25 | × | 12.00 | [10 empty] | ═ | 111 | Sft
[16 empty] | Total | ═ | 3204.8825 | Sft
Deduction:
|  | 5 | × | 6.00 | × | 4.00 | [10 empty] | ═ | 120 | Sft
|  | 2 | × | 6.00 | × | 4.00 | [10 empty] | ═ | 48 | Sft
|  | 2 | × | 3.00 | × | 1.00 | [10 empty] | ═ | 6 | Sft
|  | 3 | × | 3.00 | × | 4.00 | [10 empty] | ═ | 36 | Sft
|  | 1 | × | 2.00 | × | 1.00 | [10 empty] | ═ | 2 | Sft
[16 empty] | Total | ═ | 212 | Sft
|  |  | NET QTY: |  | ( | 3204.8825 | ─ | 212 | ) | [6 empty] | Total | ═ | 2992.8825 | Sft
18 | P/L C.C. Topping 2" thick (1:2:4)….
| Over Roof | 1 | × | 26.37 | × | 15.13 | [10 empty] | ═ | 398.9781 | Sft
|  | 1 | × | 10.00 | × | 7.50 | [10 empty] | ═ | 75 | Sft
|  | 1 | × | 24.75 | × | 16.00 | [10 empty] | ═ | 396 | Sft
|  | 1 | × | 7.13 | × | 16.13 | [10 empty] | ═ | 115.0069 | Sft
|  | 1 | × | 13.50 | × | 15.13 | [10 empty] | ═ | 204.255 | Sft
[16 empty] | Total | ═ | 1189.24 | Sft
19 | C.C.Plaster 3/8" (1:4) upto 20"….
| Same Qty as Item No. 17 | [15 empty] | ═ | 7547.58 | Sft
20 | White washing three coats…….
| D.D.Room | 1 | × | 23.00 | × | 16.00 | [10 empty] | ═ | 368 | Sft
| Lounge | 1 | × | 23.00 | × | 12.00 | [10 empty] | ═ | 276 | Sft
| Bed Room | 2 | × | 12.00 | × | 16.00 | [10 empty] | ═ | 384 | Sft
| Passage | 1 | × | 13.75 | × | 4.00 | [10 empty] | ═ | 55 | Sft
| Guest Room | 1 | × | 12.00 | × | 14.00 | [10 empty] | ═ | 168 | Sft
| Lobby | 1 | × | 6.00 | × | 4.50 | [10 empty] | ═ | 27 | Sft
| Kitchen | 1 | × | 8.75 | × | 12.75 | [10 empty] | ═ | 111.5625 | Sft
| Bath | 1 | × | 8.50 | × | 6.50 | [10 empty] | ═ | 55.25 | Sft
| Bath | 1 | × | 7.00 | × | 7.00 | [10 empty] | ═ | 49 | Sft
| Guest Room | 1 | × | 6.00 | × | 9.00 | [10 empty] | ═ | 54 | Sft
| Bath | 1 | × | 6.00 | × | 4.00 | [10 empty] | ═ | 24 | Sft
| Kitchen | 1 | × | 8.75 | × | 12.75 | [10 empty] | ═ | 111.5625 | Sft
[16 empty] | Total | ═ | 1683.375 | Sft
21 | Primary coat of chalk distemper.
| Same Qty as Item No. 17 | [15 empty] | ═ | 7547.58 | Sft
22 | Distempering two coats.
| Same Qty as Item No.26 | [15 empty] | ═ | 7547.58 | Sft
23 | R.C.C Spouts…..
|  | 1 | × | 6 | [12 empty] | ═ | 6 | Nos.
24 | PNS & Painting of doors & windows any type 3 coats…
| Same Qty as Item No.13 |  |  |  |  | 756.4775 | × | 2 | [8 empty] | ═ | 1512.955 | Sft
25 | Vertical blind window…..
| W | 5 | × | 6.00 | × | 4.00 | [9 empty] | Total | ═ | 120 | Sft
| W | 2 | × | 4.50 | × | 4.00 | [9 empty] | Total | ═ | 36 | Sft
[16 empty] | Total | ═ | 156 | Sft
PART-B MAIN BUILDING
01 | Febr: of mild steel RCC………
| 4% Qty of Item No.03 |  |  |  |  | 1763.8317 | - | 5.1025 | % | [7 empty] | ═ | 89.9995 | Cwt
02 | S/F in position iron steel grill…..
|  | 5 | × | 6.00 | × | 4.00 | [10 empty] | ═ | 120 | Sft
|  | 2 | × | 4.50 | × | 4.00 | [10 empty] | ═ | 36 | Sft
|  | 6 | × | 3.00 | × | 4.00 | [10 empty] | ═ | 72 | Sft
[16 empty] | Total | ═ | 228 | Sft
PART-C MAIN BUILDING
01 | 1-1/2" thick deodar wood framing….
|  | 2 | × | 3.50 | × | 7.00 | [9 empty] | Total | ═ | 49 | Sft
02 | White marble flooring 3/4" thick….
| D.D.Room | 1 | × | 23.00 | × | 16.00 | [10 empty] | ═ | 368 | Sft
| Lounge | 1 | × | 23.00 | × | 12.00 | [10 empty] | ═ | 276 | Sft
| Bed Room | 2 | × | 12.00 | × | 16.00 | [10 empty] | ═ | 384 | Sft
| Passage | 1 | × | 13.75 | × | 4.00 | [10 empty] | ═ | 55 | Sft
| Guest Room | 1 | × | 12.00 | × | 14.00 | [10 empty] | ═ | 168 | Sft
| Lobby | 1 | × | 6.00 | × | 4.50 | [10 empty] | ═ | 27 | Sft
| Kitchen | 1 | × | 8.75 | × | 12.75 | [10 empty] | ═ | 111.5625 | Sft
[16 empty] | Total | ═ | 1389.5625 | Sft
SUB-ENGINEER |  |  |  |  | ASSISSTANT ENGINEER | [8 empty] | EXECUTIVE ENGINEER
BUILDINGS SUB-DIVISION |  |  |  |  | BUILDINGS SUB-DIVISION | [8 empty] | BUILDINGS DIVISION
TANDO MOHAMMAD KHAN |  |  |  |  | TANDO MOHAMMAD KHAN | [8 empty] | TANDO MOHAMMAD KHAN

## Cartage Main Bldgs (hidden)
Material Cartage Satement
NAME OF WORK:- Constt: of Catg: -II Bunglow for BPS-18 to BPS-19 at B&R Colony T.M.Khan (Bunglow No-3) (01 No).
PART-A CIVIL WORK (i) MAIN BUILDINGS
Sr.# | Description | Qty: | Cement |  | Hill Sand |  | Stone Metal |  | Stone Bajri |  | Steel |  | Bricks
01. | C.C S/Ballast (1:4:8) | 873.645 | 9.47 | 82.7342 | 47.38 | 413.933 | 94.76 | 827.866 | - | - | - | - | - | -
02. | C.C S/Ballast (1:5:10) | 132.6781 | 7.8 | 10.3489 | 49 | 65.0123 | 98 | - | - | - | - | - | 1350 | 1791.1539
03. | P.B.Work in Foundation | 962 | 3.44 | 33.0928 | 25.7 | 247.234 | - | - | - | - | - | - | 1350 | 12987
04. | Feb: Of M/Steel | 90 | - | - | - | - | - | - | - | - | - | 4.5 | - | -
05. | R.C.C Work (1:2:4) | 1764 | 19.1 | 336.924 | 48 | 846.72 | - | - | 88 | 1552.32 | - | - | - | -
06. | P.B.Work G/Floor | 3922.2903 | 3.44 | 134.9268 | 25.7 | 1008.0286 | - | - | - | - | - | - | 1350 | 52950.9187
07. | C.Plaster (1:6) 1/2" Thick | 7547.58 | 0.53 | 40.0022 | 4 | 301.9032 | - | - | - | - | - | - | - | -
08. | C.Plaster (1:4) 3/8" Thick | 7547.58 | 0.57 | 43.0212 | 3 | 226.4274 | - | - | - | - | - | - | - | -
09. | C.Plaster (1:6) 3/4" Thick | #REF! | 1.14 | #REF! | 5.5 | #REF! | - | - | - | - | - | - | - | -
10. | Matt:Glazed Tile | 0 | 2.16 | 0 | 5.2 | 0 | - | - | - | - | - | - | - | -
11. | L/Floor app:glazed | #REF! | 2.16 | #REF! | 5.2 | #REF! | - | - | - | - | - | - | - | -
12. | P/LC.CToping1-1/2" thick | 0 | 2.2 | 0 | 5.5 | 0 | - | - | 11 | 0 | - | - | - | -
13. | P/LC.CToping3" thick | 0 | 4.4 | 0 | 11 | 0 | - | - | 22 | 0 | - | - | - | -
14. | P/LC.CToping2" thick | 1189.24 | 3 | 35.6772 | 7.4 | 88.0038 | - | - | 14.7 | 174.8183 | - | - | - | -
15. | P.B.Work Other Than.. | #REF! | 2.16 | #REF! | 5.2 | #REF! | - | - | - | - | - | - | - | -
| Total Quantity: | - | - | #REF! | - | #REF! | - | 827.866 | - | 1727.1383 | - | 4.5 | - | 67729.0726
| Rate as per R.A.A |  |  | 16.53 |  | 2432.52 |  | 2758.12 |  | 2172.04 |  | 698.38 |  | 1032.44
| Amount |  |  | #REF! |  | #REF! |  | 22833.5378 |  | 37514.1343 |  | 3142.71 |  | 69926.2037
| Total Rs |  |  |  | #REF! | /=
SUB-ENGINEER |  |  |  | ASSISSTANT ENGINEER | [6 empty] | EXECUTIVE ENGINEER
BUILDINGS SUB-DIVISION |  |  |  | BUILDINGS SUB-DIVISION | [6 empty] | BUILDINGS DIVISION
TANDO MOHAMMAD KHAN |  |  |  | TANDO MOHAMMAD KHAN | [6 empty] | TANDO MOHAMMAD KHAN

## Cartage Paved CY wall (hidden)
Material Cartage Satement
NAME OF WORK:- Constt: of Catg: -II Bunglow for BPS-18 to BPS-19 at B&R Colony T.M.Khan (Bunglow No-3) (01 No).
PART-A CIVIL WORK (ii) PAVED COURT YARD WALL
Sr.# | Description | Qty: | Cement |  | Hill Sand |  | Stone Metal |  | Stone Bajri |  | Steel |  | Bricks
01. | C.C S/Ballast (1:4:8) | #REF! | 9.47 | #REF! | 47.38 | #REF! | 94.76 | #REF! | - | - | - | - | - | -
02. | P.B.Work in Foundation | #REF! | 3.44 | #REF! | 25.7 | #REF! | - | - | - | - | - | - | 1350 | #REF!
03. | C.C 1:3:6 | #REF! | 13 | #REF! | 46 | #REF! | - | - | 92 | #REF! | - | - | - | -
04. | C.Plaster (1:6) 1/2" Thick | #REF! | 0.53 | #REF! | 4 | #REF! | - | - | - | - | - | - | - | -
05. | C.Plaster (1:4) 3/8" Thick | #REF! | 0.57 | #REF! | 3 | #REF! | - | - | - | - | - | - | - | -
06. | Cement Pointing 1:2 | 1189.24 | 0.72 | 8.5625 | 1.8 | 21.4063 | - | - | - | - | - | - | - | -
07. | P.B.Work Other Than.. | #REF! | 2.16 | #REF! | 5.2 | #REF! | - | - | - | - | - | - | 1350 | #REF!
| Total Quantity: | - | - | #REF! | - | #REF! | - | #REF! | - | #REF! | - | 0 | - | #REF!
| Rate as per R.A.A |  |  | 16.53 |  | 2432.52 |  | 2758.12 |  | 2172.04 |  | 698.38 |  | 1032.44
| Amount |  |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | 0 |  | #REF!
| Total Rs |  |  |  | #REF! | /=
SUB-ENGINEER |  |  |  | ASSISSTANT ENGINEER | [6 empty] | EXECUTIVE ENGINEER
BUILDINGS SUB-DIVISION |  |  |  | BUILDINGS SUB-DIVISION | [6 empty] | BUILDINGS DIVISION
TANDO MOHAMMAD KHAN |  |  |  | TANDO MOHAMMAD KHAN | [6 empty] | TANDO MOHAMMAD KHAN

## Cartage Paved CY (hidden)
Material Cartage Satement
NAME OF WORK:- Constt: of Catg: -II Bunglow for BPS-18 to BPS-19 at B&R Colony T.M.Khan (Bunglow No-3) (01 No).
PART-A CIVIL WORK (iii) PAVED COURT YARD
Sr.# | Description | Qty: | Cement |  | Hill Sand |  | Stone Metal |  | Stone Bajri |  | Steel |  | Bricks
01. | C.C 1:4:8 | #REF! | 9.47 | #REF! | 47.38 | #REF! | 94.76 | #REF! | - | - | - | - | - | -
02. | C.C Topping 2" thick | #REF! | 3 | #REF! | 7.4 | #REF! | - | - | 14.7 | #REF! | - | - | - | -
03. |  | 0 | 2.16 | 0 | 5.2 | 0 | - | - | - | - | - | - | - | -
| Total Quantity: | - | - | #REF! | - | #REF! | - | #REF! | - | #REF! | - | 0 | - | 0
| Rate as per R.A.A |  |  | 16.53 |  | 2432.52 |  | 2758.12 |  | 2172.04 |  | 698.38 |  | 1032.44
| Amount |  |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | 0 |  | 0
| Total Rs |  |  |  | #REF! | /=
SUB-ENGINEER |  |  |  | ASSISSTANT ENGINEER | [6 empty] | EXECUTIVE ENGINEER
BUILDINGS SUB-DIVISION |  |  |  | BUILDINGS SUB-DIVISION | [6 empty] | BUILDINGS DIVISION
TANDO MOHAMMAD KHAN |  |  |  | TANDO MOHAMMAD KHAN | [6 empty] | TANDO MOHAMMAD KHAN

## Part B W.S & S.F (hidden)
NAME OF WORK:- Constt: of Catg: -II Bunglow for BPS-18 to BPS-19 at B&R Colony T.M.Khan (Bunglow No-3) (01 No).
PART "B" PROVIDING INTERNAL W/SUPPLY & S/FITTING
S NO: | NAME OF ITEMS | QTY: |  | RATE | UNIT | AMOUNT
1 | P/F Orisa type white or colour glazed earthen ware W.C pan with cost of low level plastic flush tank of 3 gallons capacity of approved quality I/c making requiste number of holes in wall, plinth & floor and making good in cement concrete 1:2:4 (a) W.C pan orisa type 23" with plastic tank of low down 3 gallons trap & C.I thimble (Superior Quality) (i) with 4" dia C.I trap (Ch.No.1,S.I.No.3(a)(i),(ii)/P2). | 3 | Nos | 12003.2 | Each | 36009.6
2 | P/F European type white glazed earthen ware wash down W.C pan complete with and i/c the cost of white/black plastic seat (Best quality) and lid with c.p brass hinges & buffers 3-gallons white glazed earthen ware low level flushing cistern with siphon fitting 1-1/2" dia white porcelain enamelled flush bend 3/4" dia and making req: No: of holes in walls plinth & floor for pipe connections and making good in C.C 1:2:4 (Foreign quality). (Ch.No.1,S.I.No:5/P-2) | 1 | Nos: | 11477.4 | Each | 11477.4
3 | P/F 24"x18" lavatory basin in white glazed earthen ware complete with & i/c the cost of W.I or C.I cantilever brackets 6 inche built into wall, painted white in two coats after a primary cost of red lead paint a pair of 1/2" dia chrome plate trap 1-1/2" dia rubber plug & chrome plated chain 1-1/4" dia malloable iron or c.p brass trap malloable iron or brass union & making req: No: of holes in walls plinth & floor for pipe connection and making good in C.C 1:2:4 ( Foreign or Equivalent ) (Ch.No.1,S.I.No:8/P-3) | 3 | Nos: | 4253.9 | Each | 12761.7
4 | Add: extra for labour for providing & fixing of earthen ware pedestal white or colour glazed (Foreign or equivalent) (Ch.No.1,S.I.No:9/P-3) | 3 | Nos: | 938.47 | Each | 2815.41
5 | P/F Steel Sink stainless sized 36"x18" local make complete with cost iron or wrought iron brackets 6 inches built in wall, 1-1/2" rubber plug chrome brass chain 1-1/2", c.p brass waste with 1-1/2" plate PVC waste pipe and making req: No:of holes in walls plinth & floor for pipe connection and making good in 1:2:4 (Standard pattern).(Ch.No.1,S.I.No:19(b)/P-6) | 1 | Nos: | 5162.3 | Each | 5162.3
6 | P/F in position nyloon connection complete with 1/2" dia brass stop ock two brass nuts & lining jointed to lead pipe with plumber wiped solder joints (1/2" inches lead pipe to be of not less than 4 Ibs per lineal year) (Ch.No.1,S.I.No.23/P-06). | 6 | Nos | 447.15 | Each | 2682.9
7 | P/F M.S clamps of the approved design to 4" dia C.I pipe sockets I/c the cost of cutting and making good to wall or MS bolts and nuts 4" into wall I/c pipe distance pipces extra painting to match the coour of the building (Ch.No.3,S.I.No.2/P-9). | 18 | Nos | 72.16 | Each | 1298.88
8 | P/F 6"x4" C.C gully trap with 4" outlet complete with 4" thick 1:2:4 C.C for bed and 1/2" thick cement plaster ( 1:3) to the karo C.I grating 6"x6" & C.I cover and frame 12"x 12" ( inside) etc complete (a). C.C gully trap 6"x 6" x 4" with C.I cover and frame (Ch.No.10,S.I.No.1(b)(i)/P- 21). | 4 | Nos: | 1358.17 | Each | 5432.68
9 | Providng G.I pipes specials & clamps etc I/c fixing cutting and fitting complete with & I/c the cost of breading through walls & roof making good etc painting two coats after cleaning the pipe etc with white sink Zink paint with pigment to match the colo9ur of the building and testing with water to a pressure head of 200 feet and handing (Ch.No.4,S.I.No.01/(i) /P-12).
| (a) 1/2" dia pipe | 250 | Rft | 73.21 | P.Rft | 18302.5
| (b) 3/4" dia pipe | 300 | Rft | 95.79 | P.Rft | 28737
| (c)1" dia pipe | 150 | Rft | 128.55 | P.Rft | 19282.5
10 | Add extra labour for concealed G.I pipe and fittings i/c making recess in the wall for pipe & making good in cement mortar etc complete. (Ch.No.4,S.I.No:2/P-12)
| (a) 1/2" dia pipe | 250 | Rft | 7.82 | P.Rft | 1955
| (b) 3/4" dia pipe | 300 | Rft | 8.45 | P.Rft | 2535
| (c)1" dia pipe | 150 | Rft | 9.96 | P.Rft | 1494
11 | Providing and fixing handle valves (china).(Ch.No.6,S.I.No.5/P-17)
| (a) 1/2" dia pipe | 4 | Nos: | 200.42 | Each | 801.68
| (b) 3/4" dia pipe | 2 | Nos: | 271.92 | Each | 543.84
| (c)1" dia pipe | 2 | Nos: | 365.42 | Each | 730.84
12 | S/F cancealed stop cock of superior quality with crystal head 1/2" dia (Ch.No.6,S.I.No:11(b)/P-18) | 12 | Nos: | 509.74 | Each | 6116.88
13 | S/F long bib cock of crystal head with c.p 1/2" dia (Ch.No.6,S.I.No. 13(b)/P-19). | 10 | Nos | 1384.24 | Each | 13842.4
14 | S/F Jet shower with rod of superior quality with c.p head 1/2" dia (Ch.No.6,S.I.No:15/P-19) | 4 | Nos: | 1142.24 | Each | 4568.96
15 | S/F Bath room accessories (7-pieces) i/c towel rod, brush holder, soap tray, shelf of approved quality and design i/c cost of screws, nuts etc complete. (Master Brand (Ch.No.6,S.I.No:23/P-19) | 3 | Nos: | 10322.4 | Each | 30967.2
16 | S/F cancealed tee stop cock of superior quality with crystal head 1/2" dia (Ch.No.6,S.I.No:12(b)/P-18) | 10 | Nos: | 889.46 | Each | 8894.6
|  | TOTAL |  |  |  | 216413.27
|  | ADD 20% Below |  |  | - | 43282.654
|  | TOTAL PART-B |  |  |  | 173130.616
|  | SAY |  |  |  | 99000
Non-Shedule items
01. | P/F UPV floor trap | 4 | Nos: | 652 | Each | 2608
02. | P/F 4"×4"UPV branch | 4 | Nos: | 1374 | Each | 5496
03. | P/F UPV 4"×4" plain branch | 4 | Nos: | 1220 | Each | 4880
04. | P/F UPV Plug bend | 4 | Nos: | 1158 | Each | 4632
05. | P/F UPV Palin bend | 4 | Nos: | 882 | Each | 3528
06. | P/F UPV pipe 4" dia | 84 | Rft | 291 | P.Rft | 24444
| Total Non-Schedule Item's Amount |  |  |  |  | 45588
| Schedule Item's Amount |  |  |  |  | 173130.616
| Grand Total of W/S & S/F |  |  |  |  | 218718.616
| SUB-ENGINEER ASSISSTANT ENGINEER |  |  | EXECUTIVE ENGINEER
| BUILDINGS SUB-DIVISION BUILDINGS SUB-DIVISION |  |  | BUILDINGS DIVISION
| TANDO MOHAMMAD KHAN TANDO MOHAMMAD KHAN |  |  | TANDO MOHAMMAD KHAN

## Part D (hidden)
NAME OF WORK:- Constt: of Catg: -II Bunglow for BPS-18 to BPS-19 at B&R Colony T.M.Khan (Bunglow No-3) (01 No).
PART "D" EXTERNAL DRAINGE & W/SUPPLY
S NO: | NAME OF ITEMS | QTY: |  | RATE | UNIT | AMOUNT
"A" SCHEDULE ITEMS
1 | Excavation for pipe line entrenches, and pits in soft soils i.e trimming and dressing sides to true alignment and shape leveling of beds of trenches to correct level and grade, cutting joint holes and disposal of surplus earth with in a one chain as directed by Engineer incharge providing fence guards, lights flags and temporary crossings for non vehicular traffic where ever required lift upto 5 ft: ( 1.52.mm) and lead upto one chain ( 30.5mm) (Ch.No.III,S.I.No.A-1/P-60,P.H.E) | 1080 | Cft | 3600 | %Cft | 38880
2 | Providing RCC pipe with collars class (B) and digging the trenches to required depth and fixing in position i/c cutting fitting and jointing with maxphat composition & cement mortar 1:1 and testing with water pressure to a head of 4 feet above the top of the highest pipe and refilling with excavated staff.(Ch.No.II,S.I.No:A-2/P-15,P.H.E) | 50 | Rft | 199.25 | P.Rft | 9962.5
| (a) 6" dia RCC pipe | 70 | Rft | 163 | P.Rft | 11410
| (b) 9" dia RCC pipe | 50 | Rft | 163 | P.Rft | 8150
3 | Construction of main holes or inspection chamber for required dia of circulor sewer and 3" 6" depth with walls of B.B in Cemant sand mortar 1:3 Cement plaster 1:3 1/2" thick I/side of walls 1" thick over bending & chanel of clear opening 1-1/2 x 1-1/2" (457mm) of 1.75 Cft (88.90kg) embeded in plain C.C. 1:2:4 & fixing 1" (25mm) dia M.S steps (150mm) wide projecting 4" (102mm) from the face of wall at 12" (305mm) C/C duly painted etc complete as per specification and drawing No. D.P/1of P.II Sch: citculor one.(Ch.No.II,S.I.No.P (a)/P-46,P.H.E) | 6 | Nos | 14748 | Each | 88488
|  | Total Part "C" |  |  |  | 156890.5 | /=
|  | Add 20% Below |  |  |  | 31378.1 | /=
|  | Total |  |  |  | 125512.4 | /=
| SUB-ENGINEER ASSISSTANT ENGINEER |  |  | EXECUTIVE ENGINEER
| BUILDINGS SUB-DIVISION BUILDINGS SUB-DIVISION |  |  | BUILDINGS DIVISION
| TANDO MOHAMMAD KHAN TANDO MOHAMMAD KHAN |  |  | TANDO MOHAMMAD KHAN
GENERAL ABSTRACT
| PART "A" | #REF! | /=
| PART "B" | 99000 | /=
| PART "C" | 156890.5 | /=
| PART "D" | #REF! | /=
| G.TOTAL | #REF! | /=

## Lay out plan (hidden)
SUB-ENGINEER | ASSISTANT ENGINEER | EXECUTIVE ENGINEER
BUILDINGS SUB-DIVISION | BUILDINGS SUB DIVISION | BUILDINGS DIVISION
TANDO MOHAMMAD KHAN | TANDO MUHAMMAD KHAN | TANDO MUHAMMAD KHAN

## Lead chart (hidden)
SUB-ENGINEER | ASSISTANT ENGINEER | EXECUTIVE ENGINEER
BUILDINGS SUB-DIVISION | BUILDINGS SUB DIVISION | BUILDINGS DIVISION
TANDO MOHAMMAD KHAN | TANDO MUHAMMAD KHAN | TANDO MUHAMMAD KHAN

## Rate Analysis (R.A.A) (hidden)
(Rate Analysis)
NAME OF WORK:- Constt: of Catg: -II Bunglow for BPS-18 to BPS-19 at B&R Colony T.M.Khan (Bunglow No-3) (01 No).
Cartage of Hill Sand from Bolahri Quarry to Site of work
[6 empty] | M | F |  | 1 Mile = 8 Furlog
| 01. From Quarry to N.H.Way. |  |  |  |  | 3 | 0 |  | 1Furlong = 660 foot
| 02. From Quarry to 113/0 122/0 of N.H.Way. |  |  |  |  | 9 | 0
| 03. From 0/0 4/4 of Hyd: Ring Road. |  |  |  |  | 4 | 4
| 04. From 2/0 21/4 of Hyd:T.M.Khan. |  |  |  |  | 19 | 4
| 05. From 0/0 0/0 T.M.Khan to Site. |  |  |  |  | 0 | 0
[5 empty] | Total | 35 | 4 | FALSE
[5 empty] | Say total | 36 |  | 35
Lead
| 01. Carriage of 1st 6 miles |  |  |  | Rs:- | 771.96
| 02. Remaining |  | 30 | miles
|  | @Rs. | 32.56 | per %cft | Rs:- | 976.8
[5 empty] | Total | 1748.76 |  |  |  | 1748.76
Cartage of Stone Metal from Onger to Site of work
[6 empty] | M | F
| 01. From Quarry to N.H.way. |  |  |  |  | 3 | 0
| 02. From Quarry to 103/0 122/0 of N.H.Way. |  |  |  |  | 19 | 0
| 03. From 0/0 4/4 of Hyd: Ring Road. |  |  |  |  | 4 | 4
| 04. From 2/0 21/4 of Hyd:T.M.Khan. |  |  |  |  | 19 | 4
| 05. From 0/0 0/0 T.M.Khan to Site. |  |  |  |  | 0 | 0
[5 empty] | Total | 45 | 4 | FALSE
[5 empty] | Say total | 46 |  | 46
Lead
| 01. Carriage of 1st 6 miles |  |  |  | Rs:- | 771.96
| 02. Remaining |  | 40 | miles
|  | @Rs. | 32.56 | per %Cft | Rs:- | 1302.4
[5 empty] | Total | 2074.36 |  |  |  | 2074.36
Cartage of Bajri from T.M.Khan to Site of work
[6 empty] | M | F
| 01. From Quarry to 14/0 of N.H.way. |  |  |  |  | 14 | 0
| 02. From Quarry 110/40 to 122/0 of N.H.Way. |  |  |  |  | 11 | 4
| 03. From 0/0 4/4 of Hyd: Ring Road. |  |  |  |  | 4 | 4
| 04. From 2/0 21/4 of Hyd:T.M.Khan. |  |  |  |  | 19 | 4
| 05. From 0/0 0/0 T.M.Khan to Site. |  |  |  |  | 0 | 0
[5 empty] | Total | 48 | 8 | 1
[5 empty] | Say total | 49 |  | 49
Lead
| 01. Carriage of 1st 6 miles |  |  |  | Rs:- | 771.96
| 02. Remaining |  | 43 | miles
|  | @Rs. | 32.56 | per %cft | Rs:- | 1400.08
[5 empty] | Total | 2172.04 |  |  |  | 2172.04
Cartage of Cement from Zeal Pak Factory to Site of work
[6 empty] | M | F
| 01. From 2/0 21/4 of Hyd:T.M.Khan. |  |  |  |  | 17 | 4
| 02. From 0/0 0/0 T.M.Khan to Site. |  |  |  |  | 0 | 0
[5 empty] | Total | 17 | 4 | 1
[5 empty] | Say total | 18 |  | 18
Lead
| 01. Carriage of 1st 3 miles |  |  |  | Rs:- | 7.53
| 02. Remaining |  | 15 | miles
|  | @Rs. | 0.6 | per bag | Rs:- | 9
[5 empty] | Total | 16.53 |  |  |  | 16.53
Cartage of Brick from Kilen to Site of work
[6 empty] | M | F
| 01. From Brick Kilen 0/0 5/0 of Tando Fazal Sery Road |  |  |  |  | 5 | 6
| 02. From Sery Road 13/4 to 21/4 of Hyd:T.M.Khan. |  |  |  |  | 8 | 0
| 03. From 0/0 0/0 T.M.Khan to Site. |  |  |  |  | 0 | 0
[5 empty] | Total | 13 | 6 | FALSE
[5 empty] | Say total | 14 |  | 13
Lead
| 01. Carriage of 1st 6 miles |  |  |  | Rs:- | 771.96
| 02. Remaining |  | 8 | miles
|  | @Rs. | 32.56 | per O% Nos. | Rs:- | 260.48
[5 empty] | Total | 1032.44 |  |  |  | 1032.44
Cartage of Steel from Hyd. City to Site of work
[6 empty] | M | F
| 01. From 2/0 21/4 of Hyd:T.M.Khan. |  |  |  |  | 19 | 4
| 02. From 0/0 25/0 T.M.Khan to Site. |  |  |  |  | 0 | 0
[5 empty] | Total | 19 | 4 | 1
[5 empty] | Say total | 20 |  | 20
Lead
| 01. Carriage of 1st 6 miles |  |  |  | Rs:- | 411.38
| 02. Remaining |  | 14 | miles
|  | @Rs. | 20.5 | per Ton | Rs:- | 287
[5 empty] | Total | 698.38 |  |  |  | 698.38
SUB-ENGINEER |  |  |  | ASSISTANT ENGINEER |  | EXECUTIVE ENGINEER
BUILDINGS SUB-DIVISION |  |  |  | BUILDINGS SUB DIVISION |  | BUILDINGS DIVISION
TANDO MOHAMMAD KHAN |  |  |  | TANDO MUHAMMAD KHAN |  | TANDO MUHAMMAD KHAN