## Sheet3
|  | Guidelines / Regulations for Procurement of Works | [8 empty] | (Annexure A-I)
(Annexure- A)
PROCUREMENT PLAN (Development/Capital)
| Serial No/ADP* | Name of Scheme & Estimated Cost | Allocated Funds | Cost of ongoing works (Expenditure already incurred) | Funds earmarked for ongoing works | Cost of New Works (Components) | Funds for New Works (e-e) | Nature of Procurement | Method of Procurement | Anticipated / Actual Date of Advertisement | Anticipated / Actual Date of Start | Anticipated / Actual Date of Completion
| a | b | c | d | e | f | g | h | i | j | k | l
Construction/Addition of Class Rooms , Providing Missing Facilites & Rehablitation of existing Primary Schools in Tal: Sakrand & Q.Amed Distt:SBA Under PAK MDG,S Community Development Programme 2015-16 (12-units) (Constituwncy NA-214
| 1 | GBPS Murad Ali Chandio (Rehabilitation) | 1.514 | __ | __ | 1.514 | 1.514 | National Compitative Bidding | Single Stage one Envelope Procedure | 26/4/2016 | 5 .2016 | 31/12/2016
| 2 | Do - Electric Work | 0.079 |  |  | 0.079 | 0.079 | Do | Do | Do | Do | Do
| 3 | GBPS Muhala Ghullam Nabi Magsi (Rehabilitation) | 1.434 |  |  | 1.434 | 1.434 | Do | Do | Do | Do | Do
| 4 | Do - Electric Work | 0.061 |  |  | 0.061 | 0.061 | Do | Do | Do | Do | Do
| 5 | GBPS Wali Muhammad Unar (1 C/R & Rehabilitation) | 1.443 |  |  | 1.443 | 1.443 | Do | Do | Do | Do | Do
| 6 | Do - Electric Work | 0.146 |  |  | 0.146 | 0.146 | Do | Do | Do | Do | Do
| 7 | GBPS Sher Khan Jamali (Rehabilitation) | 1.076 |  |  | 1.076 | 1.076 | Do | Do | Do | Do | Do
| 8 | Do - Electric Work | 0.079 |  |  | 0.079 | 0.079 | Do | Do | Do | Do | Do
| 9 | GBPS Chattan Shah (Rehabilitation) | 2 |  |  | 2 | 2 | Do | Do | Do | Do | Do
| 10 | Do - Electric Work | 0.079 |  |  | 0.079 | 0.079 | Do | Do | Do | Do | Do
| 11 | GBPS Ladho chandio (Rehabilitation) | 1.233 |  |  | 1.233 | 1.233 | Do | Do | Do | Do | Do
| 12 | Do - Electric Work | 0.079 |  |  | 0.079 | 0.079 | Do | Do | Do | Do | Do
| 13 | GBPS Ghullam Sarwar Laghari (1 C/R ,Lav:B & Rehabilitation) | 1.618 |  |  | 1.618 | 1.618 | Do | Do | Do | Do | Do
| 14 | Do - Electric Work | 0.077 |  |  | 0.077 | 0.077 | Do | Do | Do | Do | Do
| 15 | GBPS Noor Muhammad Brohi (Rehabilitation) | 1.106 |  |  | 1.106 | 1.106 | Do | Do | Do | Do | Do
| 16 | Do - Electric Work | 0.078 |  |  | 0.078 | 0.078 | Do | Do | Do | Do | Do
| 17 | GBPS Sarang Rustmani (C/wall, Lav:B & Rehabilitation) | 1.111 |  |  | 1.111 | 1.111 | Do | Do | Do | Do | Do
| 18 | Do - Electric Work | 0.064 |  |  | 0.064 | 0.064 | Do | Do | Do | Do | Do
| 19 | GBPS Ibrahim Khaskhali (C/wall, Lav:B & Rehabilitation) | 1.112 |  |  | 1.112 | 1.112 | Do | Do | Do | Do | Do
| 20 | Do - Electric Work | 0.064 |  |  | 0.064 | 0.064 | Do | Do | Do | Do | Do
| 21 | GBPS Abdul Hakeem Khaskhali (C/R, C/wall & Lav:B) | 1.683 |  |  | 1.683 | 1.683 | Do | Do | Do | Do | Do
| 22 | Do - Electric Work | 0.077 |  |  | 0.077 | 0.077 | Do | Do | Do | Do | Do
| 23 | GBPS Muhammad Hassan Solangi (Rehabilitation) | 1.554 |  |  | 1.554 | 1.554 | Do | Do | Do | Do | Do
| 24 | Do - Electric Work | 0.056 |  |  | 0.056 | 0.056 | Do | Do | Do | Do | Do
Executive Engineer
Education Works Division
Shaheed Benazir Abad