## Measurement
S.No | 9 |  | SCHEDULE "B"
PART "A"
Construction of road from Mirwah KotGhulam Mohammad road to Village Ali Mohammad Tapedar Deh 255 Mile:-0/0-0/5 (1.00 Kms) Taluka Kot Ghulam Mohammad
S.No | Item of work. | [8 empty] | Quantity |  |  | Rate |  |  | Unit.
1 | F O R M A T I O N:-
Earth work for road embankment by buldozers, including ploughing, mixing, clod breaking, dressing, compacting with optimum moisture content. Lead upto 100 ft and lift upto 5.0 ft. in all types of soil exceptrock( If earth work is done by other than departmental agency)
(a) COMPACTING UPTO 85% DENSITY
| Say Qty. |  |  |  | 115900 |  | Cft. | @ | Rs. | 3656.23 |  | Per %0 Cft. |  |  | Rs. |  | 423757
(b) COMPACTION 95-100% DENSITY
| Say Qty. |  |  |  | 26850 |  | Cft. | @ | Rs. | 6190.17 |  | Per %0 Cft. |  |  | Rs. |  | 166206
(a) COMPACTING UPTO 85% DENSITY
| Say Qty. |  |  |  | 0 |  | Cft. | @ | Rs. | 3656.23 |  | Per %0 Cft. |  |  | Rs. |  | 0
(b) COMPACTION 95-100% DENSITY
| Say Qty. |  |  |  | 0 |  | Cft. | @ | Rs. | 6190.17 |  | Per %0 Cft. |  |  | Rs. |  | 0
2 | SUB BASE COURSE:-
Preparing Sub Base Course by supplying and spreading stone metal of 2"-11/2" in guage of approved quality from approved quarry in required thickness (6" in 2 layers) to proper camber and grade, i/c hand packing, filling voids with 10 cft screening and non plastic quarry fines of approved quality and guage from approved source, watering and compacting to achieve 98-100% density as per modified AASHO specification. (Rate i/cs all cost of materials T&P, labours and carriage upto site of work.
| Say Qty. |  |  |  | 11507 |  | Cft. | @ | Rs. | 9262.91 |  | Per % Cft. |  |  | Rs. |  | 1065883
3 | BRICK ON EDGING:-
Laying Brick on end edging including supplying 9"x41/2"x3" first class bricks, excavation for laying edging with small size parallel to the road. Rate includes all cost of materials, T&P, labours, and carriage upto site of work.
| Say Qty. |  |  |  | 3836 |  | Rft. | @ | Rs. | 2729.96 |  | Per % Rft. |  |  | Rs. |  | 104721
4 | BASE COURSE:-
Preparing base course including supplying and spreading stone metal of approved quality properly graded to maximum size of 1 1/2" in required thickness of (3") to proper camber and grade including supplying and spreading 15 cft. Screening and non plastic quarry fines, filling depressions with stone metal after initial rolling including watering and compacting the same so as to achieve 100% density as per modified AASHO specifications.(Rate includes providing and using templates, camber plates, screens, forms etc. as directed). Rate includes all cost of materials, T&P, labours and carriage upto site of work.
| Say Qty. |  |  |  | 11507 |  | Cft. | @ | Rs. | 10304.23 |  | Per % Cft. |  |  | Rs. |  | 1185707.7461
5 | THREE COAT SURFACE DRESSING:-
Providing surface dressing three coat on new or existing surface with 79 Ibs Bitumen of 80/100 penetration and 9.75 cft of crush bajri of required size of 3/4"-3/8", including cleaning the road surface, rolling after each etc. complete. Rate includes all cost of materials, labours, T&P, and carriage upto site of work.
| Say Qty. |  |  |  | 23014 |  | Sft. | @ | Rs. | 4230.21 |  | Per % Sft. |  |  | Rs. |  | 973540.5294
6 | EARTHWOR ON BERMS
Earthork on Berm for embankment (Berms) from barrow pits including laying in 6" layers. Clod breaking ramming, dressing etc complete lead upto 100' ft: and lift upto 5.0 ft (in ordinary Soil).
| Say Qty. |  |  |  | 28532 |  | Cft | @ | Rs. | 3656.23 |  | Per %0Cft. |  |  | Rs. |  | 104319.5544
| Say Qty. |  |  |  | 0 |  | Cft | @ | Rs. | 3656.23 |  | Per %0Cft. |  |  | Rs. |  | 0
[12 empty] | Total |  |  | Rs. |  | 4024134.8299
Deduct Different Cost of | [8 empty] | 8.12 |  | Ton Bitumen |  |  | (-) | Rs. |  | 152233.76
|  |  | @ Rs. |  |  | 18748 |  | Per Ton
[12 empty] | Grand Total |  |  | Rs. |  | 3871901.0699
NOTE:- |  | 1 |  | Item / Quantities / Rates and amount are estimated provisional and will be corrected in accordance to the Detail working estimate sanctioned by competent authority.
|  | 2 |  | No Premium will be allowed on Non Schedule Item.
|  | 3 |  | Diff: Cost of Bitumen as announced by the Attock Refinery will be adjusted accordingly.
CONTRACTOR | [13 empty] | EXECUTIVE ENGINEER
HIGHWAYS DIVISION
MIRPURKHAS

## Culv
S.No | 9 |  | SCHEDULE "B"
PART "B"
Construction of road from Mirwah KotGhulam Mohammad road to Village Ali Mohammad Tapedar Deh 255 Mile:-0/0-0/5 (1.00 Kms) Taluka Kot Ghulam Mohammad
MEASUREMENT CUM ABSTRACT SHEET
S.NO |  | I T E M O F W O R K S | [11 empty] | RATE |  |  |  |  | UNIT |  | AMOUNT
1 | EXCAVATION
Excavation in foundation of Building, Bridges and other structures including dagbelling dressing, refilling around structure with excavated earth, watering and ramming.lead upto 5.00 ft. (In Ordinary soil)
| Qty. |  | 1056 |  |  | Cft. |  | @ Rs | 3176.25 |  | Per %0 Cft. | [8 empty] | Rs. | 3354 | /=
2 | CEMENT CONCRETE RATIO 1:4:8
Cement Concrete brick or stone ballast 1 1/2" to 2" gauge. Ratio 1:4:8
| Qty. |  | 239 |  |  | Cft. |  | @ Rs | 9416.28 |  | Per % Cft. | [8 empty] | Rs. | 22505 | /=
3 | PUCCA BRICK WORK RATIO 1:4
Pucca brick work in foundation and plinth in cement sand mortar Ratio 1:4
| Qty. |  | 474 |  |  | Cft. |  | @ Rs | 12501.41 |  | Per % Cft. | [8 empty] | Rs. | 59257 | /=
4 | CEMENT CONCRETE (1:2:4)
Cement concrete plain including placing, compacting, finishing and curing, complete (including screening and washing of stone aggregate without shuttering ( Ratio 1:2:4)
| Qty. |  | 72 |  |  | Cft. |  | @ Rs | 14429.25 |  | Per % Cft. | [8 empty] | Rs. | 10389 | /=
5 | FEBRICATION
Febrication of mild steel reinforcement for cement concrete including cutting, bending, laying in position, making joints and fastenings including cost of binding wire (also includes removal of rust from bars.)
| Qty. |  | 5.05 |  | Cwt. |  |  | @ Rs | 4820.2 |  | Per Cwt. | [8 empty] | Rs. | 24342 | /=
6 | R.C.C. WORK. RATIO 1:2:4
Reinforced cement concrete work including all labour and materials except the cost of steel reinforcement and its labour for bending and binding which will be paid separately. This rate also includes all kinds of forms moulds: lifting shuttering curing rendering and finishing the exposed surface (including screening and washing of shingle).R.C.work in roof slab, beams, columns rafts, lintels and other structural members laid in situ or precast laid in position complete in all respects. Ratio (1:2:4) 90 Ibs cement 2 Cft. sand 4 Cft. Shingle 1/8" to 1/4" gauge.
| Qty. |  | 80 |  | Cft. |  |  | @ Rs | 337 |  | Per Cft. | [8 empty] | Rs. | 26960 | /=
7 | BRICK ON EDGE FLOORING
Brick on edge flooring laid in 1:6 cement mortar over a bed, 3/4" thick cement mortar Ratio 1:6
| Qty. |  | 68 |  | Sft. |  |  | @ Rs | 5256.63 |  | Per % Sft. | [8 empty] | Rs. | 3575 | /=
7 | ERECTION AND REMOVAL
Erection and removal of centering for R.C.C. or plain cement concrete works of Partal wood ( 2nd class) (a) Vertical
| Qty. |  | 28 |  | Sft. |  |  | @ Rs | 3127.41 |  | Per % Sft. | [8 empty] | Rs. | 876 | /=
8 | CEMENT PLASTER RATIO 1:3
Cement Plaster 1:3 upto 20.0' height. 1/2" thick.
| Qty. |  | 261 |  | Sft. |  |  | @ Rs | 2344.58 |  | Per % Sft. | [8 empty] | Rs. | 6119 | /=
[10 empty] | Total 01 No. culvert | [9 empty] | Rs. | 157377 | /=
[12 empty] | Total:- | 1 |  |  | Nos |  |  |  | Rs. | 157377 | /=
Cost of Schedule Item | [6 empty] | (Part -A) | [8 empty] | Rs. |  | 4024134.8299 |  |  | /-
Deduct Difference Cost of Bitumen | [11 empty] | (-) |  |  |  | Rs. |  | 152233.76 |  |  | /-
Cost of Schedule Item | [6 empty] | (Part -B) | [8 empty] | Rs. |  | 157377 |  |  | /-
[15 empty] | Total Bid amount | Rs. |  | 4029278.0699 |  |  | /-
NOTE:- |  | 1 |  | Difference in cost of construction material is to be allowed as per notificaiton / circulars issued by standing Rates committee (S.R.C) from time to time.
|  | 2 |  | No Cartage of material what-ever so is will be paid to contractor separately.
|  | 3 |  | No Premium will be allowed on Non Schedule Item.
CONTRACTOR | [16 empty] | EXECUTIVE ENGINEER
HIGHWAYS DIVISION
MIRPURKHAS