## Estimate
NAME OF WORK: |  |  |  | ONE TIME GRANT REPAIR OF GOVERNMENT GIRLS HIGH SCHOOL HUSSAIN PATO TALUKA FAIZ GANJ DISTRICT KHAIRPUR SEMIS CODE. 415010522
Sr. No. | NAME OF ITEM | [11 empty] | QTY | RATE | UNIT | AMOUNT
1 | Dismantling R.C.C Work (S.I.No –20 / P-120)
| C/wall P-Beam | 1 | x | 100 | x | 0.75 | x | 0.5 |  |  |  | = | 37.5
[13 empty] | 38 | 5545 | %Sft | Rs. | 2107.1
2 | Dismantling brick work in lime or cement mortar. (S.I.No –13 / P-10)
| C/wall | 1 | x | 100 | x | 0.375 | x | 5 |  |  |  | = | 187.5
[13 empty] | 188 | 1285.63 | %Cft | Rs. | 2416.9844
3 | Removing cement or lime plaster.(S.I.No –13 / P-53
| C-Room | 6 | x | 2 | x | (20+18) | x | 3 |  |  |  | = | 1368
| S/W | 1 | x | 2 | x | (105+7.0) | x | 3 |  |  |  | = | 672
[13 empty] | 2040 | 121.05 | %Sft | Rs. | 2469.42
4 | Dismanlting lime or concrete concrete under water Dismantling cement concrete plain 1: 2: 4:(S.I.No –19 (c) / P-10)
| C/R | 2 | x | 20 | x | 16 | x | 0.25 |  |  |  | = | 160
| Ver | 1 | x | 41.13 | x | 7 | x | 0.25 |  |  |  | = | 71.9775
[14 empty] | 3327.5 | %Cft | Rs. | 0
5 | Excavation in foundation of building bridges and other structure i/c dag belling dressing refilling around structure with excavated earth watering and ramming earth lead upto one chain and lift upto five feet (S.I.No – 18-b / P-4)
| S-Tank | 1 | x | 8 | x | 6 | x | 4 |  |  |  | = | 192
[13 empty] | 192 | 3176.25 | %0Cft | Rs. | 609.84
6 | Cement concrete brick or stone ballast 1 1/2" to 2" gauge. (c) Ratio 1 : 5 : 10 (S.I.No –4 / P-05)
| S-Tank | 1 | x | 8 | x | 6 | x | 0.33 |  |  |  | = | 15.84
[13 empty] | 16 | 8694.95 | %Cft | Rs. | 1391.192
7 | Pacca brick work in foundation & plinth in cement S.sand mortor ratio 1:6 (S.I.NO.4,e / P-20 )
| C/wall | 1 | x | 100 | x | 1.13 | x | 2 |  |  |  | = | 226
[13 empty] | 226 | 11948.36 | %Cft | Rs. | 27003.2936
8 | Rcc work in all labour and material except the cost of steel r/f and its labour for Bending and binding wire which will be paid separatey.This rate also i/c all kinds of forms moulds lifting shutterinhg curring rendering and finishing the exposed surface(a) R C Work In roof slab beams coloumns rafts lintels and other structure etc complete ratio 1:2:4 (S.I.NO.6-A P- 16 )
| C.Wall | 1 | x | 100 | x | 1.13 | x | 0.5 |  |  |  | = | 56.5
| S-T Column | 2 | x | 8 | x | 6 | x | 0.33 |  |  |  | = | 31.68
[13 empty] | 89 | 337 | P-Sft | Rs. | 29993
9 | Fabrication of mild steel r/f for c.,c i/c cutting bending dbinding laying in Position i/c removal of rust from bars (S.I.NO.8-E P-16)
| Qty of RCC |  |  |  |  | 89x5/112 | [6 empty] | 3.97
[13 empty] | 3.97 | 5001.7 | P-Cwt | Rs. | 19856.749
10 | pacca brick work other than building including striking of joints upto 20 feet height in:(e) Cement sand mortar.1:6(S.I.No.07, P.No.22).
| C/wall | 1 | x | 100 | x | 0.75 | x | 6 |  |  |  | = | 450
| Pillars | 1 | x | 16 | x | 1.13 | x | 0.37 | x | 6 |  | = | 40.1376
[13 empty] | 490 | 12346.65 | %Cft | Rs. | 60498.585
11 | Pacca brick work in ground floor in:Cement sand mortar. 1:6 (S.I.No.05, P.No.21).
[14 empty] | 12674.36 | %Sft | Rs. | 0
12 | Supplying and filling sand under floor and plugging in walls.(S.I.No.29, P.No.26).
[13 empty] | 0 | 1141.25 | %Cft | Rs. | 0
13 | Providing and Laying 3"thick topping cement concrete (1:2:4) including surface finishing and dividing into panels (S.I.No.16 P.No.42).
| Lav: | 3 | x | 4 | x | 5 | [5 empty] | = | 60
[13 empty] | 60 | 4411.82 | %Sft | Rs. | 2647.092
14 | Applying floating coat of Cement 1/32" thick. (S.I.No: 14, P.No: 53).
| Qty Same as Item No: 03 | [10 empty] | = | 2040
[13 empty] | 2040 | 660 | %Cft | Rs. | 13464
15 | Cement plaster ½” thick upto 20’height ratio 1:6 (S.I.No.13-b P-51)
| Qty Same as Item No: 14 | [10 empty] | = | 2040
| P-Pit | 2 | x | 43.37 | x | 2.75 | [5 empty] | = | 238.535
| """ | 2 | x | 24.87 | x | 2.75 | [5 empty] | = | 136.785
| C/wall | 1 | x | 60 | x | 5 | [5 empty] | = | 300
| """ | 10 | x | 2 | x | 0.37 | x | 5 |  |  |  | = | 37
2752.32
[13 empty] | 2752.32 | 2206.6 | %Sft | Rs. | 60732.6931
16 | Cement plaster 3/8” thick upto 20’ height ratio 1:4 (S.I.No.10-a P-51)
| Qty same as item No: 15 | [10 empty] | = | 2752.32
[13 empty] | 2752.32 | 2197 | %Sft | Rs. | 60468.4704
17 | Making Notice board made with cement.(S.I.No: 1, P.No: 94).
|  | 2 | x | 8 | x | 4 | [5 empty] | = | 64
[13 empty] | 64 | 58.11 | P-Sft | Rs. | 3719.04
18 | Cement concrete plain including placing compacting, finishing and curing, comlete (including screening and washing at stone aggregate without shuttering. (f) Ratio. 1:2 :4 (S.I.No: 5, P.No: 16).
| Lavt: | 2 | x | 5 | x | 4 | x | 0.17 |  |  |  | = | 6.8
[13 empty] | 6.8 | 14429.25 | %Cft | Rs. | 981.189
19 | White glazed tiles 1/4" thick dado jointed in white cement and laid over 1:2 cement sand mortar 3/4" thick including finishing. (S.I.No: 37, P.No: 45).
| Lavt: | 2 | x | 2 x (5.0+ 4.0) x 5.00 | [7 empty] | = | 180
[13 empty] | 180 | 28253.61 | %Sft | Rs. | 50856.498
20 | Laying floors of approved coloured glazed tiles 1/4" thick laid in white cement and pigment on a bed of 3/4" thick cement mortar 1:2. (S.I.No: 37, P.No: 44).
| Lavt: | 2 | x | 5 | x | 4 | [5 empty] | = | 40
[13 empty] | 40 | 27747.06 | %Sft | Rs. | 11098.824
21 | Providing and laying HALA or pattern tiles glazed 6" x 6" x 1/4" on floor or wall facing in required colour and pattern of STILE specification jointed in white cement and pigment over a base of 1:2 grey cement mortar 3/4" thick including washing and filling of joints with slurry of white cement and pigment in desired shape with finishing, cleaning and cost of wax polish etc. complete including cutting tiles to proper profile. (S.I.No: 61, P.No: 47).
| G-Pillor | 2 | x | 2 x (1.50 + 1.50) x 8.00 | [7 empty] | = | 96
| F/S | 1 | x | 43.337 | x | 2 | [5 empty] | = | 86.674
| Pillor | 4 | x | 1.5 | x | 10 | [5 empty] | = | 60
242.674
[13 empty] | 242.674 | 47651.56 | %Sft | Rs. | 115637.9467
22 | Supplying fixing Girders (material Sch: item No: 140)
|  | 2 | x | 4 | x | 26.37 | x | 12 | / | 112 |  | = | 22.6029
|  | 1 | x | 1 | x | 9 | x | 12 | / | 112 |  | = | 0.96429
23.5671
[13 empty] | 23.5671 | 3850 | P-Cwt | Rs. | 90733.5
23 | Supplying fixing T-Irons (material Sch: item No: 144)
|  | 22 | x | 43.37 | x | 2.25 | / | 112 |  |  |  | = | 19.168
[13 empty] | 19.168 | 3575 | P-Cwt | Rs. | 68525.5681
24 | Second class tile roofing consisting of 4" earth and 1" mud plaster with Gobri leeping over 1/2"thick cement plaster 1:6 with 34 Lbs. Of hot bitumen coating sand blinded, provided over one layer of 12" x 6"x2" tiles laid in 1:6 cement mortar including 1:2 cement pointing under neath of tiles complete including curing etc. (S.I.No: 02, P.No:33).
|  | 1 | x | 43.37 | x | 26.37 | [5 empty] | = | 1143.6669
[13 empty] | 1143.6669 | 7607.25 | %Sft | Rs. | 87001.6003
25 | Supplying & fixing in position iron/steel grill of 3/4" x 1/4" size flat iron of approved design including painting 3 coats etc. complete (weight not to be less than 3.7 Lbs./Sq . Foot of finished grill). (S.I.No: 26,P- No: 93).
| Ver Open: | 4 | x | 4 | x | 5 | [5 empty] | = | 80
|  | 6 | x | 3 | x | 1.08 | x | 3.5 |  |  |  | = | 19.44
99.44
[13 empty] | 99.44 | 180.5 | P-Sft | Rs. | 17948.92
26 | Cement pointing struck joints on walls. (a) Ratio 1:2 (S.I.No: 29,P- No:53).
| C.Wall | 1 | x | 60 | x | 5 | [5 empty] | = | 300
[13 empty] | 300 | 1287.4 | %Sft | Rs. | 3862.2
27 | First class deodar wood wrought joinery for doors and windows Fixed in position i/c chowkats holds fasts hings iron tower volts chocks cleats Handles etc complete( Only shutters) (S.I.No.7, b / P-57)
| D | 2 | x | 3.5 | x | 6.75 | [5 empty] | = | 47.25
| W | 6 | x | 3 | x | 1.12 | x | 3.58 |  |  |  | = | 72.1728
119.4228
[13 empty] | 119.4228 | 902.93 | P-Sft | Rs. | 107830.4288
28 | Extra Lead for 03 Miles
| Qty Same as Item No: 12 | [10 empty] | = | 0
[13 empty] | 0 | 579.41 | % Cft | Rs. | 0
29 | Making & fixing steel grated door with 1/16" thick sheeting including angle iron frame 2" x 2" 3/8"and 3/4" square bars 4" centre to centre with locking arrangemtnt. (S.I.No.24, P-92)
| D | 1 | x | 8 | x | 6 | [5 empty] | = | 48
[13 empty] | 48 | 726.72 | P-Sft | Rs. | 34882.56
30 | Providing and fixing G.I frames /Choukhats of size 7" x 2" or 4 1/2" x 3" for windows using 20 gauge G.I sheet I/c welded hinges and fixing at site with necessary hold fasts, filling with cement sand slurry of ratio 1:6 and repairing the jambs. The cost also i/c all carriage , tools and plants used in making and fixing.(S.I.No.28, b / P-92)
|  | 6 | x | 2 | x | 4 | [5 empty] | = | 48
|  | 6 | x | 4 | x | 3.5 | [5 empty] | = | 84
132
[13 empty] | 132 | 240.5 | P-Sft | Rs. | 31746
31 | Providing and fixing G.I frames /Choukhats of size 7" x 2" or 4 1/2" x 3" for door using 20 gauge G.I sheet I/c welded hinges and fixing at site with necessary hold fasts, filling with cement sand slurry of ratio 1:6 and repairing the jambs. The cost also i/c all carriage , tools and plants used in making and fixing.(S.I.No.29, P.No.92).
| Door | 2 | x | 2 | x | 7 | [5 empty] | = | 28
|  | 2 | x | 1 | x | 3.5 | [5 empty] | = | 7
35
[13 empty] | 35 | 228.9 | P-Sft | Rs. | 8011.5
32 | RCC Spouts (S.No: 14 P-17)
|  | 1 | x | 4 | [7 empty] | = | 4
[12 empty] | = | 4 | 261.25 | P-Sft | Rs. | 1045
33 | White Washing 3 Coats (S.I.No.226/ P-53)
| C/R | 2 | x | 20 | x | 16 | [5 empty] | = | 640
| Ver | 1 | x | 41.13 | x | 7 | [5 empty] | = | 287.91
927.91
[13 empty] | 927.91 | 829.95 | %Sft | Rs. | 7701.189
34 | Colour Washing 2 Coats (S.I.No.256/ P-53)
| Qty Same as Item No: 25 | [10 empty] | = | 300
| C/R | 1 | x | 43.37 | x | 12 | [5 empty] | = | 520.44
| Ver | 2 | x | 26.37 | x | 12 | [5 empty] | = | 632.88
1453.32
[13 empty] | 1453.32 | 859.9 | %Sft | Rs. | 12497.0987
35 | Primary coat of Chalk under distembering (S.I.No.23/ P-53)
| C/R | 2 | x | 2 x ( 20.0 +16.0) x 12.00 + 11.50 | [7 empty] | = | 1692
2
| Ver | 1 | x | 2 x ( 41.13 +7.00) x 12.00 + 11.50 | [7 empty] | = | 1131
2
| F/Side | 1 | x | 43.13 | x | 12 | [5 empty] | = | 517.56
| Lav | 2 | x | 2 x (5.0 + 4.0) x 4.00 | [7 empty] | = | 144
| O/S | 1 | x | 2 x (6.50 + 5.50) x 8.00 | [7 empty] | = | 192
| C.Wall | 1 | x | 260 | x | 5 | [5 empty] | = | 1300
4976.56
[13 empty] | 4976.56 | 442.75 | %Sft | Rs. | 22033.7194
36 | Distempering three coats (S.i.No.24 b P.No.53).
| Qty same as item No: 34 | [10 empty] | = | 4976.56
[13 empty] | 4976.56 | 1079.65 | %Sft | Rs. | 53729.43
37 | Painting doors & windows any type i/c edges of 3 coats (S.I.No.4c-ii, P.No.67).
| C/R | 2 | x | 2 | x | 4 | x | 7 |  |  |  | = | 112
| W | 6 | x | 2 | x | 4 | x | 4 |  |  |  | = | 192
| Lavt D | 2 | x | 2 | x | 2 | x | 7 |  |  |  | = | 56
360
[13 empty] | 360 | 1506.45 | %Sft | Rs. | 5423.22
38 | Painting Grader Bars three coats (S.I.No.14d P-65)
| Girder | 2 | x | 4 | x | 26.37 | x | 2.67 |  |  |  | = | 563.2632
| "" | 1 | 9 | 51 | x | 0.67 | [5 empty] | = | 34.17
| Tears | 22 | x | 43.37 | x | 0.67 | [5 empty] | = | 639.2738
| M-Gate | 1 | x | 2 | x | 8 | x | 6 |  |  |  | = | 96
1332.707
[13 empty] | 1332.707 | 908.4 | %Sft | Rs. | 12106.3104
[14 empty] | Total |  | Rs. | 969144.3083
| SUB-ENGINEER | [9 empty] | CHAIRMAN PROCUREMENT COMMITTEE HM, GGHS, HUSSAIN PATO TALUKA FAIZ GANJ
PART- B W/S & FITTING
1 | S/F squting type white glazed earth were W.C pan with internal i/c the cost of flush cirtion with inlet fitting and flesh pipe with band making good in cement concrete 1:2:4 (i) w.C not less that 19” clear opening between flushing 3 galons pushing tank with 4” dai C.P trap and C.I thumble
[13 empty] | 2 | 4846.6 | Each | Rs. | 9693.2
2 | P/F 22” x 16” lavatory basin in white glazed ware complete with and i.c the cost of w.i or cantilever brackets 6” buil to into walls paited etc complete (SI No: /P-10)
[13 empty] | 1 | 4694.8 | Each | Rs. | 4694.8
3 | Providing G.I pipe special and clamps etc fixing cutting and fitting complete with all nuts and bolts cutting trench upto 24” feet deep raffling watering ramming
| 1/2" Dia | [11 empty] | 25 | 73.21 | P-Rft | Rs. | 1830.25
| 3/4" Dia | [11 empty] | 33 | 95.79 | P-Rft | Rs. | 3161.07
| 1" Dia | [11 empty] | 15 | 128.55 | P-Rft | Rs. | 1928.25
4 | P/F 6’x2” or 6”x3” C I Floor trap of the approved self cleaning design With A c etc .(SI No: /P-20 )
[13 empty] | 2 | 2024.43 | Each | Rs. | 4048.86
5 | Nyloon connection
[13 empty] | 3 | 447.15 | Each | Rs. | 1341.45
6 | S/F long bib cock 1/2" dia of superior quality
[13 empty] | 2 | 1109.46 | Each | Rs. | 2218.92
7 | S/F C.P cock 1/2" dia of superior quality
[13 empty] | 2 | 889.46 | Each | Rs. | 1729
8 | P/F 4” dia C.I Soil Vent pipe i/c cutting and fitting and extra painting to match the colour of the building
[13 empty] | 36 | 333.29 | P-Rft | Rs. | 11998.44
9 | S/F fiber glass tank of approved quality and design and wall thickness specified i/c nuts and bolts and fixing sin plate from Pf C.C 1:6 and making connection for inlete out let and over flow pipe etc complete
[13 empty] | 1 | 21989.61 | P-No | Rs. | 21989.61
10 | Providing and fixing of piston pump local made single phase 220
[13 empty] | 1 | 5494.57 | P-No | Rs. | 5494.57
11 | Boring for tube well in all water bearing soils from ground level upto 100 ft or 30.5 meter depth i/c sinking and with drawing of caseing 80mm (3: Dia)(PHE-S.I.No: 1 (a) P-41)
[13 empty] | 40 | 160 | P-No | Rs. | 6400
12 | Construction of manhole or inspection chamber for the required diamter of circular sewer with walls of B.B in cement sand mortor 1:3 cement plastered 1:3 1/2" thick, inside of walls and 1" (25mm) thick over benching and channel i/c fixing C.I manhole cover with frame of clear opeining 1/2" x 1 x 1/2" (457 x 457mm) of 1.75 cwt (88.9kg) embedded in plain C.C 1:2:4 and fixing 1" (25mm) dia M.S steps 6" (150mm) wide projecting 4" (102 mm) from the face of wall at 12" (305 mm) C/C duly painted etc complete as per standard specification and drawing (S.I.No: 1, (a) P-46)
[13 empty] | 1 | 14748 | P-No | Rs. | 14748
[14 empty] | Total |  |  | 91276.42
CHAIRMAN PROCUREMENT COMMITTEE HM, GGHS, HUSSAIN PATO TALUKA FAIZ GANJ
SUB-ENGINEER

## Schedule-B
SCHEDULE-B
NAME OF WORK: |  | ONE TIME GRANT REPAIR OF GOVERNMENT GIRLS HIGH SCHOOL HUSSAIN PATO TALUKA FAIZ GANJ DISTRICT KHAIRPUR SEMIS CODE. 415010522
Sr. No. | NAME OF ITEM |  | QTY | RATE | UNIT | AMOUNT
1 | Dismantling R.C.C Work (S.I.No –20 / P-120)
|  |  | 60 | 5545 | %Sft | Rs. | 3327
2 | Dismantling brick work in lime or cement mortar. (S.I.No –13 / P-10)
|  |  | 84 | 1285.63 | %Cft | Rs. | 1079.9292
3 | Removing cement or lime plaster.(S.I.No –13 / P-53
|  |  | 1324 | 121.05 | %Sft | Rs. | 1602.702
4 | Excavation in foundation of building bridges and other structure i/c dag belling dressing refilling around structure with excavated earth watering and ramming earth lead upto one chain and lift upto five feet (S.I.No – 18-b / P-4)
|  |  | 192 | 3176.25 | %0Cft | Rs. | 609.84
5 | Cement concrete brick or stone ballast 1 1/2" to 2" gauge. (c) Ratio 1 : 5 : 10 (S.I.No –4 / P-05)
|  |  | 16 | 8694.95 | %Cft | Rs. | 1391.192
6 | Pacca brick work in foundation & plinth in cement S.sand mortor ratio 1:6 (S.I.NO.4,e / P-20 )
|  |  | 455 | 11948.36 | %Cft | Rs. | 54365.038
7 | Rcc work in all labour and material except the cost of steel r/f and its labour for Bending and binding wire which will be paid separatey.This rate also i/c all kinds of forms moulds lifting shutterinhg curring rendering and finishing the exposed surface
|  |  | 106 | 337 | P-Sft | Rs. | 35722
8 | Fabrication of mild steel r/f for c.,c i/c cutting bending dbinding laying in Position i/c removal of rust from bars (S.I.NO.8-E P-16)
|  |  | 4.73 | 5001.7 | P-Cwt | Rs. | 23658.041
9 | pacca brick work other than building including striking of joints upto 20 feet height in:(e) Cement sand mortar.1:6(S.I.No.07, P.No.22).
|  |  | 600 | 12346.65 | %Cft | Rs. | 74079.9
10 | Applying floating coat of Cement 1/32" thick. (S.I.No: 14, P.No: 53).
|  |  | 1324 | 660 | %Cft | Rs. | 8738.4
11 | Cement plaster ½” thick upto 20’height ratio 1:6 (S.I.No.13-b P-51)
|  |  | 1324 | 2206.6 | %Sft | Rs. | 29215.384
12 | Cement plaster 3/8” thick upto 20’ height ratio 1:4 (S.I.No.10-a P-51)
|  |  | 1324 | 2197 | %Sft | Rs. | 29088.28
13 | Primary coat of Chalk under distembering (S.I.No.23/ P-53)
|  |  | 2736 | 442.75 | %Sft | Rs. | 12113.64
14 | Distempering three coats (S.i.No.24 b P.No.53).
|  |  | 2736 | 1079.65 | %Sft | Rs. | 29539.224
15 | Painting doors & windows any type i/c edges of 3 coats (S.I.No.4c-ii, P.No.67).
|  |  | 104 | 1506.45 | %Sft | Rs. | 1566.708
|  |  |  | TOTAL |  | Rs. | 306097.2782
________________% Above / Below (Amount to be added / deducted) Rs.______________________ Grand Total Rs.__________________ Total Amount in word:__________________________________________________ _____________________________________________________________________ Note:- Quantities and rates may be chagned aa per / according to the Technical Sanction by the competent authority.
CONTRACTOR |  |  | CHAIRMAN PROCUREMENT COMMITTEE HM, GGHS, HUSSAIN PATO TALUKA FAIZ GANJ
PART- B W/S & FITTING
1 | S/F squting type white glazed earth were W.C pan with internal i/c the cost of flush cirtion with inlet fitting and flesh pipe with band making good in cement concrete 1:2:4 (i) w.C not less that 19” clear opening between flushing 3 galons pushing tank with 4” dai C.P trap and C.I thumble
|  |  | 1 | 4846.6 | Each | Rs. | 4846.6
2 | P/F 22” x 16” lavatory basin in white glazed ware complete with and i.c the cost of w.i or cantilever brackets 6” buil to into walls paited etc complete (SI No: /P-10)
|  |  | 1 | 4694.8 | Each | Rs. | 4694.8
3 | Providing G.I pipe special and clamps etc fixing cutting and fitting complete with all nuts and bolts cutting trench upto 24” feet deep raffling watering ramming
| 1/2" Dia |  | 10 | 73.21 | P-Rft | Rs. | 732.1
| 3/4" Dia |  | 20 | 95.79 | P-Rft | Rs. | 1915.8
4 | P/F 6’x2” or 6”x3” C I Floor trap of the approved self cleaning design With A c etc .(SI No: /P-20 )
|  |  | 3 | 2024.43 | Each | Rs. | 6073.29
5 | Nyloon connection
|  |  | 4 | 447.15 | Each | Rs. | 1788.6
6 | S/F long bib cock 1/2" dia of superior quality
|  |  | 1 | 1109.46 | Each | Rs. | 1109.46
7 | S/F C.P cock 1/2" dia of superior quality
|  |  | 1 | 889.46 | Each | Rs. | 889.46
8 | P/F 4” dia C.I Soil Vent pipe i/c cutting and fitting and extra painting to match the colour of the building
|  |  | 1 | 333.29 | P-Rft | Rs. | 333.29
|  |  | TOTAL |  |  | Rs. | 22383.4
________________% Above / Below (Amount to be added / deducted) Rs.______________________ Grand Total Rs.__________________ Total Amount in word:__________________________________________________ _____________________________________________________________________ Note:- Quantities and rates may be chagned aa per / according to the Technical Sanction by the competent authority.
CONTRACTOR |  |  | CHAIRMAN PROCUREMENT COMMITTEE HM, GGHS, HUSSAIN PATO TALUKA FAIZ GANJ

## Comparative Statement
MATERIAL STATEMENT
S.No | Name of Item | Qty: |  |  | Cement P-Bags | H-Sand 100 Cft | Stone 100 Cft | Bajri 100 Cft | Bricks %0 Nos | Steel P-Ton
1 | C.C 1:5:10 | 16 | 2.816 | Cft | 1.248 | 7.84 | 15.68 | *** | *** | ***
2 | R.C.C 1:2:4 | 56.5 | 9.944 | Cft | 9.944 | 24.86 | *** | 49.72 | *** | ***
3 | Pacca Brick Work | #VALUE! |  | Cft | #VALUE! | #VALUE! | *** | *** | #VALUE! | ***
4 | P/L 3" Thick Top: | #REF! | #REF! | Sft | #REF! | #REF! | *** | #REF! | *** | ***
5 | C.Plaster 1:6 | 2752.32 | 14.5873 | Sft | 14.5873 | 110.0928 | *** | *** | *** | ***
6 | C.Plaster 1:4 | 2752.32 | 15.6882 | Sft | 15.6882 | 82.5696 | *** | *** | *** | ***
7 | C.C Plain 1:2:4 | 6.8 | 0.204 | Cft | 1.1968 | 2.992 | ** | 5.984 | *** | ***
8 | Applying F- Coat | 2040 | 61.2 | Sft | 8.16 | *** | *** | *** | *** | ***
9 | Cement Pointing | 300 | 1.71 | Sft | 2.16 | 5.4 | *** | *** | *** | ***
10 | Marble Floor | 0 | 0 | Sft | 0 | 0 | *** | *** | *** | ***
11 | Tiles | 462.674 | 2.6372 | Sft | 5.2745 | 27.7604 | *** | *** | *** | ***
12 | Tiles Roofing | 1143.6669 |  | Sft | 5.8327 | 48.7202 | *** | *** | 2287.3338 | ***
13 | Fabrication | 0 | *** | Cwt | *** | *** | *** | *** | *** | 0
Total |  |  | #REF! |  | #VALUE! | #VALUE! | 15.68 | #REF! | #VALUE! | 0
COST OF CARRIAGE OF MATERIAL
S.No | Name of Work |  |  |  |  | Qty: | Rate | Unit | Amount
1 | Stone Metal |  |  |  |  | 15.68 | 1390.6 | % Cft | 218.0461
2 | Sand |  |  |  |  | #VALUE! | 6828.12 | % Cft | #VALUE!
3 | Bajri |  |  |  |  | #REF! | 1325.48 | % Cft | #REF!
4 | Cemet |  |  |  |  | #VALUE! | 140.73 | P.Bag | #VALUE!
5 | Bricks |  |  |  |  | #VALUE! | 617.5 | %0Nos | #VALUE!
6 | Steel |  |  |  |  | 0 | 186.15 | P-Tons | 0
| Total: - | [6 empty] | = | #VALUE!
SUB-ENGINEER
EXECUTIVE ENGINEER EDUCATION WORKS DIVISION KHAIRPUR
ASSISTANT ENGINEER EDUCATION WORKS SUB-DIVISION KHAIRPUR

## Sheet1
RATE ANYLISIS
REHABILITATION/MISSING FACILITIES @ GGPS ALI NAWAZ MATILO U/C SHAH LADHANI TALUKA AND DISTRICT KHAIRPUR (SEMIS CODE NO: 415030188)
1 | CEMENT (Lucky Cement Factory) | M -
i | Cement Factory to Hyderabad N.H.W | 51.7
ii | Hyderabad to Khairpur N.H.W | 170.1
iii | N.H.W Khairpur to site o work | 4
|  | 225.8 |  | - | 2 | = | 223.8
COST OF CARTAGE
i | 1st 2 miles | Rs. 7/53 | 7.53
ii | Remaining 222 miles 0/60 P-Mile | Rs. 132 | 133.2
|  | Rs. | 140.73
2 | HILL SAND
Cartage of Bholari, Hill Sand of approved quality from approved quality to site of work i/c loading and unloading etc
i | From Bholari to Hyderabad N.H.W | 16.4
ii | From N.H.W Hyderabad to Khairpur N.H.W | 173.3
iii | From Khairpur N.H.W to site of work | 4
|  | 193.7 |  | - | 2 | = | 191.7
COST OF CARTAGE
i | For 6 miles | Rs. 7/53 | 771.96
ii | Remaining 186 miles 32/56 P-Miles | Rs. 132 | 6056.16
|  | Rs. | 6828.12
3 | STONE BAJRI
i | Lead from Ubhan Shah to N.H.W Kotdiji | 5
ii | From N.H.W Kotdiji to Khairpur N.H.W | 14
iii | Khairpur N.H.W to site of work | 4
|  | 23 |  |  |  | = | 23
COST OF CARTAGE
i | 1st 6 miles | Rs. 7/53 | 771.96
ii | Remaining 17 miles 32/56 P-Miles | Rs. 132 | 553.52
|  | Rs. | 1325.48
4 | STONE METAL
i | Lead from Ubhan Shah to N.H.W Kotdiji | 6.5
ii | From N.H.W Kotdiji to Khairpur N.H.W | 14
iii | Khairpur N.H.W to site of work | 4
|  | 24.5 |  |  |  | = | 24.5
COST OF CARTAGE
i | 1st 6 miles | Rs. 7/53 | 771.96
ii | Remaining 19 miles 32/56 P-Miles | Rs. 132 | 618.64
|  | Rs. | 1390.6
5 | STEEL
i | Lead from Sukkur to Barrage Zone | 1
ii | Lead From Barrage zone to N.H.W Sukkur | 1.4
iii | Lead from N.H.W Sukkur to Khairpur @ Thehri | 8
|  | 10.4 |  |  |  | = | 11
COST OF CARTAGE
i | 1st 6 miles | Rs. 7/53 | 771.96
ii | Remaining 5 miles 32/56 P-Miles | Rs. 132 | 162.8
|  | Rs. | 934.76 |  |  | / 5 = | 186.15
6 | BRICKS
i | Lead from Kilen to site of work | 6
COST OF CARTAGE
i | 1st 6 miles | Rs. 7/53 | 617.5 |  |  | %0Nos

## Summary
SUMMARY OF COST
NAME OF WORK:
"A" | COST OF Civil Work (i/c Carriage of Mterial) |  | RS. | #VALUE!
"B" | Cost Of Part B W/S & S/Fitting |  | RS. | 14748
"C" | Cost Of Electrification |  | RS. | 150000
"D" | 1 % Contingency |  | RS. | #VALUE!
|  | Total | RS. | #VALUE!
"E" | 1 % T.P.V |  | RS. | #VALUE!
|  | G-Total | RS. | #VALUE!
|  | Say | RS. | 1529000
|  | In Millions | RS. | 1.529
SUB-ENGINEER
EXECUTIVE ENGINEER EDUCATION WORKS DIVISION KHAIRPUR
ASSISTANT ENGINEER EDUCATION WORKS SUB-DIVISION KHAIRPUR