## Sheet1
STANDARD PROCUREMENT PLAN 140115JPG (22070*991)
ANNUAL PROCUREMENT PLAN
(WORKS, GOOD & SERVICES)
FINANCIAL YEAR 2 0 1 5 - 1 6
AGENDA NO.01
Sr no | Description of Procurement | Quality (where applicable) | Estimated unit cost where applicable | Estimated total cost in (M) | Funds allocated in (M) | Source of funds (ADP/Non ADP) | Proposed procurment method | Timing of Procurement |  |  |  | Remarks
[8 empty] | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr
01. | 02. | 03. | 04. | 05. | 06. | 07. | 08. | 09. | 10. | 11. | 12 | 13.
(CIVIL WORKS)
1/363 | REHABLTATION OF HIGH/MIDDLE/PRIMARY SCHOOLS OF DISTRICT KHAIRPUR SCHEME PROPOSED BY TALUKA PRESIDENT (PPPP)@ |  | 20.000 Block | 20.000 Block | 5.000
1 | Maintenance & Repair to GGPS Kaman Kanhar
A | Civil Work | 01 No: | 1.1 | 1.25 | 0.3125 | ADP | Single Stage Single Envelope | 0.0781 | 0.0781 | 0.0781
B | Electric Work |  | 0.15 | 0.15
2 | Maintenance & Repair to GBPS Wada Mahesar
A | Civil Work | 01 No: | 1.1 | 1.25 | 0.3125 | ADP | -do- | 0.0781 | 0.0781 | 0.0781
B | Electric Work |  | 0.15
3 | Rehabilitation of GGPS Gath Rajpar
A | Civil Work | 01 No: | 1.15 | 1.25 | 0.3125 | ADP | -do- | 0.0781 | 0.0781 | 0.0781 | -
B | Electric Work |  | 0.08
4 | Rehabilitation of GBPS Din Mohammad Khokhar
A | Civil Work | 01 No: | 1.2 | 1.25 | 0.3125 | ADP | -do- | 0.0781 | 0.0781 | 0.0781 | -
B | Electric Work |  | 0.05
5 | Rehabilitation of GBHS Pharharo
A | Civil Work | 01 No: | 1.15 | 1.25 | 0.3125 | ADP | -do- | 0.0781 | 0.0781 | 0.0781 | -
B | Electric Work |  | 0.08
6 | Rehabilitation of GBPS Khalid Hussain Rajpar
A | Civil Work | 01 No: | 1.15 | 1.25 | 0.3125 | ADP | -do- | 0.0781 | 0.0781 | 0.0781 | -
B | Electric Work |  | 0.07
7 | Rehabilitation at Govt:Boys Elementary School Kazimabad U/C Gambat-II
A | Civil Work | 01 No: | 2.2 | 2.5 | 0.625 | ADP | -do- | 0.156 | 0.156 | 0.156 | -
B | Electric Work |  | 0.8
8 | Rehabilitation at GBPS Sagyoon (Circle) U/C Sagyoon
A | Civil Work | 01 No: | 2.1 | 2.5 | 0.625 | ADP | -do- | 0.156 | 0.156 | 0.156 | -
B | Electric Work |  | 0.3
9 | Construction of 01 C/R & Rehabilitation/Renovation of GBPS Ali Sher Kubar
A | Civil Work | 01 No: | 2.4 | 2.5 | 0.625 | ADP | -do- | 0.156 | 0.156 | 0.156 | -
B | Electric Work |  | 0.08
10 | Repair Renovation & Rehab; of GBPS Rasool Bux Chang
A | Civil Work | 01 No: | 2.35 | 2.5 | 0.625 | ADP | -do- | 0.156 | 0.156 | 0.156 | -
B | Electric Work |  | 0.14
11 | Rehabilitation/Renovation of GGPS Memon Mohalla Luquman Khairpur
A | Civil Work | 01 No: | 1.1 | 1.25 | 0.3125 | ADP | -do- | 0.0781 | 0.0781 | 0.0781 | -
B | Electric Work |  | 0.13
12 | Rehabilitation/Renovation of GBPS Panj Hatti Khairpur
A | Civil Work | 01 No: | 1.1 | 1.25 | 0.3125 | ADP | -do- | 0.0781 | 0.0781 | 0.0781 | -
B | Electric Work |  | 0.12
13/313 | Rehabilitation/RenovationXEN;/AEN/ Education Works Offices Khairpur
A | Civil Work | 01 No: | 13 | 16.885 | 4.925 | ADP | -do- | 1.2312 | 1.2312 | 1.2312 | -
B | Electric Work |  | 1
14/313 | Rehabilitation/Renovation/Additional class Rooms And Missing Facilities At GPS Sajan Rind
A | Civil Work | 01 No: | 2.4131 | 2.815 |  | ADP | -do- |  |  | - | -
B | Electric Work |  | 0.5
| PROVINCIAL LOCAL GOVT; 2014-15 PROG | [9 empty] | -
15/1229 | Construction & Establishment of Science Laboratories for High School Baberloi (External Development)
A | Civil Work | 01 No: | 1.5 |  |  | ADP | -do- |  |  | - | -
B | Electric Work
16/232 | Establishment of Boys/Girls Degree College in Sindh 2010-11 Prog: Government Degree College Therhi (Laboratries Block)
A | Civil Work | 01 No: | 30 | 88.477 |  | ADP | -do- |  |  | - | -
B | Electric Work
17/660 | Repair/Renovation & Maintenance of GPS Muhammad Ali Janwari @ Village Haji Sadoro Khan Janwari Khairpur
A | Civil Work | 01 No: | 1.8 | 2 | 1 | ADP | -do- | 0.25 | 0.25 | - | -
B | Electric Work |  | 0.2
18/661 | Rehabilitation/Missing Facilities Additional of Two Class Room @ GBPS Pir Bux Maitlo
A | Civil Work | 01 No: | 3 | 3.5 | 1.33 | ADP | -do- | 0.3325 | 0.3325 | - | -
B | Electric Work |  | 0.2
19/662 | Construction of Compound Wall GGPS Manganwari
A | Civil Work | 01 No: | 1 | 1 | 1 | ADP | -do- | 0.25 | 0.25 | - | -
20/663 | Rehabilitation of GPS Khuda Bux Maitlo Kingri
A | Civil Work | 01 No: | 1.3 | 1.4 | 0.7 | ADP | -do- | 0.175 | 0.175 | - | -
B | Electric Work |  | 0.08
21/664 | Rehabilitation of GPS Wada Mahesar
A | Civil Work | 01 No: | 0.9 | 1 | 1 | ADP | -do- | 0.25 | 0.25 | - | -
B | Electric Work |  | 0.08
22/665 | Construction of School Building & Paver Block at GPS Sher Muhammad Chang
A | Civil Work | 01 No: | 2.5 | 3 | 1.14 | ADP | -do- | 0.285 | 0.285 | - | -
B | Electric Work |  | 0.15
23/666 | Renovation/Repair of GGPS Siyal Mohalla Old Bus Stand Station Road Ranipur
A | Civil Work | 01 No: | 0.9 | 1 | 1 | ADP | -do- | 0.25 | 0.25 | - | -
B | Electric Work |  | 0.08
24/667 | Construction of School Building at Village Nazar Muhammad Panhyar
A | Civil Work | 01 No: | 3 | 3.6 | 1.368 | ADP | -do- | 0.342 | 0.342 | - | -
B | Electric Work |  | 0.2
25/668 | Construction of C/Wall i/c Lavatory Block @ School Muhammad Sachal Panhyar
A | Civil Work | 01 No: | 1.3 | 1.5 | 0.75 | ADP | -do- | 0.1875 | 0.1875 | - | -
B | Electric Work |  | 0.15
26/669 | Construction of additional Class Room & Compound wall of GBPS Muhammad Akram Veesar
A | Civil Work | 01 No: | 1.7 | 1.87 | 0.935 | ADP | -do- | 0.23375 | 0.23375 | - | -
B | Electric Work |  | 0.08
27/670 | Construction/Re-Construction of Class Room & Compound wall of GBPS Bago Dhoro @ Muhammad Ismail Kubar
A | Civil Work | 01 No: | 1.3 | 1.5 | 0.75 | ADP | -do- | 0.1875 | 0.1875 | - | -
B | Electric Work |  | 0.06
28/671 | Construction/Re Construction of Class Room & Compound Wall of GBPS Ali Sher Dasti
A | Civil Work | 01 No: | 1.3 | 1.5 | 0.75 | ADP | -do- | 0.1875 | 0.1875 | - | -
B | Electric Work |  | 0.06
29/672 | Renovation of Existing Buyilding & Provision Of Lavatory Block at GBPS Riaz Hussain Rind
A | Civil Work | 01 No: | 0.8 | 1 | 1 | ADP | -do- | 0.25 | 0.25 | - | -
B | Electric Work |  | 0.16
30/673 | Construction of Additional Class Room & Compound Wall of GBPS Qadirdad Lashari
A | Civil Work | 01 No: | 0.8 | 1 | 1 | ADP | -do- | 0.25 | 0.25 | - | -
B | Electric Work |  | 0.06
31/674 | Construction/Re Construction of Class Room & Compound Wall of GBPS Qadir Ibupoto
A | Civil Work | 01 No: | 1.3 | 1.5 | 0.75 | ADP | -do- | 0.1875 | 0.1875 | - | -
B | Electric Work |  | 0.06
32/675 | Construction of Additional Class Room & Renovation of Existing Building & Compound Wall Of Govt: Elementary School Mithal Jogi
A | Civil Work | 01 No: | 1.3 | 1.5 | 0.75 | ADP | -do- | 0.1875 | 0.1875 | - | -
B | Electric Work |  | 0.15
33/676 | Construction/Re Construction of Class Room and Compound Wall of GGPS Muhammad Siddique Bambhan
A | Civil Work | 01 No: | 1.3 | 1.5 | 0.75 | ADP | -do- | 0.1875 | 0.1875 | - | -
B | Electric Work |  | 0.06
34/677 | Construction/Re Construction of Class Room & Compound Wall of GGPS Pahlwan Khan Shar
A | Civil Work | 01 No: | 1.3 | 1.5 | 0.75 | ADP | -do- | 0.1875 | 0.1875 | - | -
B | Electric Work |  | 0.06
COMMUNITY DEVELOPMENT PROGRAMME FOR SUSTAINABLE DEVELOPOMENT GOALS 2015-16
35 | Construction of Primary School Building GBPS Gul Hassan Thebo
A | Civil Work | 01 No: | 2.3 | 2.5 | 2.5 | Non-ADP | -do- | 2.5 | - | - | -
B | Electric Work |  | 0.12
36 | Government Masjid Primary School Gaman Khan Shar
A | Civil Work | 01 No: | 1.8 | 2 | 2 | Non-ADP | -do- | 2 | - | - | -
B | Electric Work |  | 0.1
37 | Government Boys Primary School Allah Dino Mojae
A | Civil Work | 01 No: | 1.4 | 1.5 | 1.5 | Non-ADP | -do- | 1.5 | - | - | -
38 | Government Boys Primary School Ahmedpur Mohalla Ranipur
A | Civil Work | 01 No: | 1.7 | 2 | 2 | Non-ADP | -do- | 2 | - | - | -
B | Electric Work |  | 0.16
39 | Government Boys Primary School Mohram Bhanbhro
A | Civil Work | 01 No: | 1 | 1.1 | 1.1 | Non-ADP | -do- | 1.1 | - | - | -
B | Electric Work |  | 0.05
OGDCL/CSR YEAR 2015-16
40 | Renovation of Auditorium Hall Govt:Sachal Sarmast Degree College Ranipur
A | Civil Work | 01 No: | 1.5 |  |  | Non-ADP | -do- | - | - | - | -
B | Electric Work
41 | Establishment of Government Boys Degree College @ Sobho Dero
A | Civil Work | 01 No: | 120 | 44 |  | Non-ADP | -do- | - | - | - | -
B | Electric Work
224 | Estt:of Boys / Girls Degree Colleges in Sindh (21 Units)
42 | Govt: Boys Degree College Sirai Piyaro
A | Civil Work (External Development) | 01 No: | 2 |  |  | ADP | -do- | - | - | - | -
B | Electric Work |  | 1 |  |  | ADP | -do- | - | - | - | -
(ELECTRICAL WORK) DISTRICT ADP SCHEMES
43/302 | Rehabiltation/Missing facilities/Addition 2 Class Room at GBPS Gujo Phulpoto | 01 No: | 0.05 | 0.05
44/304 | Rehabiltation/Missing facilities Usman Bhayo | 01 No: | 0.05 | 0.05
45/307 | Rehabiltation/Missing facilities/Addition2 Class Room GPS Muhammad Yousif Bhayo | 01 No: | 0.12 | 0.12
46/308 | Rehabiltation/Missing Facilities GBPS Essan Bhayo | 01 No: | 0.05 | 0.05
47/310 | Rehabiltation of Girls Primary School Village Ghulam Mustafa Kundhar | 01 No: | 0.05 | 0.05
48/312 | Rehabiltation School Village Perano Naich | 01 No: | 0.05 | 0.05
49/324 | Rehabltation /Missing facilities GBPSNoor Muhammad | 01 No: | 0.05 | 0.05
50/333 | Rehabltation/Missing Facilities Mangsi | 01 No: | 0.05 | 0.05
51/350 | Rehabilitation/Missing facilities at GBPS Hajna Mohalla Luquman Khairpur (Balance Work) | 01 No: | 0.15 | 0.15
52/357 | Rehabilitation/Missing facilities at Kotpul | 01 No: | 0.07 | 0.07
53/358 | Construction of Library Village Gagri | 01 No: | 0.15 | 0.15
162 | PROVINCIAL ADP(ELECTRICAL WORKS)
UP GRADATION OF P.S TO M.S IN SINDH
2007-08 PROG; ADP 162 2014-15 AT
54 | GGPS Bangul Khan Chandio | 01 No: | 0.16 | 0.16
55 | GPS Mataro Pato U/C Bapho | 01 No: | 0.16 | 0.16
56 | GBPS Radhar | 01 No: | 0.16 | 0.16
57 | GBPS Watni Wada | 01 No: | 0.16 | 0.16
58 | GBPS Soomar Mallah | 01 No: | 0.16 | 0.16
161 | ESTT;OF SINGLE SECTION HIGH SCHOOLIN SINDH 2008-09 PROG; ADP 280 2014-15
59 | Boys Single Section High School Haji Mohammad Ishaque Laghari U/c Hindyari | 01 No: | 0.5 | 0.5
60/177 | Establishment of Single Section High School@ Mir Ali Bazar Khairpur 2012-13 Prog:( First Floor) | 01 No: | 0.25 | 0.25
61/182 | Establishment of Single Section High School At Shaheed Benazer Bhutto Model Village Tajjal 2012-13 Programme | 01 No: | 0.6 | 0.6
232 | Establishment of Boys/Girls Degree College In Sindh 2010-11 Programme
62 | Govt:Degree College Kot Diji (Laboratories Block) | 01 No: | 0.5 | 0.5
63/1229 | Construction & Establishment of Science | 01 No: | 0.75 | 0.75
Laboratories for High School Baberloi
EXECUTIVE ENGINEER
EDUCATION WORKS DIVISION
KHAIRPUR