## Annual Procurement Plan 2016-17
Revised Procurement Plan for the Year 2016-17 (Office of the Executive Engineer, Highways Division, Badin). Annexure A-I
(Annexure-A)
Procurement Plan (Development /Capital).
Sr.No: | Name of Schemes & Estimated Cost | Allocated Funds | Cost of ongoing works (Expenditure already incurred). | Funds earmarked for ongoing Work | Cost of New Works (components) | Funds for new works (c-e) | Nature of Procurement | Method of Procurement | Anticipated/ Actual Date of Advertisement | Anticipated/ Actual Date of start | Anticipated/ Actual Date of completion
a | b | c | d | e | f | g | h | i | j | k | l
1 | Construction of Road From Kapri Mori Dumbalo road to Village Fateh Muhammad Halepoto Mile 0/0-0/5+440' = 1.13Kms. | 4.457 | 0 | 0 | 8.914 | 4.457 | Civil Work | Single stage -1 Envelop Procedure | August -2016 | September -2016 | Marach-2018
2 | Construction of Road From Behdhmi Ismail Bhatti Road to Village Bahadur Khan lund Mile 0/0-1/0+110' = 1.63Kms. | 6.57 | 0 | 0 | 13.14 | 6.57 | Civil Work | Single stage -1 Envelop Procedure | August -2016 | September -2016 | Marach-2018
3 | Construction of Road From Makhandi Road to Village Bachal Mandhro Mile 0/0-0/7+170' = 1.43Kms. | 5.8855 | 0 | 0 | 11.771 | 5.8855 | Civil Work | Single stage -1 Envelop Procedure | August -2016 | September -2016 | Marach-2018
4 | Construction of Road From Imam Wah Regulator Inspection Path Tarai road to Village Ghuram Nohani Mile 0/0-1/4+330'=2.50 Kms. | 9.9955 | 0 | 0 | 19.991 | 9.9955 | Civil Work | Single stage -1 Envelop Procedure | August -2016 | September -2016 | September-2018
5 | Construction of Road From Golarachi Ahmed Rajo road @ Mile 13/0 to Village Malik Lal Muhammad Mile 0/0-1/3 = 2.20Kms. | 9.9535 | 0 | 0 | 19.907 | 9.9535 | Civil Work | Single stage -1 Envelop Procedure | August -2016 | September -2016 | September-2018
6 | Construction of Road From Tando Bago Nindo road to Village Hussain Buledi Mile 0/0-0/5+330' = 1.10 Kms. | 10 | 2.4315 | 7.317 | 8.41 | 2.683 | Civil Work | Single stage -1 Envelop Procedure | August -2016 | September -2016 | Marach-2018
7 | Construction of Road From Tando Ghulam Ali Gulab Leghari road to Village Muhammad Moosa Khskheli/ Ali Bux Khaskheli Mile 0/0-0/6+220'. | 5.2895 | 0 | 0 | 10.579 | 5.2895 | Civil Work | Single stage -1 Envelop Procedure | August -2016 | September -2016 | Marach-2018
8 | Improvement of Road From Saeedpur to Ghulam Shah road Mile 3/4-5/2 = 2.80 Kms. | 7.308 | 0 | 0 | 14.616 | 7.308 | Civil Work | Single stage -1 Envelop Procedure | August -2016 | September -2016 | Marach-2018
9 | Improvement of Road From Saeedpur to Ghulam Shah road Mile 5/2-6/4 = 2.00 Kms. | 5.092 | 0 | 0 | 10.184 | 5.092 | Civil Work | Single stage -1 Envelop Procedure | August -2016 | September -2016 | Marach-2018
10 | Improvement/Rehabilitation of road in Taluka Talhar (2012-13) Improvement of Road From Hyderabad Badin road to P.A.F Base Talhar Mile 0/0-0/2 = 0.40 Kms. | 3 | 0 | 17.199 | 2.545 | 2.545 | Civil Work | Single stage -1 Envelop Procedure | August -2016 | September -2016 | September-2017
11 | Improvement of Matli Phulkara road Mile 0/5-1/6. | 9.671 | 0 | 0 | 19.342 | 9.671 | Civil Work | Single stage -1 Envelop Procedure | August -2016 | September -2016 | September-2018
12 | Improvement of Matli Phulkara road Mile 2/7-4/1. | 9.839 | 0 | 0 | 19.678 | 9.839 | Civil Work | Single stage -1 Envelop Procedure | August -2016 | September -2016 | September-2018
13 | Construction of Bridges in District Badin (2013-14) Repair of 3'ft Span Culverts along road from Pangrio Jhudo road to Kamil Khoso/ Misri Khoso (02 Nos) | 2.5 | 18.99 | 1.7592 | 0.5548 | 0.5548 | Civil Work | Single stage -1 Envelop Procedure | August -2016 | September -2016 | Marach-2017
14 | Construction of Bridges in Taluka Badin. (i) Construction of 45' Rft Bridge Over Scape Opposite Village Ramzan Mallah. (ii) Construction of 20' Rft Bridge Over Suni Gunni Opposite Village Qabool Muhammad Chandio. (iii) Construction of 15' Rft Bridge Over Suni Gunni Opposite Village Soomar Lund. | 5.488 | 0 | 0 | 10.976 | 5.488 | Civil Work | Single stage -1 Envelop Procedure | August -2016 | September -2016 | Marach-2018
15 | Improvement of Matli Phulkara road Mile 1/6-2/7. | 9.684 | 0 | 0 | 19.368 | 9.684 | Civil Work | Single stage -1 Envelop Procedure | August -2016 | September -2016 | September-2018
16 | Improvement of Matli Phulkara road Mile 4/1-5/4. | 9.503 | 0 | 0 | 19.006 | 9.503 | Civil Work | Single stage -1 Envelop Procedure | August -2016 | September -2016 | September-2018
17 | Improvement of Matli Phulkara road Mile 5/4-6/2. | 5.2505 | 0 | 0 | 10.501 | 5.2505 | Civil Work | Single stage -1 Envelop Procedure | August -2016 | September -2016 | September-2018
18 | Construction of Bridges in District Badin (2013-14) Construction of 3'ft Span Culvert Sufi Dika Road @ Mile 3/1 Opposite Village Khamiso Lund. | 2.5 | 18.99 | 2.314 | 0.186 | 0.186 | Civil Work | Single stage -1 Envelop Procedure | August -2016 | September -2016 | Marach-2017
19 | Construction of road from Chak No.7 Village Khamiso Thaemor Towards Village Hassan Lodho Mile 0/0-0/6+440'= 1.30 KMs. | 2.5 | 0 | 0 | 9.846 | 2.5 | Civil Work | Single stage -1 Envelop Procedure | August -2016 | September -2016 | Marach-2018
20 | Construction of 30 Rft Bridge Over Sunny Guni Opposite Village Panai Mallah i/c road Approache. | 2 | 0 | 0 | 6.425 | 2 | Civil Work | Single stage -1 Envelop Procedure | August -2016 | September -2016 | Marach-2017
21 | Construction of 45 Rft Brdige Over MIR Out Fall Drain RD-47 Opposite Village Yousif Warar i/c Road Mile 0/0-0/7+330'=1.50 KMs. | 4.6 | 1.7483 | 2 | 11.799 | 2.6 | Civil Work | Single stage -1 Envelop Procedure | August -2016 | September -2016 | Marach-2018
22 | Construction of road from Pini Ladho Rajo road to Inspection Path of Qazia Wah Old Mile 0/0-1/4+330'= 1.50 KMs. | 4.6 | 2 | 3.5 | 11.843 | 1.1 | Civil Work | Single stage -1 Envelop Procedure | August -2016 | September -2016 | Marach-2018
23 | Construction of road from Dumbalo Budho Qambrani road to Ali Muhammad Arain road upto Village Umerdin High School Mile 0/5-1/3+330'=1.30 KMs | 4.6 | 2 | 3.8 | 8.945 | 0.8 | Civil Work | Single stage -1 Envelop Procedure | August -2016 | September -2016 | Marach-2018
24 | Construction of road from Ansari Sugar Mill Mirwah Gorchani road to Village Muhammad Rahim Rind Mile 0/3+220'-1/1=1.13 KMs | 1.5 | 1.2955 | 1 | 8.464 | 0.2955 | Civil Work | Single stage -1 Envelop Procedure | August -2016 | September -2016 | Marach-2018
25 | Construction of road from Phattan Parhiyar Ahmed Rajo road to Village Kacho Khan Chang Mile 0/5+300'-1/2=0.90 KMs | 6 | 2 | 5 | 7.069 | 2.069 | Civil Work | Single stage -1 Envelop Procedure | August -2016 | September -2016 | Marach-2018
26 | Construction of road from Kamaro Regulator road to Village Phul Mandhro Via Ranjho Khan Chang Mile 1/0-1/3=0.60 KMs | 4 | 1.25 | 3.2 | 7.538 | 0.8 | Civil Work | Single stage -1 Envelop Procedure | August -2016 | September -2016 | Marach-2018
27 | Improvement of road from Dumbalo Kapri Mori road to Village Haji Dodo Gishkori Mile 0/7-1/7=1.60 KMs | 4.5 | 1.75 | 3.7 | 7.966 | 0.8 | Civil Work | Single stage -1 Envelop Procedure | August -2016 | September -2016 | Marach-2018
28 | Improvement of road from Talhar Tando Bago Road @ Mile7/2 to Village Mansoorabad Mile 0/0-2/0+330'=0.50 KMs | 1.3 | 0 | 0 | 2.631 | 1.3 | Civil Work | Single stage -1 Envelop Procedure | August -2016 | September -2016 | September-2017
29 | Improvement of road from Matli Tando Ghulam Ali road to Village Muhammad Rahim Nizamani Mile 0/0-2/3 | 5 | 0 | 0 | 20 | 5 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
30 | Construction of road from Badin Tando Bago road to Village Bachal Mallah Mile 0/0-0/3+220'=0.67 KMs. | 1.409 | 0 | 0 | 5.636 | 1.409 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
31 | Construction of road from Badin Khoski road to Village Muhammad Inrahim Soomro Mile 0/0-1/0+330'=1.70 KMs. | 3.5903 | 0 | 0 | 14.361 | 3.5903 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
32 | Construction of road from Hyderabad Matli road @ Mile 25/6 to Village Rasgon Shakoor Mehajer Mile 0/0-1/0 =1.60 KMs. | 3.25 | 0 | 0 | 13 | 3.25 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
33 | Construction of road from Phalkara Seelgam road to Village Haji Nisar Kaimkhani Mile 0/0-0/5 =1.00 KMs. | 1.913 | 0 | 0 | 7.652 | 1.913 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
34 | Improvement of road from Phalkara Shaikh Bhirkio road to Village Hamid Halepoto Mile 1/4-3/2+330'=2.00KMs. | 3.1597 | 0 | 0 | 12.639 | 3.1597 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
35 | Improvement of road from Saban Dasti road to Village Jan Muhammad Leghari Mile 0/0-0/6 = 1.20KMs. | 1.6485 | 0 | 0 | 6.594 | 1.6485 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
36 | Construction of road from Tando Ghulam Ali Dumbalo road to Village Ali Dooker Mile 0/0-1/0+330 = 1.70 KMs. | 3.4152 | 0 | 0 | 13.661 | 3.4152 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
37 | Construction of road from Tando Ghulam Ali Matli road to Village Ali Muhammad Lund upto Village Punhu Lund Mile 0/0-0/4+550' = 0.96 KMs. | 1.9175 | 0 | 0 | 7.67 | 1.9175 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
38 | Construction of road from Tando Bago Dehi road to Village Sono Gurgaiz Mile 0/0-0/2+330' =0.50 KMs. | 1.147 | 0 | 0 | 4.588 | 1.147 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
39 | Construction of road from Tando Bago Jhudo road from Village Bakhoo Chandio to Village Haji Dato Panhwar Mile 0/0-0/3+330'=0.70KMs. | 1.5023 | 0 | 0 | 6.009 | 1.5023 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
40 | Construction of road from Talhar Rajo Khanani road to Village Haji Ahmed Sand Mile 0/0-0/5. | 2.0175 | 0 | 0 | 8.07 | 2.0175 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
41 | Construction of road from Tando Bago Jhudo road @ mile 4/0 to Village Ghulam Rasool Jamali Mile 0/0-0/5 =1.00 KMs. | 2.122 | 0 | 0 | 8.488 | 2.122 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
42 | Construction of road from Tando Bago Pangrio road Waryal Shah stop to Village Shahnawaz Jamali mile 0/0-0/2= 0.40 KMs. | 0.8905 | 0 | 0 | 3.562 | 0.8905 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
43 | Construction of road from Tando Bago Dehi road @ point Charvo Sim Nali to Village Karam Khan Jamali and Noor Muhammad Dal mile 0/0-0/4+330'= 0.90KMs. | 1.9866 | 0 | 0 | 7.9462 | 1.9866 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
44 | Construction of road from Ghulam Shah road @ Misri Rahimoon to Village Muhammad Rahimoon Mile 0/0-1/4= 2.40 KMs. | 4.9977 | 0 | 0 | 19.991 | 4.9977 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
45 | Construction of 30 Rft Bridge over Mir Wali Opposite Village Ahmed shah Lakyari. | 1.125 | 0 | 0 | 4.5 | 1.125 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
46 | Construction of road from Singhari L.B.O.D Mukhtiar road to Village Abdul Lateef Brohi Mile 0/0-0/6 = 1.20 KMs. | 2.5655 | 0 | 0 | 10.262 | 2.5655 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
47 | Construction of road from Allah Dino Mandhro Master Ahmed Turk to Village Talib Bucho Mile 0/0-1/0 =1.60 KMs. | 3.4848 | 0 | 0 | 13.939 | 3.4848 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
48 | Construction of road from Talib Bucho road to Village Bachal Jakhro Mile 0/0-0/6+330'= 1.30 KMs. | 2.8247 | 0 | 0 | 11.299 | 2.8247 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
49 | Construction of road from Golarachi Ahmed Rajo road Chak No.02 Towards Chak No.04 upto Mario Oil Field Mile 0/0-1/0= 1.60 KMs. | 3.1885 | 0 | 0 | 12.754 | 3.1885 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
50 | Construction of road from Gul Mir Shah Bijari road to Village Yousif Manai Jat Mile 0/0-1/3 = 2.20 KMs. | 4.2075 | 0 | 0 | 16.83 | 4.2075 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
51 | Improvement of road from Kario Khorwah road @ Mile 3/0 to Dubi Regulator Mile 1/1-3/0=2.40 KMs. | 2.6248 | 0 | 0 | 10.499 | 2.6248 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
52 | Construction of road from Tando Ghulam Ali Saban Dasti road to Village Molvi Dilawar Gishkori Mile 0/0-0/1+640' = -.394 KMs. | 0.8 | 0 | 0 | 3.2 | 0.8 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
53 | Construction of road from Ansari Sugar Mills Mirwah road to Village Rawal Lashari Mile 0/0-0/2+290 = 0.488 KMs. | 0.98525 | 0 | 0 | 3.941 | 0.98525 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
54 | Improvement of road from Shaikh Bhirkio Gulab Leghari road to Village Haji Allah Dino Serewal mile 0/0-1/1= 1.80 KMs. | 2.225 | 0 | 0 | 8.9 | 2.225 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
55 | Construction of road from Hyderabad Matli road to Village Khair Muhammad Notkani Mile 0/0-1/0 =1.60 KMs. | 0.957 | 0 | 0 | 3.828 | 0.957 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
56 | Improvement of road from Mir Khan Stop Kapri Mori road to Village Bachal Arisar Mile 0/0-0/5+330' =1.10 KMs. | 1.4518 | 0 | 0 | 5.807 | 1.4518 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
57 | Construction of road from Ansari Sugar Mills Mirwah Kalro Mori road to Village Dr. Muhammad Ali Khoso Mile 0/0-0/2 =0.40 KMs. | 1 | 0 | 0 | 4 | 1 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
58 | Improvement of road from Gulab Leghari Tando Ghulam Ali road to Village Mohib Ali Leghari Mile 0/0-1/1= 1.80 KMs. | 2.21 | 0 | 0 | 8.84 | 2.21 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
59 | Improvement of road from Ansari Sugar Mill Mirwah road to Village Karam Ali Nizamani Mile 0/0-0/3+330' =0.70 KMs. | 0.826 | 0 | 0 | 3.304 | 0.826 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
60 | Construction of road from Matli Tando Ghulam ali road @ 16/6 to Village Bharu Bheel Mile 0/0-1/2+220'= 2.067KMs. | 4.9893 | 0 | 0 | 19.957 | 4.9893 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
61 | Construction of road from Ansari Sugar Mill Mirwah road to Village Allah Dino Rathore Mile 0/0-0/3+550'= 0.77 KMs. | 1.5675 | 0 | 0 | 6.27 | 1.5675 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
62 | Construction of road from Dumbalo Kapri Mori Larho Mori road to Village Kot Jan Muhammad Arain Mile o/0-0/3 =0.60 KMs. | 1.2255 | 0 | 0 | 4.902 | 1.2255 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
63 | Construction of road from Ansari Sugar Mill Mirwah road to Village Lukman Panhwar Mile 0/0-1/0=1.72 KMs. | 3.57 | 0 | 0 | 14.28 | 3.57 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
64 | Construction of road from Ansari Sugar Mill Mirwah road to Village Aqil Dal & Usman Dal Mile 0/0-1/2=2.0 KMs. | 4.143 | 0 | 0 | 16.572 | 4.143 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
65 | Vonstruction of roadfrom Digri Amanabad road to Village Muhammad Din Bhurghri Mile 0/0-0/5. | 2.255 | 0 | 0 | 9.02 | 2.255 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
66 | Construction of road from Dumbalo Dadhar road to Village Qamardin Ahmdani & Naseer Arain Mile 0/0-0/7. | 2.5 | 0 | 0 | 10 | 2.5 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
67 | Construction of road from Dumbalo Dadhar reoad to Village Rono Kolhi Mile 0/0-0/4. | 1.7942 | 0 | 0 | 7.177 | 1.7942 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
68 | Improvement of road from Gulab Leghari Tando Ghulam Ali road to Village Mir Khan Rind Mile 0/0-0/2. | 0.537 | 0 | 0 | 2.148 | 0.537 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
69 | Construction of road from Ali Muhammad Arain road to Village Jalal Khan Khoso Mile 0/0-1/1 =1.80 KMS. | 3.805 | 0 | 0 | 15.22 | 3.805 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
70 | Construction of road from Mataro Kario road at point Jarki Shakh to Village Dodo Chang Mile 0/0-0/2. | 0.8 | 0 | 0 | 3.2 | 0.8 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
71 | Construction of road from Mataro Kario road at point Jarki Shakh to Village Fahid Farm Mile 0/0-0/1. | 0.4 | 0 | 0 | 1.6 | 0.4 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
72 | Improvement of road from Tando Bago Dehi road to Village Sono Khan Jamali Mile 0/0-2/4=4.00KMs. | 4.999 | 0 | 0 | 19.996 | 4.999 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
73 | Improvement of road from Tando Bago Dehi road to Village Sono Khan Jamali Mile 2/4-3/0+330'= 0.90 KMs. | 1.2337 | 0 | 0 | 4.935 | 1.2337 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
74 | Construction of road from Sangi Pharho Khairpur Gambo road Hesbani stop to Village LBOD via Oilpur Shakh Mile 0/0-1/2+330'= 2.10 KMs. | 4.9793 | 0 | 0 | 19.917 | 4.9793 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
75 | Construction of road from Sangi Pharho Khairpur Gambo road Hesbani stop to Village LBOD via Oilpur Shakh Mile 1/2+330'- 1/7 = 0.90 KMs. | 2.0938 | 0 | 0 | 8.375 | 2.0938 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
76 | Construction of road from Tando Bago Jhudho road to Village Pelwan Leghari to Village Sultan Ahmed Senharo Mile 0/0-1/2 = 2.00 KMs. | 4.505 | 0 | 0 | 18.02 | 4.505 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
77 | Construction of road from Vohanai Nindo road at Umar Khokhar to Village Bachal Khakhar Mile 0/0-0/6. | 2.75 | 0 | 0 | 11 | 2.75 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
78 | Construction of road from Fareed Farm Allahabad road to Village Khan Muhammad Chandio Mile 0/0-1/1 = 1.80 KMs. | 3.831 | 0 | 0 | 15.324 | 3.831 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
79 | Construction of road from Badin Khoski New By Pass road to Village Muhammad Moosa Soomro Mile 0/0-0/7 = 1.40 KMs. | 3.0427 | 0 | 0 | 12.171 | 3.0427 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
80 | Construction of road from Soomar Abro road to Village Sikno Soomro (Dhabro) Mile 0/0-0/4 = 0.80 KMs. | 4.987 | 0 | 0 | 19.948 | 4.987 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
81 | Construction of road from Morjhar Head Regulator road to Village Harchandabad Mile 0/0-0/4 = 0.80 KMs. | 1.7252 | 0 | 0 | 6.901 | 1.7252 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
82 | Construction of road from Kario Mataro road @ point 4/0 Inspection Path Imam Wah to Village Muhammad Khan Chandio Mile 0/0-1/1 = 1.80 KMs. | 3.767 | 0 | 0 | 15.068 | 3.767 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
82 | Construction of road from Muhammad Qasim Samoon to Village Salar Chandio Mile 0/0-1/1 = 1.80 KMs. | 3.7138 | 0 | 0 | 14.855 | 3.7138 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
84 | Construction of road from Saifal Mori Hanif Shah road to Village Amin Muhammad Samoon Mile 0/0-0/5 = 1.00 KMs. | 2.1528 | 0 | 0 | 8.611 | 2.1528 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
85 | Construction of road from Rasheed Mallah road to Village Ghulam Muhammad Junejo Mile 0/0-0/6 = 1.20 KMs. | 2.5343 | 0 | 0 | 10.137 | 2.5343 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
86 | Construction of road from Saifal Mori to Village Thako Kolhi Mile 0/0-0/5 = 1.00 KMs. | 2.127 | 0 | 0 | 8.508 | 2.127 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
87 | Construction of road from Seerani Bhughra Memon Inspection Path eoad to Village Muhammad Rahim Soomro Via Haroon Mandhro Mile 0/0-1/1+220' =1.87 KMs. | 4.125 | 0 | 0 | 16.5 | 4.125 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
88 | Construction of road from Inspection Path Mirwah 83- Regulator Murad Shah War to connect Seerani Bhughra Memon road Mile 0/0-1/3+330' =2.30 KMs. | 4.95 | 0 | 0 | 19.8 | 4.95 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
89 | Recondition of 50 RFT Bridge over Amir Shah Sim Nali. | 1.875 | 0 | 0 | 7.5 | 1.875 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
90 | Improvement of road from Badin Kadhan road to Village Yousif Jamali(Balance Length=0.40 KMs). | 0.5 | 0 | 0 | 2 | 0.5 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
91 | Improvement of road from Kadhan Seerani road to Village Mitho Khaskheli (Balance Length 1.40 KMs). | 3 | 0 | 0 | 12 | 3 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
92 | Improvement of road from Badin Khoski By Pass road to Village Wali Muhammad Jamali (4.00 KMS). | 5 | 0 | 0 | 20 | 5 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
93 | Improvement of road from Sunni Guni to Mithi Mori (Balance Length 2.00 KMs) | 3 | 0 | 0 | 12 | 3 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
94 | Improvement of Saeedpur Ghulam Shah road Mile 0/4-7/2 =1.20 KMs. | 1.5 | 0 | 0 | 6 | 1.5 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
95 | Improvement of Dabharo Khadaro road Mile 3/0-4/1. | 2.25 | 0 | 0 | 9 | 2.25 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
96 | Improvement of road from Rajo Khanani to Mehtab Ali Shah Mile 2/1-3/4 | 2.75 | 0 | 0 | 11 | 2.75 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
97 | Construction of road from Khadim Ali Shah road to Village Muhammad Maeen Bajeer Farm/ Urs Bajeer & Natho Gaho Mile 0/0-0/7. | 2.8 | 0 | 0 | 11.2 | 2.8 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
98 | Construction of road from Wali Muhammad Jamali Rabhan road to Village Genhwer Mugheri Via Peenghar Khaskheli Mile 0/0-0/4= 2.40 KMs. | 4.7678 | 0 | 0 | 19.071 | 4.7678 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
99 | Improvement of Road from Tando Bago Jhudho road to Kot Amir Ali Shah (1.20 KMs) | 1.575 | 0 | 0 | 6.3 | 1.575 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
100 | Construction of road from Tando Ghulam Ali Bohro Sahib Khan road to Village Mehmood Kaimkhani Mile 0/0-0/5. | 2 | 0 | 0 | 8 | 2 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
101 | Construction of road from Khoski Artillary Chak road to Village Lal Muhammad Hothi Mile 0/0-0/5. | 2 | 0 | 0 | 8 | 2 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
102 | Construction of road from Chak No.32 Oil Field road to Village Haji Siddique Gujjer Mile 0/0-0/7. | 1.175 | 0 | 0 | 4.7 | 1.175 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
103 | Improvement of road from Dumbalo Kapri Mori road to Kot Abdullah Mile 0/0-0/6. | 1.25 | 0 | 0 | 5 | 1.25 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
104 | Improvement of road from Matli Tando Ghulam Ali road to Village Dodo Khan Nizamani Mile 0/0-1/0. | 3 | 0 | 0 | 12 | 3 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
105 | Repair/Renovation of Bridges & Culverts in District Badin(Emergency Work). | 5 | 0 | 0 | 20 | 5 | Civil Work | Single stage -1 Envelop Procedure | September -2016 | September -2016 | Marach-2018
106 | Construction of Golrachi By pass road from Badin Sujawal road at Mile 17/7 Sorhadi Shakh to connect Badin Sujawal road @ Mile to 21/0 Mile 0/0-4/0 (Remaining Work). | 50 | 25.5 | 0 | 71.992 | 24.5 | Civil Work | Single stage -1 Envelop Procedure | December-2016 | January-2018 | June-2018
EXECUTIVE ENGINEER
HIGHWAYS DIVISION
BADIN