SPPRA BIDDING DOCUMENT

SINDH PUBLIC PROCUREMENT REGULATORY AUTHORITY (SPPRA)

STANDARD FORM OF BIDDING DOCUMENT

(Civil Works – Large Works)

This SBD shall be used for large works costing more

than Rs.50 Million

2011

INSTRUCTIONS TO

PROCUREMENT AGENCIES

INSTRUCTIONS TO PROCURING AGENCY

(Not to be included in bidding documents)

As  stated  in Clause  IB.7  of  the  Instructions  to  Bidders,  the complete bidding  documents

shall comprise of eleven items listed therein and any Addenda issued in accordance with

Clause IB.9. The Standard Bidding Documents, in addition to Invitation for Bids, includes

the following:

1  Instructions to Bidders.

2.    Bidding Data.

3.      General Conditions of Contract, Part I (GCC).

4.  Special Conditions of Contract, Part II (SCC).

5.  Specifications

6.  Form of Bid and Appendices to Bid.

7.  Bill of Quantities.

8.  Form of Bid Security.

9.  Form of Agreement.

10.  Form  of  Performance  Security, Mobilization  Advance  Guarantee,  Indenture

Security Bond and Integrity pact.

11.  Drawings.

The  Instructions  to  Bidders  can  be  used  as  given. Procuring  agency may  have  to  make

changes  in  the  text  under  some  special  circumstances subject  to  provisions  of  Rules and

Regulations.

General  Conditions of  Contract  shall  not  be  changed.  Procuring  agency  may  carry  out

changes in General Conditions of Contract through Special Conditions of Contract, as per

provisions  of  Sindh  Public  Procurement  Rules  2010,  updated  from  time  to  time,  in

Province of Sindh. However, such changes in General Conditions shall be made with due

care.  Completion  of  the  Forms  and  preparation  of  Bill  of  Quantities  should  be  made  as

suggested hereinafter.

Procuring  Agency is  required  to  prepare  the  following documents for  completion  of  the

bidding documents:

(i)  	Special Conditions of Contract Part-II (SCC)

(ii)  	Specifications.

(iii)  	Bill of Quantities.

(iv)  	Drawings

A.  Notice Inviting Tender

1.  	The “Notice  Inviting  Tender” is advertised  in  the  newspapers  shall  appear  in  at

least three widely circulated leading dailies of English, Urdu and Sindhi languages

as well as on SPPRA Website as explained in the SPP Rules, 2010 (17) (2). All the

blank spaces are to be filled in by the procuring agency.

2.  	 The eligible bidders are defined in Clause IB.3 of Instructions to Bidders.

3.  	The notice shall be published so as to give the interested bidders, sufficient time

for  preparation  and  submission  of  bids  which shall be minimum of 15 days for  National

Competitive  Bidding  (NCB)  and  minimum of  45  days  for  International

Competitive Bidding (ICB) SPP Rule 18.

4. 	 Non-refundable tender fee for the sale of bidding documents shall be nominal so as

to  cover cost  of photocopying  or printing  only SPP  Rule  20. However,  cost  of

mailing  the  documents  on  request  of  the  interested  bidder  may  be  charged

separately. Last  date  for  the  sale  of  the  bidding  documents is mentioned  in  the

Notice Inviting Tender.

5.  	The procuring agency shall require the bidders to furnish a bid security not below

one  percent  and  not  exceeding  five  percent  of  the  bid  price,  which  shall  remain

valid for a period of 28 days beyond the validity period for bids, in order to provide

the  procuring  agency  reasonable  time  to  act,  if  the  security  is  to  be  called,  SPP

Rule 37(1).

6.  	The  venue and  time of  receipt  of  bids  and  the venue  and  time  of opening  of  bids

are  to  be mentioned  in  Notice Inviting  Tender.  Last  date  for  the  receipt  and

opening of bids shall be the same SPP Rule 41(1).

7.   	In IB 11.1  (b) of bidding  data, procuring agency  should  list  relevant information,

which  is considered  vital  at  the  time  of post-qualification,  when  prequalification

process is not followed. Subsequently, this information is required to be submitted

along  with  bid and  shall  be  verified  by  the procuring  agency  during  evaluation

process.

8. 	 All blank spaces in the bidding data are to be filled in by the procuring agency to

complete this document.

9. 	 Referring to IB 19.2 (b) of bidding data, the Bid Reference Number should be the

same as given in Notice Inviting Tenders and form of bid.

B.  Instructions to Bidders and Bidding Data

1	.  If the works are not financed from a loan/credit, IB 2.1 of bidding data should be

modified accordingly.

2. 	 Procuring agency shall  prepare  the  documents  listed  at Serial  Nos. b, d, e, f, g, i,

and k of IB  7.1  of  Instructions  to  Bidders in  order  to  complete  the  bidding

documents comprising the Bid.

3.	  For completion of documents at Serial No. g and i, detailed instructions are given

at Para C below.

4.  	Referring  to IB 7.1 of bidding  data,  the  period  should  be  inserted  as given  in  the

bidding documents and Notice Inviting Tender (NIT).

5.  	In IB 11.1  (b) of bidding  data,  the  bidder  shall  provide  additional  or  updated

information to the procuring agency regarding the post-qualification criteria as and

when required.

6. 	 Referring  to  IB 14.1 of bidding  data,  a bid  validity  period  shall  be  specified

therein, keeping in view the nature of the procurement, it shall not exceed 90 days

in  case  of  National  Competitive  Bidding (NCB)  and  120  days  in  case  of

International Competitive Bidding (ICB) SPP Rule 38(1).

.

7.  	Referring to IB 15.1 of bidding data, the amount is to be filled in by the procuring

agency; bid  security shall not be below than one  percent  and  not  exceeding  five

percent of the bid price SPP Rule 37(1).

C.  Form of Bid and Appendices to Bid

1.  Form of Bid:

Only Bid Reference Number shall be filled in by the procuring agency (refer Para

A.8 above). All other blanks spaces are to be filled in by the bidder.

2.  Appendix-A to Bid:

(a)  	The  minimum  amount  of  third  party  insurance  should  be  assessed  by  the

procuring agency and entered at Sr. No. 3.

(b)  	The time for completion of the whole of the works shall be entered by the

procuring agency at Sr. No. 5.

(c)  	The amount of Liquidated Damages per day of delay shall be entered by the

procuring agency at Sr. No. 7.

Amount of the Liquidated Damages for each day of delay in completion of

the whole of the works, or if applicable, for any Section thereof, shall be (a

sum equal to 10% of the estimated cost of the works divided by one-fourth

of the number of days specified as completion time).

Formula: LD (per day) = 10% of Estimated or Bid Cost ÷ [0.25 ×Time for

completion (days)].

(d)	  The  Defects  Liability  Period  is  to  be  entered  by  the procuring  agency

keeping in view the nature and size of the work at Sr. No. 7.

This is generally taken as 365 days/one year.

(e)  	The minimum amount of Interim Payment Certificate should be determined

by the procuring agency depending upon the size and duration of the works

and to be entered at Sr. No 10.

3.  Appendix-B to Bid:

Where  foreign  currency  payments  are  foreseen; the  entire  Appendix-B  to bid

should be left blank to be filled in by the bidder.

Where  no  foreign  currency  payments  are  foreseen,  the procuring agency should

stamp this Appendix-B as “Not Used” and, referring to 1.1.4.6 and 13.4 of GCC,

and state  in SCC that  all  payments  shall  be  in  local  currency  only.  Clause  IB-13

should also be modified accordingly through the changes in bidding data.

4.  Appendix-C to Bid:

(a)   	 National Competitive Bidding (NCB):

Escalations on  local  funded  projects/schemes  shall be  paid  to  the

contractor  only  on  following  items  with  their  base  prices  and  sources

shown in the bidding document at time of issuing NIT:-

(i) Steel (ii) Cement (iii) Wood for Doors, windows & Partition walls

(iv) Bitumen (v) Bricks.

(b)    	International Competitive Bidding (ICB):

(i)  	Contracts  having  duration  of  twelve  months  or  more  should  be

liable  to  price  adjustment as  per  conditions  of  contract. Provided

that the procuring agency may  add or delete any item from the list

given at the relevant appendix, as deemed appropriate.

(ii)  	Blank  spaces  for  weight-age of  each  cost  item  in  column  3  of  the

table  should  be  filled in by  the procuring agency, while  preparing

the bidding documents.

(iii)  	In  case  the  price  adjustable  items  are  not  covered  in  the  Federal

Bureau of  Statistics,  the  base  price  and  the  source  thereof  shall  be

mentioned  by  the  procuring  agency  and  the  corresponding  column

of the table should be amended accordingly.

(iv) 	 This  mechanism shall  be  applicable  only  for  price  adjustment  in

local currency.

(v) 	 Price  adjustment as  mentioned  above shall  be  applicable  to  all

contracts including item rate, lump sum and %age quoted above or

below  on  Composite  Schedule of Rates  (CSR),  provided these

provisions are part of the contract.

5.  Appendix-D to Bid:

Bills  for  various  items  are  given  by  way  of  example  only.  The procuring agency

should  prepare  the  Bill  of  Quantities  (BoQs)  appropriate  to  the  works.  In

preparation of the Bill of Quantities, columns under (1), (2), (3) and (4) in item rate

contract should  be  completed  by  the procuring agency, whereas, spaces  under

columns  (5)  and  (6)  as  well  as  the totals  at  the  bottom  shall  be  left  blank to  be

filled in by the bidder. But in case of Composite Schedule of Rates, all columns are

to be filled by procuring agency, only percentage above or below are to be quoted

by bidder.

Referring to Schedule of Day Work Rates for labour, materials and constructional

plant, types of labour, materials and constructional plant under column (2) as well

as  quantities  under column  (4)  are  given  by  way  of  example  only.  The procuring

agency should determine the types of labour, materials and constructional plant as

well  as  the  quantities  thereof,  estimated  to  be  utilized,  on day  work  basis

depending upon the nature of the works.

Percentage for overhead and profit on labour and materials, and the total amounts

should be left blank to be filled in by the bidder.

Day Work summary is to be left blank to be filled in by the bidder.

6.  Appendix-E to Bid:

If  the procuring agency requires  partial  completion  of  the works  by sections  (for

example  Parts-A,  B,  C  etc.),  these  should  be  identified  and  time  for  completion

thereof, are to be specified, and the blank spaces may be filled in by the procuring

agency.

7.  Appendix-F to Bid:

The procuring agency may  expand  the  requirements  as  stated  in  this  Appendix,

keeping in view the requirements of the works.

8.  Appendix-G to Bid:

It  pertains  to  the  list  of  major equipments  to  be  provided  by  the  bidder  if

applicable. All blank spaces are to be filled in by the bidder.

9.  Appendix-H to Bid:

The  bidder  has  to  provide  details  about  camps  and  housing  facilities. Procuring

agency may  modify  the  requirements  as  stated in  this Appendix, keeping  in  view

requirements of the works.

10.  Appendix-I to Bid:

The  bidder  has  to  provide  list  of  sub-contractors  along  with  the  details  of  works

assigned. The blank spaces are to be filled in by the bidder.

11.  Appendix-J to Bid:

The bidder has to provide the estimated value of work to be executed in the period

mentioned therein. The blank spaces are to be filled in by the bidder.

12.  Appendix-K to Bid:

The bidder has to provide the organizational chart for supervisory staff and labour.

The blank spaces are to be filled in by the bidder.

13.  Appendix-L to Bid:

Procuring agency shall provide the  Integrity  Pact form duly signed, stamped and

submit the same along with the bid.

D.   Forms

1.  Bid Security:

Procuring agency,  before  issuing  the bidding documents, should fill  in following

blank spaces:

(a)  	Amount/ Percentage of bid security, in words as well as figures, which

should be the same as provided at Sub-Para A.5 above.

(b) 	Bid Reference Number should be the same as per Sub-Para B.7 above.

(c)	Standard Forms of Securities provided in this document are to be issued by a

scheduled bank.

E.  Special Conditions of Contract

1.  	Name  and  full address  of  the procuring agency as  well  as  that  of  the  Engineer in

charge or in case a consultant is hired by the procuring agency, then Consultant‟s

Engineer,  as  the  case  may  be, should  be  filled  in  by  the procuring agency in  the

blank spaces provided under Sub-Para (a) (i) and (iv) of Sub-Clause 1.1 of SCC.

2.  	Referring to first paragraph of Sub-Clause 3.1 of GCC, information as applicable is

provided there under.

3. 	 Referring to Sub-Clause 1.5 of GCC, the procuring agency may add, in the order of

priority, such other documents which form part of the contract.

4	Referring  to 8.3 of GCC, the procuring agency should  specify  the  form  in  which

the programme is to be submitted by the bidder, e.g., Critical Path Method (CPM),

Bar Chart or Programme Evaluation and Review Technique (PERT).

5.  	(a) 	 Referring to Sub-Clause 5.3 of GCC, if the procuring agency desires the

Bidder to use  the  services  of nominated  subcontractor(s),  the procuring

agency should make necessary provisions of provisional sums and provide

blank  spaces to  be filled in  the  percentage  rate(s)  and  estimated  amounts,

resulting there from in Appendix-D to Bid. The blank spaces for the rate(s)

and the estimated amount(s) shall be filled in by the bidder.

(b) 	 Suitable text referring to such provisions should be added in SCC.

If provisional sums and Day Work are not to be provided, then same should be

mentioned in special conditions of contract.

6.  Mobilization Advance/Advance Payment:

Procuring agency shall extend mobilization advance to the contractor on submission of Bid

Bond/ Bank Guarantee.

7. 	 Referring  to 20.6  of  GCC,  the  procuring  agency  should  state  the  venue  of

Arbitration, which should be located within the province of Sindh and according to

Arbitration Act, 1940 (up dated from time to time).

8.  	Addresses of the procuring agency and the Engineer or in case a consultant is hired

by the procuring agency, then Consultant’s Engineer, as the case may be, are to be

entered by the procuring agency to completely fill in the blanks in Sub-Clause 1.3.

F.   Specifications.

To be prepared and incorporated by the procuring agency.

(Precise and clear specifications are prerequisite for bidders to respond realistically

and competitively to the requirements of the procuring agency without qualifying

or  conditioning  their  bids.  In  the  context  of  both  national  and  international

competitive  bidding,  the specifications  must  be  drafted  to  permit  the  widest

possible  competition  and,  at  the  same  time,  present  a  clear  statement  of  the

required  standards  of  materials, plant,  other  supplies,  and  workmanship  to  be

provided. Only if this is  done, the objectives of  economy, efficiency  and  equality

in  procurement  will be  realized,  responsiveness  of  bids  be  ensured,  and  the

subsequent task of bid evaluation be facilitated.  The specifications should require

that all materials, plant, and other supplies to be incorporated in the works are new,

unused,  of  the  most  recent  or  current  models,  and  incorporate  all  recent

improvements in design and materials unless provided otherwise in the contract. A

clause setting out the scope of the works is often included at the beginning of the

specifications,  and  it  is  customary  to  give  a  list  of  the drawings.  Where  the

contractor  is  responsible  for  the  design  of  any  part  of  the  permanent works,  the

extent of his obligations must be stated.

Specification  shall  be  generic and  shall  not  include  references  to  brand  names,

model  numbers,  catalogue  numbers  or  similar  classifications.  However,  if  the

procuring  agency is  convinced  that  the  use  of  or  a  reference  to  a  brand  name  or

catalogue  number  is  essential  to  complete  an  otherwise  incomplete  specification,

such use or reference shall be qualified with the words “or equivalent”.

Care must be taken in drafting specifications to ensure that they are not restrictive.

In  the  specification  of  standards  for  materials,  plant,  other  supplies,  and

workmanship,  recognized  international  standards  should  be  used  as  much  as

possible.  The  specifications  shall  consider  all  site  conditions, but  not  limited  to

seismic and weather conditions, and environmental impact. Where other particular

standards  are  used,  whether  national  or other  standards,  the specifications  should

state  that  materials,  plant,  other  supplies,  and  workmanship  meeting  other

recognised  standards,  and  which  ensure  equal  performance,  to  the  mentioned

standards, will also be acceptable.)

G.  Drawings

To be prepared and incorporated by the procuring agency.

TABLE OF CONTENTS

CONTENTS    										Page No.

INVITATION FOR BIDS  										4

Form 													5

INSTRUCTIONS TO BIDDERS 									 6

A.  General

IB.1  Scope of Bid 											 7

IB.2  Source of Funds  										 7

IB.3  Eligible Bidders   										 7

IB.4  One Bid Per Bidder										 8

IB.5  Cost of Bidding  										 8

IB.6  Site Visit  											 8

B.  Bidding Documents

IB.7  Contents of Bidding Documents  								 9

IB.8  Clarification of Bidding Documents  								 9

IB.9  Amendment of Bidding Documents  								 9

C.  Preparation of Bids

IB.10. Language of Bid  										10

IB.11  Documents Accompanying the Bid  								10

IB.12  Bid Prices  											11

IB.13  Currencies of Bid and Payment  								12

IB.14  Bid Validity  											12

IB.15  Bid Security  											13

IB.16  Alternate Proposals by Bidder  								13

IB.17  Pre-Bid Meeting  										14

IB.18  Format and Signing of Bid  									14

D.  Submission of Bids

IB.19  Sealing and Marking of Bids  									15

IB.20  Deadline for Submission of Bids  								15

IB.21  Late Bids  											16

IB.22  Modification, Substitution and Withdrawal of Bids  					16

E.  Bid Opening and Evaluation

IB.23  Bid Opening  											16

IB.24  Process to be Confidential  									17

IB.25  Clarification of Bids  										17

IB.26  Examination of Bids and Determination of Responsiveness  					17

IB.27  Correction of Errors  										18

IB.28  Evaluation and Comparison of Bids  								18

F.  Award of Contract

IB.29  Award  												19

IB.30  Procuring Agency’s Right to Accept any Bid and to Reject any or all Bids

19

IB.31  Notification of Award  									20

IB.32  Performance Security  										20

IB.33  Signing of Contract Agreement  								20

IB.34  General Performance of the Bidders  								21

IB.35  Integrity Pact  											21

IB.36  Instructions Not Part of Contract  								21

B.37   Arbitration 											21

BIDDING DATA  												22

FORM OF BID AND APPENDICES TO BID 							 27

FORM OF BID  											 28

Appendix-A to Bid  		: Special Stipulations  							 30

Appendix-B to Bid  		: Foreign Currency Requirements  					 31

Appendix-C to Bid  		: Price Adjustment (Under Clause 70)  				 32

Appendix-D to Bid  		: Bill of Quantities  33

Appendix-E to Bid  		: Proposed Construction Schedule  					 51

Appendix-F to Bid 		 : Method of Performing the Work  					 52

Appendix-G to Bid  		: List of Major Equipment – Related

Items 									 53

Appendix-H to Bid 		 : Construction Camp and Housing

Facilities 									 55

Appendix-I to Bid  		: List of Subcontractors  						56

Appendix-J to Bid  		: Estimated Progress Payments  					57

Appendix-K to Bid  		: Organization Chart of the Supervisory

Staff and Labour 							58

Appendix-L to Bid  		: Integrity Pact 							59

FORMS

BID SECURITY  										61

PERFORMANCE SECURITY  								63

CONTRACT AGREEMENT  								65

MOBILIZATION ADVANCE GUARANTEE 						67

INDENTURE BOND FOR SECURED ADVANCE 					69

PART-I: GENERAL CONDITIONS OF CONTRACT            					74

PART-II: SPECIAL CONDITIONS OF CONTRACT         					 147

SPECIFICATIONS                   									168

DRAWINGS                   										169

INVITATION

FOR BIDS

NOTICE INVITING TNDERS

Date: ________________

Provincial Government Funds Grant No: ADP No.1458

Bid Reference No: ______________

1.  The Executive Engineer Highways Division Badin

(Name of Procuring Agency)

“	(The Procuring Agency”) has received/ applied for funds from the

Sindh Government Under ADP No.1458      towards the cost of _______________________

(Name of Funding Agency/GOP/Provincial Government/Any Other)   (Name of Project/Scheme)

and it is intended that part of the proceeds of the loan/grant/funds will be applied to

eligible payments under the contract for the Construction of Golarchi By Pass Road Badin Sujawal Road @ Mile 17/7 Srhai Shakh to Connect Badin Sujawal Road @ Mile 21/0 Mile 0/0-4/0(Remaining Work)

(Brief description of the Works)

Bidding is open to all interested bidders.

2.  Procuring agency invites sealed bids from interested firms or persons licensed by the

Pakistan  Engineering  Council (PEC) in  the  category CE01 or above for  the works

and in discipline_______ and registered with relevant tax authorities. A foreign bidder

is entitled to bid only in a joint venture with a Pakistani Firm in accordance with the

relevant provisions of PEC bye-laws.

3.  Bidders  may  obtain  information by acquiring the bidding  documents (BD) from  the

Office  of  the  procuring  agency,  up  to      (Insert  the  date  and  time)    at

Address: Hyderabad Road Badin Near Caltex Petrol Pump (Phone 0297-920094)

(Mailing Address)

Email Address:- Badineehighways@gmail.com .

4.  A complete set of  BD may  be purchased by an interested bidder on submission of a

written application to the above office and upon payment of a non-refundable fee of

Rs. 3000/-

5.  All  bids  must  be accompanied  by  a bid  security in  the  amount  of  Rs. 3598600/-

(Rupees Thirty Five Lac Ninety Eight Thousand & Six Hundred Only) or  an  equivalent

amount  in  a  freely convertible  currency,  and  must  be  delivered

to Executive Engineer Highways Division Badin  Indicate Address and Exact Location)

at or before 09.12.2016 to 26.12.2016 Bids will be opened at 2:00 PM on the same day, in the presence of bidders representatives who choose to attend at the same address.

- Procuring  agency  reserves  right to  annul  the  bidding  process  and  reject  all

- bids or proposals, as per SPP Rules 2010.

[Note: the bids shall be opened not later than one hour after the deadline for submission of bids]

INSTRUCTIONS

TO

BIDDERS

I-1

INSTRUCTIONS TO BIDDERS

(Note: These Instructions to Bidders along with bidding data will not be part of the Contract

and will cease to have effect once the contract is signed.)

A.        GENERAL

IB.1     Scope of Bid

1.1       Procuring agency as defined in the bidding data hereinafter called “the procuring

agency”  wishes  to  receive  bids  for  the construction  and  completion  of  works  as

Described in these bidding documents, and summarized in the bidding data hereinafter

referred to as the “Works”.

1.2      The  successful  bidder  will  be  expected  to  complete  the works  within  the  time

specified in Appendix-A to Bid.

IB.2   Source of Funds

2.1     Procuring  agency  has  received/allocated/]  applied  for  loan/grant/  Federal/

Provincial/Local  Government funds from  the  source(s)  indicated  in  the bidding  data

in various currencies towards the cost of the project /scheme specified in the bidding

data, and  it  is  intended  that  part  of  the  proceeds  of  this  loan/grant/funds will  be

applied to eligible payments under the contract for which these bidding documents are

issued.

IB.3   Eligible Bidders

3.1      This  Invitation  for  Bids  is  open  to  all interested bidders who  are  eligible  under

provisions  of Sindh  Public  Procurement  Rules as  mentioned  below and  the  criteria

given in the Notice Inviting Tender (NIT)/ Bidding Document.

Firms and individuals, national or international, may be allowed to bid for any project

where international competitive bidding is feasible.  Any conditions for participation

shall be limited to those that are essential to ensure the bidder‟s capability to fulfill the

contract in question.

(a)  Bidders may be excluded if;

(i) 	 as  a  matter  of  law  or  official  regulations,  commercial  relations  are

Prohibited with the bidder’s country by the federal

Government in case of ICB, or

(ii) 	 a firm is blacklisted/ debarred by the procuring agency and the matter

has been reported to the Authority, subject to Rule 30 of Sindh Public

Procurement Rules 2010.

(b)   Government-owned enterprises or institutions may participate only if they can

establish that they are;

(i) 	 legally and financially autonomous, and

(ii)   	operate under commercial law.

Provided that where government-owned universities or research centers in the

country  are  of  a  unique  and  exceptional  nature,  and  their  participation is

critical to project implementation, they may be allowed to participate; and

Bidders  shall  include  all  those  contractors who are  registered  or  incorporated

in  Pakistan,  irrespective  of  the  nationality  of their owners  and  professional

staff, or

(c)       Bidders are:-

(i)        pre-qualified with procuring agency for particular project/scheme;

(ii)    	 registered  with  Pakistan  Engineering  Council  in  particular  category

and discipline,

(iii)  	registered  with  relevant  tax  authorities  (income/sales  tax,  wherever

applicable)

IB.4  One Bid per Bidder

4.1  	Each  bidder  shall  submit  only  one  bid  either  by  himself,  or  as  a  partner  in  a  joint

venture.  A  bidder  who  submits  or  participates  in  more  than  one  bid  (other  than

alternatives pursuant to Clause IB.16) will be disqualified.

IB.5  Cost of Bidding

5.1  	The  bidders  shall  bear  all  costs  associated  with  the  preparation  and  submission  of

their respective bids, and the procuring agency will in no case be responsible or liable

for those costs, regardless of the conduct or outcome of the bidding process.

IB.6  Site Visit

6.1 	 The  bidders  are  advised  to  visit  and  examine  the site  of works and  its  surroundings

and  obtain all  information  that  may  be  necessary  for  preparing  the  bid  and  entering

into  a  contract  for  construction  of  the works.  All  cost  in  this  respect  shall  be  at  the

bidder‟s own expense.

6.2  	The  bidders  and  any  of  their  personnel  or  agents  will  be  granted  permission  by  the

procuring  agency  to  enter  upon  his  premises  and  lands  for  the  purpose  of  such

inspection,  but  only  upon  the  express  condition  that  the  bidders,  their  personnel  and

agents,  will  release  and  indemnify  the procuring  agency,  his  personnel  and  agents

from  and against  all  liability  in  respect  thereof  and  will  be  responsible  for  death  or

personal injury, loss of or damage to property and any other loss, damage, costs and

expenses incurred as a result of such inspection.

B.  	BIDDING DOCUMENTS

IB.7   Contents of Bidding Documents (SSP RULE 21)

7.1  	The bidding documents, in addition to invitation for bids, are those stated below and

should  be  read  in  conjunction  with  any  addenda  issued  in  accordance  with

Clause IB.9.

a.   	Instructions to Bidders.

b.  	 Bidding Data.

c.   	General Conditions of Contract, Part-I (GCC).

d.   	Special Conditions of Contract, Part-II (SCC)

e.   	Specifications.

f.   	Form of Bid and Appendices to Bid.

g.   	Bill of Quantities (Appendix-D to Bid).

h.   	Form of Bid Security.

i.  	 Form of Contract Agreement.

j.   	Forms of Performance Security, Mobilization Advance Guarantee, Integrity

Pact and Indenture bond for secured advance.

k. 	Drawings.

7.2  	The  bidders  are  expected  to  examine  carefully  the  contents  of  all  the  above

documents. Failure to comply with the requirements of bid submission will be at the

Bidder’s own  risk.  Pursuant to Clause IB.26, bids which are not substantially

responsive to the requirements of the BD will be rejected.

IB.8   Clarification of Bidding Documents (SSP RULE 23(1)):

Any interested  bidder  requiring  any  clarification(s)  in  respect  of  the  bidding

documents  may  notify  the procuring  agency in  writing  at  the procuring  agency‟s

address indicated in the Invitation for Bids/NIT. Procuring agency will respond to any

request for clarification provided they are received at least five calendar days prior to

the date of opening of bid.

Provided  that  any  clarification  in  response  to  query  by  any  bidder; shall  be

Communicated to all parties who have obtained bidding documents.

IB.9   Addendum/Modification of Bidding Documents:

9.1     At  any  time  prior  to  the  deadline  for  submission  of  bids,  the procuring  agency may,

for any reason, whether at his own initiative or in response to a clarification requested

by a interested bidder, modify the bidding documents by issuing addendum.

9.2  	Any  addendum  thus  issued  shall  be  part  of  the bidding  documents  pursuant  to sub-

clause IB 7.1 hereof  and  shall  be  communicated  in  writing  to  all bidders. Interested

bidders  shall  acknowledge  receipt  of  each  addendum  in  writing  to  the procuring

agency.

9.3  	To  afford  bidders  reasonable  time  in  which  to  take  an  addendum  into  account  in

preparing their bids, the procuring agency may extend the deadline for submission of

bids in accordance with IB.20

C.  PREPARATION OF BIDS

IB.10   Language of Bid

10.1  	The  bid  and  all  correspondence  and  documents  related  to  the  bid  exchanged  by  a

bidder and the procuring agency shall be in the language stipulated in the bidding data

and Special Conditions  of the Contract.  Supporting  documents  and  printed  literature

furnished  by  the  bidders  may  be  in  any  other  language  provided  the  same  are

accompanied  by  an  accurate  translation  of  the  relevant  parts  in  the  bid  language,  in

which case, for purposes of evaluation of the bid, the translation in bid language shall

prevail.

IB.11   Documents Accompanying the Bid

11.1 	 Each bidder shall:

(a)  	submit  a  written  authorization  on  the  letterhead  of  the  bidding  firm,

authorizing the signatory of the bid to act for and on behalf of the bidder;

(b)  	Update the information indicated and listed in the bidding data and previously

submitted  with  the  application  for  prequalification,  and  continue  to  meet  the

minimum  criteria  set  out  in  the  prequalification  documents,  which  as  a

Minimum, would include the following :

(i)  	Evidence  of  access  to  financial  resources  along with  average  annual

construction turnover;

(ii)	Financial predictions for the current year and the following two years,

including the effect of known commitments;

(iii)  	Work commitments since prequalification;

(iv)  	 Current litigation information; and

(v)  	Availability of critical equipment.

And

(c)  	furnish a technical proposal taking into account the various Appendices to Bid

specially the following:

Appendix-E to Bid  Proposed Construction Schedule

Appendix-F to Bid  Method of Performing the Work

Appendix-G to Bid  List of Major Equipment

Appendix-K to Bid  Organization Chart for Supervisory Staff

and other pertinent information such as mobilization programme etc;

11.2  	Bids  submitted  by  a  joint  venture  of  two (2) or  more  firms  shall  comply  with  the

following requirements:

(a)  	one  of  the  joint  venture  partners  shall  be  nominated  as  being  in  charge;  and

this authorization shall be evidenced by submitting a power of attorney signed

by legally authorized signatories of all the joint venture partners;

(b) 	 the bid, and in case of a successful bid, the Form of Contract Agreement shall

be signed by the authorized partner so as to be legally binding on all partners;

(c) 	 the  partner-in-charge  shall  always  be  duly  authorized  to  deal  with  the

procuring  agency regarding  all  matters  related  with  and/or  incidental  to  the

execution  of works  as  per  the  terms  and  Conditions  of  Contract  and  in  this

regard  to  incur  any  and  all  liabilities,  receive  instructions,  give  binding

undertakings and receive payments on behalf of the joint venture;

(d)  	all partners of the joint venture shall at  all times and under all circumstances

be liable jointly and severally for the execution of the contract in accordance

with the contract terms  and a statement to this  effect shall be included in  the

authorization  mentioned  under  Sub-Para (a)  above  as  well  as  in  the  Form  of

Bid and in the Form of Contract Agreement (in case of a successful bid);

(e)  	a  copy  of  the  agreement  entered  into  by  the  joint  venture  partners  shall  be

submitted with the bid stating the conditions under which it will function, its

period  of  duration,  the  persons  authorized  to  represent  and  obligate  it  and

which persons will be directly responsible for due performance of the  contract

and  can  give  valid  receipts  on  behalf  of  the  joint  venture,  the  proportionate

participation  of  the  several  firms  forming  the  joint  venture,  and  any  other

information  necessary  to  permit  a  full  appraisal  of  its  functioning.  No

amendments  /  modifications  whatsoever  in  the joint  venture  agreement  shall

be  agreed  to  between  the  joint  venture  partners without  prior  written consent

of the procuring agency;

(f)        submission  of  an  alternative  Letter  of  Intent  to  execute  a  Joint  Venture

Agreement shall be mandatory.

11.3  		Bidders shall also submit proposals of work methods and schedule, in sufficient detail

to  demonstrate  the  adequacy  of  the  bidders‟  proposals  to  meet  the  technical

specifications and the completion time referred to sub- clause IB 1.2 hereof.

IB.12  Bid Prices

12.1  		Unless stated otherwise in the bidding documents, the contract shall be for the whole

of the works as described in IB 1.1 hereof, based on the unit rates or prices submitted

by  the  bidder  or  percentage  quoted  above  or  below on the  rates  of  Composite

Schedule of Rates (CSR), as the case may be.

12.2 		 The bidders shall fill in rates and prices for all items of the works described in the Bill

of Quantities.  Items against which no rate or price is entered by a bidder  will not be

paid for by the procuring agency when executed and shall be deemed to be covered by

rates  and  prices  for  other  items  in  the  Bill  of  Quantities.  In  case  of  Composite

Schedule  of Rates,  if  the  bidder  fails  to  mention  the  percentage  above  or  below,  it

shall be deemed to be at par with the rates of Composite Schedule of Rates.

12.3  		The bid price submitted by the contractor shall include all rates and prices including

the  taxes. All  duties,  taxes  and  other  levies  payable  by  the contractor  under  the

contract,  or  for  any  other  cause during  the  currency  of  the  execution  of  the  work or

otherwise specified in the contract as on the date seven days prior to the deadline for

submission of bids.

Additional / reduced duties, taxes and levies due to subsequent additions or changes in

legislation  shall  be  reimbursed  /  deducted  as  per  Sub-Clause 13.7 of  the  General

Conditions of Contract Part-I.

12.4 		 The  rates  and  prices  quoted  by  the  bidders  are  subject  to  adjustment  during  the

performance of the contract in accordance with the provisions of Clause 13.7of GCC.

The bidders shall furnish the prescribed information for the price adjustment formulae

in  Appendix-C  to  Bid,  and  shall submit  with  their  bids  such  other  supporting

information as required under the said Clause. Adjustment in prices quoted by bidders

shall  be  allowed  as  per Sub-Para 4(ii)  of  Section  C of Instructions  to bidders  and

bidding data.

IB.13 Currencies of Bid and Payment

13.1  		The unit rates and the prices shall be quoted by the bidder entirely in Pak rupees. A

bidder  expecting  to  incur  expenditures  in  other  currencies  for  inputs  to  the works

supplied from  outside  the procuring  agency‟s country  (referred  to  as  the “Foreign

Currency Requirements”) shall indicate the  same  in  Appendix-B  to  Bid.  The

proportion  of  the bid  price (excluding  Provisional  Sums)  needed  by  him  for  the

payment of such Foreign Currency Requirements either (i) entirely in the currency of

the  bidder‟s  home country  or,  (ii)  at  the  bidder‟s  option,  entirely  in  Pak  rupees

provided  always  that  a  bidder  expecting  to  incur  expenditures  in  a  currency  or

currencies  other  than  those  stated  in  (i)  and  (ii)  above  for  a  portion  of  the  foreign

currency  requirements,  and wishing  to  be  paid  accordingly,  shall  indicate  the

respective portions in the bid.

13.2  		The  rates  of  exchange  to  be  used  by  the  bidder  for  currency  conversion  shall  be  the

selling rates published and authorized by the State Bank of Pakistan prevailing on the

date, 07 (seven) days prior to the deadline for submission of bids. For the purpose of

payments,  the  exchange  rates  used  in  bid  preparation  shall  apply  for  the  duration  of

the contract.

IB.14 Bid Validity

14.1 		 Bids shall remain valid for the period stipulated in the bidding data from the date of

opening of bid specified in clause IB.23.

14.2  		In  exceptional  circumstances,  prior  to  expiry  of  the  original, the procuring  agency

may  request  the  bidders to extend  the  period  of  validity  for  a  specified additional

period, which shall  not  be  for  more  than  one  third  of  the  original  period  of  bid

validity. The  request  and  the  responses  thereto, shall  be  made  in  writing. A  bidder

may  refuse  the  request  without the forfeiture  of  the  bid security. In  case, a bidder

agreed to the request, shall not be required or permitted to modify the bid, but will be

required to extend the validity of the bid security for the period of the extension, and

in compliance with Clause IB.15 in all respects.

IB.15 Bid Security

15.1  		Each bidder shall furnish, as part of the bid, a bid security in the amount stipulated in

the bidding  data in  Pak  Rupees  or  an  equivalent  amount  in  a  freely  convertible

currency.

15.2  		The bid security shall be at the option of the bidder, in the form of deposit at call, Pay

order or a bank guarantee issued by a Scheduled  Bank in Pakistan or from a foreign

bank  duly  counter  guaranteed  by  a  Scheduled  Bank  in  Pakistan in favour  of  the

procuring agency, which should commensurate with the bid validity period. The bank

guarantee for bid security shall be acceptable in the manner as provided at Annexure

BS-1

15.3 		 Any  bid  not  accompanied  by  an  acceptable bid security  shall  be  rejected  by  the

procuring agency as non-responsive.

15.4 		 Bid security shall be released to the unsuccessful bidders once the  contract has been

signed with the successful bidder or the validity period has expired.

15.5  		The bid security  of  the  successful  bidder shall  be returned  when  the  bidder  has

furnished the required Performance Security and signed the Contract Agreement.

15.6  		The bid security may be forfeited:

(a) 	 if the bidder withdraws his bid except as provided in sub- clause IB 22.1;

(b) 	 if  the  bidder  does  not  accept  the  correction  of  his bid  price pursuant  to sub-

clause IB 27.2 hereof; or

(c)  	In the case of successful bidder, if he fails within the specified time limit to:

(i)  	furnish the required Performance Security; or

(ii)  	sign the Contract Agreement.

IB.16 Alternate Proposals/Bids

16.1  		Each  bidder  shall  submit  only  one  bid  either by  himself,  or  as  a  member  of  a  joint

venture, until  and  unless  they  have  been  requested  or  permitted  for  alternative  bid,

then he has to purchase separate bidding documents and alternate bid shall be treated

as separate bid.

16.2  		Alternate  proposals  are  allowed  only  for  procurement  of  works  where  technical

complexity  is  involved  and  more  than  one  designs  or  technical  solutions  are  being

offered. Two stage two envelope bidding procedure will be appropriate when alternate

proposal is required.

16.3  		Alternate bid(s)  shall  contain  (a)  relevant  design  calculations;  (b)  technical

specifications;  (c)  proposed  construction  methodology;  and  (d)  any  other  relevant

details  /  conditions,  provided that  the total  sum  entered  on  the  Form  of  Bid  shall  be

that which represents complete compliance with the bidding documents.

IB.17  Pre-Bid Meeting

17.1  	Procuring agency may, on his own motion or at the request of any bidder, hold a pre-bid  meeting  to  clarify  issues  and  to  answer  any  questions  on  matters  related  to  the

bidding  documents.  The  date,  time  and  venue  of  pre-bid  meeting,  if  convened, shall

be  communicated  to  all  bidders. All  bidders  or  their  authorized  representatives  shall

be invited to attend such a pre-bid meeting at their own expense.

17.2  		The  bidders  are  requested  to  submit  questions,  if  any,  in  writing  so  as  to  reach  the

Procuring agency not later than seven (7) days before the proposed pre-bid meeting.

17.3 		 Minutes  of  the  pre-bid  meeting,  including  the  text  of  the  questions  raised  and  the

replies given, will be transmitted without delay to all bidders. Any modification of the

bidding documents listed in sub- clause IB 7.1 hereof, which may become necessary

as a result of the pre-bid meeting shall be made by the procuring agency exclusively

through  the  issue  of  an  Addendum  pursuant  to  Clause  IB.9  and  not  through  the

minutes of the pre-bid meeting.

17.4  		Absence at the pre-bid meeting will not be a cause for disqualification of a bidder.

IB.18  Format and Signing of Bid

18.1  		Bidders are particularly directed that the amount entered on the Form of Bid shall be

for performing the contract strictly in accordance with the bidding documents.

18.2  		All appendices to bid are to be properly completed and signed.

18.3  		Alteration is not to be made neither in the form of bid nor in the Appendices thereto

except in filling up the blanks as directed. If any such alterations be made or if these

instructions be not fully complied with, the bid may be rejected.

18.4 		 Each bidder shall prepare by filling out the forms without alterations and shall provide

an original copy  along  with  photocopies  as  per  the  requirement  of  the  procuring

agency specified in the bidding data. The original as well as copies of the document

shall be clearly marked as “ORIGINAL” and „COPY”, as the case may be. If there is

any discrepancy between original and copy (ies) then the original shall prevail.

18.5 		 The original and all copies of the bid shall be typed or written in indelible ink (in the

case of copies, Photostats are also acceptable) and shall be signed by a person(s) duly

authorized  to  sign  on  behalf  of  the  bidder  pursuant  to sub- clause IB 11.1(a)  hereof.

All pages of the bid shall be initialed and stamped by the person(s) signing the bid.

18.6  		The  bid  shall  contain  no  alterations,  omissions  or  additions,  except  to  comply  with

instructions issued by the procuring agency, or as are necessary to correct errors made

by the bidder. Such corrections shall be initialed by the person(s) signing the bid.

18.7 	 	Bidders shall indicate in the space provided in the Form of Bid their full  and proper

postal addresses  at  which  notices  may  be  legally  served  on  them  and  to  which  all

correspondence in connection with their bids and the contract is to be sent.

18.8  		Bidders should retain a copy of the bidding documents as their file copy.

D. 	 SUBMISSION OF BIDS

IB.19   Sealing and Marking of Bids

19.1  		Each bidder shall submit his bid as under:

(a)  	ORIGINAL and _____COPIES of the bid shall be separately sealed and put in

separate envelopes and marked as such.

(b)  	The  envelopes  containing  the  ORIGINAL  and COPIES shall be  put  in  one

sealed envelope and addressed as given in sub – clause IB 19.2 hereof.

19.2 		 The inner and outer envelopes shall:

(a) 	 be  addressed  to  the procuring  agency at  the    address  provided  in  the bidding

data;

(b)  	bear  the    name  and  identification  number  of  the  contract  as  defined  in  the

bidding data; and

(c)	 provide  a  warning  not  to  open  before  the  time  and  date  for  bid  opening,  as

specified in the bidding data.

19.3 	 	In  addition  to  the  identification  required  in sub- clause  IB 19.2  hereof,  the  inner

envelope shall indicate the name and postal address of the bidder to enable the bid to

be returned unopened in case it is declared “late” pursuant to Clause IB.21

19.4  		If  the  outer  envelope  is  not  sealed  and  marked  as  above,  the procuring agency will

assume no responsibility for the misplacement or premature opening of the Bid.

IB.20  Deadline for Submission of Bids

20.1  		(a)  	Bids must be received by the procuring agency at the address specified not

later than the time and date stipulated in the bidding data,

(b)  	Bids  with  charges  payable  will  not  be  accepted,  nor  will  arrangements  be

undertaken to collect the bids from any delivery point other than that specified

above. Bidders shall bear all expenses incurred in the preparation and delivery

of bids. No claims shall be entertained for refund of such expenses,

(c)  	Where  delivery  of  a  bid  is  by  mail  and  the  bidder  wishes  to  receive  an

acknowledgment  of  receipt  of  such  bid,  he  shall  make  a  request  for  such

acknowledgment in a separate letter attached to but not included in the sealed

bid package,

(d)  	Upon  request,  acknowledgment  of  receipt  of  bids  will  be  provided  to  those

making delivery in person or by messenger.

20.2  		The Procuring  Agency may,  at its discretion,  extend  the  deadline  for  submission  of

bids by issuing an amendment in accordance with IB 09. In such case, all rights and

obligations  of  the  procuring  agency  and  the  bidders  shall  remain  the  same  as

mentioned in the original deadline.

IB.21  Late Bids

(a)  	any bid received by the procuring agency after the deadline for submission of

bids prescribed in to clause IB 20 shall be returned unopened to such bidder.

(b)  	delays  in  the  mail,  person  in  transit,  or  delivery  of  a  bid  to  the  wrong  office

shall  not  be  accepted  as  an  excuse  for  failure  to  deliver  a  bid  at  the  proper

place and time. It shall be the bidder‟s responsibility to submit the bid in time.

IB.22  Modification, Substitution and Withdrawal of Bids

22.1  	Any bidder may modify, substitute or withdraw his bid after bid submission provided

that  the  modification,  substitution  or  written  notice  of  withdrawal  is  received  by  the

procuring agency prior to the deadline for submission of bids.

22.2 	 The modification, substitution, or notice for withdrawal of any bid shall be prepared,

sealed, marked and delivered in accordance with the provisions of Clause IB.19 with

the  outer  and  inner  envelopes  additionally  marked  “MODIFICATION”,

“SUBSTITUTION” or “WITHDRAWAL” as appropriate.

22.3  	No bid may be modified by a bidder after the deadline for submission of bids except

in accordance with to sub - clauses IB 22.1 and IB 27.2.

22.4  	Withdrawal of a bid during the interval between the deadlines for submission of bids

and the expiration of the period of bid validity specified in the Form of Bid may result

in forfeiture of the bid security in pursuance to clause IB 15.

E.  BID OPENING AND EVALUATION.

IB.23  Bid Opening

23.1  	Procuring agency  will  open  the  bids,  including  withdrawals,  substitution  and

modifications  made  pursuant  to Clause  IB.22,  in  the  presence  of  bidders‟

representatives  who  choose  to  attend,  at  the  time,  date  and  location  stipulated  in  the

bidding data. The bidders or their representatives who are in attendance shall sign an

attendance sheet.

23.2 	 Envelopes  marked  “MODIFICATION”,  “SUBSTITUTION” or “WITHDRAWAL”

shall be opened and read out first. Bids for which an acceptable notice of withdrawal

has been submitted pursuant to clause IB.22 shall not be opened.

23.3  	Procuring agency shall read aloud the name of the bidder, total bid price and price of

any  Alternate  Proposal(s),  if  any,  discounts,  bid  modifications,  substitution  and

withdrawals,  the  presence  or  absence  of bid  security,  and  such  other  details  as  the

procuring agency may consider appropriate, and total amount of each bid, and of any

alternative  bids  if  they  have  been  requested  or  permitted,  shall  be  read  aloud  and

recorded when opened.

23.4  	Procuring Agency shall prepare minutes of the bid opening, including the information

disclosed to those present in accordance with the sub-clause IB.23.3.

IB.24   Process to be Confidential. (SPP Rule 53)

24.1 	 Information  relating  to  the  examination,  clarification,  evaluation  and  comparison  of

bid and recommendations for the award of a contract shall not be disclosed to bidders

or  any  other  person  not  officially  concerned  with  such  process  before  the

announcement  of  bid  evaluation  report in  accordance  with  the  requirements  of  Rule

45, which states that Procuring agencies shall announce the  results of bid evaluation

in the form of a report giving reasons for acceptance or rejection of bids. The report

shall  be  hoisted  on  website  of  authority  and  that  of  procuring  agency  if  it  website

exists and intimated to all bidders at least seven (7) days prior to the award of contract

The announcement  to  all bidders  will  include  table(s)  comprising  read  out  prices,

discounted  prices,  price  adjustments  made,  final  evaluated  prices  and

recommendations  against  all  the  bids  evaluated.  Any  effort  by  a  bidder  to  influence

the  procuring  agency‟s  processing  of  bids  or  award  decisions  may  result  in  the

rejection of such bidder‟s bid. Whereas, any  bidder  feeling  aggrieved, may  lodge  a

written complaint as per Rule 31; however mere fact of lodging a complaint shall not

warrant suspension of the procurement process.

IB.25  Clarification of Bid (SPP Rule 43)

25.1  		To assist in the examination, evaluation and comparison of bids, the procuring agency

may, at its discretion, ask any bidder for clarification of the bid, including breakdowns

of unit rates. The request for clarification and the response shall be in writing but no

change in the price or substance of the bid shall be sought, offered or permitted except

as required to confirm the correction of arithmetic errors discovered by the procuring

agency in the evaluation of the bids in accordance with clause IB 28.

IB.26  Examination of Bids and Determination of Responsiveness

26.1  		Prior to the detailed evaluation of bids, the procuring agency will determine whether

the  bidder fulfills  all  codal  requirements of  eligibility  criteria given  in  the  tender

notice  such  as  registration  with  tax  authorities,  registration  with  PEC  (where

applicable),  turnover  statement,  experience  statement,  and  any  other  condition

mentioned in the NIT and bidding document. If the bidder does not fulfill any of these

conditions, it shall not be evaluated further.

26.2  		Once  found  to  be  fulfilling  the  eligibility  criteria,  as  mentioned  in sub- clause

26.1,

the bids  of eligible  bidders  will  be  evaluated  for  technical  responsiveness  as  per

specification  and  criteria  given  in  the bidding  documents.  Technical  and financial

evaluations  may  be  carried  out in  accordance  with single  stage-single one envelope,

single stage-two envelopes, two stage or two stage-two envelopes bidding procedures,

depending on the selection procedure adopted by the procuring agency.

26.3   	 A bid will be considered technically responsive if it (i) has been properly signed; (ii)

is  accompanied  by  the  required  bid security;  and  (iii) conforms  to  all  the  terms,

conditions and specifications of the bidding documents, without material deviation or

reservation.  A  material  deviation  or  reservation  is  one  (i)  which  affect  in  any

substantial  way  the  scope,  quality  or  performance  of  the works;  (ii)  which  limits  in

any substantial way, inconsistent with the bidding documents, the procuring agency‟s

rights  or  the  bidder‟s  obligations  under  the contract;  or  (iii)  adoption/rectification

whereof  would  affect  unfairly  the  competitive  position  of  other  bidders  presenting

substantially responsive bids.

26.4 	If a bid has major deviations to the commercial requirements and technical

specifications will be considered technically non responsive. As a general rule, major

deviations are those that if accepted, would not fulfill the purposes for which the bid

is requested, or would prevent a fair comparison or affect the ranking of the bids that

are compliant with the bidding documents.

(A).	 Major (material) Deviations include:-

(i)	has been not properly signed;

(ii) 	is not accompanied by the bid security of required amount and manner;

(iii) 	stipulating price adjustment when fixed price bids were called for;

(iv) 	failing to respond to specifications;

(v)	failing to comply with Mile-stones/Critical dates provided in Bidding

Documents;

(vi)	sub-contracting contrary to the Conditions of Contract specified in Bidding

Documents;

(vii)	refusing to bear important responsibilities and liabilities allocated in the

Bidding Documents, such as performance guarantees and insurance coverage;

(viii)  	taking exception to critical provisions such as applicable law, taxes and duties

and dispute resolution procedures;

(ix)	a material deviation or reservation is one :

(a)	which affect in any substantial way the scope, quality or performance of

the works;

(b)	adoption/rectification whereof would affect unfairly the competitive

position of other bidders presenting substantially responsive bids.

(B) Minor Deviations

Bids that offer deviations acceptable to the Procuring Agency and

which can be assigned a monetary value may be considered substantially

responsive at least as to the issue of fairness. This value would however be added

as an adjustment for evaluation purposes only during the detailed evaluation

process.

26.5  	If a bid is not substantially responsive, it will be rejected by the procuring agency, and

may  not  subsequently  be  made  responsive  by  correction  or  withdrawal  of  the non-conforming deviation or reservation.

IB.27  Correction of Errors before Financial Evaluation

27.1  	Bids  determined  to  be  substantially  responsive  will  be  checked  by  the procuring

agency for any arithmetic errors. Errors will be corrected by the procuring agency as

follows:

(a) 	 where there is a discrepancy between the amounts in figures and in words, the

amount in words will govern; and

(b)  	where  there  is  a  discrepancy  between  the  unit  rate  and  the  line  item  total

resulting from multiplying the unit rate by the quantity, the unit rate as quoted

will  govern,  unless  in  the  opinion  of  the  procuring  agency  there  is  an

obviously  gross  misplacement  of  the  decimal  point  in  the  unit  rate,  in  which

case  the  line  item  total  as  quoted  will  govern  and  the  unit  rate  will  be

corrected.

27.2  	The  amount  stated  in  the  Form  of  Bid  will  be  adjusted  by  the procuring  agency in

accordance  with  the  above  procedure  for  the  correction  of  errors  and  with  the

concurrence of the bidders. The amount thus corrected shall be considered as binding

upon the bidder. If the bidder does not accept the corrected bid price, his bid will be

rejected,  and  the bid  security shall  be  forfeited  in  accordance  with sub- clause IB

15.6(b) hereof.

IB.28  Financial Evaluation and Comparison of Bids

28.1  	The procuring  agency will  evaluate  and  compare  only  the  Bids  determined  to  be

substantially responsive in accordance with clause IB 26.

28.2  	In evaluating the Bids, the procuring agency will determine for each bid the evaluated

bid price by adjusting the bid price as follows:

(a)  	making any correction for errors pursuant to clause IB 27;

(b)	excluding provisional sums (if any), for contingencies in the Summary Bill of

Quantities, but including competitively priced Day work; and

(c) 	making  an  appropriate  adjustment  for  any  other  acceptable  variation  or

deviation.

28.3 	 The estimated effect of the price adjustment provisions of the conditions of contract,

applied over the period of execution of the contract, shall not be taken into account in

Bid evaluation.

28.4 	 If the bid of the successful bidder is seriously unbalanced in relation to the procuring

agency’s  estimate  of  the  cost  of  work  to  be  performed  under  the  contract,  the

procuring agency may require the bidder to produce detailed price analyses for any or

all  items  of  the  Bill  of  Quantities  to  demonstrate  the  internal  consistency  of  those

prices  with  the  construction  methods  and  schedule  proposed.  After  evaluation  of  the

price analyses, the procuring agency may require that the amount of the Performance

Security set forth in clause IB.32 be increased at the expense of the successful bidder

to a level sufficient to protect the procuring agency against financial loss in the event

of default of the successful bidder under the contract.

28.5      Bidders  may  be  excluded  if  involved  in “Corrupt and Fraudulent Practices”

means either one or any combination of the practices given below SPP Rule2(q);

(i) 	“Coercive Practice” means any impairing or harming, or threatening to impair or

harm, directly or indirectly, any party or the property of the party to influence the

actions of a party to achieve a wrongful gain or to cause a wrongful loss to another

party;

(ii) 	“Collusive Practice” means any arrangement between two or more parties to the

procurement  process  or  contract  execution,  designed  to  achieve  with  or  without

the  knowledge  of  the  procuring  agency  to  establish  prices  at  artificial,

noncompetitive levels for any wrongful gain;

(iii)	 “Corrupt Practice” means  the  offering,  giving,  receiving  or  soliciting,  directly

or  indirectly,  of  anything  of  value  to  influence  the  acts  of  another  party  for

wrongful gain;

(iv)  	“Fraudulent  Practice”  means  any  act  or  omission,  including  a

misrepresentation, that knowingly or recklessly misleads, or attempts to mislead, a

party to obtain a financial or other benefit or to avoid an obligation;

(v)  	“Obstructive Practice” means  harming  or  threatening  to  harm,  directly  or

indirectly,  persons  or  their  property  to  influence  their  participation  in  a

procurement  process,  or  affect  the  execution  of  a  contract  or  deliberately

destroying,  falsifying,  altering  or  concealing  of  evidence  material  to  the

investigation or making false statements before investigators in order to materially

impede  an  investigation  into  allegations  of  a  corrupt,  fraudulent,  coercive  or

collusive practice; or threatening, harassing or intimidating any party to prevent it

from  disclosing  its  knowledge  of  matters  relevant  to  the  investigation  or  from

pursuing  the  investigation,  or  acts  intended  to  materially  impede  the  exercise  of

inspection and audit rights provided for under the Rules.

28.6  	Evaluation Report (SPP Rule 45)

After the completion of evaluation process, as described in clauses IB 27 and IB 28,

the procuring agency shall announce the results of bid evaluation in the form of report

(available on the website of the authority) giving reasons for acceptance and rejection

of  bid.  The report  shall be  hoisted  on  website  of  the  authority  and  that  of  procuring

agencies if its website exists and intimated to all bidders at least seven (7) days prior

to the award of contract.

F.  	AWARD OF CONTRACT

IB.29 	 Award (SPP Rule 49)

29.1  	Subject  to clauses  IB 30  and  IB 34  and  provision  of  the  rule:  The procuring  agency

shall  award  the  contract  to  the  bidder  whose  bid  has  been  determined  to  be

substantially  responsive  to the bidding documents, and  who  has  offered  the  lowest

evaluated bid, but  not  necessarily  the  lowest  submitted  price,  within  the  original  or

extended period of bid validity. Provided that such bidder has been determined to be

eligible in accordance with the provisions of clause IB 03 and qualify pursuant to sub-clause IB

29.2  	Procuring  agency,  at  any  stage  of  the  bid  evaluation,  having  credible  reasons  for  or

having prima  facie evidence  of  any  deficiency(ies) in contractor‟s capacities, may

require the contractor to provide information concerning their professional, technical,

financial, legal or managerial competence whether already pre-qualified or not for the

said project.

Provided, that  such  qualification  shall  only  be  laid  down  after  recording  reasons

thereof, in writing. They shall form part of the records of that bid evaluation report.

IB.30  	Procuring  Agency’s Right to reject all  Bids or  Annul/Cancellation the  Bidding

Process (SPP Rule 25)

Notwithstanding clause  IB 29 and  provision  of  the  rule:  (1)  A procuring  agency

reserves may cancel the bidding process at any time prior to the acceptance of a bid or

proposal; (2) The procuring agency shall incur no liability towards bidders solely by

virtue  of  its  invoking  sub –rule  (1);  (3)  Intimation  of  the  cancellation  of  bidding

process shall be given promptly to all bidders and bid security shall be returned along

with  such  intimation; (4)  The procuring  agency shall,  upon  request  by  any  of  the

bidders, communicate to such bidder, grounds for cancellation of the bidding process,

but is not required to justify such grounds.

IB.31. 	 Notification/Publication of the Award of Contract (SPP Rule 25).

31.1  	Prior  to  expiry of  the  period  of  bid  validity,  including  extension, prescribed  by  the

procuring  agency,  the procuring  agency shall  notify  the  successful  bidder  in  writing

(“Letter of Acceptance”) that his bid has been accepted. This letter shall mention the

sum  which  the procuring  agency will  pay to the contractor  in  consideration  of  the

execution and completion of the works by the contractor as prescribed by the contract

(hereinafter and in the conditions of contract called the “Contract Price”).

31.2  	No negotiation  with  the  bidder  having  evaluated  as  lowest  responsive  or  any  other

bidder  shall  be  permitted,  however, procuring  agency may  hold meetings  to  clarify

any item in the bid evaluation report.

31.3 	 The  notification  of  award  and  its  acceptance  by  the  bidder  will  constitute  the

formation of the contract, binding the procuring agency and the bidder till signing of

the formal Contract Agreement.

31.4 	 Upon  furnishing  by  the  successful  bidder  of  a  Performance  Security and  signing  of

the  contract,  the procuring  agency will  promptly  notify the  name  of  the  successful

bidder to all bidders and return their bid securities accordingly.

31.5    	Within  seven  days  of the  award  of  contract,  procuring  agency  shall  publish  on  the

website of the Authority and on its own website, if such a website exists, the results of

the  bidding  process,  identify  the  bid  through  procurement  identifying  numbers,  and

the following information:

(1)	 Evaluation Report;

(2)	  Form of Contract and letter of Award;

(3) 	 Bill of Quantities or Schedule of Requirement.

31.6  Debriefing (SPP Rule 51).

(a)  	 A bidder may ask the procuring agency for reasons for non acceptance of his

bid and may request for a debriefing meeting and procuring agency shall give

him  the  reasons  for  such  non  acceptance,  either  in  writing  or  by  holding  a

debriefing meeting with such a bidder.

(b) 	 The requesting bidder shall bear all the costs of attending   such a debriefing.

IB.32  Performance Security (SPP Rule 39)

32.1 	 The successful bidder shall furnish to the procuring agency a Performance Security in

the form of pay order or demand draft or bank guarantee, and the amount stipulated in

the bidding  data and  the Conditions  of Contract  within  a  period  of 28 days  after  the

receipt of Letter of Acceptance.

32.2  	Failure  of  the  successful  bidder  to  comply  with  the  requirements  of  Sub-clause

IB.32.1 or clauses IB 33 or IB 35 shall constitute sufficient grounds for the annulment

of the award and forfeiture of the bid security.

32.3      Validity  of  performance  security  shall  extend  at  least  ninety  says  beyond  the  date  of

completion of contract,  or as mentioned in the bidding data to cover defects liability

period or maintenance period subject to final acceptance by the procuring agency.

.

IB.33 	 Signing of Contract Agreement (SPP Rule 39)

33.1 	 Within 14 days from the date of furnishing of acceptable Performance Security under

the  Conditions  of Contract,  the procuring  agency will  send  the  successful  bidder  the

Contract Agreement in the form provided in the bidding documents, incorporating all

agreements between the parties.

33.2 	 The formal Agreement between the procuring agency and the successful bidder shall

be executed within 14 days of the receipt of the Contract Agreement by the successful

bidder from the procuring agency.

33.3  	 A procurement contract shall come into force when the procuring agency requires signs

contract,  the  date  on  which  the  signatures  of  both  the  procuring  agency  and  the

successful bidder are affixed to the written contract. Such affixing of signatures shall

take place within the time prescribed in the bidding documents.

Provided that the procuring agency may reduce the maximum time limit for signing of

contract, as and when required, and shall be mentioned in the bidding documents.

33.4    Stamp Duty.

The formal Agreement between the Procuring Agency and the successful bidder shall

be  duly  stamped  at  rate  of ----%  of  bid  price  (updated  from  time  to  time)  stated  in

Letter of Acceptance

IB.34   General Performance of the Bidders

Procuring agency may  in  case  of  consistent  poor  performance of  the  contractor  and

his  failure  to  remedy  the  underperforming  contract  may  take  such  action  as  may  be

deemed appropriate under the circumstances of the case including the rescinding the

contract and/or black listing of such  contractor and debarring him from participation

in future bidding process.

IB.35   Integrity Pact (SPP Rule 89)

The bidder shall  sign  and  stamp  the  Integrity  Pact  provided  at Appendix-L  to the

bidding  documents  for  all  Provincial/Local  Government  procurement  contracts

exceeding  Rupees  ten  million.  Failure  to  provide  such  Integrity  Pact  shall  make  the

bidder non-responsive.

IB.36   Instructions not Part of Contract

Bids shall be prepared and submitted in accordance with these Instructions which are

provided  to  assist  bidders  in  preparing  their  bids,  and  do  not  constitute  part  of    the

bid or the Contract Documents.

IB.37   Arbitration (SPP Rule 34)

Any  dispute  that  is  not  amicably  resolved  shall  be  finally  settled,  unless  otherwise

specified  in  the  Contract,  under the Arbitration  Act  1940  updated  from  time  to  time

and would be  held anywhere in the  Province  of  Sindh  at  the  discretion  of procuring

agency.

BIDDING

DATA

NOTES ON BIDDING DATA

This Section is intended to assist the procuring agency in providing the specific information

in relation to corresponding clauses in Instructions to Bidders and should be prepared to suit

each individual contract.

The procuring  agency should  provide  in  the bidding  data information  and  requirements

specific  to  the  circumstances  of  the  procuring  agency,  the  processing  of  the  bid,  the

applicable  rules  regarding bid price  and  currency,  and  the bid  evaluation  criteria  that  will

apply to the bids.  In preparing this section, the following aspects should be checked:

(1)  Information  that  specifies  and  complements  the  provisions  of  section;  Instruction  to

Bidders must be incorporated.

(2)    Amendments and/or supplements, if any, to the provisions of Instructions to Bidders,

necessitated by the circumstances of each individual contract, can be introduced only

in this section since Instructions to Bidders will remain unchanged.

Contact/Bidding Data

(This  section  should  be  filled  in  by  the procuring  agency before  issuance  of  the bidding

documents.)  The following specific data for the works to be tendered shall complement,

amend,  or  supplement  the  provisions  in  the  Instructions  to  Bidders.  Wherever there is a

conflict, the provisions herein shall prevail over those in the Instructions to Bidders.

[Instructions are provided, as needed, in italics.]

Instructions to Bidders

Clause Reference

  - Name and address of the procuring agency: Executive Engineer Highways Division Badin, Address Hyderabad Road Badin Near Caltex Petrol Pump.

1.2  	Name of the Project and Summary of the works: Construction of Golarchi By Pass Road Badin Sujawal Road @ Mile 17/7 Sorhai Shakh to Connect Badin Sujawal Road @ Mile 21/0 Mile 0/0-4/0 (Remaining Work).

[Insert brief summary, including relationship to other contracts under the Project.  If

the works are to be tendered in separate contracts, describe all the contracts.]

  - Name of the Borrower/Source of Financing/Funding Agency/Funding Source;

[Insert the  ADP No.1458 (2016-17) name  of  Borrower  and statement  of

relationship with the procuring agency, if different from the Borrower.

This insertion should correspond to the information provided in the Invitation

for Bids.]

2.1  Amount and Type of Financing/Scheme Cost and Allocated Funds.

8.1  Time limit for clarification:

[Minimum  number of  days  to  seek clarification by the interested bidder  may  be

inserted as no later than 5 working days prior to last date of submission.]

10.1   Bid language:  English

[The same language in which the bidding documents are written in English, should be

used in National/ International Competitive Bidding.]

11.1   	(a)   Prequalification Information to be updated (where applicable): Pakistan Engineering Council Code CE01

[Indicate what items of information submitted with application for prequalification is

to  be  updated.    It  may include but  not  limited  to  (i) Evidence  of access to financial

resources,(ii)latest status of financial resources commitment for two years (including

the  current  year),  (iii)  works awarded during the interim  period,(iv) availability of

essential critical equipment, and(v) information about litigation presently in process.]

11.1  (b)  Furnish and Technical Proposal (in case of two envelope method) or Company

Profile in single stage single envelope:

The  bidder has to  submit  a  technical  proposal  in  sufficient  detail  to  demonstrate  the

adequacy of the bid in meeting requirements for timely completion of the works.

13.1  Bidders to quote entirely in Pak. rupees but specify the percentages of foreign

currency they require, if applicable.

14.1  Period of Bid Validity:90 Days

[Insert  number  of  days  after  the  deadline  for bid opening.  This period  should  be

realistic, allowing sufficient time to evaluate the Bids, bearing in mind the complexity

of works,  and  the  time  required  for  obtaining  references,  clarifications,  clearances,

and approvals (including the Financing Agency's "No Objection" if it is a bilateral or

multilateral  funding  agency  financed  project)  and  for  notification  of  the  award.

Normally  the  validity  period  should  not  exceed 90 days for  NCB  and  120  days  for

ICB.]

  - Amount of Bid Security: 3598600/-(Rupees Thirty Five Lac Ninety Eight Thousand

& Six Hundred Only).

[This amount should be the same as also quoted in the Invitation for Bids.  To avoid

disclosure of bid price, a fixed sum should be specified, in preference to a percentage

of  the bid  price.  The  sum has  to  be  within  the limits  of  5%  of  estimated  cost. The

percentage  should  be  lower  in  case  of  larger  works  and  higher  in  case  of  smaller

works, but not less than 1% and not exceed the limit of 5%.]

  - Venue, time, and date of the pre-Bid meeting: Executive Engineer Highways

Division Badin,

[Insert address of venue, or indicate that the meeting will not take place.  The meeting

should  take  place  not  later  than 7days in  case  of  NCB  and  no  later  than  15  days  in

case of ICB before the deadline for bid submission. It should take place concurrently

with the site visit, if any (see Sub-Clause IB-6).]

18.4  Number of copies of the bid to be completed and returned:

[Usually one original and ..... copies (number to be specified by the procuring

agency)]

  - (a)  Procuring Agency's address for the purpose of bid submission:

  - Executive Engineer Highways Division Badin

Address Hyderabad Road Badin Near Caltex Petrol Pump.

[Should match the receiving address provided in the Invitation for Bids.]

(b)  Name and Identification Number of the Contract:

20.1  (a)  Deadline for submission of bids:

[The time and date should be the same as that given in the Invitation for Bids unless

subsequently amended pursuant to IB.20.2.]

(b)  Venue, time, and date of bid opening:

[Date should be the same as that given for the deadline for submission of Bids [IB.20]

but  time  for  opening  of  bids  shall  be  at  least  thirty  minutes  after  the  time  for  the

deadline for submission of bids, but not later than one hour].

32.1  Standard  form and  amount  of  Performance  Security  acceptable  to  the  procuring

agency:

[Select  the  kind  of  Performance  Security  (bank  guarantee,  call  deposit,  pay  order),

and  indicate  the  amount/percentage. A bank guarantee has  to  be unconditional as

given in the sample form given with the bidding document. An amount not more than

10  percent  of  the contract price  is  commonly  specified  for  bank  guarantees. This

percentage should match with that stipulated in Appendix-A to Bid.]

32.3  Stamp duty

0.35% will be paid by successful bidder as stamp duty.

[% will depend upon the rules]

FORM OF BID

AND

APPENDICES TO BID

FB-1

FORM OF BID

Bid Reference No. ________________

(Name of Contract/Work)

To:

_______________________________

______________________________

_______________________________

1.  Having examined the bidding documents including Instructions to Bidders,  Bidding

Data, and Conditions of Contract, Specifications, Drawings and Bill of Quantities and

Addenda  Nos.  _________________________________  for  the  execution  of  the

above-named work,  we/I,  the  undersigned,  offer  to  execute  and  complete the work

and  remedy  any  defects  therein  in  conformity  with  the  Conditions  of  Contract,

Specifications,  Drawings,  Bill  of  Quantities  and  Addenda  for  the  sum  of

Rs.  _______________________________________________________ (Rupees

__________________________________________________________)  or such

other sum as may be ascertained in accordance with the said conditions.

2.  We/I understand that all the Appendices attached hereto form part of this bid.

3.  As security for due performance of the undertakings and obligations of this bid, we/I

submit herewith a bid security in the amount of Rupees ________________

(Rs. ______________________) drawn in your favour or made payable to procuring

agency and  valid  for  a  period  of  ___________days  beginning  from  the  date, bid is

opened.

4.  We/I undertake,  if  our bid is  accepted,  to  commence  the works  and  to  complete  the

whole of the works comprised in the contract within the time stated in Appendix-A to

Bid.

5.  We/I agree to abide by this bid for the period of ______ days from the date fixed for

opening the same and it shall remain binding upon us and may be accepted at any

time before the expiration of that period.

6.  Unless and until a formal Agreement is prepared and executed, this bid, together with

your written acceptance thereof, shall constitute a binding contract between us.

7.  We do hereby declare that the bid is made without any collusion, comparison of

figures or arrangement with any other bidder for the works.

We understand that you are not bound to accept the lowest or any bid you may receive.

9. We undertake, if our/my bid is accepted, to execute the Performance Security referred to in

Clause 10 of Conditions of Contract for the due performance of the Contract.

10.  We  confirm,  if  our  bid  is  accepted,  that  all  partners  of  the  joint  venture  shall  be  liable

jointly and severally for the execution of the Contract and the composition or the constitution

of  the  joint  venture  shall  not  be  altered  without  the  prior  consent  of  the  procuring  agency.

(Please delete this in case of Bid form a single bidder)

in the capacity of _______duly authorized to sign Bids for and on behalf of

Dated this ___________day of________________20______

Signature: ________________________

_____________________________________________________

(Name of Bidder in Block Capitals)

(Seal)

Address:___________________________________________________________

__________________________________________________________________

__________________________________________________________________

Witness:

Signature: _____________________________

Name: ________________________________

Address: __________________________________________________________

____________________________________________________________

Occupation:________________________________________________________

.

Appendix-A to Bid

SPECIAL STIPULATIONS

Clause

Conditions of Contract

| 1 | Engineer representing Consulting Firm hired by the procuring agency to issue variation in case of emergency. | 3.1 | Up to 2% of the contract price stated in the Letter of Acceptance. |
| --- | --- | --- | --- |
| 2 | Amount of Performance Security | 4.2 | Up to 10% of contract price. Total amount including performance security and retention money deducted from bills should not exceed 10% of contract price stated in the Letter of Acceptance |
| 3. | Time for Furnishing Programme | 8.3 | Within 42 days from the date of Receipt of Letter of Acceptance. |
| 4. | Minimum amount of Third Party Insurance | 18.3 | Rs. _________ per occurrence with number of occurrences unlimited. |
| 5. | Time for Commencement | 8.1 | Within 14 days from the date of receipt of Engineer‟s Notice to Commence, this shall be issued within fourteen (14) days after signing of Contract Agreement |
| 6. | Time for Completion (works & sections) | 8.2 & 10.2 | _______days from the date of receipt of Engineer‟s Notice to Commence. |
| 7. | Amount of Liquidity Damages/Delay Damages/Penalties | 8.7 | ---------Damages per day (are to be mentioned) but total amount will not be more than 10% of contract Price. |
| 8. | Defects Liability Period | 11.1 | _________days from the effective date of Taking Over Certificate. |
| 9. | Percentage of Retention Money | 14.2 | 10 % of the amount of Interim/Running Payment Certificate. |
| 10. | Limit of Retention Money | 14.2 | 5 % of Contract Price stated in the Letter of Acceptance. |
| 11. | Minimum amount of Interim/Running Payment Certificates | 14.2 | Rs. __________________ |
| 12. | Time of Payment from delivery of Engineer‟s Interim/Running Payment Certificate to the procuring agency. . | 14.7 | 30 days in case of local currency or 42 days in case of foreign funded projects |
| 13. | Mobilization Advance | 14.2 | . 10% of Contract Price stated in the Letter of Acceptance. |

B-1

Appendix-B to Bid

FOREIGN CURRENCY REQUIREMENTS

1.  	The bidder may  indicate  herein  below  his  requirements  of  foreign  currency  (if  any),

with reference to various inputs to the works.

2.	  Foreign Currency Requirement as percentage of the bid price excluding Provisional

Sums _______%.

- Table of Exchange Rates

| Unit of Currency | Equivalent in Pak. Rupees |
| --- | --- |

Australian Dollar					  --------------------------

Euro  							--------------------------

Japanese Yen  						--------------------------

U.K. Pound  						--------------------------

U.S. Dollars 						 --------------------------

---------------------------  				--------------------------

--------------------------- 				 --------------------------

BC-1

Appendix-C to Bid

PRICE ADJUSTMENT UNDER CLAUSE 70/13.8

OF CONDITIONS OF CONTRACT

A.  Weight ages or coefficients are used for price adjustment.

The  source  of  indices  and  the  weight ages  or  coefficients  for  use  in  the  adjustment

formula under Clause 13.8 shall be as follows:

(To be filled by the procuring agency)

| Cost Element | Description | Weight ages | Applicable index |
| --- | --- | --- | --- |
| 1 | 2 | 3 | 4 |
| (i) | Fixed Portion | 0.350 |  |
| (ii) | Local Labor |  | Government of Pakistan (GoP) Federal Bureau of Statistics (FBS) Monthly Statistical Bulletin. |
| (iii) | Cement – in bags |  | “ “ “ |
| (iv) | Reinforcing Steel |  | “ “ “ |
| (v) | High Speed Diesel (HSD) |  | “ “ “ |
| (vi) | Bricks |  |  |
| (vii) | Bitumen |  |  |
| (viii) |  |  |  |
|  | Total | 1.000 |  |

Notes:

1)   	 Indices for “(ii)” to “(vii)” are taken from the Government of Pakistan Federal Bureau

of  Statistics,  Monthly  Statistical  Bulletin.  The  base  cost  indices  or  prices  shall  be

those applying 15 days prior to the latest day for submission of bids. Current indices

or prices shall be those applying 28 days prior to the last day of the billing period.

2)  	 Any fluctuation in the indices or prices of materials other than those given above shall

not be subject to adjustment of the Contract Price.

3)  	 Fixed  portion  shown  here  is  for  typical  road  project, procuring  agency to  determine

the weight age of  Fixed  Portion  considering  only  those  cost  elements  having  cost

impact of seven (7) percent or more on his specific project.

Appendix-D to Bid.

BILL OF QUANTITIES

A.  Preamble

1.  	The  Bill  of  Quantities  shall  be  read  in  conjunction  with  the Conditions  of  Contract,

Specifications and Drawings.

2.  	The  quantities  given  in  the  Bill  of  Quantities  are  estimated  and  provisional,  and  are

given to provide a common basis for bidding. The basis of payment will be the actual

quantities  of  work  executed and  measured  by  the  Contractor  and  verified  by  the

Engineer  and  valued  at  the  rates  and  prices  entered  in  the  priced  Bill  of  Quantities,

where  applicable,  and  otherwise  at  such  rates  and  prices  as  the  Engineer  may  fix  as

per the Contract ( in case of item not mentioned in Bill of Quantities).

3.  	The rates and prices entered in the priced Bill of Quantities shall, except insofar as it

is otherwise provided under the contract include all costs of contractor’s plant, labour,

supervision, materials, execution, insurance, profit, taxes and duties, together with all

general risks, liabilities and obligations set out or implied in the contract. Furthermore

all  duties,  taxes  and  other  levies  payable  by  the contractor  under  the contract,  or  for

any  other  cause,  as  on  the  date 14 days  prior  to  deadline  for  submission  of  Bids in

case of  ICB/NCB respectively, shall be included in the rates and prices and the total

bid price submitted by the bidder.

4.  	A  rate  or  price  shall  be  entered  against  each  item  in  the  priced  Bill  of  Quantities,

whether  quantities  are  stated  or  not.  The  cost  of  items  against  which  the contractor

will have failed to enter  a rate or price shall be deemed to be covered by  other rates

and prices entered in the Bill of Quantities and shall not be paid separately.

5. 	 The whole cost of complying with the provisions of the Contract shall be included in

the items provided in the priced Bill of Quantities, and where no items are provided,

the cost shall be deemed to be distributed among the rates and prices entered for the

related items of the works.

6.  	General directions and description of work and materials are not necessarily repeated

nor  summarised  in  the  Bill  of  Quantities.  References to  the  relevant  sections  of  the

bidding  documents  shall  be  made  before  entering  prices  against  each  item  in  the

priced Bill of Quantities.

7.  	Provisional  sums  included  and  so  designated  in  the  Bill  of  Quantities  shall  be

expended  in  whole  or  in  part  at  the  direction  and  discretion  of  the  Engineer  in

accordance with sub-clause 13.5 of Part I, General Conditions of Contract.

BD-1

Appendix-D to Bid

BILL OF QUANTITIES (SAMPLE)

B.  	Work Items.  (Road /PHE Work)*

1. 	 The Bill of Quantities contains the following Bills and Items:

Bill No. 1    		 -    Earthworks

Bill No. 2              	 -    Hard Crust and Surface Treatment

Bill No. 3    		 -    Culverts and Bridges

Bill No. 4    		 -    Subsurface Drains, Pipe Laying and Man holes

Bill No. 5    		 -    Tube wells, Pump houses and Compound wall

Bill No. 6    		  -    Miscellaneous Items

Day work Schedule

Summary Bill of Quantities

2.  	Bidders shall price the Bill of Quantities in Pakistani Rupees only.

*Procuring Agency can add and delete the Items as per its requirement.

BD-2

Appendix-D to Bid

BILL OF QUANTITIES (SAMPLE)*

B.  	Work Items (Buildings)

1.  	The Bill of Quantities contains the following Bills and Items:

Bill No. 1    		-  	Plinth and Foundation.

Bill No. 2    		- 	 Ground floor.

Bill No. 3    		-  	First and Subsequent Floors.

Bill No. 4    		-  	Internal Water Supply and Sanitary Fittings.

Bill No. 5   		 - 	 Internal Electrification.

Bill No. 6    		-  	Miscellaneous Items

Bill No. 7   		 - 	 External Development

Day work Schedule

Summary Bill of Quantities

2.  	Bidders shall price the Bill of Quantities in Pakistani Rupees only.

*    	Procuring Agency can add and delete the Items as per its requirement

BD-3

Appendix-D to Bid

Part-A

BILL OF QUANTITIES (SAMPLE)

Bill No. 1 Earthworks/Plinth and Foundation

| Item | Description | Unit | Quantity | Rate |  | Amount Rupees. |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Rupees in Figures. | Rupees in Word |  |
| 1 | 2 | 3 | 4 | 5 |  | 6 |
| 1 | Preparing Base Course by supplying and spreading the stone metal of approved quarry properly graded to maximum size of 1 ½” in required thickness to proper camber & grade i/c supplying and speeding 15 cft screening and non-plastic quarry fines filling depresions with stone mantels after initial rolling i/c watering and compacting to achieve 100 % density as per modified AASHO specification. Rate includes all coats of materials labours, T&P & carriage to site of work. | %CFT | 12672 CFT | 9003.13 | (Rupees Nine Thousand & Three & Ps: Thirteen) only. | 1140877 |
| 2 | Providing surface dressing (2 coat) on new or existing surface with 55 Lbs bitumen of 80/100 penetrations and 6.75 CFT crushed Bujri of 1/2-3/4" guage including cleaning the road surface rolling with power roller etc complete rate includes all costs of material T&P labour and carriage to chain. | %CFT | 152064 CFT | 2905.33 | (Rupees Two Thousand Nine Hundred & Five & Ps: Thirty Three) only. | 4417961 |
| 3 | Laying to proper line and grade mixed ASPHALT 2" thick concrete Pavers finished hydraulic /electric control prepared to specified formula according approved by Engineer Incharge i/c rollinged finished to proper line grade level camber etc complete Rate i/c's take coat with bitumen 60/70 penetration Asphaltic plant to of work etc complete. | %CFT | 522086 CFT | 9215.07 | (Rupees Nine Thousand Two Hundred & Fifteen & Ps: Zero Seven) only. | 48110590 |
| 4 | GRANULAR LAYER @ SHOULDERS. Preparing Sub-Base Course by supplying and spreading stone metal of 1 ½” to 2' gauge. | %CFT | 141398 CFT | 7122.86 | (Rupees Seven Thousand One Hundred & Twenty Two & Ps: Eighty Six) only. | 10071582 |
| 5 | KILO METER POST. P/F Precast RCC K.M post including foundation work painting and lettering as Directed each (item No.18d P-17) Highways Schedule Item. | Each | 6Nos | 5600.00 | (Rupees Five Thousand & Six Hundred) only . | 33600 |
| 6 | VILLAGE BOARD. P/F Informatory sign Rectangular Shape 4x3" comprising 2Nos: 3" dia G.I. pipe post including painting writing as Directed each (Item No.18 C-ii P-17 Highways Schedule Items. | Each | 4Nos | 16956.00 | (Rupees Sixteen Thousand Nine Hundred & Fifty Six) only. | 67824 |
| 7 | COUTION BOARD. P/F Traffic Sign 3" dia G.I. pipe post and sign and equilateral triangle shape each side 3' long i/c painting and marking as directed each (Item No.18 (A) P/ No:17 Highways Schedule Items. | Each | 5Nos | 14600 | (Rupees Fourteen Thousand Six Hundred) only. | 73000 |
| 8 | CAT EYES / ROAD STUDS. Supplying and Fixing each Reflectorize road studs double face flush surface type. | Each | 1978 | 596.23 | (Rupees Five Hundred & Ninty Six & Ps: Twenty Three) only. | 1179343 |
| 9 | THARMO PLASTIC PAINT. Pavement marking in reflective Thermo plastic paint floor lines of 6"width. | P.RFT | 54384 | 41.24 | (Rupees Forty One & Twenty Four) only. | 2242796 |
|  |  |  |  |  | Total | 67337573 |
| 10 | Deduct Dif: Cost of Bitumen | P.Tons | 293.74 | 18748.00 | (Rupees Eighteen Thousand Seven Hundred Forty Eight) only. | 5506981 |
|  |  |  |  |  | Total | 61830591 |
| Note No Premium will be allowed on above items No:07 (Difference cost of Bitumen). Contractor & Department are abide by the condition of sanction estimate, Item of work, Quantity, Rate & Premium as per Technical Sanctioned accorded by the competent authority in case of any variation in Schedule "B" of Tender. |  |  |  |  |  |  |

CONTRACTOR .								EXECUTIVE ENGINEER

HIGHWAYS DIVISION

BADIN

BD-4

Appendix-D to Bid

Part-B

BILL OF QUANTITIES (SAMPLE)

Bill No. 2 Hard Crust and Surface Treatment /Ground Floor.

P.B Stone Pitching

| Item | Description | Unit | Quantity | Rate |  | Amount Rupees. |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Rupees in Figures. | Rupees in Word |  |
|  | 2 | 3 | 4 | 5 |  | 6 |
| 01 | Excavation in foundation of buildings Bridges & other structure including dig belling dressing refilling around the structures with excavated earth watering & ramming lead upto 100 Ft:& lift upto 5' ft(in ordinary soil) | % Cft | 2640 CFT | 3176.25 | (Rupees Three Thousand One Hundred Seventy Six & Ps: Twenty Five) only. | 8385 |
| 02 | Foundation and plinth (Random, Rubble Masonary uncaused in cement sand mortar (Ratio 1:4) | % Cft | 2640 CFT | 19025.05 | (Rupees Nineteen Thousand & Twenty Five & Ps: Zero Five) only. | 502261 |
| 03 | Stone pitching including Sub-Base with hammer dressed stone on surface laid in course including carriage of materials with in chain (item 23 P/32) | % Cft | 19183 | 5377.63 | (Rupees Five Thousand Three Hundred & Seventy Seven & Ps: Sixty Three) only. | 1031591 |
| 04 | Painting on stone work raised in cement sand motor ratio 1:3 (Item 20-c P/53) | % Cft | 25577 SFT | 1758 | (Rupees One Thousand Seven Hundred & Fifty Eight & Ps: Zero Eight) only. | 449664 |
|  |  |  |  |  | Total | 1991902 |
| Note Contractor & Department are abide by the condition of sanction estimate, Item of work, Quantity, Rate & Premium as per Technical Sanctioned accorded by the competent authority in case of any variation in Schedule "B" of Tender. |  |  |  |  |  |  |

CONTRACTOR .								EXECUTIVE ENGINEER

HIGHWAYS DIVISION

BADIN

BD-5

Appendix-D to Bid

Part-C

BILL OF QUANTITIES (SAMPLE)

Bill No. 3 Culverts and Bridges/First and Subsequent Floors

PC-4 Span Culvert

| Item | Description | Unit | Quantity | Rate |  | Amount Rupees. |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Rupees in Figures. | Rupees in Word |  |
| 1 | 2 | 3 | 4 | 5 |  | 6 |
| 01 | Errection and removal of centering for R.C.C plain C.C work for pertal Wood (Vertical). | %Sft | 1500 | 3127.41 | (Rupees Three Thousand One Hundred Twenty Seven & Ps: Forty One) only. | 46911 |
| 302 | Fabrication of mild steel reinforcement concrete including cutting, bending laying in position making joints and fastening including cost binding wire (also included removal of rust from bars) etc, complete . | CWT | 11.16 | 4820.20 | (Rupees Four Thousand Eight Hundred & Twenty & Ps: Twenty) only. | 53793 |
| 303 | Cement concrete plain including flooring compacting, compacting including spreading washing of stone aggregate. (C.C Ratio 1:2:4) | CFT | 630 | 14429.25 | (Rupees Fourteen Thousand Four Hundred Twenty Nine & Ps: Twenty Five) only. | 90904 |
|  |  |  |  | Total |  | 191608 |
| Note Contractor & Department are abide by the condition of sanction estimate, Item of work, Quantity, Rate & Premium as per Technical Sanctioned accorded by the competent authority in case of any variation in Schedule "B" of Tender. |  |  |  |  |  |  |

CONTRACTOR.							EXECUTIVE ENGINEER

HIGHWAYS DIVISION

BADIN

BD-6

Appendix-D to Bid

BILL OF QUANTITIES (SAMPLE)

Bill No. 4 Subsurface Drains/ Pipe Laying and Man holes/Internal water Supply

and Sanitary Fittings

| Item | Description | Unit | Quantity | Rate |  | Amount Rupees. |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Rupees in Figures. | Rupees in Word |  |
| 1 | 2 | 3 | 4 | 5 |  | 6 |
| 401 |  |  |  |  |  |  |
| 402 |  |  |  |  |  |  |
| 403 |  |  |  |  |  |  |
| 404 |  |  |  |  |  |  |
| 405 |  |  |  |  |  |  |
| 406 |  |  |  |  |  |  |
| Total for Bill No. 4 ________________ (Carried forward to Summary Page) |  |  |  |  |  |  |

BD-7

Appendix-D to Bid

BILL OF QUANTITIES (SAMPLE)

Bill No. 5 Tube wells and Pump-houses/Internal Electrification

| Item | Description | Unit | Quantity | Rate |  | Amount Rupees. |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Rupees in Figures. | Rupees in Word |  |
| 1 | 2 | 3 | 4 | 5 |  | 6 |
| 501 |  |  |  |  |  |  |
| 502 |  |  |  |  |  |  |
| 503 |  |  |  |  |  |  |
| 504 |  |  |  |  |  |  |
| 505 |  |  |  |  |  |  |
| 506 |  |  |  |  |  |  |
| Total for Bill No. 5 ________________ (Carried forward to Summary Page) |  |  |  |  |  |  |

BD-8

Appendix-D to Bid

BILL OF QUANTITIES (SAMPLE)

Bill No. 6 -                   Miscellaneous Items

| Item | Description | Unit | Quantity | Rate |  | Amount Rupees. |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Rupees in Figures. | Rupees in Word |  |
| 1 | 2 | 3 | 4 | 5 |  | 6 |
| 601 | Mobilization Cost |  |  |  |  |  |
| 502 |  |  |  |  |  |  |
| 503 |  |  |  |  |  |  |
| 504 |  |  |  |  |  |  |
| 505 |  |  |  |  |  |  |
| 506 |  |  |  |  |  |  |
| Total for Bill No. 6 ________________ (Carried forward to Summary Page) |  |  |  |  |  |  |

BD-9

Appendix-D to Bid

BILL OF QUANTITIES (SAMPLE)

Bill No. 7                    External Development

| Item | Description | Unit | Quantity | Rate |  | Amount Rupees. |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Rupees in Figures. | Rupees in Word |  |
| 1 | 2 | 3 | 4 | 5 |  | 6 |
| 601 | Items of water supply & drainage |  |  |  |  |  |
| 602 | Paths & parks |  |  |  |  |  |
| 603 | External electrification |  |  |  |  |  |
| 604 |  |  |  |  |  |  |
| 605 |  |  |  |  |  |  |
| 606 |  |  |  |  |  |  |
| Total for Bill No. 7 ________________ (Carried forward to Summary Page) |  |  |  |  |  |  |

BD-10

Appendix-D to Bid

BILL OF QUANTITIES

C.  		Day work Schedule

General

1.  	Reference is made to Sub-Clause 13.6 of the General Conditions of Contract. Work

shall  not  be  executed  on  a  day  work  basis  except  by  written  order  of  the  Engineer.

Bidders shall enter basic rates for day work items in the Schedules, which rates shall

apply to any quantity of day work ordered by the Engineer. Nominal quantities have

been  indicated  against  each  item  of day work,  and  the  extended  total  for day work

shall be carried forward to the bid price.

Day work Labour

2.  	In calculating payments due to the contractor for the execution of day work, the actual

time of classes of labour directly doing the day work ordered by the Engineer and for

which they are competent to perform will be measured excluding meal breaks and rest

periods.  The  time  of  gangers  (charge  hands)  actually  doing  work  with  the  gang  will

also be measured but not the time of foreman or other supervisory personnel.

3.  	The contractor shall be entitled to payment in respect of the total time that labour is

employed on day work, calculated at the basic rates entered by him in the Schedule of

day work  Rates  for  labour  together  with  an  additional  percentage,  payment  on  basic

rates representing the contractor’s profit, overheads, etc., as described below:

a)  	the basic rates for labour shall cover all direct costs to the contractor, including

(but  not  limited  to)  the  amount  of  wages  paid  to  such  labour,  transportation

time,  overtime,  subsistence  allowances  and  any  sums  paid  to  or  on  behalf  of

such  labour  for  social  benefits  in  accordance  with  Pakistan  law.  The basic

rates will be payable in local currency only; and

b)  	the  additional  percentage  payment  to  be  quoted  by  the bidder and  applied  to

costs incurred under (a) above shall be deemed to cover the contractor’s profit,

overheads,  superintendence,  liabilities  and  insurances  and  allowances  to

labour timekeeping and clerical and office work; the use of consumable stores,

water,  lighting  and  power;  the  use  and  repair  of staging,  scaffolding,

workshops  and  stores,  portable  power  tools,  manual  plant  and  tools;

supervision by the contractor’s staff, foremen and other supervisory personnel;

and charges incidental to the foregoing.

BD-11

Appendix-D to Bid

SCHEDULE OF DAYWORK RATES

I.  Labour

| Item No. | Description | Unit | Nominal Quantity | Rate (Rs) in Figures. | Rate Rs: in Words | Extended Amount (Rs) |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 |
| D101 | Ganger | Hr | 500 |  |  |  |
| D102 | Laborer | Hr | 5,000 |  |  |  |
| D103 | Brick layer | Hr | 500 |  |  |  |
| D104 | Mason | Hr | 500 |  |  |  |
| D105 | Carpenter | Hr | 500 |  |  |  |
| D106 | Steel work Erector | Hr | 500 |  |  |  |
|  | ------etc------ | Hr | 500 |  |  |  |
| D113 | Driver for vehicle up to 10 tons | Hr | 1000 |  |  |  |
| D114 | Operator for excavator, dragline, shovel or crane | Hr | 500 |  |  |  |
| D115 | Operator for tractor, (tracked) with dozer blade or ripper | Hr | 500 |  |  |  |
| D122 | Sub Total Allow _____________ percent of subtotal for Contractor’s overhead, profit, etc, in accordance with Paragraph 3(b) of Day work Schedule ________________________ Total for Day work: Labour : __________________ (Carried forward to Day work Summary |  |  |  |  |  |

BD-12

Appendix-D to Bid

Day work Material

4.  	The contractor shall be entitled to payment in respect of materials used for day work

(except  for  materials  for  which  the  cost  is  included  in  the  percentage  addition  to

labour costs as detailed heretofore), at the basic rates entered by him in the Schedule

of  Day work  Rates  for  materials  together  with  an  additional  percentage  payment  on

the basic rates to cover overhead charges and profit, as follows:

a)  	the  basic  rates  for  materials  shall  be  calculated  on  the  basis  of  the    invoiced

price,  freight,  insurance,  handling  expenses,  damage,  losses,  etc.,  and  shall

provide for delivery to store for stockpiling at the site. The basic rates shall be

stated  in  local  currency  but  payment  will  be  made  in  the  currency  or

currencies expended upon presentation of supporting documentation;

b) 	 the additional percentage payment shall be quoted by the bidder and applied to

the  equivalent local currency payments made under Sub-Para(a) above; and

c) 	 the  cost  of  hauling  materials  used  on  work  ordered  to  be  carried  out  as  Day

work from the store or stockpile on the site to the place where it is to be use d

will be paid in accordance with the terms for Labour and Constructional Plant

in this Schedule.

BD-13

Appendix-D to Bid

SCHEDULE OF DAYWORK RATES

II.  Materials

| Item No. | Description | Unit | Nominal Quantity | Rate (Rs) in Figures. | Rate Rs: in Words | Extended Amount (Rs) |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 |
| D201 | Cement, ordinary Portland or equivalent in bags | M:Ton | 200 |  |  |  |
| D202 | Mild Steel reinforcing bar up to 16mm diameter to BS 4449 or equivalent | M:Ton | 100 |  |  |  |
| D203 | Fine aggregate for concrete as specified in Clause____________ | Cu: M | 1000 |  |  |  |
| D204 | -------etc-------- |  |  |  |  |  |
| D222 | Gelignite (Noble Special Galantine 60 % or equivalent) including caps, fuse, wire and requisite accessories | M:Ton | 10 |  |  |  |
| D223 | Sub Total Allow _____________ percent of subtotal for Contractor’s overhead, profit, etc, in accordance with Paragraph 4(b) of Day work Schedule ________________________ Total for Day work: Materials __________________ (Carried forward to Day work Summary |  |  |  |  |  |

.

BD-14

Appendix-D to Bid

Day Work Constructional Plant

5.  	The contractor shall be entitled to payments in respect of constructional plant already

on site and  employed  on  Day work  at  the  basic  rental  rates  entered  by  him  in  the

Schedule of Day work Rates for constructional plant. The said rates shall be deemed

to  include  complete  allowance  for  depreciation,  interest,  indemnity  and  insurance,

repairs,  maintenance,  supplies,  fuel,  lubricants,  and  other  consumables,  and  all

overhead,  profit  and  administrative  costs  related  to  the  use  of  such  equipment.  The

cost of drivers, operators and assistants will be paid for separately as described under

the section on Day work Labour.

6. 	In calculating the payment due to the Contractor for constructional plant employed on

Day work,  only  the  actual  number  of  working  hours  will  be  eligible  for  payment,

except  that  where  applicable  and  agreed  with  the  Engineer,  the  traveling  time  from

the  part  of  the site where  the  constructional  plant  was  located  when  ordered  by  the

Engineer to be employed on Day work and the time for return journey thereto shall be

included for payment.

7.  	The basic rental rates for constructional plant employed on Day work shall be stated

in Pakistani Rupees.

BD-15

Appendix-D to Bid

SCHEDULE OF DAYWORK RATES

- Constructional Plant

| Item No. | Description | Unit | Nominal Quantity | Rate (Rs) in Figures. | Rate Rs: in Words | Extended Amount (Rs) |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 |  | 5 | 6 |
| D301 | Excavator ,face shovel or dragline: 1. Up-to and including 1 Cu.M. 2. Over 1 Cu.M to 2 Cu. M 3. Over 2 Cu. M | Hr Hr Hr | 500 400 100 |  |  |  |
| D302 | Tractor (tracked) including bull or angle dozer 1. Up-to and including 150 HP 2. Over 150 to 200 HP 3. Over 200 to 250 HP | Hr Hr Hr | 500 400 200 |  |  |  |
| D303 | Tractor with ripper: 1. Up-to and including 200 HP 2. Over 200 to 250 HP | Hr Hr | 400 200 |  |  |  |
| D304 | -----------etc--------- |  |  |  |  |  |
|  | Total for day work: Constructional Plant _________________ (Carried forward to day work summary) |  |  |  |  |  |

BD-16

Appendix-D to Bid

DAYWORK

Summary (Day work)

Amount (Rs.) (I) Total for day work: Labour ____________ (II) Total for day work: Materials ____________ (III) Total for day work: Constructional Plant ____________

Total for day work ___________________ (Carried forward to summary page of Bill of Quantities)

BD-17

Appendix-D to Bid

BILL OF QUANTITIES (SAMPLE)

SUMMARY

- Amount (Rs.) Bill No. 1: Earthworks/Plinth and Foundation Bill No. 2: Culverts and Bridges/Ground Floor Bill No. 3: Subsurface Drains/Internal Water Supply & Sanitary Fittings Bill No 4: Subsurface Drains/ Pipe Laying and Man holes/Internal water Supply and Sanitary Fittings Bill No. 5 Tube wells and Pump-houses/Internal Electrification Bill No. 6 Miscellaneous Items Bill No. 7 External Development

Sub-Total of Bills ____________ Day work _________________ Bid Price _________________

Note:  All  Provisional  Sums  are  to  be  expended  in  whole  or,  in  part  at  the  direction  and

discretion  of  the  Engineer  in  accordance  with  Sub-Clauses  52.4  and  58.2  of  the  General

Conditions of Contract Part- I.

BE-1

Appendix-E to Bid

PROPOSED CONSTRUCTION SCHEDULE

Pursuant  to  Sub-Clause  43.1  of  the  General  Conditions  of  Contract,  the works  shall  be

completed  on  or  before  the  date  stated  in  Appendix-A  to  Bid.  The bidder shall provide as

Appendix-E to Bid, the Construction Schedule in the bar chart (CPM, PERT or any other to

be specified herein) showing the sequence of work items and the period of time during which

he proposes to complete each work item in such a manner that his proposed programme for

completion  of  the  whole  of  the works  and  parts  of  the works  may  meet procuring  agency’s

completion targets  in  days  noted  below  and counted from the date of receipt of Engineer’s

Notice  to  Commence  (Attach  sheets  as  required  for  the  specified  form  of  Construction

Schedule):

Description          			Time for Completion

1)  Whole works   			__________________ days

2)  Part-A         			__________________ days

3)  Part-B       				__________________ days

4) ___________     			__________________ days

5)  ___________      			__________________ days

BF-1

Appendix-F to Bid

METHOD OF PERFORMING THE WORK

[The bidder is  required  to  submit  a  narrative  outlining  the  method  of  performing  the  work.

The narrative should indicate in detail and include but not be limited to:

1.  	Organization  Chart  indicating  head  office  and  field  office  personnel  involved  in

management and supervision, engineering, equipment maintenance and purchasing.

2.  	Mobilization in Pakistan, the type of facilities including personnel accommodation,

office accommodation,  provision  for  maintenance  and  for  storage,  communications,

security and other services to be used.

3.  	The method of executing the works, the procedures for installation of equipment and

machinery and transportation of equipment and materials to the site.

BG-1

Appendix-G to Bid

LIST OF MAJOR EQUIPMENT – RELATED ITEMS

[The bidder will provide on Sheet 2 of this Appendix a list of all major equipment and related

items, under separate heading for items owned, to be purchased or to be arranged on lease by

him to  carry  out  the works.  The information shall include make, type, capacity, and

anticipated  period  of  utilization  for  all  equipment  which  shall  be  in  sufficient  detail  to

demonstrate fully that the equipment will meet all requirements of the Specifications.]

BG-2

Appendix-G to Bid

LIST OF MAJOR EQUIPMENT (SAMPLE)

| Owned Purchased or Leased | Description of Unit (Make, Model, Year) | Capacity HP Rating | Condition | Present Location or Source. | Date of Delivery at Site | Period of Work on Project |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 |
| - Owned |  |  |  |  |  |  |
| b. To be Purchased |  |  |  |  |  |  |
| c. To be arranged on Lease |  |  |  |  |  |  |

BH-1

Appendix-H to Bid

CONSTRUCTION CAMP AND HOUSING FACILITIES

The  Contractor  in  accordance with  Clause 6 of  the  Conditions  of  Contract  shall  provide

description of his construction camp‟s facilities and staff housing requirements.

The  contractor  shall  be  responsible  for  pumps,  electrical  power,  water  and  electrical

distribution  systems,  and  sewerage  system including  all  fittings,  pipes  and  other  items

necessary for servicing the contractor‟s construction camp.

The bidder shall  list  or  explain  his  plans  for  providing  these  facilities  for  the  service  of  the

contract as follows:

1.  	Site Preparation (clearing, land preparation, etc.).

2.  	Provision of Services.

a)  	Power (expected power load, etc.).

b)  	Water (required amount and system proposed).

c)  	Sanitation (sewage disposal system, etc.).

3.  	Construction of Facilities

a)  	Contractor‟s Office. Workshop and Work Areas (areas required and proposed

layout, type of construction of buildings, etc.).

b)  	Warehouses and Storage Areas (area required, type of construction and

layout).

c)  	Housing and Staff Facilities (Plans for housing for proposed staff, layout, type

of construction, etc.).

4.  	Construction Equipment Assembly and Preparation (detailed plans for carrying out

this activity).

5.	Other Items Proposed (Security services, etc.).

BI-1

Appendix-I to Bid

LIST OF SUBCONTRACTORS

I/We  intend  to  subcontract the  following  parts  of  the  work  to  subcontractors.  In my/our

opinion, the subcontractors named hereunder are reliable and competent to perform that part

of the work for which each is listed.

Enclosed are documentation outlining experience of subcontractors, the curriculum vitae and

experience  of  their  key  personnel  who  will  be  assigned  to  the contract,  equipment  to  be

supplied by them, size, location and type of contracts carried out in the past.

| Part of Works (Give Details) | Subcontractor (With Complete Address) |
| --- | --- |
| 1 | 2 |

BJ-1

Appendix-J to Bid

ESTIMATED PROGRESS PAYMENTS (SAMPLE)

Bidder‟s estimate of the value of work which would be executed by him during each of the

periods  stated  below,  based  on  his  Programme  of  the  works  and  the Rates  in  the  Bill  of

Quantities, expressed in Pakistani Rupees:

| Quarter/ Year/ Period | Amounts (in thousands) |
| --- | --- |
| 1 | 2 |
| Ist Quarter |  |
| 2nd Quarter |  |
| 3rd Quarter |  |
| 4th Quarter |  |
| 5th Quarter |  |
| 6th Quarter |  |
| 7th Quarter |  |
| 8th Quarter |  |
| 9th Quarter |  |
| Bid Price. |  |

BK-1

Appendix-K to Bid

ORGANIZATION CHART

FOR THE

SUPERVISORY STAFF AND LABOUR

(To be filled in by the bidder)

BL-1

Appendix-L to Bid

(INTEGRITY PACT)

DECLARATION OF FEES, COMMISSION AND BROKERAGE ETC; PAYABLE BY

CONTRACTORS.

(FOR CONTRACTS WORTH RS. 10.00 MILLION OR MORE)

Contract No.01       Dated __________________

Contract Value: 71.972

Contract Title:   	Construction of Golarchi By Pass Road Badin Sujawal Road @ Mile 17/7 Sorhai Shakh to Connect Badin Sujawal Road @ Mile 21/0 Mile 0/0-4/0 (Remaining work).

………………………………… [name of Contractor] hereby declares that it has not obtained

or  induced  the  procurement of  any  contract,  right,  interest,  privilege  or  other  obligation  or

benefit from Government of Sindh (GoS) or any administrative subdivision or agency thereof

or any other entity owned or controlled by it (GoS) through any corrupt business practice.

Without  limiting  the  generality  of  the  foregoing,  [name  of Contractor]  represents  and

warrants  that  it  has  fully  declared  the  brokerage,  commission,  fees  etc.  Paid or payable to

anyone and not given or agreed to give and shall not give or agree to give to anyone within

or  outside  Pakistan  either  directly  or  indirectly  through  any  natural  or  juridical  person,

including  its  affiliate,  agent,  associate,  broker,  consultant,  director,  promoter,  shareholder,

sponsor or subsidiary, any commission, gratification, bribe, finder‟s fee or kickback, whether

described  as  consultation  fee  or  otherwise,  with  the  object  of  obtaining  or  inducing  the

procurement  of  a  contract,  right,  interest,  privilege  or  other  obligation  or  benefit  in

whatsoever form from, from Procuring Agency (PA)  except that which has been expressly

declared pursuant hereto.

[name  of Contractor] accepts  full  responsibility  and  strict  liability that  it  has  made  and  will

make  full  disclosure  of  all  agreements  and  arrangements  with  all  persons  in  respect of  or

related to the transaction with PA and has not taken any action or will not take any action to

circumvent the above declaration, representation or warranty.

[name  of  Contractor]  accepts  full  responsibility  and  strict  liability  for  making  any  false

declaration,  not  making  full  disclosure,  misrepresenting  facts  or  taking  any  action  likely  to

defeat the purpose of this declaration, representation and warranty. It agrees that any contract,

right, interest, privilege or other obligation or benefit obtained or procured as aforesaid shall,

without prejudice to any other rights and remedies available to PA under any law, contract or

other instrument, be voidable at the option of PA.

Notwithstanding  any  rights  and  remedies  exercised  by  PA  in  this  regard,  [name  of

Supplier/Contractor/Consultant] agrees to indemnify PA for any loss or damage incurred by it

on account of its corrupt business practices and further pay compensation to PA in an amount

equivalent  to  ten  time  the  sum  of  any  commission,  gratification,  bribe,  finder’s  fee  or

kickback given by [name of Contractor] as aforesaid for the purpose of obtaining or inducing

the  procurement  of  any  contract,  right,  interest,  privilege  or  other  obligation  or  benefit  in

whatsoever form from PA.

………………………

[Procuring Agency]                                               [Contractor]

FORMS

BID SECURITY

PERFORMANCE SECURITY

CONTRACT AGREEMENT

MOBILIZATION ADVANCE GUARANTEE

INDENTURE BOND FOR SECURED ADVANCE

BS-1

BID SECURITY

(Bank Guarantee)

Security Executed on _______________________________________________________

(Date)

Name of Surety (Bank) with Address: ________________________________________

(Scheduled Bank in Pakistan)

Name of Principal (Bidder) with Address _______________________________________

________________________________________________________________________

Penal Sum of Security Rupees. _____________________ (Rs. _____________________)

Bid Reference No. _______________________________________________________

KNOW ALL MEN BY THESE PRESENTS, that in pursuance of the terms of the bid and at

the request  of  the  said  Principal  (Bidder) we,  the Surety  above  named,  are  held  and  firmly

bound unto ______________________________________________________

(hereinafter called the 'Procuring Agency') in the sum stated above for the payment of which

sum  well  and  truly  to  be  made,  we  bind  ourselves,  our  heirs,  executors,  administrators  and

successors, jointly and severally, firmly by these presents.

THE  CONDITION  OF  THIS  OBLIGATION  IS  SUCH,  that  whereas  the  Bidder  has

submitted the accompanying bid dated ______ for Bid No. _______ for_______(Particulars

of Bid) to the said Procuring Agency; and

WHEREAS, the Procuring Agency has required as a condition for considering said bid that

the bidder furnishes a bid security in the above said sum from a Scheduled Bank in Pakistan

or  from  a  foreign  bank  duly  counter-guaranteed  by  a  Scheduled    Bank in Pakistan,  to  the

procuring agency, conditioned as under:

(1)      	that  the bid  security shall  remain  in  force  up  to  and  including  the  date  28  days  after

the deadline for validity of bids as stated in the Instructions to bidders or as it may be

extended  by  the procuring  agency,  notice  of  which  extension(s)  to  the  Surety  is

hereby waived;

(2)  	that the bid security of unsuccessful bidders will be returned by the procuring agency

after expiry of its validity or upon signing of the Contract Agreement; and

(3)  	that in the event of  failure of the successful bidder to execute the proposed Contract

Agreement  for  such  work  and  furnish  the  required  Performance  Security,  the  entire

said sum be paid immediately to the said procuring agency pursuant to Clause 15.6 of

the Instruction to bidders for the successful bidder's failure to perform.

NOW THEREFORE, if the successful bidder shall, within the period specified therefore, on

the prescribed form presented to him for signature enter into a formal Contract with the said

procuring agency in accordance with his bid as accepted and furnish within twenty eight (28)

days of his being requested to do so, a Performance Security with good and sufficient surety,

as  may  be  required,  upon  the  form  prescribed  by  the  said procuring  agency for  the  faithful

performance and proper fulfilment of the said Contract or in the event of non-withdrawal of

the said bid within the time specified for its validity then this obligation shall be void and of

no effect, but otherwise to remain in full force and effect.

PROVIDED THAT the Surety shall forthwith pay the procuring agency, the said sum upon

first  written  demand  of  the  procuring  agency  (without  cavil  or  argument)  and  without

requiring  the procuring  agency to  prove  or  to  show  grounds  or  reasons  for  such  demand,

notice of which shall be sent by the procuring agency by registered post duly addressed to the

Surety at its address given above.

PROVIDED ALSO THAT the procuring agency shall be the sole and final judge for deciding

whether  the Principal  (Bidder)  has  duly  performed  his  obligations  to  sign  the  Contract

Agreement and to furnish the requisite Performance Security within the time stated above, or

has  defaulted  in  fulfilling  said  requirements  and  the  Surety  shall  pay  without  objection the

said sum upon demand from the procuring agency forthwith and without any reference to the

Principal (Bidder) or any other person.

IN WITNESS WHEREOF, the above bounden Surety has executed the instrument under its

seal  on  the  date  indicated  above,  the name  and  seal  of  the  Surety  being  hereto  affixed  and

these  presents  duly  signed  by  its  undersigned  representative  pursuant  to  authority  of  its

governing body.

SURETY (Bank)

WITNESS:                   					  Signature ___________________

1. __________________________________		  Name      ___________________

__________________________________                           Title       ____________________

Corporate Secretary (Seal)                                                    Corporate Secretary (Seal)

- __________________________

__________________________

Name, Title & Address

PS-1

FORM OF PERFORMANCE SECURITY

(Bank Guarantee)

Guarantee No.____________________

Executed on _____________________

Expiry date _____________________

[Letter by the Guarantor to the Procuring Agency]

Name of Guarantor (Bank) with address:_______________________________________

(Scheduled Bank in Pakistan)

Name of Principal (Contractor) with address:____________________________________

________________________________________________________________________

Penal Sum of Security (express in words and figures)_____________________________

________________________________________________________________________

Letter of Acceptance No. ________________________________Dated ______________

KNOW  ALL  MEN  BY  THESE  PRESENTS,  that  in  pursuance  of  the  terms  of  the bidding

documents and above said Letter of Acceptance (hereinafter called the Documents) and at the

request of the said Principal we, the Guarantor above named, are held and firmly bound unto

the  __________________________________________________  (hereinafter  called  the

procuring agency) in the penal sum of the amount stated above for the payment of which sum

well  and  truly  to  be  made  to  the  said  procuring  agency,  we  bind  ourselves,  our  heirs,

executors, administrators and successors, jointly and severally, firmly by these presents.

THE  CONDITION  OF  THIS  OBLIGATION  IS SUCH,  that  whereas  the  Principal  has

accepted  the  procuring  agency's  above  said  Letter  of  Acceptance  for  ________

________________________________  (Name  of  Contract)  for  the  _______________

_______________________________ (Name of Project).

NOW THEREFORE, if the Principal (Contractor) shall well and truly perform and fulfill all

the undertakings, covenants, terms and conditions of the said Documents during the original

terms of the said Documents and any extensions thereof that may be granted by the procuring

agency,  with  or  without  notice  to  the  Guarantor,  which  notice  is,  hereby, waived  and  shall

also well and truly perform and fulfill all the undertakings, covenants terms and conditions of

the Contract and of any and all modifications of said Documents that may hereafter be made,

notice of which modifications to the Guarantor being hereby waived, then, this obligation to

be  void;  otherwise  to  remain  in  full  force  and  virtue  till  all  requirements  of  Clause 49,

Defects Liability, of Conditions of Contract are fulfilled.

Our total liability under this Guarantee is limited to the sum stated above and it is a condition

of  any  liability  attaching  to  us  under this Guarantee  that  the  claim  for  payment  in  writing

shall be received by us within the validity period of this Guarantee, failing which we shall be

discharged of our liability, if any, under this Guarantee.

We, ____________________________________ (the Guarantor), waiving all objections  and

defenses under the Contract, do hereby irrevocably and independently guarantee to pay to the

procuring  agency without  delay  upon  the procuring  agency's  first  written  demand  without

cavil or arguments and without requiring the procuring  agency to prove or to show grounds

or  reasons  for  such  demand  any  sum  or  sums  up  to  the  amount  stated  above,  against  the

procuring agency's written declaration that the Principal has refused or failed to perform the

obligations under the Contract which payment will be effected by the Guarantor to Procuring

Agency‟s designated Bank & Account Number.

PROVIDED ALSO THAT the procuring agency shall be the sole and final judge for deciding

whether the Principal (Contractor) has duly performed his obligations under the Contract or

has defaulted in fulfilling said obligations and the Guarantor shall pay without objection any

sum  or  sums  up  to  the  amount  stated  above  upon first  written  demand  from  the procuring

agency forthwith and without any reference to the Principal or any other person.

IN WITNESS WHEREOF, the above-bounden Guarantor has executed this Instrument under

its  seal  on  the  date  indicated  above,  the  name  and corporate  seal  of  the  Guarantor  being

hereto  affixed  and  these  presents  duly  signed  by  its  undersigned  representative,  pursuant  to

authority of its governing body.

_______________

Guarantor (Bank)

Witness:

1. _______________________        					   Signature _______________

_______________________           				   Name __________________

Corporate Secretary (Seal)

Title ___________________

2.  _______________________

_______________________    					  _______________________

Name, Title & Address      					   Corporate Guarantor (Seal)

CA-1

FORM OF CONTRACT AGREEMENT

THIS CONTRACT AGREEMENT (hereinafter called the “Agreement”) made on the

________________  day  of__________(month)  20_____  between

_______________________________________________________________________

(hereafter  called  the  “Procuring  Agency”)  of  the  one  part  and

_____________________________________ (hereafter called the “Contractor”) of the other

part.

WHEREAS  the Procuring  Agency is  desirous  that  certain works,  viz  _______________

should  be  executed  by  the  Contractor  and  has  accepted  a bid by  the  Contractor  for  the

execution and completion of such works and the remedying of any defects therein.

NOW this Agreement witnesses-- as follows:

1.  In  this  Agreement  words  and  expressions  shall  have  the  same  meanings  as  are

respectively assigned to them in the Conditions of Contract hereinafter referred to.

2.  The  following  documents  after  incorporating  addenda,  if  any,  except  those  parts

relating to Instructions to bidders shall be deemed to form and be read and construed

as part of this Agreement, viz:

(a) 	 The Contract Agreement;

(b)  	The Letter of Acceptance;

(c)  	The completed Form of Bid;

(d)  	Special Stipulations (Appendix-A to Bid);

(e)  	The Special Conditions of Contract – Part II;

(f)  	The General Conditions – Part I;

(g)  	The priced Bill of Quantities (Appendix-D to Bid);

(h) 	 The completed Appendices to Bid (B, C, E to L);

(i) 	 The Drawings;

(j) 	 The Specifications.

(k)  	_____________________________ (any other)

3. 	 In  consideration  of  the  payments  to  be  made  by  the  procuring  agency  to  the

Contractor  as  hereinafter  mentioned,  the  Contractor  hereby  covenants  with  the

procuring  agency to  execute  and  complete  the works and  remedy  defects  therein  in

conformity and in all respects with the provisions of the contract.

4.  	Procuring  agency hereby  covenants  to  pay  the contractor,  in  consideration  of  the

execution and completion of the works as per provisions of the contract, the contract

Price or such other sum as may become payable under the provisions of the contract

at the times and in the manner prescribed by the contract.

CA-2

IN WITNESS WHEREOF the parties hereto have caused this Agreement to be executed on

the day, month and year first before written in accordance with their respective laws.

Signature of the Contactor Signature of Procuring Agency

______________________  _____________________

(Seal)  (Seal)

Signed, Sealed and Delivered in the presence of:

Witness:  Witness:

________________________  ______________________________

(Name, Title and Address)  (Name, Title and Address)

MG-1

MOBILIZATION ADVANCE GUARANTEE

Bank Guarantee No.______________________ Date ______________________________

WHEREAS ______________(hereinafter  called  the  'Procuring  Agency')  has  entered  into  a

Contract for ___________________________________________________________

(Particulars of Contract)

with _________________ (hereinafter called the "Contractor').

AND  WHEREAS,  the Procuring  Agency has  agreed  to  advance  to  the  Contractor,  at  the

Contractor's  request,  an  amount  of  Rupees  _________________________  (Rs  _________  )

which amount shall be advanced to the Contractor as per provisions of the Contract.

AND  WHEREAS,  the Procuring  Agency has  asked  the  Contractor  to  furnish  Guarantee  to

secure  the  mobilization  advance  for  the  performance  of  his  obligations  under  the  said

Contract.

AND WHEREAS, ________________________________________________________

(Scheduled Bank in Pakistan)

(hereinafter called the “Guarantor”) at the request of the Contractor and in consideration of

the procuring agency agreeing to make the above advance to the Contractor, has agreed to

furnish the said Guarantee.

NOW,  THEREFORE,  the  Guarantor  hereby guarantees  that  the  Contractor  shall  use  the

advance for the purpose of above mentioned Contract and if he fails and commits default in

fulfilment  of  any  of  his  obligations  for  which  the  advance  payment  is  made,  the  Guarantor

shall  be  liable  to  the  procuring  agency  for  payment  not  exceeding  the  aforementioned

amount.

Notice  in  writing  of  any  default,  of  which  the procuring  agency shall  be  the  sole  and  final

judge, on the part of the Contractor, shall be given by the procuring agency to the Guarantor,

and on such first written demand, payment shall be made by the Guarantor of all sums then

due under this Guarantee without any reference to the Contractor and without any objection.

This  Guarantee  shall  remain  in  force  until  the  advance  is  fully  adjusted  against  payments

from  the  Interim  Payment  Certificates  of  the  Contractor  or  until

_______________________________________whichever is earlier.

(Date)

The Guarantor's liability under this Guarantee shall not in any case exceed the sum of Rupees

_______________________________________(Rs _______________________).

This Guarantee shall remain valid up to the aforesaid date and shall be null and void after the

aforesaid  date  or  earlier  if  the  advance  made  to  the  Contractor  is  fully  adjusted  against

payments  from Interim  Payment  Certificates  of  the  Contractor  provided  that  the  Guarantor

agrees  that  the  aforesaid  period  of  validity  shall  be  deemed  to  be  extended  if  on  the  above

mentioned date the advance payment is not fully adjusted.

GUARANTOR

1.  Signature________________

2.  Name    _________________

3.  Title      _________________

WITNESS

1.  ______________________

______________________

Corporate Secretary (Seal)

2.  _______________________   		  __________________________

(Name Title & Address)         			Corporate Guarantor (Seal)

INDENTURE FOR SECURED ADVANCES.

(For use in cases in which is contract is for finished work and the contractor has entered into

an agreement for the execution of a certain specified quantity of work in a given time).

This INDENTURE made the ……………………….. day of  ...............................

………………….  20……….………    BETWEEN (hereinafter      called      "the

Contractor" which expression shall where the context so admits or implied be deemed

to include  his  heirs,  executors,  administrators  and  assigns)  of  the  one  part  and

THE GOVERNOR  OF  SINDH  (hereinafter  called  "the  Government"  of  the  other

part).

WHEREAS by an agreement, dated (hereinafter called the said agreement, the

contractor has agreed to perform the under-mentioned works (hereinafter referred to as

the said work):-

(Here enter (the description of the works).

1

AND WHEREAS the contractor has applied to the …………………………………..

……..…………………..for an advance to him of Rupees ……………..……………………

(Rs.  .................. )  on  the  security  of  materials  absolutely  belonging  to  him  and  brought  by

him  to  the  site  of  the  said  works  the  subject  of  the  said  agreement  for  use  in  the

construction of such of the said works as he has undertaken to execute at rates fixed for the

finished  work  (inclusive  of  the  cost  of  materials  and  labour  and  other  charge)  AND

WHEREAS the Government has agreed to advance to the Contractor the sum of Rupees, (Rs.

......................... ) on the security of materials the quantities and other particulars of which are

detailed in Part II of Running Account Bill (B). the said works signed by the contractor

Fin R.Form.l7.A

On ……………………………. and on such covenants and conditions as are hereinafter

contained and  the  Government  has  reserved  to  itself  the  option  of  marking  any  further

advance or advances on the security of other materials brought by the Contractor to the site

of the said works.

NOW   THIS   INDENTURE   WTTNESSETH      that   in   pursuance   of the   said

agreement and in consideration of the sum of Rupees……………………………..

(Rs. ……………………) on or before the execution of these presents paid to the Contractor

by the Government (the receipt whereof the Contractor doth hereby acknowledge) and of such

further  advances  (if  any)  as  may  be  made  to  him  as  aforesaid  (all  of  which  advances are

hereinafter  collectively  referred  to  as  the  said  amount)  the  Contractor  doth  hereby assign

unto the Government the said materials by way of security for the said amount

And doth hereby covenant and agree with the Government and declare ay

follow :-

(1)              That the said sum of Rupees. …………………………………………… RS.

…………………… ) So advanced by the Government to the Contractor as aforesaid

and all  or  any  further  sum  or  sums  which  may  be  advanced  as aforesaid  shall  be

employed  by the  contractor  in  or  towards  expending  the  execution  of the said  works

and for no other purpose whatsoever.

(2)  	That the materials detailed in the said Running Account Bill (B) which have

been offered to and accepted by (he Government as security for the said amount are

absolutely by the Contractors own property free from encumbrances of any kind and

the  Contractor will  not  make  any  application  for  or  receive  a  further  advance  on  the

security  of  materials which  are  not  absolutely  his  own  property  and  free  from

encumbrances  of  any  kind  and  the contractor  hereby  agrees,  at  all  times,  to

indemnify  and  save  harmless  the Government  against  all  claims  whatsoever  to

any materials in respect of which an advance has been made to him as aforesaid.

(3)  	That  the  said  materials  detailed  in  the  said  Running Account  Bill  (B) and  all  other

materials  on  the  security  of  which  any  further  advance  or  advances  may  hereafter

be made  as  aforesaid  (hereinafter  called  the  said  materials)  shall  be  used  by  the

Contractor solely    in the   execution of the said works in accordance with the

directions of the Divisional Officer  (hereinafter  called  the  Divisional

Officer) and in the terms of the said agreement.

(4)  	That  the  Contractor  shall  make  at  his  own  cost  all  necessary  and

adequate arrangement  for  the  proper  watch,  safe custody  and  protection  against  all

risks  of  the  said material  and  that  until  used  in  construction  as  aforesaid  the  said

materials shall remain at jt he site of the said works in the Contractor's custody and at

his own risk and on his own responsibility and shall at all times be open to inspection

by (he Divisional Officer or any officer authorized by him. In the event of the said

materials  of  any  part  (hereof  being stolen,  destroyed  or  damaged  or becoming

deteriorated  in  a  greater  degree  than  is  due  to reasonable  use  and  wear thereof

Contractor  will  forthwith  replace  the  same  with  other materials  of  like  qualify  or

repair  and  make  good  the  same  as  required  by  the  Divisional

Officer  and  the  materials  so  brought  to  replace  the  said  materials  so  repaired  and

made good shall also be considered as security for the said amount.

(5)  	Hurt the said materials shall not on any account be removed from the site of

the said works except with the written permission of the Divisional Officer or an

officer authorized by him in that behalf

(6) 	 That   the   said   amount shall   be payable   in   full   when   or before the

Contractor receives payment, from the Government of the price payable to him for

the said  works  under  the  terms  and  provisions  of  the  said  agreement PROVIDED

THAT  if any intermediate payments are made to the contractor on account of work

done then on the occasion   of each such payment the Government will be at liberty to

make  a  recovery from  the  Contractors  Bill  for  such  payment by  deducting  there

from in the value of the said materials (hen actually used in the construction and in

respect  of  which  recovery  has not  been  made  previously the  value  for  this  purpose

being determined in respect of each description of material at (he rates at which the

amount of the advances made under these presents were calculated.

(7) 	 at   if  the   Contractor   shall   at   any  time   make   any   default   in   the

performance  or  observation  in  any  respect  of  any  of  the  terms  and  provisions  of  the

said

agreement  or  of  these presents  the  total  amount  of  the  advance  or  advances that  may

still be  owing  to  the    Government  shall    immediately  on  the  happening  of  such

default  be repayable  by  the  Contractor  to  the  Government  together  with  interest

thereon  at  twelve  percent  per  annum from  the  date  or  respective  dates  of  such

advance or advances to the date or repayment and with all costs, charges, damages

and expenses  incurred  by  the Government  in   or for  the  recovery  thereof or the

enforcement of this  security  or otherwise by reason of (he default of the Contractor

and  any  moneys  so  becoming  due and payable  shall  constitute  a  debt  due  from  the

Contractor to the Government and the Contractor hereby covenants and agrees with

the Government to repay and the same respectively to it accordingly.

(8)  	That the Contractor    hereby    charges    all    the      said materials    with the

repayment to the Government of the said sum of Rupees..............  ...............................

(Rs.    ............................................................................................. )  and any  further  sum

or  sums  which  may  be  advanced  as  aforesaid  and a l l costs  charges  damages  and

expenses payable under these present PROVIDED ALWAYS and it is hereby agreed

and declared that not, withstanding anything in the said agreement and without prejudice

to  the  powers  contained  therein  if  and  whether  the  covenant  for payment  and

repayment hereinbefore contained  shall  become  enforceable and  the  money  owing

shall not be paid to accordingly.

Once  there with  the  Government  may  at  any  time  thereafter  adopt  all  or  any  of

following courses as it may deem best ;-

(a)  	Seize and utilize the said materials or any part thereof in the completion of the

said    works      on    behalf  of  the    Contractor    in    accordance    with  the

provisions    in  that  behalf  contained  in  the  said  agreement  debiting  the

Contractor with the actual cost of effecting such completion the amount due

in      respect      of  advances      under    these      presents      and      crediting    the

Contractor  with  the  value    of  work  done  as  he  had  carried  it  out  in

accordance with the said agreement and at the  rates thereby provided.  If the

balance      is      against    the      Contractor  he      is    to    pay    the    same    to    the

Government on demand.

(b)  	Remove  and  sell  by  public  auction  the  seized  materials  or  any  part  thereof

and out of the moneys arising from the sale retain all the sums aforesaid repayable

to    the    Government  under  these  presents  and  pay  over  the surplus (if any) to the

Contractor.

(c) 	Deduct all or any part of the moneys owing out of the security deposit or any

sum due to the Contractor under the said agreement.

(9)       That except as is expressly provided by the presents interest on the

said advance shall not be payable.

(10)   	That in the event of any conflict between the provisions of these presents and

the  said  agreement  the  provisions  of  these  presents shall  prevail  and  in  the  event  of

any dispute or difference arising over the construction or effect of these presents the

settlement  of  which  has not  been  hereinbefore  expressly  provided  for  the  same  shall

be referred to the Superintending Engineer/Executive District Officer/Officer one grade

higher to officer signed the agreement Circle whose……………. decision shall be final

and  the  provisions  of  the  Arbitration  Act 1940 for  the  time  being in  force  so  far  as

they are applicable shall apply to any such reference.

Singed, sealed and delivered by*

In the presence of

SEAL   	1st witness

2nd witness

Signed, sealed and delivered by*

In the presence of

SEAL

1st witness

2nd witness

Notes on the Conditions of Contract

The Conditions of Contract comprise two parts:

(a)  	Part I  -  	General Conditions of Contract

(b)  	Part II  - 	 Special Conditions of Contract

Over the years, a number of “model” General Conditions of Contract have evolved. The one

used  in  these  Standard  Bidding  Documents  was  prepared  by  the  International  Federation  of

Consulting Engineers (Federation International des Ingenieurs-Conseils, or FIDIC), and is

commonly known as the FIDIC Conditions of Contract. (The used version is the harmonized

Edition March 2006).

The FIDIC Conditions of Contract have been prepared for an ad measurement (unit price or

unit rate) type of contract, and cannot be used without major modifications for other types of

contract, such as lump sum, turnkey, or target cost contracts.

The  standard  text  of  the  General  Conditions  of  Contract  chosen  must  be  retained  intact  to

facilitate  its  reading  and  interpretation  by bidders  and  its  review  by  the procuring  agency.

Any  amendments and  additions  to  the  General  Conditions,  specific  to  the  contract  in  hand,

should be introduced in the Particular Conditions of Contract.

The use of standard conditions of contract for all civil works will ensure comprehensiveness

of coverage, better balance of rights or obligations between procuring agency and Contractor,

general  acceptability  of  its  provisions,  and  savings  in  time  and  cost  for  bid  preparation  and

review, leading to more economic prices.

The  FIDIC  Conditions  of  Contract  are  copyrighted and  may  not  be  copied,  faxed,  or

reproduced.  Without taking any responsibility of its being accurate, Pakistan Engineering

Council  with  prior  consent  of  FIDIC  Secretariat,  has  reproduced  herein  the  FIDIC  General

Conditions  of  Contract  for  reference  purpose only  which  cannot  be  used  by  the  users  for

preparing their bidding documents. The bidding document may include a purchased copy, the

cost  of  which  can  be  retrieved  as  part  of  the  selling  price  of  the  bidding  document.

Alternatively, the FIDIC Conditions of Contract can be referred to in the bidding documents,

and the bidders are advised to obtain copies directly from FIDIC.*

_____________________________________________________________________________________* Add the following text if the bidding documents, as issued, do not include a copy:

“Copies of the FIDIC Conditions of Contract can be obtained from:

To request such permission please contact:

FIDIC CASE POSTALE, CH-1215 Switzerland;

Tel. +41 22 799 49 00;

Fax; +41 22 799 49 01

E-mail: fidic@fidic.org.

Conditions of Contract

for CONSTRUCTION

FOR  BUILDING  AND  ENGINEERING

WORKS DESIGNED BY THE EMPLOYER

Multilateral  Development  Bank  Harmonised  Edition

March 2006

General Conditions

This  publication  is  exclusive  for  use  as  provided  under  a  Licence

Agreement between a Participating Bank and FIDIC, and, consequently,

no  part  of  this  publication  may  be  reproduced,  translated,  adapted,  stored

in  a  retrieval  system  or  communicated,  in  any  form  or  by  any  means,

whether mechanical,  electronic,  magnetic,  photocopying,  recording  or

otherwise, without prior permission in writing from FIDIC. To request such

permission,  please  contact:  FIDIC,  Case  Postal  311,  CH-1215  Geneva

15, Switzerland; Tel. +41 22 799 49 00; Fax +41 22 799 49 01; E-mail:

Fidic@fidic.org. FIDIC is not responsible for the accuracy or completeness

of translations  of  this  publication  unless  such  translation  explicitly

indicates otherwise.

FEDERATION    INTERNATIONALE    DES    INGENIEURS-CONSEILS

INTERNATIONAL    FEDERATION    OF    CONSULTING    ENGINEERS

INTERNATIONALE    VEREINIGUNG    BERATENDER    INGENIEURE

FEDERACION INTERNACIONAL DE INGENIEROS CONSULTORES

General Conditions

CONTENTS

Definitions listed alphabetically

GENERAL PROVISIONS

1.1  Definitions

1.2  Interpretation

1.3  Communications

1.4  Law and Language

1.5  Priority of Documents

1.6  Contract Agreement

1.7  Assignment

1.8  Care and Supply of Documents

1.9  Delayed Drawings or Instructions

1.10  Employer’s Use of Contractor’s Documents

1.11  Contractor’s Use of Employer’s Documents

1.12  Confidential Details

1.13  Compliance with Laws

1.14  Joint and Several Liability

1.15  Inspections and Audit by the Bank

2  THE EMPLOYER

2.1  Right of Access to the Site

2.2  Permits, Licenses or Approvals

2.3  Employer’s Personnel

2.4  Employer’s Financial Arrangements

2.5  Employer’s Claims

3  THE ENGINEER

3.1  Engineer’s Duties and Authority

3.2  Delegation by the Engineer

3.3  Instructions of the Engineer

3.4  Replacement of the Engineer

3.5  Determinations

4  THE CONTRACTOR

4.1  Contractor’s General Obligations

4.2  Performance Security

4.3  Contractor’s Representative

4.4  Subcontractors

4.5  Assignment of Benefit of Subcontract

4.6  Co-operation

4.7  Setting Out

4.8  Safety Procedures

4.9  Quality Assurance

4.10  Site Data

4.11  Sufficiency of the Accepted Contract Amount

4.12  Unforeseeable Physical Conditions

4.13  Rights of Way and Facilities

4.14  Avoidance of Interference

4.15  Access Route

4.16  Transport of Goods

4.17  Contractor’s Equipment

4.18  Protection of the Environment

4.19  Electricity, Water and Gas

4.20  Employer’s Equipment and Free-Issue Materials

4.21  Progress Reports

4.22  Security of the Site

4.23  Contractor’s Operations on Site

4.24  Fossils

5  NOMINATED SUBCONTRACTORS

5.1  Definition of “nominated Subcontractor”

5.2  Objection to Nomination

5.3  Payments to nominated Subcontractors

5.4  Evidence of Payments

6  STAFF AND LABOUR

6.1  Engagement of Staff and Labour

6.2  Rates of Wages and Conditions of Labour

6.3  Persons in the Service of Employer

6.4  Labour Laws

6.5  Working Hours

6.6  Facilities for Staff and Labour

6.7  Health and Safety

6.8  Contractor’s Superintendence

6.9  Contractor’s Personnel

6.10  Records of Contractor’s Personnel and Equipment

6.11  Disorderly Conduct

6.12  Foreign Personnel

6.13  Supply of Foodstuffs

6.14  Supply of Water

6.15  Measures against Insect and Pest Nuisance

6.16  Alcoholic Liquor or Drugs

6.17  Arms and Ammunition

6.18  Festival and Religious Customs

6.19  Funeral Arrangements

6.20  Prohibition of Forced or Compulsory Labour

6.21  Prohibition of Harmful Child Labour

6.22  Employment Records of Workers

7  PLANT, MATERIALS AND WORKMANSHIP

7.1  Manner of Execution

7.2  Samples

7.3  Inspection

7.4  Testing

7.5  Rejection

7.6  Remedial Work

7.7  Ownership of Plant and Materials

7.8  Royalties

8  COMMENCEMENT, DELAYS AND SUSPENSION ...........................................................................................................

8.1  Commencement of Works

8.2  Time for Completion

8.3  Programme

8.4  Extension of Time for Completion

8.5  Delays Caused by Authorities

8.6  Rate of Progress

8.7  Delay Damages

8.8  Suspension of Work

8.9  Consequences of Suspension

8.10  Payment for Plant and Materials in Event of Suspension

8.11  Prolonged Suspension

8.12  Resumption of Work

9  TESTS ON COMPLETION

9.1  Contractor’s Obligations

9.2  Delayed Tests

9.3  Retesting

9.4  Failure to Pass Tests on Completion

10  EMPLOYER’S TAKING OVER

10.1  Taking Over of the Works and Sections

10.2  Taking Over of Parts of the Works

10.3  Interference with Tests on Completion

10.4  Surfaces Requiring Reinstatement

11  DEFECTS LIABILITY

11.1  Completion of Outstanding Work and Remedying Defects

11.2  Cost of Remedying Defects

11.3  Extension of Defects Notification Period

11.4  Failure to Remedy Defects

11.5  Removal of Defective Work

11.6  Further Tests

11.7  Right of Access

11.8  Contractor to Search

11.9  Performance Certificate

11.10     Unfulfilled Obligations

11.11     Clearance of Site

12  MEASUREMENT AND EVALUATION

12.1  Works to be Measured

12.2  Method of Measurement

12.3  Evaluation

12.4  Omissions

13  VARIATIONS AND ADJUSTMENTS

13.1  Right to Vary

13.2  Value Engineering

13.3  Variation Procedure

13.4  Payment in Applicable Currencies

13.5  Provisional Sums

13.6  Day work

13.7  Adjustments for Changes in Legislation

13.8  Adjustments for Changes in Cost

14  CONTRACT PRICE AND PAYMENT

14.1  The Contract Price

14.2  Advance Payment

14.3  Application for Interim Payment Certificates

14.4  Schedule of Payments

14.5  Plant and Materials intended for the Works

14.6  Issue of Interim Payment Certificates

14.7  Payment

14.8  Delayed Payment

14.9  Payment of Retention Money

14.10 Statement at Completion

14.11 Application for Final Payment Certificate

14.12 Discharge

14.13 Issue of Final Payment Certificate

14.14 Cessation of Employer’s Liability

14.15 Currencies of Payment

15  TERMINATION BY EMPLOYER

15.1  Notice to Correct

15.2  Termination by Employer

15.3  Valuation at Date of Termination

15.4  Payment after Termination

15.5  Employer’s Entitlement to Termination for Convenience

15.6  Corrupt or Fraudulent Practices

16  SUSPENSION AND TERMINATION BY CONTRACTOR

16.1  Contractor’s Entitlement to Suspend Work

16.2  Termination by Contractor

16.3  Cessation of Work and Removal of Contractor’s Equipment

16.4  Payment on Termination

17  RISK AND RESPONSIBILITY

17.1  Indemnities

17.2  Contractor’s Care of the Works

17.3  Employer’s Risks

17.4  Consequences of Employer’s Risks

17.5  Intellectual and Industrial Property Rights

17.6  Limitation of Liability

17.7  Use of Employer’s Accommodation/Facilities

18  INSURANCE

18.1  General Requirements for Insurances

18.2  Insurance for Works and Contractor’s Equipment

18.3  Insurance against Injury to Persons and Damage to Property

18.4  Insurance for Contractor’s Personnel

19   FORCE MAJEURE

19.1  Definition of Force Majeure

19.2  Notice of Force Majeure

19.3  Duty to Minimize Delay

19.4  Consequences of Force Majeure

19.5  Force Majeure Affecting Subcontractor

19.6  Optional Termination, Payment and Release

19.7  Release from Performance

20  CLAIMS, DISPUTES AND ARBITRATION

20.1  Contractor’s Claims

20.2  Appointment of the Dispute Board

20.3  Failure to Agree on the Composition of the Dispute Board

20.4  Obtaining Dispute Board’s Decision

20.5  Amicable Settlement

20.6  Arbitration

20.7  Failure to Comply with Dispute Board’s Decision

20.8  Expiry of Dispute Board’s Appointment

APPENDIX: DISPUTE BOARD

General Conditions of Dispute Board Agreement

Annex: Procedural Rules

INDEX OF SUB-CLAUSES    77

Definitions listed alphabetically

1.1.4.1  	Accepted Contract Amount  		1.1.4.7  	Interim Payment Certificate

1.1.2.11  	Bank 1.1.6.5 Laws

1.1.3.1  	Base Date  				1.1.1.3  	Letter of Acceptance

1.1.1.9  	Bill of Quantities  			1.1.1.4 	 Letter of Tender

1.1.2.12  	Borrower  				1.1.4.8 	 Local Currency

1.1.3.2  	Commencement Date  		1.1.5.3  	Materials

1.1.1.1  	Contract 1.1.2.1 Party

1.1.1.2  	Contract Agreement  			1.1.4.9  	Payment Certificate

1.1.1.10 	 Contract Data  			1.1.3.8  	Performance Certificate

1.1.4.2  	Contract Price  			1.1.6.6  	Performance Security

1.1.2.3  	Contractor  				1.1.5.4 	 Permanent Works

1.1.6.1  	Contractor’s Documents  		1.1.5.5  	Plant

1.1.5.1  	Contractor’s Equipment  		1.1.4.10  	Provisional Sum

1.1.2.7  	Contractor’s Personnel  		1.1.4.11  	Retention Money

1.1.2.5  	Contractor’s Representative  		1.1.1.7  	Schedules

1.1.4.3  	Cost  					1.1.1.9  	Schedule, Payment Currencies

1.1.6.2  	Country  				1.1.5.6  	Section

1.1.2.9  	DB  					1.1.6.7  	Site

1.1.3.9  	day  					1.1.1.5  	Specification

1.1.1.9  	Daywork Schedule  			1.1.4.12  	Statement

1.1.3.7  	Defects Notification Period  		1.1.2.8  	Subcontractor

1.1.1.6  	Drawings  				1.1.3.5  	Taking-Over Certificate

1.1.2.2  	Employer  				1.1.5.7  	Temporary Works

1.1.6.3  	Employer’s Equipment  		1.1.1.8  	Tender

1.1.2.6  	Employer’s Personnel  		1.1.3.6  	Tests after Completion

1.1.2.4  	Engineer  				1.1.3.4 	 Tests on Completion

1.1.2.10  	FIDIC  				1.1.3.3  	Time for Completion

1.1.4.4 	Final Payment Certificate  		1.1.6.8  	Unforeseeable

1.1.4.5  	Final Statement  			1.1.6.9  	Variation

1.1.6.4  	Force Majeure  			1.1.5.8  	Works

1.1.4.6  	Foreign Currency  			1.1.3.9 	 year

1.1.5.2  	Goods

General Conditions

General Provisions

1.1

Definitions

In the Conditions of Contract (“these Conditions”), which include Particular Conditions,

Parts  A  and  B,  and  these  General  Conditions,  the  following  words  and  expressions

shall    have    the    meanings    stated.    Words    indicating    persons    or    parties    include corporations and other legal entities, except where the context requires otherwise.

1.1.1

The Contract  1.1.1.1  “Contract” means the Contract Agreement, the Letter of Acceptance, the

Letter of Tender, these Conditions, the Specification, the Drawings, the

Schedules, and the further documents (if any) which are listed in the

Contract Agreement or in the Letter of Acceptance.

1.1.1.2  “Contract Agreement” means the contract agreement referred to in Sub-

Clause 1.6 [ Contract Agreement ].

1.1.1.3  “Letter of Acceptance” means the letter of formal acceptance, signed by

the  Employer,  of  the  Letter  of  Tender,  including  any  annexed  memoranda

comprising  agreements  between  and  signed  by  both  Parties.  If  there  is  no

such  letter  of  acceptance,  the  expression  “Letter  of  Acceptance”  means  the

Contract  Agreement  and  the  date  of  issuing  or  receiving  the  Letter  of

Acceptance means the date of signing the Contract Agreement.

1.1.1.4  “Letter of Tender” means the document entitled letter of tender or letter of

bid,  which  was  completed  by  the  Contractor  and  includes  the  signed  offer to  the

Employer for the Works.

1.1.1.5  “Specification” means the document entitled specification, as included in

the  Contract,  and  any  additions  and  modifications  to  the  specification  in  accordance

with the Contract. Such document specifies the Works.

1.1.1.6  “Drawings” means the drawings of the Works, as included in the Contract,

and any additional and modified drawings issued by (or on behalf of) the Employer in

accordance with the Contract.

1.1.1.7  “Schedules” means the document(s) entitled schedules, completed by the

Contractor and submitted with the Letter of Tender, as included in the Contract. Such

document  may  include  the  Bill  of  Quantities,  data,  lists,  and schedules  of  rates  and/or prices.

1.1.1.8  “Tender” means the Letter of Tender and all other documents which the

Contractor submitted with the Letter of Tender, as included in the Contract.

1.1.1.9  “Bill of Quantities”, “Daywork Schedule” and “Schedule of Payment

Currencies” mean  the documents so  named (if any)  which  are comprised in the

Schedules.

1.1.1.10   “Contract Data” means the pages completed by the Employer entitled

contract data which constitute Part A of the Particular Conditions.

1.1.2

Parties and Persons	1.1.2.1  “Party” means the Employer or the Contractor, as the context requires.

1.1.2.2  “Employer” means the person named as employer in the Contract Data

and the legal successors in title to this person.

1.1.2.3  “Contractor” means the person(s) named as contractor in the Letter of

Tender  accepted  by  the  Employer  and  the  legal  successors  in title  to  this

person(s).

1.1.2.4  “Engineer” means the person appointed by the Employer to act as the

Engineer  for  the  purposes  of  the  Contract  and  named  in  the  Contract  Data, or other  person  appointed  from  time  to  time  by  the  Employer  and  notified  to the Contractor under Sub-Clause 3.4 [ Replacement of the Engineer ].

1.1.2.5  “Contractor’s  Representative”  means  the  person  named  by  the

Contractor in the Contract or appointed from time to time by the Contractor under

Sub-Clause  4.3  [  Contractor’s  Representative  ],  who  acts  on  behalf  of  the

Contractor.

1.1.2.6  “Employer’s Personnel” means the Engineer, the assistants referred to in

Sub-Clause 3.2 [ Delegation by the Engineer ] and all other staff, labour and other

employees  of  the  Engineer  and  of  the Employer;  and  any  other personnel

notified  to  the  Contractor,  by  the  Employer  or  the  Engineer,  as Employer’s

Personnel.

1.1.2.7  “Contractor’s Personnel” means the Contractor’s Representative and all

personnel  whom  the  Contractor  utilizes  on  Site,  who  may include  the  staff,

labour  and  other  employees  of  the  Contractor  and  of  each  Subcontractor;  and

any other personnel assisting the Contractor in the execution of the Works.

1.1.2.8  “Subcontractor”  means  any  person  named  in  the  Contract  as  a

subcontractor,  or  any  person  appointed  as  a  subcontractor,  for  a  part  of  the

Works; and the legal successors in title to each of these persons.

1.1.2.9  “DB” means the person or three persons appointed under Sub-Clause 20.2

[ Appointment of the Dispute Board ] or Sub-Clause 20.3 [ Failure to Agree on

the Composition of the Dispute Board ].

1.1.2.10  “FIDIC” means the Federation International des Engineer-Councils,

International federation of consulting engineers.

1.1.2.11  “Bank” means the financing institution (if any) named in the Contract Data.

1.1.2.12  “Borrower” means the person (if any) named as the borrower in the

Contract Data.

1.1.3

Dates, Tests, Periods and Completion

1.1.3.1 “Base Date” means the date 28 days prior to the latest date for submission and completion of the Tender.

1.1.3.2  	“Commencement Date” means the date notified under Sub-Clause 8.1

[ Commencement of Works ].

1.1.3.3  “Time for Completion” means the time for completing the Works or a Section (as the case may be) under Sub-Clause 8.2 [ Time for Completion ], as stated in the Contract

Data (with any extension under Sub-Clause 8.4 [ Extension of Time for Completion ]),calculated from the Commencement Date.

1.1.3.4  “Tests on Completion” means the tests which are specified in the Contract or agreed by both Parties or instructed as a Variation, and which are carried out under Clause 9 [ Tests on Completion ] before the Works or a Section (as the case may be) are taken over by the Employer.

1.1.3.5  “Taking-Over Certificate” means a certificate issued under Clause 10

[ Employer’s Taking Over ].

1.1.3.6  “Tests after Completion” means the tests (if any) which are specified in the Contract  and  which  are  carried  out  in  accordance  with  the  Specification  after the Works or a Section (as the case may be) are taken over by the Employer.

1.1.3.7  “Defects Notification Period” means the period for notifying defects in the Works    or    a    Section   (as    the    case    may    be)    under                Sub-Clause    11.1

[  Completion  of  Outstanding  Work  and  Remedying  Defects  ],  which  extends over  twelve  months  except  if  otherwise  stated  in  the  Contract  Data  (with  any

extension    under    Sub-Clause 11.3  [Extension    of    Defects    Notification

Period  ]),  calculated  from  the  date  on  which  the  Works  or  Section  is

completed  as  certified  under  Sub-Clause  10.1  [  Taking  Over  of  the Works

and Sections ].

1.1.3.8   “Performance Certificate” means the certificate issued under Sub-Clause

11.9  [ Performance Certificate ].

1.1.3.9  “day” means a calendar day and “year” means 365 days.

1.1.4

Money and Payments  	1.1.4.1  “Accepted Contract Amount” means the amount accepted in the Letter of

Acceptance  for  the  execution  and  completion  of  the  Works  and  the

Remedying of any defects.

1.1.4.2 “Contract  Price”  means  the  price  defined  in  Sub-Clause  14.1 [ The

Contract Price ], and includes adjustments in accordance with the Contract.

1.1.4.3  “Cost” means all expenditure reasonably incurred (or to be incurred) by the

Contractor,  whether  on  or  off  the  Site,  including  overhead  and  similar

charges, but does not include profit.

1.1.4.4  “Final Payment Certificate” means the payment certificate issued under

Sub-Clause 14.13 [ Issue of Final Payment Certificate ].

1.1.4.5  “Final Statement” means the statement defined in Sub-Clause 14.11

[ Application for Final Payment Certificate ].

1.1.4.6  “Foreign Currency” means a currency in which part (or all) of the Contract

Price is payable, but not the Local Currency.

1.1.4.7  “Interim Payment Certificate” means a payment certificate issued under

Clause  14  [  Contract  Price  and  Payment  ],  other  than  the  Final  Payment

Certificate.

1.1.4.8  “Local Currency” means the currency of the Country.

1.1.4.9  “Payment Certificate” means a payment certificate issued under Clause 14

[ Contract Price and Payment].

1.1.4.10  “Provisional Sum” means a sum (if any) which is specified in the Contract as a  provisional  sum,  for  the  execution  of  any  part  of  the  Works  or  for  the

supply  of  Plant,  Materials  or  services  under  Sub-Clause  13.5  [  Provisional

Sums ].

1.1.4.11  “Retention Money” means the accumulated retention moneys which the

Employer retains under Sub-Clause 14.3 [ Application for Interim Payment

Certificates ] and pays under Sub-Clause

14.9  [ Payment of Retention Money ].

1.1.4.12  “Statement” means a statement submitted by the Contractor as part of an application, under Clause 14 [ Contract Price and Payment ], for a payment

certificate.

1.1.5

Works and Goods  		1.1.5.1  “Contractor’s Equipment” means all apparatus, machinery, vehicles and

other things required for the execution and completion of the Works and the

remedying of any defects. However, Contractor’s Equipment excludes

Temporary Works, Employer’s Equipment (if any), Plant, Materials and any

other things intended to form or forming part of the Permanent Works.

1.1.5.2  “Goods” means Contractor’s Equipment, Materials, Plant and Temporary

Works, or any of them as appropriate.

1.1.5.3  “Materials” means things of all kinds (other than Plant) intended to form or forming part of the Permanent Works, including the supply-only materials (if any) to be supplied by the Contractor under the Contract.

1.1.5.4  “Permanent Works” means the permanent works to be executed by the

Contractor under the Contract.

1.1.5.5  “Plant” means the apparatus, machinery and vehicles intended to form or forming part of the Permanent Works, including vehicles purchased for the

Employer and relating to the construction or operation of the Works.

1.1.5.6  “Section” means a part of the Works specified in the Contract Data as a

Section (if any).

1.1.5.7  “Temporary Works” means all temporary works of every kind (other than

Contractor’s Equipment) required on Site for the execution and completion

of the Permanent Works and the remedying of any defects.

1.1.5.8  “Works” mean the Permanent Works and the Temporary Works, or either of them as appropriate.

1.1.6

Other Definitions  1.1.6.1  “Contractor’s Documents” means the calculations,

computer programs

and  other  software,  drawings,  manuals,  models  and  other  documents  of  a

technical nature (if any) supplied by the Contractor under the Contract.

1.1.6.2   “Country” means the country in which the Site (or most of it) is located,  where the Permanent Works are to be executed.

1.1.6.3  “Employer’s Equipment” means the apparatus, machinery and vehicles (if any) made available by the Employer for the use of the Contractor in the

execution of the Works, as stated in the Specification; but does not include

Plant which has not been taken over by the Employer.

1.1.6.4  “Force Majeure” is defined in Clause 19 [ Force Majeure ].

1.1.6.5  “Laws” means all national (or state) legislation, statutes, ordinances and otherlaws, and regulations and by-laws of any legally constituted public authority.

1.1.6.6  “Performance Security” means the security (or securities, if any) under

Sub-Clause 4.2 [ Performance Security ].

1.1.6.7   “Site” means the places where the Permanent Works are to be executed, including storage and working areas, and to which Plant and Materials are to be

delivered, and any other places as may be specified in the Contract as forming

part of the Site..

1.1.6.8  “Unforeseeable” means not reasonably foreseeable by an experienced

contractor by the Base Date.

1.1.6.9  “Variation” means any change to the Works, which is instructed or

approved as a variation under Clause 13 [ Variations and Adjustments ].

1.2 Interpretation 	 In the Contract, except where the context requires otherwise:

(a)  	words indicating one gender include all genders;

(b)       words indicating the singular also include the plural and words indicating the plural also include the singular;

(c)  	provisions including the word “agree”, “agreed” or “agreement” require the agreement to be record in writing;

(d) 	 “written”  or  “in  writing”  means  hand-written,  type-written,  printed  or electronically made, and resulting in a permanent record; and

(e)  	the word “tender” is synonymous with “bid”, and “tenderer” with “bidder” and the words “tender documents” with “bidding documents".

The marginal words and other headings shall not be taken into consideration in

the interpretation of these Conditions.

In these Conditions, provisions including the expression “Cost plus profit” require this profit  to  be  one-twentieth (5%) of this Cost unless otherwise indicated  in  the Contract Data.

1.3

Communications  	Wherever these Conditions provide for the giving or issuing of approvals, certificates, consents,  determinations,  notices,  requests  and  discharges,  these

communications

shall be:

(a)   in writing and delivered by hand (against receipt), sent by mail or courier, or transmitted using  any  of  the  agreed  systems  of  electronic  transmission  as stated in the Contract Data; and

(b)  delivered, sent or transmitted to the address for the recipient’s communications

as stated in the Contract Data. However:

(i)  if the recipient gives notice of another address, communications shall

thereafter be delivered accordingly; and

(ii)  if the recipient has not stated otherwise when requesting an approval or

consent, it may be sent to the address from which the request was issued.

Approvals, certificates, consents and determinations shall not be unreasonably

withheld or delayed. When a certificate is issued to a Party, the certifier shall send a copy to the other Party. When a notice is issued to a Party, by the other Party or the

Engineer, a copy shall be sent to the Engineer or the other Party, as the case may be.

1.4

Law and Language

The  Contract  shall  be  governed  by  the  law  of  the  country  or  other  jurisdiction stated in the Contract Data.

The ruling language of the Contract shall be that stated in the Contract Data.

The language for communications shall be that stated in the Contract Data. If no

language is stated there, the language for communications shall be the ruling

language of the Contract.

1.5

Priority of Documents

The documents forming the Contract are to be taken as mutually explanatory of

one another.  For  the  purposes  of  interpretation,  the  priority  of  the  documents shall be in accordance with the following sequence:

(a)  	the Contract Agreement (if any),

(b) 	 the Letter of Acceptance,

(c)  	the Tender,

(d)  	the Particular Conditions - Part A,

(e) 	the Particular Conditions - Part B,

(f)  	these General Conditions,

(g)  	the Specification,

(h)  	the Drawings, and

(i)  	the Schedules and any other documents forming part of the Contract.

If an ambiguity or discrepancy is found in the documents, the Engineer shall issue any necessary clarification or instruction.

TABLE OF CONTENTS

PART II  - SPECIAL/PARTICULAR CONDITIONS OF

CONTRACT

Clause  					Title  						Page

1.1 	Definitions

3.1 	Engineer‟s Duties and Authority 							145

145

4.3  	Contractor‟s Representative

6.10	 Records of Contractor‟s Personnel and equipment  					145

7.9  	 Use of Pakistani Materials and Services						145

8.1 	Commencement of Works 								145

8.11  	Prolonged Suspension									145

8.3 	Programme

13.1 	Right to vary

13.3 	Variation procedure

13.8 	Adjustment for changes in cost

14.1	Contract Price

14.2	Advance Payment

14.5 	Plants and Materials intended for Works

14.8 	Delayed Payments

1	5.2	Termination by Employer/Procuring Agency

15.6	Corrupt and fraudulent Practices (Integrity Pact).

16.4	Payment on Termination

17.3 	Employer‟s/Procuring Agency‟s Risks

18.1	General Requirements for Insurance

19.6	Optional Termination, Payment and release by the Employer

20.1	Contractor‟s Claims

20.2	Appointment of the Dispute Board / Notification of the Committee

20.3	Failure to agree on the composition of the Dispute Board.

20.4	Obtaining Dispute Board‟s Decision

20.5 	Amicable Settlement.

20.6 	Arbitration

20.7 	Failure to comply with Dispute Board‟s Decision

20.8	Expiry of Dispute Board‟s Appointment

APPE

NDIX. General Conditions of Dispute Board Agreement

Annex	 PROCEDURAL RULES

PART II - SPECIAL /PARTICULAR CONDITIONS OF CONTRACT

1.1  Definitions

1.1.1.4  	“Form of Bid” is synonymous with “Letter of Tender”.

1.1.1.5   	“Bid” is synonymous with “Tender”.

1.1.1.10 	“Bidding” is synonymous with “contract”.

The following paragraph is added:

1.1.1.11“Programme” means the programme to be submitted by the contractor in accordance with

Sub-Clause 8.3 and any approved revisions thereto.

1.12.2    	 “Employer” is synonymous with “Procuring Agency”

1.1.2.9 “DB” is synonymous with “Committee”.

1.1.3.1 Replace 28 days by 7 days in LCB and 15 days in ICB..

1.1.3.7   “Defects notification Period” is synonymous with “Defects liability Period”.

1.15       Inspections and Audit by the Bank

Deleted

Procuring  Agency  can  retain  this  clause  with  or  without  changes,  in  case  of  contracts

under Project, Bank and donor’s programme.

3.1  Engineer’s Duties and Authority.

The following paragraph is added after duties:

Procuring  agency  shall  ensure  that  the  Engineer‟s  Representative/Staff  is  a  professional

engineer as defined in the Pakistan Engineering Council Act 1975 (V of 1976)

4.3  Contractor’s Representative

The following text is to be added after last line:

The contractor‟s authorised representative and his other professional engineers working at site

shall register themselves with the Pakistan Engineering Council.

6.10      Records of Contractor’s Personnel and Equipment

The following paragraph is added:

The Contractor shall, upon request by the Engineer at any time in relation to any item

of hired Contractor‟s Equipment, forthwith notify the Engineer in writing the name and address

of the Owner of the equipment and shall certify that the agreement for the hire thereof contains

a provision in accordance with the requirements set forth above.

those items mentioned in the Appendix –C (B).

Similarly  reduction  in  the  cost  of  these  materials  will  also  be  recovered  from  the

contractor accordingly

14.1     The Contract Price

Sub-para (d) is deleted.

14.2   Advance Payment

The Text is deleted and replaced with following:

Advance Payment/Mobilization Advance shall be made available to the Contractor by

the procuring agency on following conditions:

Mobilization Advance/Advance Payment

(i)   Mobilization  advance  up  to  10  %  of  the  Contract  Price  may  be  paid  by  the  procuring

agency  to the  Contractor  on  the  works  costing  Rs2.5  million  or  above  on  following

conditions:

a.   	on submission by the Contractor of a mobilization advance guarantee for the

full amount of the advance in the specified form, from a Scheduled Bank in

Pakistan, acceptable to the procuring agency;

b.  	 contractor shall pay interest on the mobilization advance at the rate of 10% per

annum on the advance; and

(ii)  	This Advance including the interest shall be recovered in 5 equal installments

from the 5 R.A bills and in case the number of bills is less than 5 then 1/5 of

the advance inclusive of the interest thereon shall be recovered from each bill

and  the  balance  together  with  interest  be  recovered  from  the  final  bill.  It  may

be insured that there is sufficient amount in the final bill to enable recovery of

the Mobilization Advance.

14.5     Plants and Materials intended for Works

Add the following paragraph as sub-clause 14.5 (d) for Secured Advance on non – perishable

materials and sub-clauses (a), (b) and (c) will be applicable for plants only :-

(I)  	 The Contractor shall be entitled to receive from the procuring agency Secured Advance against an  INDENTURE  BOND  in  Public  Works  Account  Form  No.31                      (Fin.  R.  Form  No.  2)

acceptable to the procuring agency of such sum as the Engineer may consider proper in respect

of non-perishable materials brought at the site but not yet incorporated in the Permanent Works

provided that:

(i) 	  The materials are in accordance with the specifications for the permanent works;

(ii)   	Such  materials  have  been  delivered  to  the  site  and  are  properly  stored  and  protected

against  loss  or  damage  or  deterioration  to  the  satisfaction  and  verification  of  the

Engineer/Assistant Engineer but at the risk and cost of the Contractor;

(iii)  	 The Contractor‟s records of the requirements, orders, receipts and use of materials are

kept  in  a  form  approved  by  the  Engineer,  and  such  records shall  be  available  for

inspection by the Engineer;

(iv)	   The  Contractor  shall  submit  with  his  monthly  statement  the  estimated  value  of  the

materials on site together with such documents as may be required by the Engineer for

the  purpose  of    valuation  of  materials  and  providing  evidence  of  ownership  and

payment therefore;

(v)  	 Ownership of such materials shall be deemed to vest in the procuring agency and these

materials  shall  not  be  removed  from  the  site  or  otherwise  disposed  of  without  written

permission of the procuring agency;

(vi)  	The sum payable for such materials on site shall not exceed 75 % of the (i) landed cost

of imported materials, or (ii) ex-factory / ex-warehouse price of locally manufactured or

produced materials, or (iii) market price of stands other materials;

(vii) 	  Secured Advance shall not be allowed unless and until the previous advance, if any, is

fully recovered;

(viii) 	 Detailed account of advances must be kept in part II of running account bill or a

separate statement; and

(ix)   	Secured  Advance  may  be  permitted  only  against  materials/quantities  anticipated  to  be

consumed / utilized on the work within a period of 3 months from the date of issue of

secured  advance  and  in  no  case  for  full  quantities  of  materials  for  the  entire

work/contract.

(II) 	  Recovery of Secured Advance:

Secured Advance paid on non-perishable materials to the Contractor under the above

provisions  shall  be  effected  from  the  monthly  payments  on  actual  consumption  basis,

but  not  later  than  period  specified in  the  rules  not  more  than  three  months  (even  if

Unutilized);

14.8   Delayed Payment

Second Para is replaced with following text:

In the event of the failure of the Procuring Agency to make the payment within the time

Stated, the procuring agency shall pay to the contractor in case of ICB contracts only,

the compensation at rate of KIBOR+2% per annum in local currency and Libor+1% for

foreign currency, upon all sums to be paid from the date of which the same would have

been paid.

15.2     Termination by Employer

The following Para is added at the end of the sub-clause:

Provided  further,  that  in  addition  to the  action  taken  by  the  procuring  agency

against the Contractor under this Clause, the procuring agency may also refer the case

of default of the Contractor to Pakistan Engineering Council for punitive action under

the  Construction  and  Operation  of  Engineering  Works  Bye-Laws  1987,  as  amended

from time to time.

15.6     Corrupt and fraudulent Practices.

The following text is to be added as 3rd paragraph:

Successful Contractor has to provide Integrity Pact (for contracts worth

Rs.10.0 million and above).

If  the  Contractor  or  any  of  his  Subcontractors,  agents  or  servants  is  found  to  have

violated  or  involved  in  violation  of  the  Integrity  Pact  signed  by  the  Contractor  as

Appendix-L to his Bid, then the procuring agency shall be entitled to:

(a)	 Recover  from  the  Contractor  an  amount  equivalent  to  ten  times  the  sum  of  any

Commission, gratification, bribe, finder’s fee or kickback given by the Contractor or

Any of his Subcontractors, agents or servants;

(b) 	 Terminate the Contract; and

(c)  	Recover from the Contractor any loss or damage to the procuring agency as a result of

such termination or of any other corrupt business practices of the Contractor or any of

his Subcontractors, agents or servants.

The termination under sub-Para (b) of this Sub-Clause shall proceed in the manner prescribed

under  sub-clauses 15.2 &  15.5  and  the  payment  under  Sub-Clause  15.4  shall  be  made  after having  deducted  the  amounts  due  to  the  procuring  agency  under  Sub-Para  (a)  and  (c)  of  this Sub-Clause.

16.4      Payment on Termination

Sub-paragraph (c) is deleted.

17.3 	 Employer’s/ Procuring Agency’s Risks

Sub-Clause 17.3 (h) is deleted.

The following text is added in Clause 18.1 (GCC):

18.1 	 General Requirements for Insurance

The  contractor  shall  be  obliged  to  place  all  insurances  relating  to  the contract  (including,  but not  limited  to,  the  insurances  referred  to  in  Clauses 18.1,18.2,18.3,18.4)  with  Insurance

Company having at least AA rating from PACRA/JCR in favour of the Employer//Procuring Agency valid for a period 28 days after beyond the Bid Validity date.

Costs of such insurances shall be borne by the contractor.

19.6      Optional Termination, Payment and release by the Employer

Sub-clauses (c), (d) and (e) are deleted.

20.6     Arbitration

Text will be replaced as under;

Any dispute in respect of which:

(a)   	The decision, of the Dispute Board has not become final and binding pursuant to sub-clause 20.2, and

(b)       Amicable settlement has not been reached within the period stated in sub-clause 20.5,

shall  be  finally  settled, under  the  provisions  of  the  Arbitration  Act,  1940  as  amended  or  any statutory  modification/Rules  of  Conciliation  And  Arbitration PEC  Islamabad or  re-enactment

Thereof for the time being in force.

The place of arbitration shall be …………………, in Sindh Province.

Procuring  Agency  can  retain  this  clause  without  changes,  in  case  of  contracts  under  Project,

Bank and donor’s programme except the place of arbitration shall be …………………, in Sindh Province.

Annex   PROCEDURAL RULES

Procuring  Agency  can  retain  these  rules  with  or  without  changes,  in  case  of  contracts  under Project, Bank and donor’s programme.

PART II –SPECIAL/PARTICULAR CONDITIONS OF CONTRACT

INDEX              						 		 CLAUSE

Adjustment for changes in cost                                                          13.8

Advance Payment                                                                              14.2

Amicable Settlement.                                                                         20.5

Appointment of the Dispute Board / Notification of the Committee20.2

Arbitration                                                                                          20.6

Commencement of Works                                                                   8.1

Contractor’s Representative                                                                 4.3

Contractor’s Claims                                                                           20.1

Contract Price                                                                                    14.1

Corrupt and fraudulent Practices (Integrity Pact).                             15.6

Definitions                                                                                            1.1

Delayed Payments                                                                              14.8

Employer’s/Procuring Agency’s Risks                                              17.3

Engineer’s Duties and Authority                                                         3.1

Expiry of Dispute Board’s Appointment                                           20.8

Failure to agree on the composition of the Dispute Board.              20.3

Failure to comply with Dispute Board’s Decision                            20.7

General Conditions of Dispute Board Agreement                   Appendix

General Requirements for Insurance                                                 18.1

Optional Termination, Payment and release by the Employer          19.6

Obtaining Dispute Board’s Decision                                                20.4

Payment on Termination                                                                   15.6

Plants and Materials intended for Works                                          14.5

PROCEDURAL RULES                                                             Annex

Prolonged Suspension                                                                        8.11

Programme                                                                                         8.3

Records of Contractor’s Personnel and equipment                            6.10

Right to vary                                                                                       13.1

Termination by Employer/Procuring Agency                                    15.2

Use of Pakistani Materials and Services                                             7.9

Variation procedure                                                                            13.3

SPECIFICATIONS

DRAWINGS