GOVERNMENT OF SINDH

PUBLIC HEALTH ENGINEERING DIVISION DADU

STANDARD BIDDING DOCUMENTS

PROCUREMENT OF WORKS (SPPRA BIDDING DOCUMENTS)

For Contracts (Small) amounting between Rs. 4.0 (M) to Rs. 50.00  (M).

Name of Work:		(01) Construction of Compound Wall i/c Surface Drain,

C.C Block for Various Mohalla Zone-“A” under Basic

Human Facilities Drainage Scheme Johi .

N.I.T NO: & DATE:		NO: TC/  1334      /   dated;-15-12-2016

DATE OF ISSUE:                  10-01-2017

DATE OF OPENING:           11-01-2017

TENDER ISSUED TO:      .	     							.

D.R.NO: & DATE:            .	     							.

STANDARD BIDDING DOCUMENT IS INTENDED AS MODEL FOR

ADMEASUREMENTS (PERCENTAGE RATE FOR UNIT RATES IN A BILL OF QUANTITIES TYPES OF CONTRACT THE MAIN TEXT REFERS TO ADMEASUREMENTS CONTRACTOS.

EXECUTIVE ENGINEER

Public Health Engineering Division

DADU

BIDDING DATA

(This section  should be filled in by the office of the Executive Engineer,

Public Engineering Division Dadu, before issuance of the bidding documents).

| (a) | Name of Procuring Agency:- | The Executive Engineer Public Health Engineering Division Dadu. |
| --- | --- | --- |
| (b) | Brief Description of works:- | (01) Construction of Compound Wall i/c Surface Drain,C.C Block for Various Mohalla Zone-“A” under Basic Human Facilities Drainage Scheme Johi . |
| © | Procuring Agency Address:- | The Executive Engineer Public Health Engineering Division Dadu. Near Gharibabad Muhalla Dadu. |
| (d) | Estimated Cost:- | Rs: 12.400 Million |
| (e) | Amount of Bid Security:- | Rs:6,20,000/- |
| (f) | Period of Bid Validity (Days):- | (90 days) |
| (g) | Security Deposit (i/c Bid Security):- | (10%) |
| (h) | Percentage, if any, to be deducted from bills:- | (7.50% Income Tax) & (8% Security Deposit). |
| (i) | Deadline for submission of Bids along with time:- | 10-01-2017 @ 1.30 PM |
| (j) | Venue, time & date of Bid Opening:- | 11-01-2017 @ 2.00 PM |
| (k) | Time for completion from written order of commence:- | (24 Months) |
| (l) | Liquidity Damages:- | (1% on estimated cost per day subject to minimum of 10%) |
| (m) | Deposit receipt No: date & Amount (in words and figure):- | C.D No:_____________ dated:-______________ Amount Rs:_____________Bank_____________. ._______________________________________. M/S____________________________________. |

EXECUTIVE ENGINEER

Public Health Engineering Division

DADU

INSTRUCTIONS TO BIDDERS

(Note: (These Instructions to Bidders (IB) along with Bidding Data will not be part of

Contract and will cease to have effect once the Contract is signed).

A. GENERAL

IB.1 Scope of Bid & Source of Funds

  - Scope of Bid

The Procuring Agency as defined in the Bidding Data (hereinafter called ―the Procuring Agency‖) wishes to receive Bids for the Works summarized in the Bidding Data (hereinafter referred to as ―the Works‖).

Bidders must quote for the complete scope of work. Any Bid covering partial scope of work will be rejected as non-responsive.

  - Source of Funds

The Procuring Agency has arranged funds from its own sources or Federal/ Provincial /Donor agency or any other source, which may be indicated accordingly in bidding data towards the cost of the project/scheme.

IB.2 Eligible Bidders

2.1 Bidding is open to all firms and persons meeting the following requirements:

a) Duly licensed by the Pakistan Engineering Council (PEC) in the appropriate category for value of works.

Provided that the works costing Rs. 4.00 million or less shall not require any registration with PEC .

b) Duly pre-qualified with the Procuring Agency. (Where required).

In the event that prequalification of potential bidders has been undertaken, only bids from prequalified bidders will be considered for award of Contract.

c) If prequalification has not undertaken, the procuring agency may ask information and documents not limited to following:-

(i) Company profile;

(ii) Works of similar nature and size for each performed in last 3/5 years;

(iii) Construction equipments;

(iv) Qualification and experience of technical personnel and key site management; Sindh Public Procurement Regulatory Authority | www.pprasindh.gov.pk 7

(v) Financial statement of last 3 years;

(vi) Information regarding litigations and abandoned works if any.

IB.3 Cost of Bidding

3.1 The bidder shall bear all costs associated with the preparation and submission of its bid

and the Procuring Agency will in no case be responsible or liable for those costs,

Regardless of the conduct or outcome of the bidding process (SPP Rules 24 & 25).

Executive Engineer

PHE Division Dadu

CONDITIONS OF CONTRACT

- GENERAL PROVISIONS

Definitions

In the Contract as defined below, the words and expressions defined shall have the following meanings assigned to them, except where the context requires otherwise:

The Contract

1.1.1 ―Contract‖ means the Contract Agreement and the other documents listed in the Contract Data.

1.1.2 ―Specifications‖ means the document as listed in the Contract Data, including Procuring Agency‘s requirements in respect of design to be carried out by the Contractor (if any), and any Variation to such document.

1.1.3 ―Drawings‖ means the Procuring Agency‘s drawings of the Works as listed in the Contract Data, and any Variation to such drawings.

Persons

1.1.4 ―Procuring Agency‖ means the person named in the Contract Data and the legal successors in title to this person, but not (except with the consent of the Contractor) any assignee.

1.1.5 ―Contractor‖ means the person named in the Contract Data and the legal successors in title to this person, but not (except with the consent of the Procuring Agency) any assignee.

1.1.6 ―Party‖ means either the Procuring Agency or the Contractor.

Dates, Times and Periods

1.1.7 ―Commencement Date‖ means the date fourteen (14) days after the date the Contract comes into effect or any other date named in the Contract Data.

1.1.8 ―Day‖ means a calendar day

1.1.9 ―Time for Completion‖ means the time for completing the Works as stated in the Contract Data (or as extended under Sub-Clause 7.3), calculated from the Commencement Date.

Money and Payments

1.1.10 ―Cost‖ means all expenditure properly incurred (or to be incurred) by the Contractor, whether on or off the Site, including overheads and similar charges but does not include any allowance for profit.

Other Definitions

1.1.11 ―Contractor‘s Equipment‖ means all machinery, apparatus and other things required for the execution of the Works but does not include Materials or Plant intended to form part of the Works.

1.1.12 ―Country‖ means the Islamic Republic of Pakistan.

1.1.13 ―Procuring Agency‘s Risks‖ means those matters listed in Sub-Clause 6.1.

1.1.14 ―Force Majeure‖ means an event or circumstance which makes performance of a Party‘s obligations illegal or impracticable and which is beyond that Party‘s reasonable control.

1.1.15 ‗Materials‖ means things of all kinds (other than Plant) to be supplied and incorporated in the Works by the Contractor.

1.1.16 ―Plant‖ means the machinery and apparatus intended to form or forming part of the Works.

1.1.17 ―Site‖ means the places provided by the Procuring Agency where the Works are to be executed, and any other places specified in the Contract as forming part of the Site.

1.1.18 ―Variation‖ means a change which is instructed by the Engineer/Procuring Agency under Sub-Clause 10.1.

1.1.19 ‗Works‖ means any or all the works whether Supply, Installation, Construction etc. and design (if any) to be performed by the Contractor including temporary works and any variation thereof.

1.1.20 ―Engineer‖ means the person notified by the Procuring Agency to act as Engineer

for the purpose of the Contract and named as such in Contract Data.

  - Interpretation

Words importing persons or parties shall include firms and organizations. Words importing singular or one gender shall include plural or the other gender where the context requires.

  - Priority of Documents.

The documents forming the Contract are to be taken as mutually explanatory of one another. If an ambiguity or discrepancy is found in the documents, the priority of the documents shall be in accordance with the order as listed in the Contract Data.

37

1.4 Law

The law of the Contract is the relevant Law of Islamic Republic of Pakistan.

1.5 Communications

All Communications related to the Contract shall be in English language.

1.6 Statutory Obligations

The Contractor shall comply with the Laws of Islamic Republic of Pakistan and shall give all notices and pay all fees and other charges in respect of the Works.

- THE PROCURING AGENCY

2.1 Provision of Site

The Procuring Agency shall provide the Site and right of access thereto at the times stated in the Contract Data. Site Investigation Reports are those that were included in the bidding documents

and are factual and interpretative reports about the surface and subsurface conditions at the Site.

2.2 Permits etc.

The Procuring Agency shall, if requested by the Contractor, assist him in applying for permits, licenses or approvals which are required for the Works.

2.3 Engineer’s/Procuring Agency’s Instructions

The Contractor shall comply with all instructions given by the Procuring Agency or the Engineer, if notified by the Procuring Agency, in respect of the Works including the suspension of all or part of the works.

2.4 Approvals

No approval or consent or absence of comment by the Engineer/Procuring Agency shall affect the Contractor‘s obligations.

- ENGINEER’S/PROCURING AGENCY’S REPRESENTATIVES

3.1 Authorized Person

The Procuring Agency shall appoint a duly authorized person to act for him and on his behalf for the purposes of this Contract. Such authorized person shall be duly identified in the Contract Data or otherwise notified in writing to the Contractor as soon as he is so appointed. In either case the Procuring Agency shall notify the Contractor, in writing, the precise scope of the authority of such authorized person at the time of his appointment.

3.2 Engineer’s/Procuring Agency’s Representative

The name and address of Engineer‘s/Procuring Agency‘s Representative is given in Contract Data. However the Contractor shall be notified by the Engineer/Procuring Agency, the delegated duties and authority before the Commencement of works.

- THE CONTRACTOR

4.1 General Obligations

The Contractor shall carry out the works properly and in accordance with the Contract. The Contractor shall provide all supervision, labour, Materials, Plant and Contractor‘s Equipment which may be required

4.2 Contractor’s Representative

The Contractor shall appoint a representative at site on full time basis to supervise the execution of work and to receive instructions on behalf of the Contractor but only after obtaining the consent of the Procuring Agency for such appointment which consent shall not be withheld without plausible reason(s) by the Procuring Agency. Such authorized representative may be substituted/ replaced by the Contractor at any time during the Contract Period but only after obtaining the consent of the Procuring Agency as aforesaid.

4.3 Subcontracting

The Contractor shall not subcontract the whole of the works. The Contractor shall not subcontract any part of the works without the consent of the Procuring Agency.

4.4 Performance Security

The Contractor shall furnish to the Procuring Agency within fourteen (14) days after receipt of Letter of Acceptance a Performance Security at the option of the bidder, in the form of Payee‘s order /Bank Draft or Bank Guarantee from scheduled bank for the amount and validity specified in Contract Data.

- DESIGN BY CONTRACTOR

5.1 Contractor’s Design

The Contractor shall carry out design to the extent specified, as referred to in the Contract Data. The Contractor shall promptly submit to the Engineer/Procuring Agency all designs prepared by him, within fourteen (14) days of receipt the Engineer/Procuring Agency shall notify any comments or, if the design submitted is not in accordance with the Contract, shall reject it stating the reasons. Contractor shall not construct any element of the works designed by him within fourteen (14) days after the design has been submitted to the Engineer/Procuring Agency or which has been rejected. Design that has been rejected shall be promptly amended and resubmitted. The Contractor shall resubmit all designs commented on taking these comments into account as necessary.

5.2 Responsibility for Design

The Contractor shall remain responsible for his bided design and the design under this Clause, both of which shall be fit for the intended purposes defined in the Contract and he shall also remain responsible for any infringement of any patent or copyright in respect of the same. The Engineer/Procuring Agency shall be responsible for the Specifications and Drawings.

- PROCURING AGENCY’S RISKS

6.1 The Procuring Agency’s Risks

The Procuring Agency‘s Risks are:-

a) war, hostilities (whether war be declared or not), invasion, act of foreign enemies, within the Country;

b) Rebellion, terrorism, revolution, insurrection, military or usurped power, or civil war, within the Country;

c) riot, commotion or disorder by persons other than the Contractor‘s personnel and other employees including the personnel and employees of Sub- Contractors, affecting the Site and/or the Works;

d) ionizing radiations, or contamination by radio-activity from any nuclear fuel, or from any nuclear waste from the combustion of nuclear fuel, radio-active toxic explosive, or other hazardous properties of any explosive nuclear assembly or nuclear component of such an assembly, except to the extent to which the Contractor/Sub-Contractors may be responsible for the use of any radio-active material;

e) Pressure waves caused by aircraft or other aerial devices travelling at sonic or supersonic speeds;

f) Use or occupation by the Procuring Agency of any part of the Works, except as may be specified in the Contract;

g) late handing over of sites, anomalies in drawings, late delivery of designs and drawings of any part of the Works by the Procuring Agency‘s personnel or by others for whom the Procuring Agency is responsible;

h) a suspension under Sub-Clause 2.3 unless it is attributable to the Contractor‘s failure; and

i) physical obstructions or physical conditions other than climatic conditions, encountered on the Site during the performance of the Works, for which the Contractor immediately notified to the Procuring Agency and accepted by the Procuring Agency.

7. TIME FOR COMPLETION

7.1 Execution of the Works

The Contractor shall commence the Works on the Commencement Date and shall proceed expeditiously and without delay and shall complete the Works, subject to Sub-Clause 7.3 below, within the Time for Completion.

7.2 Programme

Within the time stated in the Contract Data, the Contractor shall submit to the Engineer/Procuring Agency a programme for the Works in the form stated in the Contract Data.

7.3 Extension of Time

The Contractor shall, within such time as may be reasonable under the circumstances, notify the Procuring Agency/Engineer of any event(s) falling within the scope of Sub-Clause 6.1 or 10.3 of these Conditions of Contract and request the Procuring Agency/Engineer for a reasonable extension in the time for the completion of works. Subject to the aforesaid, the Procuring Agency/Engineer shall determine such reasonable extension in the time for the completion of works as may be justified in the light of the details/particulars supplied by the Contractor in connection with the such determination by the Procuring Agency/Engineer within such period as may be prescribed by the Procuring Agency/Engineer for the same; and the Procuring Agency may extend the time for completion as determined.

7.4 Late Completion

If the Contractor fails to complete the Works within the Time for Completion, the Contractor‘s only liability to the Procuring Agency for such failure shall be to pay the amount as liquidity damages stated in the Contract Data for each day for which he fails to complete the Works.

8. TAKING-OVER

8.1 Completion

The Contractor may notify the Engineer/Procuring Agency when he considers that the Works are complete.

8.2 Taking-Over Notice

Within fourteen (14) days of the receipt of the said notice of completion from the Contractor the Procuring Agency/Engineer shall either takeover the completed works and issue a Certificate of Completion to that effect or shall notify the Contractor his reasons for not taking-over the works. While issuing the Certificate of Completion as aforesaid, the Procuring Agency/Engineer may identify any outstanding items of work which the Contractor shall undertake during the

Maintenances Period.

9. REMEDYING DEFECTS

9.1 Remedying Defects

The Contractor shall for a period stated in the Contract Data from the date of issue of the Certificate of Completion carry out, at no cost to the Procuring Agency, repair and rectification work which is necessitated by the earlier execution of poor quality of work or use of below specifications material in the execution of Works and which is so identified by the Procuring Agency/Engineer in writing within the said period. Upon expiry of the said period, and subject to the Contractor‘s faithfully performing his aforesaid obligations, the Procuring Agency/Engineer

shall issue a Maintenance Certificate whereupon all obligations of the Contractor under this Contract shall come to an end. Failure to remedy any such defects or complete outstanding work within a reasonable time shall entitle the Procuring Agency to carry out all necessary works at the Contractor‘s cost. However, the cost of remedying defects not attributable to the Contractor shall be valued as a Variation.

9.2 Uncovering and Testing

The Engineer/Procuring Agency may give instruction as to the uncovering and / or testing of any work. Unless as a result of an uncovering and/or testing it is established that the Contractor‘s design, materials, plant or workmanship are not in accordance with the Contract, the Contractor shall be paid for such uncovering and/or testing as a Variation in accordance with Sub-Clause 10.2.

10. VARIATIONS AND CLAIMS

10.1 Right to Vary

The Procuring Agency/Engineer may issue Variation Order(s) in writing. Where for any reason it has not been possible for the Procuring Agency/Engineer to issue such Variations Order(s), the Contractor may confirm any verbal orders given by the Procuring Agency/Engineer in writing and if the same are not refuted/denied by the Procuring Agency/Engineer within ten (10) days of the receipt of such confirmation the same shall be deemed to be a Variation Orders for the purposes of this Sub-Clause.

10.2 Valuation of Variations

Variations shall be valued as follows:

a) At a lump sum price agreed between the Parties, or

b) Where appropriate, at rates in the Contract, or

c) In the absence of appropriate rates, the rates in the Contract shall be used as the basis for valuation, or failing which

d) At appropriate new rates, as may be agreed or which the Engineer/Procuring Agency considers appropriate, or

e) If the Engineer/Procuring Agency so instructs, at day work rates set out in the Contract Data for which the Contractor shall keep records of hours of labour and Contractor‘s Equipment, and of Materials, used.

10.3 Changes in the Quantities.

a) If the final quantity of the work done differs from the quantity in the Bill of Quantities for the particular item by more than 25 percent, provided the change exceeds 1 percent of the Initial Contract Price, the Procuring Agency/Engineer shall adjust the rate to allow for the change and will be valued as per sub clause 10.2.

b) The Engineer shall not adjust rates from changes in quantities if thereby the Initial Contract Price is exceeded by more than 15 percent, except with the prior approval of the Procuring Agency.

c) If requested by the Engineer, the contractor shall provide the Engineer with a detailed cost breakdown of any rate in the Bill of Quantities.

10.4 Early Warning

The Contractor shall notify the Engineer/Procuring Agency in writing as soon as he is aware of any circumstance which may delay or disrupt the Works, or which may give rise to a claim for additional payment. To the extent of the Contractor‘s failure to notify, which results to the Engineer/Procuring Agency being unable to keep all relevant records or not taking steps to minimize any delay, disruption, or Cost, or the value of any Variation, the Contractor‘s entitlement to extension of the Time for Completion or additional payment shall be reduced/rejected.

10.5 Valuation of Claims

If the Contractor incurs Cost as a result of any of the Procuring Agency‘s Risks, the Contractor shall be entitled to the amount of such Cost. If as a result of any Procuring Agency‘s Risk, it is necessary to change the Works, this shall be dealt with as a Variation subject to Contractor‘s notification for intention of claim to the Engineer/Procuring Agency within fourteen (14) days of the occurrence of cause.

10.6 Variation and Claim Procedure

The Contractor shall submit to the Engineer/Procuring Agency an itemized detailed breakdown of the value of variations and claims within twenty eight (28) days of the instruction or of the event giving rise to the claim. The Engineer/Procuring Agency shall check and if possible agree the value. In the absence of agreement, the Procuring Agency shall determine the value.

11. CONTRACT PRICE AND PAYMENT

11.1 (a) Terms of Payments

The amount due to the Contractor under any Interim Payment Certificate issued by the Engineer pursuant to this Clause, or to any other terms of the Contract, shall , subject to Clause 11.3, be paid by the Procuring Agency to the Contractor within 30 days after such Interim Payment Certificate has been jointly verified by Procuring Agency and Contractor, or, in the case of the Final Certificate referred to in Sub Clause 11.5, within 60days after such Final Payment Certificate has been jointly verified by Procuring Agency and Contractor; Provided that the Interim Payment shall be caused in thirty (30) days and Final Payment in 60 days in case of foreign funded project. In the event of the failure of the Procuring Agency to make payment within 90 days then Procuring Agency shall pay to the Contractor compensation at the 28 days rate of KIBOR+2% per annum in local currency and LIBOR+1% for foreign currency, upon all sums unpaid from the date by which the same should have been paid.

(b) Valuation of the Works

The Works shall be valued as provided for in the Contract Data, subject to Clause 10.

11.2 Monthly Statements

The Contractor shall be entitled to be paid at monthly intervals:

a) The value of the Works executed less to the cumulative amount paid previously; and

b) Value of secured advance on the materials and valuation of variations (if any).

The Contractor shall submit each month to the Engineer/Procuring Agency a statement showing the amounts to which he considers himself entitled.

44

11.3 Interim Payments

Within a period not exceeding seven (07) days from the date of submission of a statement for interim payment by the Contractor, the Engineer shall verify the same and within a period not exceeding thirty (30/60) days from the said date of submission by the Contractor, the Procuring Agency shall pay to the Contractor the sum subject to adjustment for deduction of the advance payments and retention money.

11.4 Retention

Retention money shall be paid by the Procuring Agency to the Contractor within fourteen (14) days after either the expiry of the period stated in the Contract Data, or the remedying of notified defects, or the completion of outstanding work, all as referred to in Sub-Clause 9.1, whichever is the later.

11.5 Final Payment

Within twenty one (21) days from the date of issuance of the Maintenance Certificate the Contractor shall submit a final account to the Engineer to verify and the Engineer shall verify the same within fourteen (14) days from the date of submission and forward the same to the Procuring Agency together with any documentation reasonably required to enable the Procuring Agency to ascertain the final contract value. Within sixty (60) days from the date of receipt of the verified final account from the Engineer, the Procuring Agency shall pay to the Contractor any amount due to the Contractor. While making such payment the Procuring Agency may, for

Reasons to be given to the Contractor in writing, withhold any part or parts of the verified amount.

11.6 Currency

Payment shall be in the currency stated in the Contract Data.

12. DEFAULT

12.1 Defaults by Contractor

If the Contractor abandons the Works, refuses or fails to comply with a valid instruction of the Engineer/Procuring Agency or fails to proceed expeditiously and without delay, or is, despite a written complaint, in breach of the Contract, the Procuring Agency may give notice referring to this Sub-Clause and stating the default.

If the Contractor has not taken all practicable steps to remedy the default within fourteen (14) days after receipt of the Procuring Agency‘s notice, the Procuring Agency may by a second notice given within a further twenty one (21) days, terminate the Contract. The Contractor shall then demobilize from the Site leaving behind any Contractor‘s Equipment which the Procuring Agency instructs, in the second notice, to be used for the completion of the Works at the risk and cost of the Contractor.

12.2 Defaults by Procuring Agency

If the Procuring Agency fails to pay in accordance with the Contract, or is, despite a written complaint, in breach of the Contract, the Contractor may give notice referring to this Sub-Clause and stating the default. If the default is not remedied within fourteen (14) days after the Procuring Agency‘s receipt of this notice, the Contractor may suspend the execution of all or parts of the Works.

If the default is not remedied within twenty eight (28) days after the Procuring Agency‘s receipt of the Contractor‘s notice, the Contractor may by a second notice given within a further twenty one (21) days, terminate the Contract. The Contractor shall then demobilize from the Site.

12.3 Insolvency

If a Party is declared insolvent under any applicable law, the other Party may by notice terminate the Contract immediately. The Contractor shall then demobilize from the site leaving behind, in the case of the Contractor‘s insolvency, any Contractor‘s Equipment which the Procuring Agency instructs in the notice is to be used for the completion of the Works.

12.4 Payment upon Termination

After termination, the Contractor shall be entitled to payment of the unpaid balance of the value of the works executed and of the Materials and Plant reasonably delivered to the site, adjusted by the following:

a) any sums to which the Contractor is entitled under Sub-Clause 10.4,

b) any sums to which the Procuring Agency is entitled,

c) if the Procuring Agency has terminated under Sub-Clause 12.1 or 12.3, the Procuring Agency shall be entitled to a sum equivalent to twenty percent (20%) of the value of parts of the Works not executed at the date of the termination, and

d) if the Contractor has terminated under Sub-Clause 12.2 or 12.3, the Contractor shall be entitled to the cost of his demobilization together with a sum equivalent to ten percent (10%) of the value of parts of the works not executed at the date of termination. The net balance due shall be paid or repaid within twenty eight (28) days of the notice of termination.

13. RISKS AND RESPONSIBILITIES

13.1 Contractor’s Care of the Works

Subject to Sub-Clause 9.1, the Contractor shall take full responsibility for the care of the Works from the Commencement Date until the date of the Procuring Agency‘s/Engineer‘s issuance of Certificate of Completion under Sub-Clause 8.2. Responsibility shall then pass to the Procuring Agency. If any loss or damage happens to the Works during the above period, the Contractor shall rectify such loss or damage so that the Works conform with the Contract. Unless the loss or damage happens as a result of any of the Procuring Agency‘s Risks, the Contractor shall indemnify the Procuring Agency, or his agents against all claims loss, damage and expense arising out of the Works.

13.2 Force Majeure

If Force Majeure occurs, the Contractor shall notify the Engineer/Procuring Agency immediately. If necessary, the Contractor may suspend the execution of the Works and, to the extent agreed with the Procuring Agency demobilize the Contractor‘s Equipment. If the event continues for a period of eighty four (84) days, either Party may then give notice of termination which shall take effect twenty eight (28) days after the giving of the notice. After termination, the Contractor shall be entitled to payment of the unpaid balance of the value of the Works executed and of the Materials and Plant reasonably delivered to the Site, adjusted by the following:

a) any sums to which the Contractor is entitled under Sub-Clause 10.4,

b) the cost of his demobilization, and

c) less any sums to which the Procuring Agency is entitled. The net balance due shall be paid or repaid within thirty five (35) days of the notice of termination.

14. INSURANCE

14.1 Arrangements

The Contractor shall, prior to commencing the Works, effect insurances of the types, in the amounts and naming as insured the persons stipulated in the Contract Data except for items (a) to (e) and (i) of the Procuring Agency‘s Risks under Sub- Clause 6.1. The policies shall be issued by insurers and in terms approved by the Procuring Agency. The Contractor shall provide the Engineer/Procuring Agency with evidence that any required policy is in force and that the premiums have been paid.

14.2 Default

If the Contractor fails to effect or keep in force any of the insurances referred to in the previous Sub-Clause, or fails to provide satisfactory evidence, policies or receipts, the Procuring Agency may, without prejudice to any other right or remedy, effect insurance for the cover relevant to such as a default and pay the premiums due and recover the same plus a sum in percentage given in Contractor Data from any other amounts due to the Contractor.

15. RESOLUTION OF DISPUTES

15.1 Engineer’s Decision

If a dispute of any kind whatsoever arises between the Procuring Agency and the Contractor in connection with the works, the matter in dispute shall, in the first place, be referred in writing to the Engineer, with a copy to the other party. Such reference shall state that it is made pursuant to this Clause. No later than the twenty eight (28) days after the day on which he received such reference, the Engineer shall give notice of his decision to the Procuring Agency (Engineer)and the Contractor. Unless the Contract has already been repudiated or terminated, the Contractor shall, in every case, continue to proceed with the work with all due diligence, and the Contractor and the Procuring Agency ( Engineer) shall give effect forthwith to every such decision of the Engineer unless and until the same shall be revised, as hereinafter provided in an arbitral award.

15.2 Notice of Dissatisfaction

If a Party is dissatisfied with the decision of the Engineer of consultant or if no decision is given within the time set out in Sub-Clause 15.1 here above, the Party may give notice of dissatisfaction referring to this Sub-Clause within fourteen (14) days of receipt of the decision or the expiry of the time for the decision. If no notice of dissatisfaction is given within the specified time, the decision shall be final and binding on the Parties. If notice of dissatisfaction is given within the specified time, the decision shall be binding on the Parties who shall give effect to it without delay unless and until the decision of the Engineer is revised by an arbitrator. If a contractor is dissatisfied with the decision of the Engineer of the department or decision is not given in time then he can approach (Engineer) within 14 days, in case of dissatisfaction with decision of ( Engineer) or not decided within 28 days, then arbitration process would be adopted as per clause 15.3.

15.3 Arbitration

A dispute which has been the subject of a notice of dissatisfaction shall be finally settled as per provisions of Arbitration Act 1940 (Act No. X of 1940) and Rules made there under and any statutory modifications thereto. Any hearing shall be held at the place specified in the Contract Data and in the language referred to in Sub-Clause 1.5.

Contractor

Executive Engineer

PHE Division Dadu

| BILL OF QUANTITY |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Name of work: - (1) |  | CONSTRUCTION OF COMPOUND WALL I/C SURFACE DRAINS & C.C BLOCK FOR VARIOUS MUHALLAS ZONE A UNDER BASIC HUMAN FACILITIES DRAINAGE SCHEME JOHI CITY. |  |  |  |  |  |  |
| Head of Account:- |  | BASIC HUMAN FACILITIES DRAINAGE SCHEME JOHI CITY.. |  |  |  |  |  |  |
| S.No: | Item | Qty: |  |  | Rate | Unit |  | Amount |
|  | COMPOUND WALL |  |  |  |  |  |  |  |
| 1 | Pacca brick work in foundation and plinth in cement sand mortar(1:6) |  |  |  |  |  |  |  |
|  | (G.S.I No. 4 P/ 20) |  |  |  |  |  |  |  |
|  | 1096.10 | Cft |  | @Rs: | 11948.36 | P%Cft | Rs: | 130966 |
| 2 | D.P.C (Damp proof course) with cement sand and shingle |  |  |  |  |  |  |  |
|  | concrete 1:2:4 i/c 2 coats of asphaltic mixture (3" thick). |  |  |  |  |  |  |  |
|  | (G.S.I-27, P-18) |  |  |  |  |  |  |  |
|  | 548.05 | Sft |  | @Rs: | 4982.18 | P%Sft | Rs: | 27305 |
| 3 | R.C.C work i/c all labour and material except the cost of steel |  |  |  |  |  |  |  |
|  | reinforcement and its labour for b/b which will be paid separately. |  |  |  |  |  |  |  |
|  | This rate also i/c all kinds of forms moulds lifting, shutting, curing, |  |  |  |  |  |  |  |
|  | rendering and finishing the exposed surface (i/c s/w of shingle) (a) R.C work in |  |  |  |  |  |  |  |
|  | roof slab beams columns rafts lintels and other structural members laid in |  |  |  |  |  |  |  |
|  | situ or prrecast laid in position complete in all respect. (I) Ratio 2:2:4 Lbs |  |  |  |  |  |  |  |
|  | cement2 Cft, sand 4 cft shingle1/8” to ¼” gauge. (G.S.I No. 6 P/ 16). |  |  |  |  |  |  |  |
|  | 41.50 | Cft |  | @Rs: | 337.00 | P%Cft | Rs: | 13986 |
| 4 | Fabrication of mild steel reinforcement for C.C i/c cutting, bending, |  |  |  |  |  |  |  |
|  | laying in position making joints and fastening i/c cost of binding wire |  |  |  |  |  |  |  |
|  | (also i/c removal of rust from bars).(G.S.I No 8 P/ 16) |  |  |  |  |  |  |  |
|  | 1.67 | Cwt |  | @Rs: | 5001.70 | P/Cwt | Rs: | 8340 |
| 5 | Pacca brick work in other then building i/c stricking of joints upto |  |  |  |  |  |  |  |
|  | 20ft height in cement, sand, mortar (1:6) (G.S.I. No 7 P/ 21) |  |  |  |  |  |  |  |
|  | 1455.00 | Cft |  | @Rs: | 12346.65 | P%Cft | Rs: | 179644 |
| 6 | Cement, Plaster (1:6) up to 12’ height ½” thick (G.S.I. No.11 P/58) |  |  |  |  |  |  |  |
|  | 4243.75 | Sft |  | @Rs: | 2206.60 | P%Sft | Rs: | 93643 |
| 7 | Cement, Plaster (1:4) up to 12’ height 3/8” thick (G.S.I. No.11 P/58) |  |  |  |  |  |  |  |
|  | 4243.75 | Sft |  | @Rs: | 2197.52 | P%Sft | Rs: | 93257 |
| 8 | Cement, Pointing struck joint on walls (1:3) (G.S.I. No.11 P/57) |  |  |  |  |  |  |  |
|  | 1928.00 | Sft |  | @Rs: | 1213.58 | P%Sft | Rs: | 23398 |
| 9 | Fabrication of heavy steel work with angles, tees, flat iron round |  |  |  |  |  |  |  |
|  | iron and sheet iron for making trusses, girders tanks etc: i/c |  |  |  |  |  |  |  |
|  | cutting tanks etc: i/c cutting drilluing rivetting i/c handling assembling |  |  |  |  |  |  |  |
|  | and fixing but excluding erection inposition. (G.S.I-2, P-90). |  |  |  |  |  |  |  |
|  | 5.35 | Cwt |  | @Rs: | 4928.49 | P/Cwt | Rs: | 26367 |
| 10 | PAINTING NEW SURFACE |  |  |  |  |  |  |  |
|  | Preparing surface and painting of door and window any type i/c Edges 3 coats |  |  |  |  |  |  |  |
|  | (G.S.I. No.5 P/6) |  |  |  |  |  |  |  |
|  | 100.00 | Sft |  | @Rs: | 2116.41 | P%Sft | Rs: | 2116 |
| 11 | White washing of two coats (G.S.I. No.26 P/55) |  |  |  |  |  |  |  |
|  | 4327.75 | Cft |  | @Rs: | 829.95 | P%Sft | Rs: | 35918 |
|  |  | Sft |  |  |  |  |  |  |
| 12 | Color Washing (2 coats) (G.S.I.No:24, P/60). |  |  |  |  |  |  |  |
|  | 6171.75 | Sft |  | @Rs: | 859.90 | P%Sft | Rs: | 53071 |
|  |  |  |  |  |  |  | Rs: | 688010 |
|  | SURFACE DRAINS |  |  |  |  |  |  |  |
| 1 | Dismantling and removing Road Metalling (G.S.I No. 51 P/ 13) |  |  |  |  |  |  |  |
|  | 250.00 | 0 |  | @ Rs: | 605.00 | P%Cft | Rs: | 1513 |
| 2 | Dismantling of Brick Work in lime or cement mortor (G.S.I No 13 P/ 10) |  |  |  |  |  |  |  |
|  | 75.00 | Cft |  | @ Rs: | 1285.63 | P%Cft | Rs: | 964 |
| 3 | Dismantling of C.C plain 1:2:4 ( G.S.I No 19 P/ 10) |  |  |  |  |  |  |  |
|  | 37.50 | Cft |  | @ Rs: | 3327.50 | P%Cft | Rs: | 1248 |
| 4 | Dismantling of C.C Reinforced Separting Reinforcement from Concrete, cleaning |  |  |  |  |  |  |  |
|  | and straighting the same. (G.S.I No 20 P/ 10) |  |  |  |  |  |  |  |
|  | 75.00 | Cft |  | @ Rs: | 5445.00 | P%Cft | Rs: | 4084 |
| 5 | Excavation in foundation of building bridges and other structures |  |  |  |  |  |  |  |
|  | i/c dig billing dressing refilling around the structures with excavated |  |  |  |  |  |  |  |
|  | Earth watering ramming up to 5ft (b) in ordinary soil (G.S.I-18/ P/4) |  |  |  |  |  |  |  |
|  | 22520 | Cft |  | @Rs | 3176.25 | P%Cft | Rs: | 71529 |
| 6 | Cement concrete plain i/c placing compacting finishing |  |  |  |  |  |  |  |
|  | and curing complete i/c screening and washing of stone |  |  |  |  |  |  |  |
|  | aggregate without shuttering Ratio 1:4:8 (G.S.I-5 P/15) |  |  |  |  |  |  |  |
|  | 4957.50 | Cft |  | @Rs | 11288.75 | P%Cft | Rs: | 559640 |
| 7 | Construction of standard open type drains connuttee block |  |  |  |  |  |  |  |
|  | of C.C 1:2:4 cost of situ to the design profiles i/c cost of mould |  |  |  |  |  |  |  |
|  | as per drawing i/c supplying floating cost of cement 1/32” thick |  |  |  |  |  |  |  |
|  | to expose surface faces finished smooth curing complete as per |  |  |  |  |  |  |  |
|  | drawing design. (P.H.S.I No D, P/ 58) |  |  |  |  |  |  |  |
|  | 6000 | Rft | Type A | @Rs | 94 | P/Rft | Rs: | 564000 |
|  | 1000 | Rft | Type B | @Rs | 174 | P/Rft | Rs: | 174000 |
|  | 500 | Rft | Type C | @Rs | 309 | P/Rft | Rs: | 154500 |
| 8 | Pacca brick work in foundation and plinth in cement sand mortar(1:6) |  |  |  |  |  |  |  |
|  | (G.S.I No. 4 P/ 20) |  |  |  |  |  |  |  |
|  | 13125.00 | Cft |  | @Rs | 11948.36 | P%Cft | Rs: | 1568222 |
|  | Cement plaster (1:4) up to 12’height ½”thick (G.S.I-11, P/51) |  |  |  |  |  |  |  |
|  | 22370.00 | Sft. |  | @Rs | 2283.93 | P%Sft | Rs: | 510915 |
| 10 | R.C.C work i/c all labour and material except the cost of steel |  |  |  |  |  |  |  |
|  | reinforcement and its labour for bending and binding which will |  |  |  |  |  |  |  |
|  | be paid separately. This rate also includes all kinds of forms moulds |  |  |  |  |  |  |  |
|  | lifting shuttering curing rendering and finishing the exposed surface |  |  |  |  |  |  |  |
|  | i/c screening and washing of shingle (a) R.C work in roof slab members |  |  |  |  |  |  |  |
|  | laid in situ or prrecast laid in position complete in a respect. (i) |  |  |  |  |  |  |  |
|  | Ratio 1;2;4 90 lbs cement 2 cft sand 4 cft shingle 1/8” to ¼” gauge. |  |  |  |  |  |  |  |
|  | (G.S.I-6 P/16) |  |  |  |  |  |  |  |
|  | 227.44 | Cft |  | @Rs | 337 | P%Cft | Rs: | 76647 |
| 11 | Fabrication of mild steel reinforcement for cement concrete i/c |  |  |  |  |  |  |  |
|  | cutting bending laying in position making joints and fastening i/c |  |  |  |  |  |  |  |
|  | cost of binding wire also includes removal of rust from bars. |  |  |  |  |  |  |  |
|  | (G.S.I-8 (a) P/16) |  |  |  |  |  |  |  |
|  | 8.12 | Cwt |  | @Rs | 5001.7 | P%Cft | Rs: | 40614 |
| 12 | Cement concrete plain i/c placing compacting, finishing |  |  |  |  |  |  |  |
|  | and curing complete i/c s/w of stone aggregate without |  |  |  |  |  |  |  |
|  | shuttering (G.S.I No. 5 p/ 15) |  |  |  |  |  |  |  |
|  | 278.52 | Cft | (RATIO 1:2;4) | @Rs | 14429.25 | P%Cft | Rs: | 40188 |
|  |  |  |  |  |  |  | Rs: | 3768064 |
|  | C.C BLOCK |  |  |  |  |  |  |  |
| 1 | Barrow pit excavation undressed lead upto 100 ft ordinary soil |  |  |  |  |  |  |  |
|  | (G.S.I. No. 3 p/ 1) |  |  |  |  |  |  |  |
|  | 45480 | Cft |  | @Rs | 2117.5 | P%Cft | Rs: | 96304 |
| 2 | Extra for every 50' additional lead or part there of |  |  |  |  |  |  |  |
|  | (a) for earth work (soft ordinary hard and very hard.) |  |  |  |  |  |  |  |
|  | 45480.00 | Cft |  | @Rs | 4837.44 | P%Cft | Rs: | 220007 |
| 3 | Earth work compaction (Soft ordinary or hard soil lying |  |  |  |  |  |  |  |
|  | earth in 6” layers leveling dressing and watering for compaction |  |  |  |  |  |  |  |
|  | etc: complete.(G.S.I.No. 13 p/ 3) |  |  |  |  |  |  |  |
|  | 68000 | Cft |  | @Rs | 354 | P%Cft | Rs: | 24072 |
| 4 | Cement concrete bricks or stone ballest ½” to 2” gauge.(Ratio 1:4:8) |  |  |  |  |  |  |  |
|  | (G.SI. No. 4 p/ 14) |  |  |  |  |  |  |  |
|  | 22440 | Cft |  | @Rs | 9416.28 | P%Cft | Rs: | 2113013 |
| 5 | Cement concrete plain i/c placing compacting, finishing |  |  |  |  |  |  |  |
|  | and curing complete i/c s/w of stone aggregate without |  |  |  |  |  |  |  |
|  | shuttering (Ratio 1:2:4) (G.S.I No. 5 p/ 15) |  |  |  |  |  |  |  |
|  | 17000 | Cft |  | @Rs | 14429.25 | P%Cft | Rs: | 2452973 |
| 6 | Erection and removal of centering for R.C.C or plain C.C works |  |  |  |  |  |  |  |
|  | of deodars wood (2nd class) (b) for partal wood (vertical). |  |  |  |  |  |  |  |
|  | (G.S.I.No. 19 p/ 17) |  |  |  |  |  |  |  |
|  | 3825 | Cft |  | @Rs | 3127.41 | P%Cft | Rs: | 119623 |
|  |  |  |  |  |  |  | Rs: | 5025992 |
|  |  |  | ABSTRACT |  |  |  |  |  |
|  | COMPOUND WALL |  |  |  |  |  | Rs: | 688010 |
|  | SURFACE DRAINS |  |  |  |  |  | Rs: | 3768064 |
|  | C.C BLOCK |  |  |  |  |  | Rs: | 5025992 |
|  |  |  |  |  |  |  | Rs: | 9482067 |
|  | Total Amount of Composite Schedule |  |  |  |  |  | Rs: |  |
|  | % | above / below on the rates of CSR |  |  |  |  |  |  |
|  | Amount to be added / deducted on the basis of premium |  |  |  |  |  | Rs: |  |
|  | Total Amount of Non Schedule items |  |  |  |  |  | Rs: |  |
|  | TOTAL AMOUNT . |  |  |  |  |  | Rs: |  |
|  | CONDITIONS |  |  |  |  |  |  |  |
| 1 | The contractor will have to remove the surplus excavated stuff |  |  |  |  |  |  |  |
|  | from the side of work to be out of town at his own cost |  |  |  |  |  |  |  |
| 2 | The contractor arrange the material for construction of work from |  |  |  |  |  |  |  |
|  | the approved quarry as shown in the estimate. |  |  |  |  |  |  |  |
| 3 | No premium should be allowed on approved / market rate. |  |  |  |  |  |  |  |
| 4 | Any error or omission in the rate description unit shall be reffered to particular schedule of rates |  |  |  |  |  |  |  |
| 5 | No cartage shall be paid seprately. |  |  |  |  |  |  |  |

|  | SUMMARY OF BILL QUANTITY |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | ABSTRACT |  |  |  |  |  |  |  |
|  | COST OF BID |  |  |  |  |  | Rs: |  |
| ( A ) | Cost based on Composite schedule of rates |  |  |  |  |  | Rs: |  |
| ( B ) | Amount of Item based on Non Schedule Items |  |  |  |  |  | Rs: |  |
|  | TOTAL COST OF BID |  |  |  |  |  | Rs: |  |

GOVERNMENT OF SINDH

PUBLIC HEALTH ENGINEERING DIVISION DADU

STANDARD BIDDING DOCUMENTS

PROCUREMENT OF WORKS (SPPRA BIDDING DOCUMENTS)

For Contracts (Small) amounting between Rs. 4.0 (M) to Rs. 50.00  (M).

Name of Work:		(02)  Construction of Surface Drain and C.C Block for

Various Mohalla Zone-“B” under Basic Humain Facilities Drainage Scheme Johi .

N.I.T NO: & DATE:		NO: TC/  1334    /   dated:-15-12-2016

DATE OF ISSUE:                 10-01-2017

DATE OF OPENING:           11-01-2017

TENDER ISSUED TO:      .	     							.

D.R.NO: & DATE:            .	     							.

STANDARD BIDDING DOCUMENT IS INTENDED AS MODEL FOR

ADMEASUREMENTS (PERCENTAGE RATE FOR UNIT RATES IN A BILL OFQUANTITIES TYPES OF CONTRACT THE MAIN TEXT REFERS TO ADMEASUREMENTS CONTRACTOS.

EXECUTIVE ENGINEER

Public Health Engineering Division

DADU

BIDDING DATA

(This section  should be filled in by the office of the Executive Engineer,

Public Engineering Division Dadu, before issuance of the bidding documents).

| (a) | Name of Procuring Agency:- | The Executive Engineer Public Health Engineering Division Dadu. |
| --- | --- | --- |
| (b) | Brief Description of works:- | (02) Construction of Surface Drain and C.C Block for Various Mohalla Zone-“B” under Basic Humain Facilities Drainage Scheme Johi. |
| © | Procuring Agency Address:- | The Executive Engineer Public Health Engineering Division Dadu. Near Gharibabad Muhalla Dadu. |
| (d) | Estimated Cost:- | Rs: 10.000 Million |
| (e) | Amount of Bid Security:- | Rs: 5,00,000/- |
| (f) | Period of Bid Validity (Days):- | (90 days) |
| (g) | Security Deposit (i/c Bid Security):- | (10`%) |
| (h) | Percentage, if any, to be deducted from bills:- | (7.50% Income Tax) & (8% Security Deposit). |
| (i) | Deadline for submission of Bids along with time:- | 10-01-2017 @ 1.30 PM |
| (j) | Venue, time & date of Bid Opening:- | 11-01-2017 @ 2.00 PM |
| (k) | Time for completion from written order of commence:- | (24 Months) |
| (l) | Liquidity Damages:- | (1% on estimated cost per day subject to minimum of 10%) |
| (m) | Deposit receipt No: date & Amount (in words and figure):- | C.D No:_____________ dated:-______________ Amount Rs:_____________Bank_____________. ._______________________________________. M/S____________________________________. |

EXECUTIVE ENGINEER

Public Health Engineering Division

DADU

INSTRUCTIONS TO BIDDERS

(Note: (These Instructions to Bidders (IB) along with Bidding Data will not be part of

Contract and will cease to have effect once the Contract is signed).

A. GENERAL

IB.1 Scope of Bid & Source of Funds

  - Scope of Bid

The Procuring Agency as defined in the Bidding Data (hereinafter called ―the Procuring Agency‖) wishes to receive Bids for the Works summarized in the Bidding Data (hereinafter referred to as ―the Works‖).

Bidders must quote for the complete scope of work. Any Bid covering partial scope of work will be rejected as non-responsive.

  - Source of Funds

The Procuring Agency has arranged funds from its own sources or Federal/ Provincial /Donor agency or any other source, which may be indicated accordingly in bidding data towards the cost of the project/scheme.

IB.2 Eligible Bidders

2.1 Bidding is open to all firms and persons meeting the following requirements:

a) Duly licensed by the Pakistan Engineering Council (PEC) in the appropriate category for value of works.

Provided that the works costing Rs. 4.00 million or less shall not require any registration with PEC .

b) Duly pre-qualified with the Procuring Agency. (Where required).

In the event that prequalification of potential bidders has been undertaken, only bids from prequalified bidders will be considered for award of Contract.

c) If prequalification has not undertaken, the procuring agency may ask information and documents not limited to following:-

(i) Company profile;

(ii) Works of similar nature and size for each performed in last 3/5 years;

(iii) Construction equipments;

(iv) Qualification and experience of technical personnel and key site management; Sindh Public Procurement Regulatory Authority | www.pprasindh.gov.pk 7

(v) Financial statement of last 3 years;

(vi) Information regarding litigations and abandoned works if any.

IB.3 Cost of Bidding

3.1 The bidder shall bear all costs associated with the preparation and submission of its bid

and the Procuring Agency will in no case be responsible or liable for those costs,

Regardless of the conduct or outcome of the bidding process (SPP Rules 24 & 25).

Executive Engineer

PHE Division Dadu

CONDITIONS OF CONTRACT

- GENERAL PROVISIONS

Definitions

In the Contract as defined below, the words and expressions defined shall have the following meanings assigned to them, except where the context requires otherwise:

The Contract

1.1.1 ―Contract‖ means the Contract Agreement and the other documents listed in the Contract Data.

1.1.2 ―Specifications‖ means the document as listed in the Contract Data, including Procuring Agency‘s requirements in respect of design to be carried out by the Contractor (if any), and any Variation to such document.

1.1.3 ―Drawings‖ means the Procuring Agency‘s drawings of the Works as listed in the Contract Data, and any Variation to such drawings.

Persons

1.1.4 ―Procuring Agency‖ means the person named in the Contract Data and the legal successors in title to this person, but not (except with the consent of the Contractor) any assignee.

1.1.5 ―Contractor‖ means the person named in the Contract Data and the legal successors in title to this person, but not (except with the consent of the Procuring Agency) any assignee.

1.1.6 ―Party‖ means either the Procuring Agency or the Contractor.

Dates, Times and Periods

1.1.7 ―Commencement Date‖ means the date fourteen (14) days after the date the Contract comes into effect or any other date named in the Contract Data.

1.1.8 ―Day‖ means a calendar day

1.1.9 ―Time for Completion‖ means the time for completing the Works as stated in the Contract Data (or as extended under Sub-Clause 7.3), calculated from the Commencement Date.

Money and Payments

1.1.10 ―Cost‖ means all expenditure properly incurred (or to be incurred) by the Contractor, whether on or off the Site, including overheads and similar charges but does not include any allowance for profit.

Other Definitions

1.1.11 ―Contractor‘s Equipment‖ means all machinery, apparatus and other things required for the execution of the Works but does not include Materials or Plant intended to form part of the Works.

1.1.12 ―Country‖ means the Islamic Republic of Pakistan.

1.1.13 ―Procuring Agency‘s Risks‖ means those matters listed in Sub-Clause 6.1.

1.1.14 ―Force Majeure‖ means an event or circumstance which makes performance of a Party‘s obligations illegal or impracticable and which is beyond that Party‘s reasonable control.

1.1.15 ‗Materials‖ means things of all kinds (other than Plant) to be supplied and incorporated in the Works by the Contractor.

1.1.16 ―Plant‖ means the machinery and apparatus intended to form or forming part of the Works.

1.1.17 ―Site‖ means the places provided by the Procuring Agency where the Works are to be executed, and any other places specified in the Contract as forming part of the Site.

1.1.18 ―Variation‖ means a change which is instructed by the Engineer/Procuring Agency under Sub-Clause 10.1.

1.1.19 ‗Works‖ means any or all the works whether Supply, Installation, Construction etc. and design (if any) to be performed by the Contractor including temporary works and any variation thereof.

1.1.20 ―Engineer‖ means the person notified by the Procuring Agency to act as Engineer

for the purpose of the Contract and named as such in Contract Data.

  - Interpretation

Words importing persons or parties shall include firms and organizations. Words importing singular or one gender shall include plural or the other gender where the context requires.

  - Priority of Documents.

The documents forming the Contract are to be taken as mutually explanatory of one another. If an ambiguity or discrepancy is found in the documents, the priority of the documents shall be in accordance with the order as listed in the Contract Data.

37

1.4 Law

The law of the Contract is the relevant Law of Islamic Republic of Pakistan.

1.5 Communications

All Communications related to the Contract shall be in English language.

1.6 Statutory Obligations

The Contractor shall comply with the Laws of Islamic Republic of Pakistan and shall give all notices and pay all fees and other charges in respect of the Works.

THE PROCURING AGENCY

2.1 Provision of Site

The Procuring Agency shall provide the Site and right of access thereto at the times stated in the Contract Data. Site Investigation Reports are those that were included in the bidding documents

and are factual and interpretative reports about the surface and subsurface conditions at the Site.

2.2 Permits etc.

The Procuring Agency shall, if requested by the Contractor, assist him in applying for permits, licenses or approvals which are required for the Works.

2.3 Engineer’s/Procuring Agency’s Instructions

The Contractor shall comply with all instructions given by the Procuring Agency or the Engineer, if notified by the Procuring Agency, in respect of the Works including the suspension of all or part of the works.

2.4 Approvals

No approval or consent or absence of comment by the Engineer/Procuring Agency shall affect the Contractor‘s obligations.

- ENGINEER’S/PROCURING AGENCY’S REPRESENTATIVES

3.1 Authorized Person

The Procuring Agency shall appoint a duly authorized person to act for him and on his behalf for the purposes of this Contract. Such authorized person shall be duly identified in the Contract Data or otherwise notified in writing to the Contractor as soon as he is so appointed. In either case the Procuring Agency shall notify the Contractor, in writing, the precise scope of the authority of such authorized person at the time of his appointment.

3.2 Engineer’s/Procuring Agency’s Representative

The name and address of Engineer‘s/Procuring Agency‘s Representative is given in Contract Data. However the Contractor shall be notified by the Engineer/Procuring Agency, the delegated duties and authority before the Commencement of works.

- THE CONTRACTOR

4.1 General Obligations

The Contractor shall carry out the works properly and in accordance with the Contract. The Contractor shall provide all supervision, labour, Materials, Plant and Contractor‘s Equipment which may be required

4.2 Contractor’s Representative

The Contractor shall appoint a representative at site on full time basis to supervise the execution of work and to receive instructions on behalf of the Contractor but only after obtaining the consent of the Procuring Agency for such appointment which consent shall not be withheld without plausible reason(s) by the Procuring Agency. Such authorized representative may be substituted/ replaced by the Contractor at any time during the Contract Period but only after obtaining the consent of the Procuring Agency as aforesaid.

4.3 Subcontracting

The Contractor shall not subcontract the whole of the works. The Contractor shall not subcontract any part of the works without the consent of the Procuring Agency.

4.4 Performance Security

The Contractor shall furnish to the Procuring Agency within fourteen (14) days after receipt of Letter of Acceptance a Performance Security at the option of the bidder, in the form of Payee‘s order /Bank Draft or Bank Guarantee from scheduled bank for the amount and validity specified in Contract Data.

- DESIGN BY CONTRACTOR

5.1 Contractor’s Design

The Contractor shall carry out design to the extent specified, as referred to in the Contract Data. The Contractor shall promptly submit to the Engineer/Procuring Agency all designs prepared by him, within fourteen (14) days of receipt the Engineer/Procuring Agency shall notify any comments or, if the design submitted is not in accordance with the Contract, shall reject it stating the reasons. Contractor shall not construct any element of the works designed by him within fourteen (14) days after the design has been submitted to the Engineer/Procuring Agency or which has been rejected. Design that has been rejected shall be promptly amended and resubmitted. The Contractor shall resubmit all designs commented on taking these comments into account as necessary.

5.2 Responsibility for Design

The Contractor shall remain responsible for his bided design and the design under this Clause, both of which shall be fit for the intended purposes defined in the Contract and he shall also remain responsible for any infringement of any patent or copyright in respect of the same. The Engineer/Procuring Agency shall be responsible for the Specifications and Drawings.

- PROCURING AGENCY’S RISKS

6.1 The Procuring Agency’s Risks

The Procuring Agency‘s Risks are:-

a) war, hostilities (whether war be declared or not), invasion, act of foreign enemies, within the Country;

b) Rebellion, terrorism, revolution, insurrection, military or usurped power, or civil war, within the Country;

c) riot, commotion or disorder by persons other than the Contractor‘s personnel and other employees including the personnel and employees of Sub- Contractors, affecting the Site and/or the Works;

d) ionizing radiations, or contamination by radio-activity from any nuclear fuel, or from any nuclear waste from the combustion of nuclear fuel, radio-active toxic explosive, or other hazardous properties of any explosive nuclear assembly or nuclear component of such an assembly, except to the extent to which the Contractor/Sub-Contractors may be responsible for the use of any radio-active material;

e) Pressure waves caused by aircraft or other aerial devices travelling at sonic or supersonic speeds;

f) Use or occupation by the Procuring Agency of any part of the Works, except as may be specified in the Contract;

g) late handing over of sites, anomalies in drawings, late delivery of designs and drawings of any part of the Works by the Procuring Agency‘s personnel or by others for whom the Procuring Agency is responsible;

h) a suspension under Sub-Clause 2.3 unless it is attributable to the Contractor‘s failure; and

i) physical obstructions or physical conditions other than climatic conditions, encountered on the Site during the performance of the Works, for which the Contractor immediately notified to the Procuring Agency and accepted by the Procuring Agency.

7. TIME FOR COMPLETION

7.1 Execution of the Works

The Contractor shall commence the Works on the Commencement Date and shall proceed expeditiously and without delay and shall complete the Works, subject to Sub-Clause 7.3 below, within the Time for Completion.

7.2 Programme

Within the time stated in the Contract Data, the Contractor shall submit to the Engineer/Procuring Agency a programme for the Works in the form stated in the Contract Data.

7.3 Extension of Time

The Contractor shall, within such time as may be reasonable under the circumstances, notify the Procuring Agency/Engineer of any event(s) falling within the scope of Sub-Clause 6.1 or 10.3 of these Conditions of Contract and request the Procuring Agency/Engineer for a reasonable extension in the time for the completion of works. Subject to the aforesaid, the Procuring Agency/Engineer shall determine such reasonable extension in the time for the completion of works as may be justified in the light of the details/particulars supplied by the Contractor in connection with the such determination by the Procuring Agency/Engineer within such period as may be prescribed by the Procuring Agency/Engineer for the same; and the Procuring Agency may extend the time for completion as determined.

7.4 Late Completion

If the Contractor fails to complete the Works within the Time for Completion, the Contractor‘s only liability to the Procuring Agency for such failure shall be to pay the amount as liquidity damages stated in the Contract Data for each day for which he fails to complete the Works.

8. TAKING-OVER

8.1 Completion

The Contractor may notify the Engineer/Procuring Agency when he considers that the Works are complete.

8.2 Taking-Over Notice

Within fourteen (14) days of the receipt of the said notice of completion from the Contractor the Procuring Agency/Engineer shall either takeover the completed works and issue a Certificate of Completion to that effect or shall notify the Contractor his reasons for not taking-over the works. While issuing the Certificate of Completion as aforesaid, the Procuring Agency/Engineer may identify any outstanding items of work which the Contractor shall undertake during the

Maintenances Period.

9. REMEDYING DEFECTS

9.1 Remedying Defects

The Contractor shall for a period stated in the Contract Data from the date of issue of the Certificate of Completion carry out, at no cost to the Procuring Agency, repair and rectification work which is necessitated by the earlier execution of poor quality of work or use of below specifications material in the execution of Works and which is so identified by the Procuring Agency/Engineer in writing within the said period. Upon expiry of the said period, and subject to the Contractor‘s faithfully performing his aforesaid obligations, the Procuring Agency/Engineer

shall issue a Maintenance Certificate whereupon all obligations of the Contractor under this Contract shall come to an end. Failure to remedy any such defects or complete outstanding work within a reasonable time shall entitle the Procuring Agency to carry out all necessary works at the Contractor‘s cost. However, the cost of remedying defects not attributable to the Contractor shall be valued as a Variation.

9.2 Uncovering and Testing

The Engineer/Procuring Agency may give instruction as to the uncovering and / or testing of any work. Unless as a result of an uncovering and/or testing it is established that the Contractor‘s design, materials, plant or workmanship are not in accordance with the Contract, the Contractor shall be paid for such uncovering and/or testing as a Variation in accordance with Sub-Clause 10.2.

10. VARIATIONS AND CLAIMS

10.1 Right to Vary

The Procuring Agency/Engineer may issue Variation Order(s) in writing. Where for any reason it has not been possible for the Procuring Agency/Engineer to issue such Variations Order(s), the Contractor may confirm any verbal orders given by the Procuring Agency/Engineer in writing and if the same are not refuted/denied by the Procuring Agency/Engineer within ten (10) days of the receipt of such confirmation the same shall be deemed to be a Variation Orders for the purposes of this Sub-Clause.

10.2 Valuation of Variations

Variations shall be valued as follows:

a) At a lump sum price agreed between the Parties, or

b) Where appropriate, at rates in the Contract, or

c) In the absence of appropriate rates, the rates in the Contract shall be used as the basis for valuation, or failing which

d) At appropriate new rates, as may be agreed or which the Engineer/Procuring Agency considers appropriate, or

e) If the Engineer/Procuring Agency so instructs, at day work rates set out in the Contract Data for which the Contractor shall keep records of hours of labour and Contractor‘s Equipment, and of Materials, used.

10.3 Changes in the Quantities.

a) If the final quantity of the work done differs from the quantity in the Bill of Quantities for the particular item by more than 25 percent, provided the change exceeds 1 percent of the Initial Contract Price, the Procuring Agency/Engineer shall adjust the rate to allow for the change and will be valued as per sub clause 10.2.

b) The Engineer shall not adjust rates from changes in quantities if thereby the Initial Contract Price is exceeded by more than 15 percent, except with the prior approval of the Procuring Agency.

c) If requested by the Engineer, the contractor shall provide the Engineer with a detailed cost breakdown of any rate in the Bill of Quantities.

10.4 Early Warning

The Contractor shall notify the Engineer/Procuring Agency in writing as soon as he is aware of any circumstance which may delay or disrupt the Works, or which may give rise to a claim for additional payment. To the extent of the Contractor‘s failure to notify, which results to the Engineer/Procuring Agency being unable to keep all relevant records or not taking steps to minimize any delay, disruption, or Cost, or the value of any Variation, the Contractor‘s entitlement to extension of the Time for Completion or additional payment shall be reduced/rejected.

10.5 Valuation of Claims

If the Contractor incurs Cost as a result of any of the Procuring Agency‘s Risks, the Contractor shall be entitled to the amount of such Cost. If as a result of any Procuring Agency‘s Risk, it is necessary to change the Works, this shall be dealt with as a Variation subject to Contractor‘s notification for intention of claim to the Engineer/Procuring Agency within fourteen (14) days of the occurrence of cause.

10.6 Variation and Claim Procedure

The Contractor shall submit to the Engineer/Procuring Agency an itemized detailed breakdown of the value of variations and claims within twenty eight (28) days of the instruction or of the event giving rise to the claim. The Engineer/Procuring Agency shall check and if possible agree the value. In the absence of agreement, the Procuring Agency shall determine the value.

11. CONTRACT PRICE AND PAYMENT

11.1 (a) Terms of Payments

The amount due to the Contractor under any Interim Payment Certificate issued by the Engineer pursuant to this Clause, or to any other terms of the Contract, shall , subject to Clause 11.3, be paid by the Procuring Agency to the Contractor within 30 days after such Interim Payment Certificate has been jointly verified by Procuring Agency and Contractor, or, in the case of the Final Certificate referred to in Sub Clause 11.5, within 60days after such Final Payment Certificate has been jointly verified by Procuring Agency and Contractor; Provided that the Interim Payment shall be caused in thirty (30) days and Final Payment in 60 days in case of foreign funded project. In the event of the failure of the Procuring Agency to make payment within 90 days then Procuring Agency shall pay to the Contractor compensation at the 28 days rate of KIBOR+2% per annum in local currency and LIBOR+1% for foreign currency, upon all sums unpaid from the date by which the same should have been paid.

(b) Valuation of the Works

The Works shall be valued as provided for in the Contract Data, subject to Clause 10.

11.2 Monthly Statements

The Contractor shall be entitled to be paid at monthly intervals:

a) The value of the Works executed less to the cumulative amount paid previously; and

b) Value of secured advance on the materials and valuation of variations (if any).

The Contractor shall submit each month to the Engineer/Procuring Agency a statement showing the amounts to which he considers himself entitled.

44

11.3 Interim Payments

Within a period not exceeding seven (07) days from the date of submission of a statement for interim payment by the Contractor, the Engineer shall verify the same and within a period not exceeding thirty (30/60) days from the said date of submission by the Contractor, the Procuring Agency shall pay to the Contractor the sum subject to adjustment for deduction of the advance payments and retention money.

11.4 Retention

Retention money shall be paid by the Procuring Agency to the Contractor within fourteen (14) days after either the expiry of the period stated in the Contract Data, or the remedying of notified defects, or the completion of outstanding work, all as referred to in Sub-Clause 9.1, whichever is the later.

11.5 Final Payment

Within twenty one (21) days from the date of issuance of the Maintenance Certificate the Contractor shall submit a final account to the Engineer to verify and the Engineer shall verify the same within fourteen (14) days from the date of submission and forward the same to the Procuring Agency together with any documentation reasonably required to enable the Procuring Agency to ascertain the final contract value. Within sixty (60) days from the date of receipt of the verified final account from the Engineer, the Procuring Agency shall pay to the Contractor any amount due to the Contractor. While making such payment the Procuring Agency may, for

Reasons to be given to the Contractor in writing, withhold any part or parts of the verified amount.

11.6 Currency

Payment shall be in the currency stated in the Contract Data.

12. DEFAULT

12.1 Defaults by Contractor

If the Contractor abandons the Works, refuses or fails to comply with a valid instruction of the Engineer/Procuring Agency or fails to proceed expeditiously and without delay, or is, despite a written complaint, in breach of the Contract, the Procuring Agency may give notice referring to this Sub-Clause and stating the default.

If the Contractor has not taken all practicable steps to remedy the default within fourteen (14) days after receipt of the Procuring Agency‘s notice, the Procuring Agency may by a second notice given within a further twenty one (21) days, terminate the Contract. The Contractor shall then demobilize from the Site leaving behind any Contractor‘s Equipment which the Procuring Agency instructs, in the second notice, to be used for the completion of the Works at the risk and cost of the Contractor.

12.2 Defaults by Procuring Agency

If the Procuring Agency fails to pay in accordance with the Contract, or is, despite a written complaint, in breach of the Contract, the Contractor may give notice referring to this Sub-Clause and stating the default. If the default is not remedied within fourteen (14) days after the Procuring Agency‘s receipt of this notice, the Contractor may suspend the execution of all or parts of the Works.

If the default is not remedied within twenty eight (28) days after the Procuring Agency‘s receipt of the Contractor‘s notice, the Contractor may by a second notice given within a further twenty one (21) days, terminate the Contract. The Contractor shall then demobilize from the Site.

12.3 Insolvency

If a Party is declared insolvent under any applicable law, the other Party may by notice terminate the Contract immediately. The Contractor shall then demobilize from the site leaving behind, in the case of the Contractor‘s insolvency, any Contractor‘s Equipment which the Procuring Agency instructs in the notice is to be used for the completion of the Works.

12.4 Payment upon Termination

After termination, the Contractor shall be entitled to payment of the unpaid balance of the value of the works executed and of the Materials and Plant reasonably delivered to the site, adjusted by the following:

a) any sums to which the Contractor is entitled under Sub-Clause 10.4,

b) any sums to which the Procuring Agency is entitled,

c) if the Procuring Agency has terminated under Sub-Clause 12.1 or 12.3, the Procuring Agency shall be entitled to a sum equivalent to twenty percent (20%) of the value of parts of the Works not executed at the date of the termination, and

d) if the Contractor has terminated under Sub-Clause 12.2 or 12.3, the Contractor shall be entitled to the cost of his demobilization together with a sum equivalent to ten percent (10%) of the value of parts of the works not executed at the date of termination. The net balance due shall be paid or repaid within twenty eight (28) days of the notice of termination.

13. RISKS AND RESPONSIBILITIES

13.1 Contractor’s Care of the Works

Subject to Sub-Clause 9.1, the Contractor shall take full responsibility for the care of the Works from the Commencement Date until the date of the Procuring Agency‘s/Engineer‘s issuance of Certificate of Completion under Sub-Clause 8.2. Responsibility shall then pass to the Procuring Agency. If any loss or damage happens to the Works during the above period, the Contractor shall rectify such loss or damage so that the Works conform with the Contract. Unless the loss or damage happens as a result of any of the Procuring Agency‘s Risks, the Contractor shall indemnify the Procuring Agency, or his agents against all claims loss, damage and expense arising out of the Works.

13.2 Force Majeure

If Force Majeure occurs, the Contractor shall notify the Engineer/Procuring Agency immediately. If necessary, the Contractor may suspend the execution of the Works and, to the extent agreed with the Procuring Agency demobilize the Contractor‘s Equipment. If the event continues for a period of eighty four (84) days, either Party may then give notice of termination which shall take effect twenty eight (28) days after the giving of the notice. After termination, the Contractor shall be entitled to payment of the unpaid balance of the value of the Works executed and of the Materials and Plant reasonably delivered to the Site, adjusted by the following:

a) any sums to which the Contractor is entitled under Sub-Clause 10.4,

b) the cost of his demobilization, and

c) less any sums to which the Procuring Agency is entitled. The net balance due shall be paid or repaid within thirty five (35) days of the notice of termination.

14. INSURANCE

14.1 Arrangements

The Contractor shall, prior to commencing the Works, effect insurances of the types, in the amounts and naming as insured the persons stipulated in the Contract Data except for items (a) to (e) and (i) of the Procuring Agency‘s Risks under Sub- Clause 6.1. The policies shall be issued by insurers and in terms approved by the Procuring Agency. The Contractor shall provide the Engineer/Procuring Agency with evidence that any required policy is in force and that the premiums have been paid.

14.2 Default

If the Contractor fails to effect or keep in force any of the insurances referred to in the previous Sub-Clause, or fails to provide satisfactory evidence, policies or receipts, the Procuring Agency may, without prejudice to any other right or remedy, effect insurance for the cover relevant to such as a default and pay the premiums due and recover the same plus a sum in percentage given in Contractor Data from any other amounts due to the Contractor.

15. RESOLUTION OF DISPUTES

15.1 Engineer’s Decision

If a dispute of any kind whatsoever arises between the Procuring Agency and the Contractor in connection with the works, the matter in dispute shall, in the first place, be referred in writing to the Engineer, with a copy to the other party. Such reference shall state that it is made pursuant to this Clause. No later than the twenty eight (28) days after the day on which he received such reference, the Engineer shall give notice of his decision to the Procuring Agency (Engineer)and the Contractor. Unless the Contract has already been repudiated or terminated, the Contractor shall, in every case, continue to proceed with the work with all due diligence, and the Contractor and the Procuring Agency ( Engineer) shall give effect forthwith to every such decision of the Engineer unless and until the same shall be revised, as hereinafter provided in an arbitral award.

15.2 Notice of Dissatisfaction

If a Party is dissatisfied with the decision of the Engineer of consultant or if no decision is given within the time set out in Sub-Clause 15.1 here above, the Party may give notice of dissatisfaction referring to this Sub-Clause within fourteen (14) days of receipt of the decision or the expiry of the time for the decision. If no notice of dissatisfaction is given within the specified time, the decision shall be final and binding on the Parties. If notice of dissatisfaction is given within the specified time, the decision shall be binding on the Parties who shall give effect to it without delay unless and until the decision of the Engineer is revised by an arbitrator. If a contractor is dissatisfied with the decision of the Engineer of the department or decision is not given in time then he can approach (Engineer) within 14 days, in case of dissatisfaction with decision of ( Engineer) or not decided within 28 days, then arbitration process would be adopted as per clause 15.3.

15.3 Arbitration

A dispute which has been the subject of a notice of dissatisfaction shall be finally settled as per provisions of Arbitration Act 1940 (Act No. X of 1940) and Rules made there under and any statutory modifications thereto. Any hearing shall be held at the place specified in the Contract Data and in the language referred to in Sub-Clause 1.5.

Contractor

Executive Engineer

PHE Division Dadu

BILL OF QUANTITY. Name of work: - (2); CONSTRUCTION OF SURFACE DRAINS & C.C BLOCK FOR VARIOUS MUHALLAS ZONE B UNDER BASIC HUMAN FACILITIES DRAINAGE SCHEME JOHI CITY.. Head of Account:-; BASIC HUMAN FACILITIES OF DRAINAGE SCHEME JOHI. S.No:; Item; Qty:.; Rate; Unit; Amount. SURFACE DRAINS. 1; Dismantling and removing Road Metalling (G.S.I No. 51 P/ 13). 250.00; Cft; @ Rs:; 605.00; P%Cft; Rs:; 1513. 2; Dismantling of Brick Work in lime or cement mortor (G.S.I No 13 P/ 10). 75.00; Cft; @ Rs:; 1285.63; P%Cft; Rs:; 964. 3; Dismantling of C.C plain 1:2:4 ( G.S.I No 19 P/ 10). 37.50; Cft; @ Rs:; 3327.50; P%Cft; Rs:; 1248. 4; Dismantling of C.C Reinforced Separting Reinforcement from Concrete, cleaning. and straighting the same. (G.S.I No 20 P/ 10). 75.00; Cft; @ Rs:; 5445.00; P%Cft; Rs:; 4084. 5; Excavation in foundation of building bridges and other structures. i/c dig billing dressing refilling around the structures with excavated. Earth watering ramming up to 5ft (b) in ordinary soil (G.S.I-18/ P/4). 21440; Cft; @Rs; 3176.25; P%Cft; Rs:; 68099. 6; Cement concrete plain i/c placing compacting finishing. and curing complete i/c screening and washing of stone. aggregate without shuttering Ratio 1:4:8 (G.S.I-5 P/15). 4985.00; Cft; @Rs; 11288.75; P%Cft; Rs:; 562744. 7; Construction of standard open type drains connuttee block. of C.C 1:2:4 cost of situ to the design profiles i/c cost of mould. as per drawing i/c supplying floating cost of cement 1/32” thick. to expose surface faces finished smooth curing complete as per. drawing design. (P.H.S.I No D, P/ 58). 7000; Rft; Type A; @Rs; 94; P/Rft; Rs:; 658000. 1000; Rft; Type B; @Rs; 174; P/Rft; Rs:; 174000. Rft; Type C; @Rs; 309; P/Rft; Rs:; 0. 8; Pacca brick work in foundation and plinth in cement sand mortar(1:6). (G.S.I No. 4 P/ 20). 13125.00; Cft; @Rs; 11948.36; P%Cft; Rs:; 1568222. Cement plaster (1:4) up to 12’height ½”thick (G.S.I-11, P/51). 23380.00; Sft.; @Rs; 2283.93; P%Sft; Rs:; 533983. 10; R.C.C work i/c all labour and material except the cost of steel. reinforcement and its labour for bending and binding which will. be paid separately. This rate also includes all kinds of forms moulds. lifting shuttering curing rendering and finishing the exposed surface. i/c screening and washing of shingle (a) R.C work in roof slab members. laid in situ or prrecast laid in position complete in a respect. (i). Ratio 1;2;4 90 lbs cement 2 cft sand 4 cft shingle 1/8” to ¼” gauge.. (G.S.I-6 P/16). 396.80; Cft; @Rs; 337; P%Cft; Rs:; 133722. 11; Fabrication of mild steel reinforcement for cement concrete i/c. cutting bending laying in position making joints and fastening i/c. cost of binding wire also includes removal of rust from bars.. (G.S.I-8 (a) P/16). 14.17; Cwt; @Rs; 5001.7; P%Cft; Rs:; 70881. 12; Cement concrete plain i/c placing compacting, finishing. and curing complete i/c s/w of stone aggregate without. shuttering (G.S.I No. 5 p/ 15). 303.00; Cft; (RATIO 1:2;4); @Rs; 14429.25; P%Cft; Rs:; 43721. Rs:; 3821180. C.C BLOCK. 1; Barrow pit excavation undressed lead upto 100 ft ordinary soil. (G.S.I. No. 3 p/ 1). 30560; Cft; @Rs; 2117.5; P%Cft; Rs:; 64711. 2; Extra for every 50' additional lead or part there of. (a) for earth work (soft ordinary hard and very hard.). 30560.00; Cft; @Rs; 4837.44; P%Cft; Rs:; 147832. 3; Earth work compaction (Soft ordinary or hard soil lying. earth in 6” layers leveling dressing and watering for compaction. etc: complete.(G.S.I.No. 13 p/ 3). 52000; Cft; @Rs; 354; P%Cft; Rs:; 18408. 4; Cement concrete bricks or stone ballest ½” to 2” gauge.(Ratio 1:4:8). (G.SI. No. 4 p/ 14). 17160; Cft; @Rs; 9416.28; P%Cft; Rs:; 1615834. 5; Cement concrete plain i/c placing compacting, finishing. and curing complete i/c s/w of stone aggregate without. shuttering (Ratio 1:2:4) (G.S.I No. 5 p/ 15). 13000; Cft; @Rs; 14429.25; P%Cft; Rs:; 1875803. 6; Erection and removal of centering for R.C.C or plain C.C works. of deodars wood (2nd class) (b) for partal wood (vertical).. (G.S.I.No. 19 p/ 17). 2925; Cft; @Rs; 3127.41; P%Cft; Rs:; 91477. Rs:; 3814064. ABSTRACT. SURFACE DRAINS; Rs:; 3821180. C.C BLOCK; Rs:; 3814064. Rs:; 7635244. Total Amount of Composite Schedule; Rs:. %; above / below on the rates of CSR. Amount to be added / deducted on the basis of premium; Rs:. Total Amount of Non Schedule items; Rs:. TOTAL AMOUNT .; Rs:. CONDITIONS. 1; The contractor will have to remove the surplus excavated stuff. from the side of work to be out of town at his own cost. 2; The contractor arrange the material for construction of work from. the approved quarry as shown in the estimate.. 3; No premium should be allowed on approved / market rate.. 4; Any error or omission in the rate description unit shall be reffered to particular schedule of rates. 5; No cartage shall be paid seprately..

GOVERNMENT OF SINDH

PUBLIC HEALTH ENGINEERING DIVISION DADU

STANDARD BIDDING DOCUMENTS

PROCUREMENT OF WORKS (SPPRA BIDDING DOCUMENTS)

For Contracts (Small) amounting between Rs. 4.0 (M) to Rs. 50.00  (M).

Name of Work:		(03)  Providing Installing Pumping Machinery for

Oxidation Pond Zone-“A” & “B” for Basic Human Facilities Drainage Scheme Johi .

N.I.T NO: & DATE:		NO: TC/      1334  /   dated:- 15-12-2016

DATE OF ISSUE:                  10-01-2017

DATE OF OPENING:            11-01-2017

TENDER ISSUED TO:      .	     							.

D.R.NO: & DATE:            .	     							.

STANDARD BIDDING DOCUMENT IS INTENDED AS MODEL FOR

ADMEASUREMENTS (PERCENTAGE RATE FOR UNIT RATES IN A BILL OF QUANTITIES TYPES OF CONTRACT THE MAIN TEXT REFERS TO ADMEASUREMENTS CONTRACTOS.

EXECUTIVE ENGINEER

Public Health Engineering Division

DADU

BIDDING DATA

(This section  should be filled in by the office of the Executive Engineer,

Public Engineering Division Dadu, before issuance of the bidding documents).

| (a) | Name of Procuring Agency:- | The Executive Engineer Public Health Engineering Division Dadu. |
| --- | --- | --- |
| (b) | Brief Description of works:- | (03) Providing Installing Pumping Machinery for Oxidation Pond Zone-“A” & “B” for Basic Human Facilities Drainage Scheme Johi . |
| © | Procuring Agency Address:- | The Executive Engineer Public Health Engineering Division Dadu. Near Gharibabad Muhalla Dadu. |
| (d) | Estimated Cost:- | Rs: 6.600 Million |
| (e) | Amount of Bid Security:- | Rs: 3,30,000/- |
| (f) | Period of Bid Validity (Days):- | (90 days) |
| (g) | Security Deposit (i/c Bid Security):- | (10`%) |
| (h) | Percentage, if any, to be deducted from bills:- | (7.50% Income Tax) & (8% Security Deposit). |
| (i) | Deadline for submission of Bids along with time:- | 10-01-2017 @ 1.30 PM |
| (j) | Venue, time & date of Bid Opening:- | 11-01-2017 @ 2.00 PM |
| (k) | Time for completion from written order of commence:- | (24 Months) |
| (l) | Liquidity Damages:- | (1% on estimated cost per day subject to minimum of 10%) |
| (m) | Deposit receipt No: date & Amount (in words and figure):- | C.D No:_____________ dated:-______________ Amount Rs:_____________Bank_____________. ._______________________________________. M/S____________________________________. |

EXECUTIVE ENGINEER

Public Health Engineering Division

DADU

INSTRUCTIONS TO BIDDERS

(Note: (These Instructions to Bidders (IB) along with Bidding Data will not be part of

Contract and will cease to have effect once the Contract is signed).

A. GENERAL

IB.1 Scope of Bid & Source of Funds

  - Scope of Bid

The Procuring Agency as defined in the Bidding Data (hereinafter called ―the Procuring Agency‖) wishes to receive Bids for the Works summarized in the Bidding Data (hereinafter referred to as ―the Works‖).

Bidders must quote for the complete scope of work. Any Bid covering partial scope of work will be rejected as non-responsive.

  - Source of Funds

The Procuring Agency has arranged funds from its own sources or Federal/ Provincial /Donor agency or any other source, which may be indicated accordingly in bidding data towards the cost of the project/scheme.

IB.2 Eligible Bidders

2.1 Bidding is open to all firms and persons meeting the following requirements:

a) Duly licensed by the Pakistan Engineering Council (PEC) in the appropriate category for value of works.

Provided that the works costing Rs. 4.00 million or less shall not require any registration with PEC .

b) Duly pre-qualified with the Procuring Agency. (Where required).

In the event that prequalification of potential bidders has been undertaken, only bids from prequalified bidders will be considered for award of Contract.

c) If prequalification has not undertaken, the procuring agency may ask information and documents not limited to following:-

(i) Company profile;

(ii) Works of similar nature and size for each performed in last 3/5 years;

(iii) Construction equipments;

(iv) Qualification and experience of technical personnel and key site management; Sindh Public Procurement Regulatory Authority | www.pprasindh.gov.pk 7

(v) Financial statement of last 3 years;

(vi) Information regarding litigations and abandoned works if any.

IB.3 Cost of Bidding

3.1 The bidder shall bear all costs associated with the preparation and submission of its bid

and the Procuring Agency will in no case be responsible or liable for those costs,

Regardless of the conduct or outcome of the bidding process (SPP Rules 24 & 25).

Executive Engineer

PHE Division Dadu

CONDITIONS OF CONTRACT

- GENERAL PROVISIONS

Definitions

In the Contract as defined below, the words and expressions defined shall have the following meanings assigned to them, except where the context requires otherwise:

The Contract

1.1.1 ―Contract‖ means the Contract Agreement and the other documents listed in the Contract Data.

1.1.2 ―Specifications‖ means the document as listed in the Contract Data, including Procuring Agency‘s requirements in respect of design to be carried out by the Contractor (if any), and any Variation to such document.

1.1.3 ―Drawings‖ means the Procuring Agency‘s drawings of the Works as listed in the Contract Data, and any Variation to such drawings.

Persons

1.1.4 ―Procuring Agency‖ means the person named in the Contract Data and the legal successors in title to this person, but not (except with the consent of the Contractor) any assignee.

1.1.5 ―Contractor‖ means the person named in the Contract Data and the legal successors in title to this person, but not (except with the consent of the Procuring Agency) any assignee.

1.1.6 ―Party‖ means either the Procuring Agency or the Contractor.

Dates, Times and Periods

1.1.7 ―Commencement Date‖ means the date fourteen (14) days after the date the Contract comes into effect or any other date named in the Contract Data.

1.1.8 ―Day‖ means a calendar day

1.1.9 ―Time for Completion‖ means the time for completing the Works as stated in the Contract Data (or as extended under Sub-Clause 7.3), calculated from the Commencement Date.

Money and Payments

1.1.10 ―Cost‖ means all expenditure properly incurred (or to be incurred) by the Contractor, whether on or off the Site, including overheads and similar charges but does not include any allowance for profit.

Other Definitions

1.1.11 ―Contractor‘s Equipment‖ means all machinery, apparatus and other things required for the execution of the Works but does not include Materials or Plant intended to form part of the Works.

1.1.12 ―Country‖ means the Islamic Republic of Pakistan.

1.1.13 ―Procuring Agency‘s Risks‖ means those matters listed in Sub-Clause 6.1.

1.1.14 ―Force Majeure‖ means an event or circumstance which makes performance of a Party‘s obligations illegal or impracticable and which is beyond that Party‘s reasonable control.

1.1.15 ‗Materials‖ means things of all kinds (other than Plant) to be supplied and incorporated in the Works by the Contractor.

1.1.16 ―Plant‖ means the machinery and apparatus intended to form or forming part of the Works.

1.1.17 ―Site‖ means the places provided by the Procuring Agency where the Works are to be executed, and any other places specified in the Contract as forming part of the Site.

1.1.18 ―Variation‖ means a change which is instructed by the Engineer/Procuring Agency under Sub-Clause 10.1.

1.1.19 ‗Works‖ means any or all the works whether Supply, Installation, Construction etc. and design (if any) to be performed by the Contractor including temporary works and any variation thereof.

1.1.20 ―Engineer‖ means the person notified by the Procuring Agency to act as Engineer

for the purpose of the Contract and named as such in Contract Data.

  - Interpretation

Words importing persons or parties shall include firms and organizations. Words importing singular or one gender shall include plural or the other gender where the context requires.

  - Priority of Documents.

The documents forming the Contract are to be taken as mutually explanatory of one another. If an ambiguity or discrepancy is found in the documents, the priority of the documents shall be in accordance with the order as listed in the Contract Data.

37

1.4 Law

The law of the Contract is the relevant Law of Islamic Republic of Pakistan.

1.5 Communications

All Communications related to the Contract shall be in English language.

1.6 Statutory Obligations

The Contractor shall comply with the Laws of Islamic Republic of Pakistan and shall give all notices and pay all fees and other charges in respect of the Works.

- THE PROCURING AGENCY

2.1 Provision of Site

The Procuring Agency shall provide the Site and right of access thereto at the times stated in the Contract Data. Site Investigation Reports are those that were included in the bidding documents

and are factual and interpretative reports about the surface and subsurface conditions at the Site.

2.2 Permits etc.

The Procuring Agency shall, if requested by the Contractor, assist him in applying for permits, licenses or approvals which are required for the Works.

2.3 Engineer’s/Procuring Agency’s Instructions

The Contractor shall comply with all instructions given by the Procuring Agency or the Engineer, if notified by the Procuring Agency, in respect of the Works including the suspension of all or part of the works.

2.4 Approvals

No approval or consent or absence of comment by the Engineer/Procuring Agency shall affect the Contractor‘s obligations.

- ENGINEER’S/PROCURING AGENCY’S REPRESENTATIVES

3.1 Authorized Person

The Procuring Agency shall appoint a duly authorized person to act for him and on his behalf for the purposes of this Contract. Such authorized person shall be duly identified in the Contract Data or otherwise notified in writing to the Contractor as soon as he is so appointed. In either case the Procuring Agency shall notify the Contractor, in writing, the precise scope of the authority of such authorized person at the time of his appointment.

3.2 Engineer’s/Procuring Agency’s Representative

The name and address of Engineer‘s/Procuring Agency‘s Representative is given in Contract Data. However the Contractor shall be notified by the Engineer/Procuring Agency, the delegated duties and authority before the Commencement of works.

- THE CONTRACTOR

4.1 General Obligations

The Contractor shall carry out the works properly and in accordance with the Contract. The Contractor shall provide all supervision, labour, Materials, Plant and Contractor‘s Equipment which may be required

4.2 Contractor’s Representative

The Contractor shall appoint a representative at site on full time basis to supervise the execution of work and to receive instructions on behalf of the Contractor but only after obtaining the consent of the Procuring Agency for such appointment which consent shall not be withheld without plausible reason(s) by the Procuring Agency. Such authorized representative may be substituted/ replaced by the Contractor at any time during the Contract Period but only after obtaining the consent of the Procuring Agency as aforesaid.

4.3 Subcontracting

The Contractor shall not subcontract the whole of the works. The Contractor shall not subcontract any part of the works without the consent of the Procuring Agency.

4.4 Performance Security

The Contractor shall furnish to the Procuring Agency within fourteen (14) days after receipt of Letter of Acceptance a Performance Security at the option of the bidder, in the form of Payee‘s order /Bank Draft or Bank Guarantee from scheduled bank for the amount and validity specified in Contract Data.

- DESIGN BY CONTRACTOR

5.1 Contractor’s Design

The Contractor shall carry out design to the extent specified, as referred to in the Contract Data. The Contractor shall promptly submit to the Engineer/Procuring Agency all designs prepared by him, within fourteen (14) days of receipt the Engineer/Procuring Agency shall notify any comments or, if the design submitted is not in accordance with the Contract, shall reject it stating the reasons. Contractor shall not construct any element of the works designed by him within fourteen (14) days after the design has been submitted to the Engineer/Procuring Agency or which has been rejected. Design that has been rejected shall be promptly amended and resubmitted. The Contractor shall resubmit all designs commented on taking these comments into account as necessary.

5.2 Responsibility for Design

The Contractor shall remain responsible for his bided design and the design under this Clause, both of which shall be fit for the intended purposes defined in the Contract and he shall also remain responsible for any infringement of any patent or copyright in respect of the same. The Engineer/Procuring Agency shall be responsible for the Specifications and Drawings.

- PROCURING AGENCY’S RISKS

6.1 The Procuring Agency’s Risks

The Procuring Agency‘s Risks are:-

a) war, hostilities (whether war be declared or not), invasion, act of foreign enemies, within the Country;

b) Rebellion, terrorism, revolution, insurrection, military or usurped power, or civil war, within the Country;

c) riot, commotion or disorder by persons other than the Contractor‘s personnel and other employees including the personnel and employees of Sub- Contractors, affecting the Site and/or the Works;

d) ionizing radiations, or contamination by radio-activity from any nuclear fuel, or from any nuclear waste from the combustion of nuclear fuel, radio-active toxic explosive, or other hazardous properties of any explosive nuclear assembly or nuclear component of such an assembly, except to the extent to which the Contractor/Sub-Contractors may be responsible for the use of any radio-active material;

e) Pressure waves caused by aircraft or other aerial devices travelling at sonic or supersonic speeds;

f) Use or occupation by the Procuring Agency of any part of the Works, except as may be specified in the Contract;

g) late handing over of sites, anomalies in drawings, late delivery of designs and drawings of any part of the Works by the Procuring Agency‘s personnel or by others for whom the Procuring Agency is responsible;

h) a suspension under Sub-Clause 2.3 unless it is attributable to the Contractor‘s failure; and

i) physical obstructions or physical conditions other than climatic conditions, encountered on the Site during the performance of the Works, for which the Contractor immediately notified to the Procuring Agency and accepted by the Procuring Agency.

7. TIME FOR COMPLETION

7.1 Execution of the Works

The Contractor shall commence the Works on the Commencement Date and shall proceed expeditiously and without delay and shall complete the Works, subject to Sub-Clause 7.3 below, within the Time for Completion.

7.2 Programme

Within the time stated in the Contract Data, the Contractor shall submit to the Engineer/Procuring Agency a programme for the Works in the form stated in the Contract Data.

7.3 Extension of Time

The Contractor shall, within such time as may be reasonable under the circumstances, notify the Procuring Agency/Engineer of any event(s) falling within the scope of Sub-Clause 6.1 or 10.3 of these Conditions of Contract and request the Procuring Agency/Engineer for a reasonable extension in the time for the completion of works. Subject to the aforesaid, the Procuring Agency/Engineer shall determine such reasonable extension in the time for the completion of works as may be justified in the light of the details/particulars supplied by the Contractor in connection with the such determination by the Procuring Agency/Engineer within such period as may be prescribed by the Procuring Agency/Engineer for the same; and the Procuring Agency may extend the time for completion as determined.

7.4 Late Completion

If the Contractor fails to complete the Works within the Time for Completion, the Contractor‘s only liability to the Procuring Agency for such failure shall be to pay the amount as liquidity damages stated in the Contract Data for each day for which he fails to complete the Works.

8. TAKING-OVER

8.1 Completion

The Contractor may notify the Engineer/Procuring Agency when he considers that the Works are complete.

8.2 Taking-Over Notice

Within fourteen (14) days of the receipt of the said notice of completion from the Contractor the Procuring Agency/Engineer shall either takeover the completed works and issue a Certificate of Completion to that effect or shall notify the Contractor his reasons for not taking-over the works. While issuing the Certificate of Completion as aforesaid, the Procuring Agency/Engineer may identify any outstanding items of work which the Contractor shall undertake during the

Maintenances Period.

9. REMEDYING DEFECTS

9.1 Remedying Defects

The Contractor shall for a period stated in the Contract Data from the date of issue of the Certificate of Completion carry out, at no cost to the Procuring Agency, repair and rectification work which is necessitated by the earlier execution of poor quality of work or use of below specifications material in the execution of Works and which is so identified by the Procuring Agency/Engineer in writing within the said period. Upon expiry of the said period, and subject to the Contractor‘s faithfully performing his aforesaid obligations, the Procuring Agency/Engineer

shall issue a Maintenance Certificate whereupon all obligations of the Contractor under this Contract shall come to an end. Failure to remedy any such defects or complete outstanding work within a reasonable time shall entitle the Procuring Agency to carry out all necessary works at the Contractor‘s cost. However, the cost of remedying defects not attributable to the Contractor shall be valued as a Variation.

9.2 Uncovering and Testing

The Engineer/Procuring Agency may give instruction as to the uncovering and / or testing of any work. Unless as a result of an uncovering and/or testing it is established that the Contractor‘s design, materials, plant or workmanship are not in accordance with the Contract, the Contractor shall be paid for such uncovering and/or testing as a Variation in accordance with Sub-Clause 10.2.

10. VARIATIONS AND CLAIMS

10.1 Right to Vary

The Procuring Agency/Engineer may issue Variation Order(s) in writing. Where for any reason it has not been possible for the Procuring Agency/Engineer to issue such Variations Order(s), the Contractor may confirm any verbal orders given by the Procuring Agency/Engineer in writing and if the same are not refuted/denied by the Procuring Agency/Engineer within ten (10) days of the receipt of such confirmation the same shall be deemed to be a Variation Orders for the purposes of this Sub-Clause.

10.2 Valuation of Variations

Variations shall be valued as follows:

a) At a lump sum price agreed between the Parties, or

b) Where appropriate, at rates in the Contract, or

c) In the absence of appropriate rates, the rates in the Contract shall be used as the basis for valuation, or failing which

d) At appropriate new rates, as may be agreed or which the Engineer/Procuring Agency considers appropriate, or

e) If the Engineer/Procuring Agency so instructs, at day work rates set out in the Contract Data for which the Contractor shall keep records of hours of labour and Contractor‘s Equipment, and of Materials, used.

10.3 Changes in the Quantities.

a) If the final quantity of the work done differs from the quantity in the Bill of Quantities for the particular item by more than 25 percent, provided the change exceeds 1 percent of the Initial Contract Price, the Procuring Agency/Engineer shall adjust the rate to allow for the change and will be valued as per sub clause 10.2.

b) The Engineer shall not adjust rates from changes in quantities if thereby the Initial Contract Price is exceeded by more than 15 percent, except with the prior approval of the Procuring Agency.

c) If requested by the Engineer, the contractor shall provide the Engineer with a detailed cost breakdown of any rate in the Bill of Quantities.

10.4 Early Warning

The Contractor shall notify the Engineer/Procuring Agency in writing as soon as he is aware of any circumstance which may delay or disrupt the Works, or which may give rise to a claim for additional payment. To the extent of the Contractor‘s failure to notify, which results to the Engineer/Procuring Agency being unable to keep all relevant records or not taking steps to minimize any delay, disruption, or Cost, or the value of any Variation, the Contractor‘s entitlement to extension of the Time for Completion or additional payment shall be reduced/rejected.

10.5 Valuation of Claims

If the Contractor incurs Cost as a result of any of the Procuring Agency‘s Risks, the Contractor shall be entitled to the amount of such Cost. If as a result of any Procuring Agency‘s Risk, it is necessary to change the Works, this shall be dealt with as a Variation subject to Contractor‘s notification for intention of claim to the Engineer/Procuring Agency within fourteen (14) days of the occurrence of cause.

10.6 Variation and Claim Procedure

The Contractor shall submit to the Engineer/Procuring Agency an itemized detailed breakdown of the value of variations and claims within twenty eight (28) days of the instruction or of the event giving rise to the claim. The Engineer/Procuring Agency shall check and if possible agree the value. In the absence of agreement, the Procuring Agency shall determine the value.

11. CONTRACT PRICE AND PAYMENT

11.1 (a) Terms of Payments

The amount due to the Contractor under any Interim Payment Certificate issued by the Engineer pursuant to this Clause, or to any other terms of the Contract, shall , subject to Clause 11.3, be paid by the Procuring Agency to the Contractor within 30 days after such Interim Payment Certificate has been jointly verified by Procuring Agency and Contractor, or, in the case of the Final Certificate referred to in Sub Clause 11.5, within 60days after such Final Payment Certificate has been jointly verified by Procuring Agency and Contractor; Provided that the Interim Payment shall be caused in thirty (30) days and Final Payment in 60 days in case of foreign funded project. In the event of the failure of the Procuring Agency to make payment within 90 days then Procuring Agency shall pay to the Contractor compensation at the 28 days rate of KIBOR+2% per annum in local currency and LIBOR+1% for foreign currency, upon all sums unpaid from the date by which the same should have been paid.

(b) Valuation of the Works

The Works shall be valued as provided for in the Contract Data, subject to Clause 10.

11.2 Monthly Statements

The Contractor shall be entitled to be paid at monthly intervals:

a) The value of the Works executed less to the cumulative amount paid previously; and

b) Value of secured advance on the materials and valuation of variations (if any).

The Contractor shall submit each month to the Engineer/Procuring Agency a statement showing the amounts to which he considers himself entitled.

44

11.3 Interim Payments

Within a period not exceeding seven (07) days from the date of submission of a statement for interim payment by the Contractor, the Engineer shall verify the same and within a period not exceeding thirty (30/60) days from the said date of submission by the Contractor, the Procuring Agency shall pay to the Contractor the sum subject to adjustment for deduction of the advance payments and retention money.

11.4 Retention

Retention money shall be paid by the Procuring Agency to the Contractor within fourteen (14) days after either the expiry of the period stated in the Contract Data, or the remedying of notified defects, or the completion of outstanding work, all as referred to in Sub-Clause 9.1, whichever is the later.

11.5 Final Payment

Within twenty one (21) days from the date of issuance of the Maintenance Certificate the Contractor shall submit a final account to the Engineer to verify and the Engineer shall verify the same within fourteen (14) days from the date of submission and forward the same to the Procuring Agency together with any documentation reasonably required to enable the Procuring Agency to ascertain the final contract value. Within sixty (60) days from the date of receipt of the verified final account from the Engineer, the Procuring Agency shall pay to the Contractor any amount due to the Contractor. While making such payment the Procuring Agency may, for

Reasons to be given to the Contractor in writing, withhold any part or parts of the verified amount.

11.6 Currency

Payment shall be in the currency stated in the Contract Data.

12. DEFAULT

12.1 Defaults by Contractor

If the Contractor abandons the Works, refuses or fails to comply with a valid instruction of the Engineer/Procuring Agency or fails to proceed expeditiously and without delay, or is, despite a written complaint, in breach of the Contract, the Procuring Agency may give notice referring to this Sub-Clause and stating the default.

If the Contractor has not taken all practicable steps to remedy the default within fourteen (14) days after receipt of the Procuring Agency‘s notice, the Procuring Agency may by a second notice given within a further twenty one (21) days, terminate the Contract. The Contractor shall then demobilize from the Site leaving behind any Contractor‘s Equipment which the Procuring Agency instructs, in the second notice, to be used for the completion of the Works at the risk and cost of the Contractor.

12.2 Defaults by Procuring Agency

If the Procuring Agency fails to pay in accordance with the Contract, or is, despite a written complaint, in breach of the Contract, the Contractor may give notice referring to this Sub-Clause and stating the default. If the default is not remedied within fourteen (14) days after the Procuring Agency‘s receipt of this notice, the Contractor may suspend the execution of all or parts of the Works.

If the default is not remedied within twenty eight (28) days after the Procuring Agency‘s receipt of the Contractor‘s notice, the Contractor may by a second notice given within a further twenty one (21) days, terminate the Contract. The Contractor shall then demobilize from the Site.

12.3 Insolvency

If a Party is declared insolvent under any applicable law, the other Party may by notice terminate the Contract immediately. The Contractor shall then demobilize from the site leaving behind, in the case of the Contractor‘s insolvency, any Contractor‘s Equipment which the Procuring Agency instructs in the notice is to be used for the completion of the Works.

12.4 Payment upon Termination

After termination, the Contractor shall be entitled to payment of the unpaid balance of the value of the works executed and of the Materials and Plant reasonably delivered to the site, adjusted by the following:

a) any sums to which the Contractor is entitled under Sub-Clause 10.4,

b) any sums to which the Procuring Agency is entitled,

c) if the Procuring Agency has terminated under Sub-Clause 12.1 or 12.3, the Procuring Agency shall be entitled to a sum equivalent to twenty percent (20%) of the value of parts of the Works not executed at the date of the termination, and

d) if the Contractor has terminated under Sub-Clause 12.2 or 12.3, the Contractor shall be entitled to the cost of his demobilization together with a sum equivalent to ten percent (10%) of the value of parts of the works not executed at the date of termination. The net balance due shall be paid or repaid within twenty eight (28) days of the notice of termination.

13. RISKS AND RESPONSIBILITIES

13.1 Contractor’s Care of the Works

Subject to Sub-Clause 9.1, the Contractor shall take full responsibility for the care of the Works from the Commencement Date until the date of the Procuring Agency‘s/Engineer‘s issuance of Certificate of Completion under Sub-Clause 8.2. Responsibility shall then pass to the Procuring Agency. If any loss or damage happens to the Works during the above period, the Contractor shall rectify such loss or damage so that the Works conform with the Contract. Unless the loss or damage happens as a result of any of the Procuring Agency‘s Risks, the Contractor shall indemnify the Procuring Agency, or his agents against all claims loss, damage and expense arising out of the Works.

13.2 Force Majeure

If Force Majeure occurs, the Contractor shall notify the Engineer/Procuring Agency immediately. If necessary, the Contractor may suspend the execution of the Works and, to the extent agreed with the Procuring Agency demobilize the Contractor‘s Equipment. If the event continues for a period of eighty four (84) days, either Party may then give notice of termination which shall take effect twenty eight (28) days after the giving of the notice. After termination, the Contractor shall be entitled to payment of the unpaid balance of the value of the Works executed and of the Materials and Plant reasonably delivered to the Site, adjusted by the following:

a) any sums to which the Contractor is entitled under Sub-Clause 10.4,

b) the cost of his demobilization, and

c) less any sums to which the Procuring Agency is entitled. The net balance due shall be paid or repaid within thirty five (35) days of the notice of termination.

14. INSURANCE

14.1 Arrangements

The Contractor shall, prior to commencing the Works, effect insurances of the types, in the amounts and naming as insured the persons stipulated in the Contract Data except for items (a) to (e) and (i) of the Procuring Agency‘s Risks under Sub- Clause 6.1. The policies shall be issued by insurers and in terms approved by the Procuring Agency. The Contractor shall provide the Engineer/Procuring Agency with evidence that any required policy is in force and that the premiums have been paid.

14.2 Default

If the Contractor fails to effect or keep in force any of the insurances referred to in the previous Sub-Clause, or fails to provide satisfactory evidence, policies or receipts, the Procuring Agency may, without prejudice to any other right or remedy, effect insurance for the cover relevant to such as a default and pay the premiums due and recover the same plus a sum in percentage given in Contractor Data from any other amounts due to the Contractor.

15. RESOLUTION OF DISPUTES

15.1 Engineer’s Decision

If a dispute of any kind whatsoever arises between the Procuring Agency and the Contractor in connection with the works, the matter in dispute shall, in the first place, be referred in writing to the Engineer, with a copy to the other party. Such reference shall state that it is made pursuant to this Clause. No later than the twenty eight (28) days after the day on which he received such reference, the Engineer shall give notice of his decision to the Procuring Agency (Engineer)and the Contractor. Unless the Contract has already been repudiated or terminated, the Contractor shall, in every case, continue to proceed with the work with all due diligence, and the Contractor and the Procuring Agency ( Engineer) shall give effect forthwith to every such decision of the Engineer unless and until the same shall be revised, as hereinafter provided in an arbitral award.

15.2 Notice of Dissatisfaction

If a Party is dissatisfied with the decision of the Engineer of consultant or if no decision is given within the time set out in Sub-Clause 15.1 here above, the Party may give notice of dissatisfaction referring to this Sub-Clause within fourteen (14) days of receipt of the decision or the expiry of the time for the decision. If no notice of dissatisfaction is given within the specified time, the decision shall be final and binding on the Parties. If notice of dissatisfaction is given within the specified time, the decision shall be binding on the Parties who shall give effect to it without delay unless and until the decision of the Engineer is revised by an arbitrator. If a contractor is dissatisfied with the decision of the Engineer of the department or decision is not given in time then he can approach (Engineer) within 14 days, in case of dissatisfaction with decision of ( Engineer) or not decided within 28 days, then arbitration process would be adopted as per clause 15.3.

15.3 Arbitration

A dispute which has been the subject of a notice of dissatisfaction shall be finally settled as per provisions of Arbitration Act 1940 (Act No. X of 1940) and Rules made there under and any statutory modifications thereto. Any hearing shall be held at the place specified in the Contract Data and in the language referred to in Sub-Clause 1.5.

Contractor

Executive Engineer

PHE Division Dadu

| BILL OF QUANTITY |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Name of work: - (3) |  | PROVIDING INSTALLING PUMPING MACHINERY FOR OXIDATION POUND ZONE A & B UNDER BASIC HUMAN FACILITIES DRAINAGE SCHEME JOHI CITY |  |  |  |  |  |  |
| HEAD OF ACCOUNT |  | BASIC HUMAN FACILITIES DRAINAGE SCHEME JOHI CITY |  |  |  |  |  |  |
| S.No: | Item | Qty: |  |  | Rate | Unit |  | Amount |
| 1 | AT OXIDTION POND ZONE A ALONG BHAN ROAD |  |  |  |  |  |  |  |
|  | Supplying & installing in position i/c transportation to site of work Electric |  |  |  |  |  |  |  |
|  | pumping set consisting of A.C Electric motor 30 BHP 3 phase 50 cycles 400/420 |  |  |  |  |  |  |  |
|  | volts 1450 RPM (4 pole) Siemens made coupled with non clogging pump |  |  |  |  |  |  |  |
|  | (Type KWPZ 65-315 size 3"x2-1/2" mounted on KSB steel framme or base plate |  |  |  |  |  |  |  |
|  | i/c KSB cupplying capable of discharge 465 GPM against a head of 72 ft, |  |  |  |  |  |  |  |
|  | i/c installing of Pumping set on C.C foundation ration 1:2:4 & C.C (1:4:8) with |  |  |  |  |  |  |  |
|  | ballest with MS nuts & bolts of 5/8"dia to be embeded in c.c foundation, i/c |  |  |  |  |  |  |  |
|  | Motot control Unit consists of circuit breaker magnetic contractor over |  |  |  |  |  |  |  |
|  | load protection under / over voltage protection phase failure protection |  |  |  |  |  |  |  |
|  | Am: meter with current transformer voltmeter with potential trnasformer |  |  |  |  |  |  |  |
|  | automatic star delta change over swithc control and power cables |  |  |  |  |  |  |  |
|  | indicating lights and all these components are fixed in a metallic |  |  |  |  |  |  |  |
|  | dust and smoke proof box. |  |  |  |  |  |  |  |
|  | (Siemens Made) i/c providing & fixing earthing set with 2'x2'x1/4" copper plate |  |  |  |  |  |  |  |
|  | buried in ground at a depth of 12' or less if water comes out from the ground |  |  |  |  |  |  |  |
|  | level with salt and choreoal etc: i/c making the pit 12'deep by excavation of all |  |  |  |  |  |  |  |
|  | type of soil earth plate to be connected with No:8 SWG bare copper wire |  |  |  |  |  |  |  |
|  | run in 1/2" G.I Pipe straight from the earth plate i/c 72 hours testing charges. |  |  |  |  |  |  |  |
|  | Zone A | 3 | Set | @Rs: | 793000 | P/Set. | Rs: | 2379000 |
| 2 | AT OXIDTION POND ZONE B ALONG PHULJI ROAD |  |  |  |  |  |  |  |
|  | Supplying & installing in position i/c transportation to site of work Electric |  |  |  |  |  |  |  |
|  | pumping set consisting of A.C Electric motor 20 BHP 3 phase 50 cycles 400/420 |  |  |  |  |  |  |  |
|  | volts 1450 RPM (4 pole) Siemens made coupled with non clogging pump |  |  |  |  |  |  |  |
|  | (Type KWPZ 65-315 size 3"x2-1/2" mounted on KSB steel framme or base plate |  |  |  |  |  |  |  |
|  | i/c KSB cupplying capable of discharge 317 GPM against a head of 72 ft, |  |  |  |  |  |  |  |
|  | i/c installing of Pumping set on C.C foundation ration 1:2:4 & C.C (1:4:8) with |  |  |  |  |  |  |  |
|  | ballest with MS nuts & bolts of 5/8"dia to be embeded in c.c foundation, i/c |  |  |  |  |  |  |  |
|  | Motot control Unit consists of circuit breaker magnetic contractor over |  |  |  |  |  |  |  |
|  | load protection under / over voltage protection phase failure protection |  |  |  |  |  |  |  |
|  | Am: meter with current transformer voltmeter with potential trnasformer |  |  |  |  |  |  |  |
|  | automatic star delta change over swithc control and power cables |  |  |  |  |  |  |  |
|  | indicating lights and all these components are fixed in a metallic |  |  |  |  |  |  |  |
|  | dust and smoke proof box. |  |  |  |  |  |  |  |
|  | (Siemens Made) i/c providing & fixing earthing set with 2'x2'x1/4" copper plate |  |  |  |  |  |  |  |
|  | buried in ground at a depth of 12' or less if water comes out from the ground |  |  |  |  |  |  |  |
|  | level with salt and choreoal etc: i/c making the pit 12'deep by excavation of all |  |  |  |  |  |  |  |
|  | type of soil earth plate to be connected with No:8 SWG bare copper wire |  |  |  |  |  |  |  |
|  | run in 1/2" G.I Pipe straight from the earth plate i/c 72 hours testing charges. |  |  |  |  |  |  |  |
|  | Zone B | 2 | Set | @Rs: | 793000 | P/Set. | Rs: | 1586000 |
| 3 | AT DISPOSAL WORK ZONE C |  |  |  |  |  |  |  |
|  | Supplying & installing in position i/c transportation to site of work Electric |  |  |  |  |  |  |  |
|  | pumping set consisting of A.C Electric motor 30 BHP 3 phase 50 cycles 400/420 |  |  |  |  |  |  |  |
|  | volts 1450 RPM (4 pole) Siemens made coupled with non clogging pump |  |  |  |  |  |  |  |
|  | (Type KWPZ 65-315 size 3"x2-1/2" mounted on KSB steel framme or base plate |  |  |  |  |  |  |  |
|  | i/c KSB cupplying capable of discharge 400 GPM against a head of 90 ft, |  |  |  |  |  |  |  |
|  | i/c installing of Pumping set on C.C foundation ration 1:2:4 & C.C (1:4:8) with |  |  |  |  |  |  |  |
|  | ballest with MS nuts & bolts of 5/8"dia to be embeded in c.c foundation, i/c |  |  |  |  |  |  |  |
|  | Motot control Unit consists of circuit breaker magnetic contractor over |  |  |  |  |  |  |  |
|  | load protection under / over voltage protection phase failure protection |  |  |  |  |  |  |  |
|  | Am: meter with current transformer voltmeter with potential trnasformer |  |  |  |  |  |  |  |
|  | automatic star delta change over swithc control and power cables |  |  |  |  |  |  |  |
|  | indicating lights and all these components are fixed in a metallic |  |  |  |  |  |  |  |
|  | dust and smoke proof box. |  |  |  |  |  |  |  |
|  | (Siemens Made) i/c providing & fixing earthing set with 2'x2'x1/4" copper plate |  |  |  |  |  |  |  |
|  | buried in ground at a depth of 12' or less if water comes out from the ground |  |  |  |  |  |  |  |
|  | level with salt and choreoal etc: i/c making the pit 12'deep by excavation of all |  |  |  |  |  |  |  |
|  | type of soil earth plate to be connected with No:8 SWG bare copper wire |  |  |  |  |  |  |  |
|  | run in 1/2" G.I Pipe straight from the earth plate i/c 72 hours testing charges. |  |  |  |  |  |  |  |
|  | Zone C | 2 | Set | @Rs: | 1067000 | P/Set. | Rs: | 2134000 |
| 4 | Providing Installing MS Pipe mad out of MS sheet 3/16" thick i/c cutting |  |  |  |  |  |  |  |
|  | folding to correct curvature and shape (Approved Based on schedule rate ) |  |  |  |  |  |  |  |
|  | 3" dia Suction uction line for Oxidation Pond |  |  |  |  |  |  |  |
|  |  | 40 | Rft | @Rs: | 386 | P/Rft. | Rs: | 15436 |
|  | 4" dia Suction uction line for Disposal work |  |  |  |  |  |  |  |
|  |  | 16 | Rft | @Rs: | 507 | P/Rft. | Rs: | 8106 |
| 5 | Providing Laying Jointing & testing High Density Polyethylene pipe (HDPE-100) |  |  |  |  |  |  |  |
|  | for W/S conforming to ISO-4427, DIN 8074, 8075 & PS 3580, |  |  |  |  |  |  |  |
|  | 1980 PS 3580 & PSI 3051 i/c earth work in ordinary soil etc: complete. |  |  |  |  |  |  |  |
|  | (P.H.S.I-1, P-26). P.N.- 10 |  |  |  |  |  |  |  |
|  | 3" dia(90 mm) Suction uction line for Oxidation Pond |  |  |  |  |  |  |  |
|  | Zone A & B |  |  |  |  |  |  |  |
|  |  | 50 | Rft. | @Rs: | 178 | P/Rft | Rs: | 8900 |
|  | 4" dia(110 mm) Suction uction line for Disposal work |  |  |  |  |  |  |  |
|  | Zone C |  |  |  |  |  |  |  |
|  |  | 32 | Rft. | @Rs: | 268 | P/Rft | Rs: | 8576 |
|  | 6" dia(160 mm) Delivery line for Oxidation Pond |  |  |  |  |  |  |  |
|  | Zone B & C |  |  |  |  |  |  |  |
|  |  | 32 | Rft. | @Rs: | 530 | P/Rft | Rs: | 16960 |
|  | 8" dia(225 mm) Delivery line for Oxidation Pond |  |  |  |  |  |  |  |
|  | Zone A |  |  |  |  |  |  |  |
|  |  | 18 | Rft. | @Rs: | 1044 | P/Rft | Rs: | 18792 |
| 6 | Providing and fixing M.S flange made of M.S plate having a thickness and total |  |  |  |  |  |  |  |
|  | weight as mentioned against each item. It includes the cost of making holes, facing |  |  |  |  |  |  |  |
|  | welding nuts bolts rubber packing white lead fitter cartage etc: complete. |  |  |  |  |  |  |  |
|  | (P.H.S- I-8 P-88 ) 1/2" thick M.S Sheet plate |  |  |  |  |  |  |  |
|  | 3" dia(90 mm) Suction uction line for Oxidation Pond |  |  |  |  |  |  |  |
|  | Zone A & B | 20 | Nos: | @Rs: | 945 | Each | Rs: | 18900 |
|  | 4" dia(110 mm) Suction uction line for Disposal work |  |  |  |  |  |  |  |
|  | Zone C | 8 | Nos: | @Rs: | 1148 | Each | Rs: | 9184 |
|  | 6" dia(160 mm) Delivery line for Oxidation Pond |  |  |  |  |  |  |  |
|  | Zone B & C | 16 | Nos: | @Rs: | 1520 | Each | Rs: | 24320 |
|  | 8" dia(225 mm) Delivery line for Oxidation Pond |  |  |  |  |  |  |  |
|  | Zone A | 10 | Nos: | @Rs: | 1973 | Each | Rs: | 19730 |
| 7 | C.I bend with flanged ends with holes i/c turning and facing flanged |  |  |  |  |  |  |  |
|  | for all sizes. (P.H.S (M) I. No 8 P/ 11) |  |  |  |  |  |  |  |
|  |  | 5 | Cwt | @Rs: | 6096 | P/Cwt. | Rs: | 31090 |
| 8 | C.I tapered flat bottomed or central tapered flanged end with holes |  |  |  |  |  |  |  |
|  | i/c turning facing flanged for all sizes (P.H.S. (M) I. No 7 P/ 11) |  |  |  |  |  |  |  |
|  |  | 2 | Cwt | @Rs: | 6096 | P/Cwt. | Rs: | 12619 |
| 9 | C.I.Tee with flanged ends with holes i/c turning and facing flanged |  |  |  |  |  |  |  |
|  | for all sizes. (P.H.S (M) I. No 8 P/ 11) |  |  |  |  |  |  |  |
|  |  | 2 | Cwt | @Rs: | 6096 | P/Cwt. | Rs: | 15118 |
| 10 | C.I sluice valve heavy pattern test pressure 21 kg /sq, cm or 300 lbs /sq inch |  |  |  |  |  |  |  |
|  | (P.H.S (M) I No 16 P/ 11) |  |  |  |  |  |  |  |
|  | 8" dia | 3 | Nos: | @Rs: | 17940 | Each. | Rs: | 53820 |
|  | 6"dia. | 4 | Nos: | @Rs: | 9360 | Each. | Rs: | 37440 |
| 11 | Reflex valve heavy pattern test pressure 21 kg /sq, cm or 300 lbs /sq inch |  |  |  |  |  |  |  |
|  | (P.H.S (M) I No 16 P/ 11) |  |  |  |  |  |  |  |
|  | 8" dia | 3 | Nos: | @Rs: | 7313 | Each. | Rs: | 21938 |
|  | 6"dia. | 4 | Nos: | @Rs: | 4063 | Each. | Rs: | 16250 |
| 12 | C.I Foot valve heavy pattern with cone type gate |  |  |  |  |  |  |  |
|  | (P.H.S (M) I No 4 P/ 10) |  |  |  |  |  |  |  |
|  | 4" dia | 4 | Nos: | @Rs: | 894 | Each. | Rs: | 3575 |
|  | 3" dia | 5 | Nos: | @Rs: | 731 | Each. | Rs: | 3656 |
| 13 | BUTT FUSION JOINT |  |  |  |  |  |  |  |
|  | 8" dia | 10 | Nos: | @Rs: | 1800 | Each | Rs | 18000 |
|  | 6"dia. | 16 | Nos: | @Rs: | 1000 | Each | Rs | 16000 |
|  | 4" dia | 8 | Nos: | @Rs: | 1000 | Each | Rs | 8000 |
|  | 3" dia | 20 | Nos: | @Rs: | 600 | Each | Rs | 12000 |
| 14 | Supplying flange adaptor ( Non sch: item) |  |  |  |  |  |  |  |
|  | 8" dia | 10 | Nos: | @Rs: | 472.50 | Each | Rs | 4725 |
|  | 6"dia. | 16 | Nos: | @Rs: | 2025 | Each | Rs | 32400 |
|  | 4" dia | 8 | Nos: | @Rs: | 1215 | Each | Rs | 9720 |
|  | 3" dia | 20 | Nos: | @Rs: | 675 | Each | Rs | 13500 |
| 15 | Jointing C.I/M.S flanged and specials pipes and inside a trenches i/c |  |  |  |  |  |  |  |
|  | supplying of the rubber packing of the required thickness nuts bolts |  |  |  |  |  |  |  |
|  | and washers etc and other tools required for jointing and testing the |  |  |  |  |  |  |  |
|  | joints in the specifies pressure etc complete (P.H.S I No 1 P/ 40) |  |  |  |  |  |  |  |
|  | 8" dia | 10 | Joints | @Rs: | 940 | P/Joint. | Rs: | 9400 |
|  | 6"dia. | 16 | Joints | @Rs: | 938 | P/Joint. | Rs: | 15008 |
|  | 4" dia | 8 | Joints | @Rs: | 513 | P/Joint. | Rs: | 4104 |
|  | 3" dia | 20 | Joints | @Rs: | 499 | P/Joint. | Rs: | 9980 |
|  |  |  |  |  |  |  | Rs: | 6596246 |
|  |  |  | ABSTRACT |  |  |  |  |  |
|  |  |  |  |  | Sch: Items | Non S.Item |  | Total |
|  | P/MACHINERY |  |  |  | Rs: 436901 | Rs: 6159345 | Rs: | 6596246 |
|  |  |  |  |  |  |  | Rs: | 6596246 |
| Total Amount of Composite Schedule _______________% above / below on the rates of CSR Amount to be added / deducted on the basis of premium Total Amount of Non Schedule items TOTAL AMOUNT. Rs: Rs: Rs: Rs: Rs: |  |  |  |  |  |  |  |  |
|  | CONDITIONS |  |  |  |  |  |  |  |
|  | 1/- | The contractor will have to remove the surplus excavated stuff from the |  |  |  |  |  |  |
|  |  | side of work to out of town at his cost . |  |  |  |  |  |  |
|  | 2/- | The Contractor arrange the materail for construction of work from the approved |  |  |  |  |  |  |
|  |  | quary as shown in the estimate |  |  |  |  |  |  |
|  | 3/- | No premum should be allowed on approved/Market rate. |  |  |  |  |  |  |
|  | 4/- | Any Error or omission in the rats, description, Units shall be refferd to particular |  |  |  |  |  |  |
|  |  | schedule of rates. |  |  |  |  |  |  |
|  | 5/- | No Cartage shall be paid seperately |  |  |  |  |  |  |

|  | SUMMARY OF BILL QUANTITY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | ABSTRACT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | COST OF BID |  |  |  |  |  |  |  |  |  |  |  |  | Rs: |  |
| ( A ) | Cost based on Composite schedule of rates |  |  |  |  |  |  |  |  |  |  |  |  | Rs: |  |
| ( B ) | Amount of Item based on Non Schedule Items |  |  |  |  |  |  |  |  |  |  |  |  | Rs: |  |
|  | TOTAL COST OF BID |  |  |  |  |  |  |  |  |  |  |  |  | Rs: |  |

GOVERNMENT OF SINDH

PUBLIC HEALTH ENGINEERING DIVISION DADU

STANDARD BIDDING DOCUMENTS

PROCUREMENT OF WORKS (SPPRA BIDDING DOCUMENTS)

For Contracts (Small) amounting between Rs. 4.0 (M) to Rs. 50.00  (M).

Name of Work:		(04)  Providing Laying Jointing P.E Pipe Delivery Main

and Pumping Machinery at Water Supply Scheme (Filtration) Dadu.

N.I.T NO: & DATE:		NO: TC/        1334    /   dated:- 15-12-2016

DATE OF ISSUE:                  10-01-2017_

DATE OF OPENING:           11-01-2017

TENDER ISSUED TO:      .	     							.

D.R.NO: & DATE:            .	     							.

STANDARD BIDDING DOCUMENT IS INTENDED AS MODEL FOR

ADMEASUREMENTS (PERCENTAGE RATE FOR UNIT RATES IN A BILL OF QUANTITIES TYPES OF CONTRACT THE MAIN TEXT REFERS TO ADMEASUREMENTS CONTRACTOS.

EXECUTIVE ENGINEER

Public Health Engineering Division

DADU

BIDDING DATA

(This section  should be filled in by the office of the Executive Engineer,

Public Engineering Division Dadu, before issuance of the bidding documents).

| (a) | Name of Procuring Agency:- | The Executive Engineer Public Health Engineering Division Dadu. |
| --- | --- | --- |
| (b) | Brief Description of works:- | (04) Providing Laying Jointing P.E Pipe Delivery Main and Pumping Machinery at Water Supply Scheme (Filtration) Dadu. |
| © | Procuring Agency Address:- | The Executive Engineer Public Health Engineering Division Dadu. Near Gharibabad Muhalla Dadu. |
| (d) | Estimated Cost:- | Rs: 39.800 Million |
| (e) | Amount of Bid Security:- | Rs: 19,90,000/- |
| (f) | Period of Bid Validity (Days):- | (90 days) |
| (g) | Security Deposit (i/c Bid Security):- | (10`%) |
| (h) | Percentage, if any, to be deducted from bills:- | (7.50% Income Tax) & (8% Security Deposit). |
| (i) | Deadline for submission of Bids along with time:- | 10-01-2017 @ 1.30 PM |
| (j) | Venue, time & date of Bid Opening:- | 11-01-2017 @ 2.00 PM |
| (k) | Time for completion from written order of commence:- | (24 Months) |
| (l) | Liquidity Damages:- | (1% on estimated cost per day subject to minimum of 10%) |
| (m) | Deposit receipt No: date & Amount (in words and figure):- | C.D No:_____________ dated:-______________ Amount Rs:_____________Bank_____________. ._______________________________________. M/S____________________________________. |

EXECUTIVE ENGINEER

Public Health Engineering Division

DADU

INSTRUCTIONS TO BIDDERS

(Note: (These Instructions to Bidders (IB) along with Bidding Data will not be part of

Contract and will cease to have effect once the Contract is signed).

A. GENERAL

IB.1 Scope of Bid & Source of Funds

  - Scope of Bid

The Procuring Agency as defined in the Bidding Data (hereinafter called ―the Procuring Agency‖) wishes to receive Bids for the Works summarized in the Bidding Data (hereinafter referred to as ―the Works‖).

Bidders must quote for the complete scope of work. Any Bid covering partial scope of work will be rejected as non-responsive.

  - Source of Funds

The Procuring Agency has arranged funds from its own sources or Federal/ Provincial /Donor agency or any other source, which may be indicated accordingly in bidding data towards the cost of the project/scheme.

IB.2 Eligible Bidders

2.1 Bidding is open to all firms and persons meeting the following requirements:

a) Duly licensed by the Pakistan Engineering Council (PEC) in the appropriate category for value of works.

Provided that the works costing Rs. 4.00 million or less shall not require any registration with PEC .

b) Duly pre-qualified with the Procuring Agency. (Where required).

In the event that prequalification of potential bidders has been undertaken, only bids from prequalified bidders will be considered for award of Contract.

c) If prequalification has not undertaken, the procuring agency may ask information and documents not limited to following:-

(i) Company profile;

(ii) Works of similar nature and size for each performed in last 3/5 years;

(iii) Construction equipments;

(iv) Qualification and experience of technical personnel and key site management; Sindh Public Procurement Regulatory Authority | www.pprasindh.gov.pk 7

(v) Financial statement of last 3 years;

(vi) Information regarding litigations and abandoned works if any.

IB.3 Cost of Bidding

3.1 The bidder shall bear all costs associated with the preparation and submission of its bid

and the Procuring Agency will in no case be responsible or liable for those costs,

Regardless of the conduct or outcome of the bidding process (SPP Rules 24 & 25).

Executive Engineer

PHE Division Dadu

CONDITIONS OF CONTRACT

- GENERAL PROVISIONS

Definitions

In the Contract as defined below, the words and expressions defined shall have the following meanings assigned to them, except where the context requires otherwise:

The Contract

1.1.1 ―Contract‖ means the Contract Agreement and the other documents listed in the Contract Data.

1.1.2 ―Specifications‖ means the document as listed in the Contract Data, including Procuring Agency‘s requirements in respect of design to be carried out by the Contractor (if any), and any Variation to such document.

1.1.3 ―Drawings‖ means the Procuring Agency‘s drawings of the Works as listed in the Contract Data, and any Variation to such drawings.

Persons

1.1.4 ―Procuring Agency‖ means the person named in the Contract Data and the legal successors in title to this person, but not (except with the consent of the Contractor) any assignee.

1.1.5 ―Contractor‖ means the person named in the Contract Data and the legal successors in title to this person, but not (except with the consent of the Procuring Agency) any assignee.

1.1.6 ―Party‖ means either the Procuring Agency or the Contractor.

Dates, Times and Periods

1.1.7 ―Commencement Date‖ means the date fourteen (14) days after the date the Contract comes into effect or any other date named in the Contract Data.

1.1.8 ―Day‖ means a calendar day

1.1.9 ―Time for Completion‖ means the time for completing the Works as stated in the Contract Data (or as extended under Sub-Clause 7.3), calculated from the Commencement Date.

Money and Payments

1.1.10 ―Cost‖ means all expenditure properly incurred (or to be incurred) by the Contractor, whether on or off the Site, including overheads and similar charges but does not include any allowance for profit.

Other Definitions

1.1.11 ―Contractor‘s Equipment‖ means all machinery, apparatus and other things required for the execution of the Works but does not include Materials or Plant intended to form part of the Works.

1.1.12 ―Country‖ means the Islamic Republic of Pakistan.

1.1.13 ―Procuring Agency‘s Risks‖ means those matters listed in Sub-Clause 6.1.

1.1.14 ―Force Majeure‖ means an event or circumstance which makes performance of a Party‘s obligations illegal or impracticable and which is beyond that Party‘s reasonable control.

1.1.15 ‗Materials‖ means things of all kinds (other than Plant) to be supplied and incorporated in the Works by the Contractor.

1.1.16 ―Plant‖ means the machinery and apparatus intended to form or forming part of the Works.

1.1.17 ―Site‖ means the places provided by the Procuring Agency where the Works are to be executed, and any other places specified in the Contract as forming part of the Site.

1.1.18 ―Variation‖ means a change which is instructed by the Engineer/Procuring Agency under Sub-Clause 10.1.

1.1.19 ‗Works‖ means any or all the works whether Supply, Installation, Construction etc. and design (if any) to be performed by the Contractor including temporary works and any variation thereof.

1.1.20 ―Engineer‖ means the person notified by the Procuring Agency to act as Engineer

for the purpose of the Contract and named as such in Contract Data.

  - Interpretation

Words importing persons or parties shall include firms and organizations. Words importing singular or one gender shall include plural or the other gender where the context requires.

  - Priority of Documents.

The documents forming the Contract are to be taken as mutually explanatory of one another. If an ambiguity or discrepancy is found in the documents, the priority of the documents shall be in accordance with the order as listed in the Contract Data.

37

1.4 Law

The law of the Contract is the relevant Law of Islamic Republic of Pakistan.

1.5 Communications

All Communications related to the Contract shall be in English language.

1.6 Statutory Obligations

The Contractor shall comply with the Laws of Islamic Republic of Pakistan and shall give all notices and pay all fees and other charges in respect of the Works.

- THE PROCURING AGENCY

2.1 Provision of Site

The Procuring Agency shall provide the Site and right of access thereto at the times stated in the Contract Data. Site Investigation Reports are those that were included in the bidding documents

and are factual and interpretative reports about the surface and subsurface conditions at the Site.

2.2 Permits etc.

The Procuring Agency shall, if requested by the Contractor, assist him in applying for permits, licenses or approvals which are required for the Works.

2.3 Engineer’s/Procuring Agency’s Instructions

The Contractor shall comply with all instructions given by the Procuring Agency or the Engineer, if notified by the Procuring Agency, in respect of the Works including the suspension of all or part of the works.

2.4 Approvals

No approval or consent or absence of comment by the Engineer/Procuring Agency shall affect the Contractor‘s obligations.

- ENGINEER’S/PROCURING AGENCY’S REPRESENTATIVES

3.1 Authorized Person

The Procuring Agency shall appoint a duly authorized person to act for him and on his behalf for the purposes of this Contract. Such authorized person shall be duly identified in the Contract Data or otherwise notified in writing to the Contractor as soon as he is so appointed. In either case the Procuring Agency shall notify the Contractor, in writing, the precise scope of the authority of such authorized person at the time of his appointment.

3.2 Engineer’s/Procuring Agency’s Representative

The name and address of Engineer‘s/Procuring Agency‘s Representative is given in Contract Data. However the Contractor shall be notified by the Engineer/Procuring Agency, the delegated duties and authority before the Commencement of works.

- THE CONTRACTOR

4.1 General Obligations

The Contractor shall carry out the works properly and in accordance with the Contract. The Contractor shall provide all supervision, labour, Materials, Plant and Contractor‘s Equipment which may be required

4.2 Contractor’s Representative

The Contractor shall appoint a representative at site on full time basis to supervise the execution of work and to receive instructions on behalf of the Contractor but only after obtaining the consent of the Procuring Agency for such appointment which consent shall not be withheld without plausible reason(s) by the Procuring Agency. Such authorized representative may be substituted/ replaced by the Contractor at any time during the Contract Period but only after obtaining the consent of the Procuring Agency as aforesaid.

4.3 Subcontracting

The Contractor shall not subcontract the whole of the works. The Contractor shall not subcontract any part of the works without the consent of the Procuring Agency.

4.4 Performance Security

The Contractor shall furnish to the Procuring Agency within fourteen (14) days after receipt of Letter of Acceptance a Performance Security at the option of the bidder, in the form of Payee‘s order /Bank Draft or Bank Guarantee from scheduled bank for the amount and validity specified in Contract Data.

- DESIGN BY CONTRACTOR

5.1 Contractor’s Design

The Contractor shall carry out design to the extent specified, as referred to in the Contract Data. The Contractor shall promptly submit to the Engineer/Procuring Agency all designs prepared by him, within fourteen (14) days of receipt the Engineer/Procuring Agency shall notify any comments or, if the design submitted is not in accordance with the Contract, shall reject it stating the reasons. Contractor shall not construct any element of the works designed by him within fourteen (14) days after the design has been submitted to the Engineer/Procuring Agency or which has been rejected. Design that has been rejected shall be promptly amended and resubmitted. The Contractor shall resubmit all designs commented on taking these comments into account as necessary.

5.2 Responsibility for Design

The Contractor shall remain responsible for his bided design and the design under this Clause, both of which shall be fit for the intended purposes defined in the Contract and he shall also remain responsible for any infringement of any patent or copyright in respect of the same. The Engineer/Procuring Agency shall be responsible for the Specifications and Drawings.

- PROCURING AGENCY’S RISKS

6.1 The Procuring Agency’s Risks

The Procuring Agency‘s Risks are:-

a) war, hostilities (whether war be declared or not), invasion, act of foreign enemies, within the Country;

b) Rebellion, terrorism, revolution, insurrection, military or usurped power, or civil war, within the Country;

c) riot, commotion or disorder by persons other than the Contractor‘s personnel and other employees including the personnel and employees of Sub- Contractors, affecting the Site and/or the Works;

d) ionizing radiations, or contamination by radio-activity from any nuclear fuel, or from any nuclear waste from the combustion of nuclear fuel, radio-active toxic explosive, or other hazardous properties of any explosive nuclear assembly or nuclear component of such an assembly, except to the extent to which the Contractor/Sub-Contractors may be responsible for the use of any radio-active material;

e) Pressure waves caused by aircraft or other aerial devices travelling at sonic or supersonic speeds;

f) Use or occupation by the Procuring Agency of any part of the Works, except as may be specified in the Contract;

g) late handing over of sites, anomalies in drawings, late delivery of designs and drawings of any part of the Works by the Procuring Agency‘s personnel or by others for whom the Procuring Agency is responsible;

h) a suspension under Sub-Clause 2.3 unless it is attributable to the Contractor‘s failure; and

i) physical obstructions or physical conditions other than climatic conditions, encountered on the Site during the performance of the Works, for which the Contractor immediately notified to the Procuring Agency and accepted by the Procuring Agency.

7. TIME FOR COMPLETION

7.1 Execution of the Works

The Contractor shall commence the Works on the Commencement Date and shall proceed expeditiously and without delay and shall complete the Works, subject to Sub-Clause 7.3 below, within the Time for Completion.

7.2 Programme

Within the time stated in the Contract Data, the Contractor shall submit to the Engineer/Procuring Agency a programme for the Works in the form stated in the Contract Data.

7.3 Extension of Time

The Contractor shall, within such time as may be reasonable under the circumstances, notify the Procuring Agency/Engineer of any event(s) falling within the scope of Sub-Clause 6.1 or 10.3 of these Conditions of Contract and request the Procuring Agency/Engineer for a reasonable extension in the time for the completion of works. Subject to the aforesaid, the Procuring Agency/Engineer shall determine such reasonable extension in the time for the completion of works as may be justified in the light of the details/particulars supplied by the Contractor in connection with the such determination by the Procuring Agency/Engineer within such period as may be prescribed by the Procuring Agency/Engineer for the same; and the Procuring Agency may extend the time for completion as determined.

7.4 Late Completion

If the Contractor fails to complete the Works within the Time for Completion, the Contractor‘s only liability to the Procuring Agency for such failure shall be to pay the amount as liquidity damages stated in the Contract Data for each day for which he fails to complete the Works.

8. TAKING-OVER

8.1 Completion

The Contractor may notify the Engineer/Procuring Agency when he considers that the Works are complete.

8.2 Taking-Over Notice

Within fourteen (14) days of the receipt of the said notice of completion from the Contractor the Procuring Agency/Engineer shall either takeover the completed works and issue a Certificate of Completion to that effect or shall notify the Contractor his reasons for not taking-over the works. While issuing the Certificate of Completion as aforesaid, the Procuring Agency/Engineer may identify any outstanding items of work which the Contractor shall undertake during the

Maintenances Period.

9. REMEDYING DEFECTS

9.1 Remedying Defects

The Contractor shall for a period stated in the Contract Data from the date of issue of the Certificate of Completion carry out, at no cost to the Procuring Agency, repair and rectification work which is necessitated by the earlier execution of poor quality of work or use of below specifications material in the execution of Works and which is so identified by the Procuring Agency/Engineer in writing within the said period. Upon expiry of the said period, and subject to the Contractor‘s faithfully performing his aforesaid obligations, the Procuring Agency/Engineer

shall issue a Maintenance Certificate whereupon all obligations of the Contractor under this Contract shall come to an end. Failure to remedy any such defects or complete outstanding work within a reasonable time shall entitle the Procuring Agency to carry out all necessary works at the Contractor‘s cost. However, the cost of remedying defects not attributable to the Contractor shall be valued as a Variation.

9.2 Uncovering and Testing

The Engineer/Procuring Agency may give instruction as to the uncovering and / or testing of any work. Unless as a result of an uncovering and/or testing it is established that the Contractor‘s design, materials, plant or workmanship are not in accordance with the Contract, the Contractor shall be paid for such uncovering and/or testing as a Variation in accordance with Sub-Clause 10.2.

10. VARIATIONS AND CLAIMS

10.1 Right to Vary

The Procuring Agency/Engineer may issue Variation Order(s) in writing. Where for any reason it has not been possible for the Procuring Agency/Engineer to issue such Variations Order(s), the Contractor may confirm any verbal orders given by the Procuring Agency/Engineer in writing and if the same are not refuted/denied by the Procuring Agency/Engineer within ten (10) days of the receipt of such confirmation the same shall be deemed to be a Variation Orders for the purposes of this Sub-Clause.

10.2 Valuation of Variations

Variations shall be valued as follows:

a) At a lump sum price agreed between the Parties, or

b) Where appropriate, at rates in the Contract, or

c) In the absence of appropriate rates, the rates in the Contract shall be used as the basis for valuation, or failing which

d) At appropriate new rates, as may be agreed or which the Engineer/Procuring Agency considers appropriate, or

e) If the Engineer/Procuring Agency so instructs, at day work rates set out in the Contract Data for which the Contractor shall keep records of hours of labour and Contractor‘s Equipment, and of Materials, used.

10.3 Changes in the Quantities.

a) If the final quantity of the work done differs from the quantity in the Bill of Quantities for the particular item by more than 25 percent, provided the change exceeds 1 percent of the Initial Contract Price, the Procuring Agency/Engineer shall adjust the rate to allow for the change and will be valued as per sub clause 10.2.

b) The Engineer shall not adjust rates from changes in quantities if thereby the Initial Contract Price is exceeded by more than 15 percent, except with the prior approval of the Procuring Agency.

c) If requested by the Engineer, the contractor shall provide the Engineer with a detailed cost breakdown of any rate in the Bill of Quantities.

10.4 Early Warning

The Contractor shall notify the Engineer/Procuring Agency in writing as soon as he is aware of any circumstance which may delay or disrupt the Works, or which may give rise to a claim for additional payment. To the extent of the Contractor‘s failure to notify, which results to the Engineer/Procuring Agency being unable to keep all relevant records or not taking steps to minimize any delay, disruption, or Cost, or the value of any Variation, the Contractor‘s entitlement to extension of the Time for Completion or additional payment shall be reduced/rejected.

10.5 Valuation of Claims

If the Contractor incurs Cost as a result of any of the Procuring Agency‘s Risks, the Contractor shall be entitled to the amount of such Cost. If as a result of any Procuring Agency‘s Risk, it is necessary to change the Works, this shall be dealt with as a Variation subject to Contractor‘s notification for intention of claim to the Engineer/Procuring Agency within fourteen (14) days of the occurrence of cause.

10.6 Variation and Claim Procedure

The Contractor shall submit to the Engineer/Procuring Agency an itemized detailed breakdown of the value of variations and claims within twenty eight (28) days of the instruction or of the event giving rise to the claim. The Engineer/Procuring Agency shall check and if possible agree the value. In the absence of agreement, the Procuring Agency shall determine the value.

11. CONTRACT PRICE AND PAYMENT

11.1 (a) Terms of Payments

The amount due to the Contractor under any Interim Payment Certificate issued by the Engineer pursuant to this Clause, or to any other terms of the Contract, shall , subject to Clause 11.3, be paid by the Procuring Agency to the Contractor within 30 days after such Interim Payment Certificate has been jointly verified by Procuring Agency and Contractor, or, in the case of the Final Certificate referred to in Sub Clause 11.5, within 60days after such Final Payment Certificate has been jointly verified by Procuring Agency and Contractor; Provided that the Interim Payment shall be caused in thirty (30) days and Final Payment in 60 days in case of foreign funded project. In the event of the failure of the Procuring Agency to make payment within 90 days then Procuring Agency shall pay to the Contractor compensation at the 28 days rate of KIBOR+2% per annum in local currency and LIBOR+1% for foreign currency, upon all sums unpaid from the date by which the same should have been paid.

(b) Valuation of the Works

The Works shall be valued as provided for in the Contract Data, subject to Clause 10.

11.2 Monthly Statements

The Contractor shall be entitled to be paid at monthly intervals:

a) The value of the Works executed less to the cumulative amount paid previously; and

b) Value of secured advance on the materials and valuation of variations (if any).

The Contractor shall submit each month to the Engineer/Procuring Agency a statement showing the amounts to which he considers himself entitled.

44

11.3 Interim Payments

Within a period not exceeding seven (07) days from the date of submission of a statement for interim payment by the Contractor, the Engineer shall verify the same and within a period not exceeding thirty (30/60) days from the said date of submission by the Contractor, the Procuring Agency shall pay to the Contractor the sum subject to adjustment for deduction of the advance payments and retention money.

11.4 Retention

Retention money shall be paid by the Procuring Agency to the Contractor within fourteen (14) days after either the expiry of the period stated in the Contract Data, or the remedying of notified defects, or the completion of outstanding work, all as referred to in Sub-Clause 9.1, whichever is the later.

11.5 Final Payment

Within twenty one (21) days from the date of issuance of the Maintenance Certificate the Contractor shall submit a final account to the Engineer to verify and the Engineer shall verify the same within fourteen (14) days from the date of submission and forward the same to the Procuring Agency together with any documentation reasonably required to enable the Procuring Agency to ascertain the final contract value. Within sixty (60) days from the date of receipt of the verified final account from the Engineer, the Procuring Agency shall pay to the Contractor any amount due to the Contractor. While making such payment the Procuring Agency may, for

Reasons to be given to the Contractor in writing, withhold any part or parts of the verified amount.

11.6 Currency

Payment shall be in the currency stated in the Contract Data.

12. DEFAULT

12.1 Defaults by Contractor

If the Contractor abandons the Works, refuses or fails to comply with a valid instruction of the Engineer/Procuring Agency or fails to proceed expeditiously and without delay, or is, despite a written complaint, in breach of the Contract, the Procuring Agency may give notice referring to this Sub-Clause and stating the default.

If the Contractor has not taken all practicable steps to remedy the default within fourteen (14) days after receipt of the Procuring Agency‘s notice, the Procuring Agency may by a second notice given within a further twenty one (21) days, terminate the Contract. The Contractor shall then demobilize from the Site leaving behind any Contractor‘s Equipment which the Procuring Agency instructs, in the second notice, to be used for the completion of the Works at the risk and cost of the Contractor.

12.2 Defaults by Procuring Agency

If the Procuring Agency fails to pay in accordance with the Contract, or is, despite a written complaint, in breach of the Contract, the Contractor may give notice referring to this Sub-Clause and stating the default. If the default is not remedied within fourteen (14) days after the Procuring Agency‘s receipt of this notice, the Contractor may suspend the execution of all or parts of the Works.

If the default is not remedied within twenty eight (28) days after the Procuring Agency‘s receipt of the Contractor‘s notice, the Contractor may by a second notice given within a further twenty one (21) days, terminate the Contract. The Contractor shall then demobilize from the Site.

12.3 Insolvency

If a Party is declared insolvent under any applicable law, the other Party may by notice terminate the Contract immediately. The Contractor shall then demobilize from the site leaving behind, in the case of the Contractor‘s insolvency, any Contractor‘s Equipment which the Procuring Agency instructs in the notice is to be used for the completion of the Works.

12.4 Payment upon Termination

After termination, the Contractor shall be entitled to payment of the unpaid balance of the value of the works executed and of the Materials and Plant reasonably delivered to the site, adjusted by the following:

a) any sums to which the Contractor is entitled under Sub-Clause 10.4,

b) any sums to which the Procuring Agency is entitled,

c) if the Procuring Agency has terminated under Sub-Clause 12.1 or 12.3, the Procuring Agency shall be entitled to a sum equivalent to twenty percent (20%) of the value of parts of the Works not executed at the date of the termination, and

d) if the Contractor has terminated under Sub-Clause 12.2 or 12.3, the Contractor shall be entitled to the cost of his demobilization together with a sum equivalent to ten percent (10%) of the value of parts of the works not executed at the date of termination. The net balance due shall be paid or repaid within twenty eight (28) days of the notice of termination.

13. RISKS AND RESPONSIBILITIES

13.1 Contractor’s Care of the Works

Subject to Sub-Clause 9.1, the Contractor shall take full responsibility for the care of the Works from the Commencement Date until the date of the Procuring Agency‘s/Engineer‘s issuance of Certificate of Completion under Sub-Clause 8.2. Responsibility shall then pass to the Procuring Agency. If any loss or damage happens to the Works during the above period, the Contractor shall rectify such loss or damage so that the Works conform with the Contract. Unless the loss or damage happens as a result of any of the Procuring Agency‘s Risks, the Contractor shall indemnify the Procuring Agency, or his agents against all claims loss, damage and expense arising out of the Works.

13.2 Force Majeure

If Force Majeure occurs, the Contractor shall notify the Engineer/Procuring Agency immediately. If necessary, the Contractor may suspend the execution of the Works and, to the extent agreed with the Procuring Agency demobilize the Contractor‘s Equipment. If the event continues for a period of eighty four (84) days, either Party may then give notice of termination which shall take effect twenty eight (28) days after the giving of the notice. After termination, the Contractor shall be entitled to payment of the unpaid balance of the value of the Works executed and of the Materials and Plant reasonably delivered to the Site, adjusted by the following:

a) any sums to which the Contractor is entitled under Sub-Clause 10.4,

b) the cost of his demobilization, and

c) less any sums to which the Procuring Agency is entitled. The net balance due shall be paid or repaid within thirty five (35) days of the notice of termination.

14. INSURANCE

14.1 Arrangements

The Contractor shall, prior to commencing the Works, effect insurances of the types, in the amounts and naming as insured the persons stipulated in the Contract Data except for items (a) to (e) and (i) of the Procuring Agency‘s Risks under Sub- Clause 6.1. The policies shall be issued by insurers and in terms approved by the Procuring Agency. The Contractor shall provide the Engineer/Procuring Agency with evidence that any required policy is in force and that the premiums have been paid.

14.2 Default

If the Contractor fails to effect or keep in force any of the insurances referred to in the previous Sub-Clause, or fails to provide satisfactory evidence, policies or receipts, the Procuring Agency may, without prejudice to any other right or remedy, effect insurance for the cover relevant to such as a default and pay the premiums due and recover the same plus a sum in percentage given in Contractor Data from any other amounts due to the Contractor.

15. RESOLUTION OF DISPUTES

15.1 Engineer’s Decision

If a dispute of any kind whatsoever arises between the Procuring Agency and the Contractor in connection with the works, the matter in dispute shall, in the first place, be referred in writing to the Engineer, with a copy to the other party. Such reference shall state that it is made pursuant to this Clause. No later than the twenty eight (28) days after the day on which he received such reference, the Engineer shall give notice of his decision to the Procuring Agency (Engineer)and the Contractor. Unless the Contract has already been repudiated or terminated, the Contractor shall, in every case, continue to proceed with the work with all due diligence, and the Contractor and the Procuring Agency ( Engineer) shall give effect forthwith to every such decision of the Engineer unless and until the same shall be revised, as hereinafter provided in an arbitral award.

15.2 Notice of Dissatisfaction

If a Party is dissatisfied with the decision of the Engineer of consultant or if no decision is given within the time set out in Sub-Clause 15.1 here above, the Party may give notice of dissatisfaction referring to this Sub-Clause within fourteen (14) days of receipt of the decision or the expiry of the time for the decision. If no notice of dissatisfaction is given within the specified time, the decision shall be final and binding on the Parties. If notice of dissatisfaction is given within the specified time, the decision shall be binding on the Parties who shall give effect to it without delay unless and until the decision of the Engineer is revised by an arbitrator. If a contractor is dissatisfied with the decision of the Engineer of the department or decision is not given in time then he can approach (Engineer) within 14 days, in case of dissatisfaction with decision of ( Engineer) or not decided within 28 days, then arbitration process would be adopted as per clause 15.3.

15.3 Arbitration

A dispute which has been the subject of a notice of dissatisfaction shall be finally settled as per provisions of Arbitration Act 1940 (Act No. X of 1940) and Rules made there under and any statutory modifications thereto. Any hearing shall be held at the place specified in the Contract Data and in the language referred to in Sub-Clause 1.5.

Contractor

Executive Engineer

PHE Division Dadu

| BILL OF QUANTITY |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Name of work: - (4) |  | PROVIDING LAYING JOINTING P.E PIPE DELIVERY MAIN AND PUMPING MACHINERY AT WATER SUPPLY SCHEME (FILTERATION) DADU. |  |  |  |  |  |  |
| HEAD OF ACCOUNT |  | WATER SUPPLY SCHEME FILTERATION DADU CITY. |  |  |  |  |  |  |
| S.No: | Item | Qty: |  |  | Rate | Unit |  | Amount |
|  | P.E PIPE 18" DIA |  |  |  |  |  |  |  |
| 1 | Dismantling and removing Road Metalling (G.S.I No. 51 P/ 13) |  |  |  |  |  |  |  |
|  | 18000.00 | Cft. |  | @ Rs: | 605.00 | P%Cft | Rs: | 108900 |
| 2 | Dismantling of Brick Work in lime or cement mortor (G.S.I No 13 P/ 10) |  |  |  |  |  |  |  |
|  | 150.00 | Cft. |  | @ Rs: | 1285.63 | P%Cft | Rs: | 1928 |
| 3 | Dismantling of C.C plain 1:2:4 ( G.S.I No 19 P/ 10) |  |  |  |  |  |  |  |
|  | 31.25 | Cft. |  | @ Rs: | 3327.50 | P%Cft | Rs: | 1040 |
| 4 | Dismantling of C.C Reinforced Separting Reinforcement from Concrete, cleaning |  |  |  |  |  |  |  |
|  | and straighting the same. (G.S.I No 20 P/ 11) |  |  |  |  |  |  |  |
|  | 75.00 | Cft. |  | @ Rs: | 5445.00 | P%Cft | Rs: | 4084 |
| 5 | Add Every 50' additional lead or part there of |  |  |  |  |  |  |  |
|  | Horizental lead (2500 Rft) |  |  |  |  |  |  |  |
|  |  | Cft. |  | @ Rs: | 1459.20 | P% Cft | Rs: | 0 |
| 1 | Excavation for pipe line entrenches and pits in soft soils i/c trimming and dressing sides to true |  |  |  |  |  |  |  |
|  | alignment and shape leveling of beds of trenches to correct level and grade cutting joint holes |  |  |  |  |  |  |  |
|  | and disposal of surplus earth within a one chain as directed by Engineer incharge providing fence |  |  |  |  |  |  |  |
|  | guards lights flags and temporary crossing for non vehicular traffic where were required lift upto |  |  |  |  |  |  |  |
|  | 5ft and lead upto one chain.(P.H.S.I-1, P-60). |  |  |  |  |  |  |  |
|  | 115500.00 | Cft |  | @Rs | 3600 | P%0Cft | Rs | 415800 |
| 7 | Providing laying & fixing in trench i/c fitting jointing and testing etc: |  |  |  |  |  |  |  |
|  | complete in all respect the high density polythylene PE pipes |  |  |  |  |  |  |  |
|  | (HDPE-100) for W/S confirming ISO 4427/DIN8074/8075 |  |  |  |  |  |  |  |
|  | B.S 3580 & PSI 3051. (P.H.S.I-1, P-25). PN 08. |  |  |  |  |  |  |  |
|  | 8900 | Rft | 18" dia | @Rs | 4205.00 | P-Rft | Rs: | 37424500 |
| 8 | HDPE (PE100) fittings (PH.Sch: of Mat: Item No:1, P-18) |  |  |  |  |  |  |  |
|  | Wlbow / Bernd 45 Degree. |  |  |  |  |  |  |  |
|  | 3 | Nos: | 18" dia | @Rs | 27667.00 | Each | Rs: | 83001 |
|  | Wlbow / Bernd 90 Degree. |  |  |  |  |  |  |  |
|  | 3 | Nos: | 18" dia | @Rs | 33201.00 | Each | Rs: | 99603 |
| 9 | But fusion joint (PH.Sch: of Mat: I-H, P-20) |  |  |  |  |  |  |  |
|  | 6 | Nos: | 18" dia | @Rs | 2800.00 | Each | Rs: | 16800 |
| 10 | Refilling the excavated stuff in trenches 6” thick Layer i/c watering ramming to |  |  |  |  |  |  |  |
|  | full compaction etc complete (P.H.S- I-24 P-77) |  |  |  |  |  |  |  |
|  | 120150.00 | Cft |  | @Rs | 2760 | P%0Cft | Rs | 331614 |
|  |  |  |  |  |  |  | Rs: | 38487270 |
|  | PUMPING MACHIMERY |  |  |  |  |  |  |  |
| 1 | Providing & installing in position i/c transportation to site of work Electric |  |  |  |  |  |  |  |
|  | Motor 60 BHP (Siemens made) 2 pole 2900 RPM 3 Phase 400 VAC 50 |  |  |  |  |  |  |  |
|  | cycles coupled with KSB centrifugal pump ETA NORM Pump type 100-200 |  |  |  |  |  |  |  |
|  | size 4"x5" i/c KSB steel frame and coupling with sleeve etc: complete capable |  |  |  |  |  |  |  |
|  | of discharging 850 gallons per minuts against a head of 160 ft i/c installation of |  |  |  |  |  |  |  |
|  | pumping set in cement concretefoundation ratio 1:2:4 with MS nuts and |  |  |  |  |  |  |  |
|  | bolts to be embeded in CC foundation i/c providing and fixing automatic |  |  |  |  |  |  |  |
|  | motor control unit (MCU) consist oil starter (MEECO Pakistan) MCCB |  |  |  |  |  |  |  |
|  | breaker 10-A to 50-A (Shihlin Taiwan) cutout 60-A (China) amper meter |  |  |  |  |  |  |  |
|  | (60-A) (SELCO China) volt meter (500-V) (SELCO China) phase |  |  |  |  |  |  |  |
|  | indication light (China0 i/c transformer oil (2 Litters) (Pannel board |  |  |  |  |  |  |  |
|  | 18"x26"x9" and internal wiring etc: complete and providing internal |  |  |  |  |  |  |  |
|  | electric wiring main or sub main PVC insulated with size 3-7/.044 |  |  |  |  |  |  |  |
|  | (6mm2) i/c providing and fixing earthing set 0.6mx6.3mmx2x2-1/2 |  |  |  |  |  |  |  |
|  | C.I plate burried in the ground at depth of 3.7 mm (12") or less |  |  |  |  |  |  |  |
|  | as per Pak PWD specification and testing of the pumping set |  |  |  |  |  |  |  |
|  | required head of 72 hours etc: complete. (Non Sch: Item). |  |  |  |  |  |  |  |
|  | 1.00 | Set |  | @Rs: | 796000 | P/Set. | Rs: | 796000 |
| 7 | Providing laying & fixing in trench i/c fitting jointing and testing etc: |  |  |  |  |  |  |  |
|  | complete in all respect the high density polythylene PE pipes |  |  |  |  |  |  |  |
|  | (HDPE-100) for W/S confirming ISO 4427/DIN8074/8075 |  |  |  |  |  |  |  |
|  | B.S 3580 & PSI 3051. (P.H.S.I-1, P-25). PN 08. |  |  |  |  |  |  |  |
|  | 24 | Rft | 6" dia (160mm) | @Rs: | 530 | P/Rft | Rs: | 12720 |
| 9 | C.I Foot valve heavy pattern with cone type gate |  |  |  |  |  |  |  |
|  | (P.H.S (M) I No 4 P/ 10) |  |  |  |  |  |  |  |
|  | 1.00 | Nos: | 6" dia | @Rs: | 1381.25 | Each. | Rs: | 1381 |
| 4 | C.I bend with flanged ends with holes i/c turning and facing flanged |  |  |  |  |  |  |  |
|  | for all sizes. (P.H.S (M) I. No 8 P/ 11) |  |  |  |  |  |  |  |
|  | 1.09 | Cwt |  | @Rs: | 6096 | P/Cwt. | Rs: | 6645 |
| 7 | C.I sluice valve heavy pattern test pressure 21 kg /sq, cm or 300 lbs /sq inch |  |  |  |  |  |  |  |
|  | (P.H.S (M) I No 16 P/ 11) |  |  |  |  |  |  |  |
|  | 1.00 | Nos: | 6" dia | @Rs: | 9360 | Each. | Rs: | 9360 |
| 8 | Reflex valve heavy pattern test pressure 21 kg /sq, cm or 300 lbs /sq inch |  |  |  |  |  |  |  |
|  | (P.H.S (M) I No 16 P/ 11) |  |  |  |  |  |  |  |
|  | 1.00 | Nos: | 6" dia | @Rs: | 4062.5 | Each. | Rs: | 4063 |
| 2 | Providing Installing G.I Pipe approved quality. |  |  |  |  |  |  |  |
|  | (Sant: Sch: Item No:1, P-125) |  |  |  |  |  |  |  |
|  | 8.00 | Rft | 6" dia | @Rs: | 695.04 | P/Rft. | Rs: | 5560 |
| 5 | C.I tapered flat bottomed or central tapered flanged end with holes |  |  |  |  |  |  |  |
|  | i/c turning facing flanged for all sizes (P.H.S. (M) I. No 7 P/ 11) |  |  |  |  |  |  |  |
|  | 0.57 | Cwt |  | @Rs: | 6096 | P/Cwt. | Rs: | 3475 |
| 3 | Manufacturing and supplying M.S flanged of different clamps made out of |  |  |  |  |  |  |  |
|  | M.S sheet 3/8" thickness i/c cutting drilling holes and welding clamps |  |  |  |  |  |  |  |
|  | with M.S pipes etc complete (Approved Based on sch: rate) |  |  |  |  |  |  |  |
|  | 10.00 | Nos: | 6" dia | @Rs: | 804.77 | Each. | Rs: | 8048 |
| 10 | Jointing C.I/M.S flanged and specials pipes and inside a trenches i/c |  |  |  |  |  |  |  |
|  | supplying of the rubber packing of the required thickness nuts bolts |  |  |  |  |  |  |  |
|  | and washers etc and other tools required for jointing and testing the |  |  |  |  |  |  |  |
|  | joints in the specifies pressure etc complete (P.H.S I No 1 P/ 40) |  |  |  |  |  |  |  |
|  | 10.00 | Joints | 6" dia | @Rs: | 938 | P/Joint. | Rs: | 9380 |
| 10 | Butt fusion joint |  |  |  |  |  |  |  |
|  | (P.H.S I No 1 P/ 40) |  |  |  |  |  |  |  |
|  | 10.00 | Joints | 6" dia | @Rs: | 1000 | P/Joint. | Rs: | 10000 |
| 10 | Flange Adopter |  |  |  |  |  |  |  |
|  | (Non Sch: Item) |  |  |  |  |  |  |  |
|  | 10.00 | Nos: | 6" dia | @Rs: | 2025 | Each | Rs: | 20250 |
|  |  |  |  |  |  |  | Rs | 886881 |
|  |  | ABSTRACT |  |  |  |  |  |  |
|  | Des cription |  |  |  | Sch: Items | Non Sch: Items | Total |  |
|  | P.E PIPE 18" DIA |  |  |  | 38487270 | 0 |  | 38487270 |
|  | PUMPING MACHIMERY |  |  |  | 70631 | 816250 |  | 886881 |
|  | Total |  |  |  | 38557901 | 816250 |  | 39374151 |
|  | Total Amount of Composite Schedule _______________% above / below on the rates of CSR Amount to be added / deducted on the basis of premium Total Amount of Non Schedule items TOTAL AMOUNT. Rs: Rs: Rs: Rs: Rs: |  |  |  |  |  |  |  |
|  | CONDITIONS |  |  |  |  |  |  |  |
|  | 1/- | The contractor will have to remove the surplus excavated stuff from the |  |  |  |  |  |  |
|  |  | side of work to out of town at his cost . |  |  |  |  |  |  |
|  | 2/- | The Contractor arrange the materail for construction of work from the approved |  |  |  |  |  |  |
|  |  | quary as shown in the estimate |  |  |  |  |  |  |
|  | 3/- | No premum should be allowed on approved/Market rate. |  |  |  |  |  |  |
|  | 4/- | Any Error or omission in the rats, description, Units shall be refferd to particular |  |  |  |  |  |  |
|  |  | schedule of rates. |  |  |  |  |  |  |
|  | 5/- | No Cartage shall be paid seperately |  |  |  |  |  |  |
|  | CONTRACTOR |  |  |  |  |  |  |  |

|  |  | SUMMARY OF BILL QUANTITY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | ABSTRACT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | COST OF BID |  |  |  |  |  |  |  |  |  |  | Rs: |  |  |  |  |
| ( A ) |  | Cost based on Composite schedule of rates |  |  |  |  |  |  |  |  |  |  | Rs: |  |  |  |  |
| ( B ) |  | Amount of Item based on Non Schedule Items |  |  |  |  |  |  |  |  |  |  | Rs: |  |  |  |  |
|  |  | TOTAL COST OF BID |  |  |  |  |  |  |  |  |  |  | Rs: |  |  |  |  |

GOVERNMENT OF SINDH

PUBLIC HEALTH ENGINEERING DIVISION DADU

STANDARD BIDDING DOCUMENTS

PROCUREMENT OF WORKS (SPPRA BIDDING DOCUMENTS)

For Contracts (Small) amounting between Rs. 4.0 (M) to Rs. 50.00  (M).

Name of Work:		(05)  Construction of Shallow Well, Pump House,

Pumping Machinery at Water Supply Scheme Ghari Taluka K.N Shah Distrcit Dadu.

N.I.T NO: & DATE:		NO: TC/    1334         /   dated:- 15-12-2016

DATE OF ISSUE:                  10-01-2017

DATE OF OPENING:           11-01-2017

TENDER ISSUED TO:      .	     							.

D.R.NO: & DATE:            .	     							.

STANDARD BIDDING DOCUMENT IS INTENDED AS MODEL FOR

ADMEASUREMENTS (PERCENTAGE RATE FOR UNIT RATES IN A BILL OF QUANTITIES TYPES OF CONTRACT THE MAIN TEXT REFERS TO ADMEASUREMENTS CONTRACTOS.

EXECUTIVE ENGINEER

Public Health Engineering Division

DADU

BIDDING DATA

(This section  should be filled in by the office of the Executive Engineer,

Public Engineering Division Dadu, before issuance of the bidding documents).

| (a) | Name of Procuring Agency:- | The Executive Engineer Public Health Engineering Division Dadu. |
| --- | --- | --- |
| (b) | Brief Description of works:- | (05) Construction of Shallow Well, Pump House,Pumping Machinery at Water Supply Scheme Ghari Taluka K.N Shah District Dadu. |
| © | Procuring Agency Address:- | The Executive Engineer Public Health Engineering Division Dadu. Near Gharibabad Muhalla Dadu. |
| (d) | Estimated Cost:- | Rs: 4.000 Million |
| (e) | Amount of Bid Security:- | Rs: 2,00,000/- |
| (f) | Period of Bid Validity (Days):- | (90 days) |
| (g) | Security Deposit (i/c Bid Security):- | (10`%) |
| (h) | Percentage, if any, to be deducted from bills:- | (7.50% Income Tax) & (8% Security Deposit). |
| (i) | Deadline for submission of Bids along with time:- | 10-01-2017 @ 1.30 PM |
| (j) | Venue, time & date of Bid Opening:- | 11-01-2017 @ 2.00 PM |
| (k) | Time for completion from written order of commence:- | (06 Months) |
| (l) | Liquidity Damages:- | (1% on estimated cost per day subject to minimum of 10%) |
| (m) | Deposit receipt No: date & Amount (in words and figure):- | C.D No:_____________ dated:-______________ Amount Rs:_____________Bank_____________. ._______________________________________. M/S____________________________________. |

EXECUTIVE ENGINEER

Public Health Engineering Division

DADU

INSTRUCTIONS TO BIDDERS

(Note: (These Instructions to Bidders (IB) along with Bidding Data will not be part of

Contract and will cease to have effect once the Contract is signed).

A. GENERAL

IB.1 Scope of Bid & Source of Funds

  - Scope of Bid

The Procuring Agency as defined in the Bidding Data (hereinafter called ―the Procuring Agency‖) wishes to receive Bids for the Works summarized in the Bidding Data (hereinafter referred to as ―the Works‖).

Bidders must quote for the complete scope of work. Any Bid covering partial scope of work will be rejected as non-responsive.

  - Source of Funds

The Procuring Agency has arranged funds from its own sources or Federal/ Provincial /Donor agency or any other source, which may be indicated accordingly in bidding data towards the cost of the project/scheme.

IB.2 Eligible Bidders

2.1 Bidding is open to all firms and persons meeting the following requirements:

a) Duly licensed by the Pakistan Engineering Council (PEC) in the appropriate category for value of works.

Provided that the works costing Rs. 4.00 million or less shall not require any registration with PEC .

b) Duly pre-qualified with the Procuring Agency. (Where required).

In the event that prequalification of potential bidders has been undertaken, only bids from prequalified bidders will be considered for award of Contract.

c) If prequalification has not undertaken, the procuring agency may ask information and documents not limited to following:-

(i) Company profile;

(ii) Works of similar nature and size for each performed in last 3/5 years;

(iii) Construction equipments;

(iv) Qualification and experience of technical personnel and key site management; Sindh Public Procurement Regulatory Authority | www.pprasindh.gov.pk 7

(v) Financial statement of last 3 years;

(vi) Information regarding litigations and abandoned works if any.

IB.3 Cost of Bidding

3.1 The bidder shall bear all costs associated with the preparation and submission of its bid

and the Procuring Agency will in no case be responsible or liable for those costs,

Regardless of the conduct or outcome of the bidding process (SPP Rules 24 & 25).

Executive Engineer

PHE Division Dadu

CONDITIONS OF CONTRACT

- GENERAL PROVISIONS

Definitions

In the Contract as defined below, the words and expressions defined shall have the following meanings assigned to them, except where the context requires otherwise:

The Contract

1.1.1 ―Contract‖ means the Contract Agreement and the other documents listed in the Contract Data.

1.1.2 ―Specifications‖ means the document as listed in the Contract Data, including Procuring Agency‘s requirements in respect of design to be carried out by the Contractor (if any), and any Variation to such document.

1.1.3 ―Drawings‖ means the Procuring Agency‘s drawings of the Works as listed in the Contract Data, and any Variation to such drawings.

Persons

1.1.4 ―Procuring Agency‖ means the person named in the Contract Data and the legal successors in title to this person, but not (except with the consent of the Contractor) any assignee.

1.1.5 ―Contractor‖ means the person named in the Contract Data and the legal successors in title to this person, but not (except with the consent of the Procuring Agency) any assignee.

1.1.6 ―Party‖ means either the Procuring Agency or the Contractor.

Dates, Times and Periods

1.1.7 ―Commencement Date‖ means the date fourteen (14) days after the date the Contract comes into effect or any other date named in the Contract Data.

1.1.8 ―Day‖ means a calendar day

1.1.9 ―Time for Completion‖ means the time for completing the Works as stated in the Contract Data (or as extended under Sub-Clause 7.3), calculated from the Commencement Date.

Money and Payments

1.1.10 ―Cost‖ means all expenditure properly incurred (or to be incurred) by the Contractor, whether on or off the Site, including overheads and similar charges but does not include any allowance for profit.

Other Definitions

1.1.11 ―Contractor‘s Equipment‖ means all machinery, apparatus and other things required for the execution of the Works but does not include Materials or Plant intended to form part of the Works.

1.1.12 ―Country‖ means the Islamic Republic of Pakistan.

1.1.13 ―Procuring Agency‘s Risks‖ means those matters listed in Sub-Clause 6.1.

1.1.14 ―Force Majeure‖ means an event or circumstance which makes performance of a Party‘s obligations illegal or impracticable and which is beyond that Party‘s reasonable control.

1.1.15 ‗Materials‖ means things of all kinds (other than Plant) to be supplied and incorporated in the Works by the Contractor.

1.1.16 ―Plant‖ means the machinery and apparatus intended to form or forming part of the Works.

1.1.17 ―Site‖ means the places provided by the Procuring Agency where the Works are to be executed, and any other places specified in the Contract as forming part of the Site.

1.1.18 ―Variation‖ means a change which is instructed by the Engineer/Procuring Agency under Sub-Clause 10.1.

1.1.19 ‗Works‖ means any or all the works whether Supply, Installation, Construction etc. and design (if any) to be performed by the Contractor including temporary works and any variation thereof.

1.1.20 ―Engineer‖ means the person notified by the Procuring Agency to act as Engineer

for the purpose of the Contract and named as such in Contract Data.

  - Interpretation

Words importing persons or parties shall include firms and organizations. Words importing singular or one gender shall include plural or the other gender where the context requires.

  - Priority of Documents.

The documents forming the Contract are to be taken as mutually explanatory of one another. If an ambiguity or discrepancy is found in the documents, the priority of the documents shall be in accordance with the order as listed in the Contract Data.

37

1.4 Law

The law of the Contract is the relevant Law of Islamic Republic of Pakistan.

1.5 Communications

All Communications related to the Contract shall be in English language.

1.6 Statutory Obligations

The Contractor shall comply with the Laws of Islamic Republic of Pakistan and shall give all notices and pay all fees and other charges in respect of the Works.

- THE PROCURING AGENCY

2.1 Provision of Site

The Procuring Agency shall provide the Site and right of access thereto at the times stated in the Contract Data. Site Investigation Reports are those that were included in the bidding documents

and are factual and interpretative reports about the surface and subsurface conditions at the Site.

2.2 Permits etc.

The Procuring Agency shall, if requested by the Contractor, assist him in applying for permits, licenses or approvals which are required for the Works.

2.3 Engineer’s/Procuring Agency’s Instructions

The Contractor shall comply with all instructions given by the Procuring Agency or the Engineer, if notified by the Procuring Agency, in respect of the Works including the suspension of all or part of the works.

2.4 Approvals

No approval or consent or absence of comment by the Engineer/Procuring Agency shall affect the Contractor‘s obligations.

- ENGINEER’S/PROCURING AGENCY’S REPRESENTATIVES

3.1 Authorized Person

The Procuring Agency shall appoint a duly authorized person to act for him and on his behalf for the purposes of this Contract. Such authorized person shall be duly identified in the Contract Data or otherwise notified in writing to the Contractor as soon as he is so appointed. In either case the Procuring Agency shall notify the Contractor, in writing, the precise scope of the authority of such authorized person at the time of his appointment.

3.2 Engineer’s/Procuring Agency’s Representative

The name and address of Engineer‘s/Procuring Agency‘s Representative is given in Contract Data. However the Contractor shall be notified by the Engineer/Procuring Agency, the delegated duties and authority before the Commencement of works.

- THE CONTRACTOR

4.1 General Obligations

The Contractor shall carry out the works properly and in accordance with the Contract. The Contractor shall provide all supervision, labour, Materials, Plant and Contractor‘s Equipment which may be required

4.2 Contractor’s Representative

The Contractor shall appoint a representative at site on full time basis to supervise the execution of work and to receive instructions on behalf of the Contractor but only after obtaining the consent of the Procuring Agency for such appointment which consent shall not be withheld without plausible reason(s) by the Procuring Agency. Such authorized representative may be substituted/ replaced by the Contractor at any time during the Contract Period but only after obtaining the consent of the Procuring Agency as aforesaid.

4.3 Subcontracting

The Contractor shall not subcontract the whole of the works. The Contractor shall not subcontract any part of the works without the consent of the Procuring Agency.

4.4 Performance Security

The Contractor shall furnish to the Procuring Agency within fourteen (14) days after receipt of Letter of Acceptance a Performance Security at the option of the bidder, in the form of Payee‘s order /Bank Draft or Bank Guarantee from scheduled bank for the amount and validity specified in Contract Data.

- DESIGN BY CONTRACTOR

5.1 Contractor’s Design

The Contractor shall carry out design to the extent specified, as referred to in the Contract Data. The Contractor shall promptly submit to the Engineer/Procuring Agency all designs prepared by him, within fourteen (14) days of receipt the Engineer/Procuring Agency shall notify any comments or, if the design submitted is not in accordance with the Contract, shall reject it stating the reasons. Contractor shall not construct any element of the works designed by him within fourteen (14) days after the design has been submitted to the Engineer/Procuring Agency or which has been rejected. Design that has been rejected shall be promptly amended and resubmitted. The Contractor shall resubmit all designs commented on taking these comments into account as necessary.

5.2 Responsibility for Design

The Contractor shall remain responsible for his bided design and the design under this Clause, both of which shall be fit for the intended purposes defined in the Contract and he shall also remain responsible for any infringement of any patent or copyright in respect of the same. The Engineer/Procuring Agency shall be responsible for the Specifications and Drawings.

- PROCURING AGENCY’S RISKS

6.1 The Procuring Agency’s Risks

The Procuring Agency‘s Risks are:-

a) war, hostilities (whether war be declared or not), invasion, act of foreign enemies, within the Country;

b) Rebellion, terrorism, revolution, insurrection, military or usurped power, or civil war, within the Country;

c) riot, commotion or disorder by persons other than the Contractor‘s personnel and other employees including the personnel and employees of Sub- Contractors, affecting the Site and/or the Works;

d) ionizing radiations, or contamination by radio-activity from any nuclear fuel, or from any nuclear waste from the combustion of nuclear fuel, radio-active toxic explosive, or other hazardous properties of any explosive nuclear assembly or nuclear component of such an assembly, except to the extent to which the Contractor/Sub-Contractors may be responsible for the use of any radio-active material;

e) Pressure waves caused by aircraft or other aerial devices travelling at sonic or supersonic speeds;

f) Use or occupation by the Procuring Agency of any part of the Works, except as may be specified in the Contract;

g) late handing over of sites, anomalies in drawings, late delivery of designs and drawings of any part of the Works by the Procuring Agency‘s personnel or by others for whom the Procuring Agency is responsible;

h) a suspension under Sub-Clause 2.3 unless it is attributable to the Contractor‘s failure; and

i) physical obstructions or physical conditions other than climatic conditions, encountered on the Site during the performance of the Works, for which the Contractor immediately notified to the Procuring Agency and accepted by the Procuring Agency.

7. TIME FOR COMPLETION

7.1 Execution of the Works

The Contractor shall commence the Works on the Commencement Date and shall proceed expeditiously and without delay and shall complete the Works, subject to Sub-Clause 7.3 below, within the Time for Completion.

7.2 Programme

Within the time stated in the Contract Data, the Contractor shall submit to the Engineer/Procuring Agency a programme for the Works in the form stated in the Contract Data.

7.3 Extension of Time

The Contractor shall, within such time as may be reasonable under the circumstances, notify the Procuring Agency/Engineer of any event(s) falling within the scope of Sub-Clause 6.1 or 10.3 of these Conditions of Contract and request the Procuring Agency/Engineer for a reasonable extension in the time for the completion of works. Subject to the aforesaid, the Procuring Agency/Engineer shall determine such reasonable extension in the time for the completion of works as may be justified in the light of the details/particulars supplied by the Contractor in connection with the such determination by the Procuring Agency/Engineer within such period as may be prescribed by the Procuring Agency/Engineer for the same; and the Procuring Agency may extend the time for completion as determined.

7.4 Late Completion

If the Contractor fails to complete the Works within the Time for Completion, the Contractor‘s only liability to the Procuring Agency for such failure shall be to pay the amount as liquidity damages stated in the Contract Data for each day for which he fails to complete the Works.

8. TAKING-OVER

8.1 Completion

The Contractor may notify the Engineer/Procuring Agency when he considers that the Works are complete.

8.2 Taking-Over Notice

Within fourteen (14) days of the receipt of the said notice of completion from the Contractor the Procuring Agency/Engineer shall either takeover the completed works and issue a Certificate of Completion to that effect or shall notify the Contractor his reasons for not taking-over the works. While issuing the Certificate of Completion as aforesaid, the Procuring Agency/Engineer may identify any outstanding items of work which the Contractor shall undertake during the

Maintenances Period.

9. REMEDYING DEFECTS

9.1 Remedying Defects

The Contractor shall for a period stated in the Contract Data from the date of issue of the Certificate of Completion carry out, at no cost to the Procuring Agency, repair and rectification work which is necessitated by the earlier execution of poor quality of work or use of below specifications material in the execution of Works and which is so identified by the Procuring Agency/Engineer in writing within the said period. Upon expiry of the said period, and subject to the Contractor‘s faithfully performing his aforesaid obligations, the Procuring Agency/Engineer

shall issue a Maintenance Certificate whereupon all obligations of the Contractor under this Contract shall come to an end. Failure to remedy any such defects or complete outstanding work within a reasonable time shall entitle the Procuring Agency to carry out all necessary works at the Contractor‘s cost. However, the cost of remedying defects not attributable to the Contractor shall be valued as a Variation.

9.2 Uncovering and Testing

The Engineer/Procuring Agency may give instruction as to the uncovering and / or testing of any work. Unless as a result of an uncovering and/or testing it is established that the Contractor‘s design, materials, plant or workmanship are not in accordance with the Contract, the Contractor shall be paid for such uncovering and/or testing as a Variation in accordance with Sub-Clause 10.2.

10. VARIATIONS AND CLAIMS

10.1 Right to Vary

The Procuring Agency/Engineer may issue Variation Order(s) in writing. Where for any reason it has not been possible for the Procuring Agency/Engineer to issue such Variations Order(s), the Contractor may confirm any verbal orders given by the Procuring Agency/Engineer in writing and if the same are not refuted/denied by the Procuring Agency/Engineer within ten (10) days of the receipt of such confirmation the same shall be deemed to be a Variation Orders for the purposes of this Sub-Clause.

10.2 Valuation of Variations

Variations shall be valued as follows:

a) At a lump sum price agreed between the Parties, or

b) Where appropriate, at rates in the Contract, or

c) In the absence of appropriate rates, the rates in the Contract shall be used as the basis for valuation, or failing which

d) At appropriate new rates, as may be agreed or which the Engineer/Procuring Agency considers appropriate, or

e) If the Engineer/Procuring Agency so instructs, at day work rates set out in the Contract Data for which the Contractor shall keep records of hours of labour and Contractor‘s Equipment, and of Materials, used.

10.3 Changes in the Quantities.

a) If the final quantity of the work done differs from the quantity in the Bill of Quantities for the particular item by more than 25 percent, provided the change exceeds 1 percent of the Initial Contract Price, the Procuring Agency/Engineer shall adjust the rate to allow for the change and will be valued as per sub clause 10.2.

b) The Engineer shall not adjust rates from changes in quantities if thereby the Initial Contract Price is exceeded by more than 15 percent, except with the prior approval of the Procuring Agency.

c) If requested by the Engineer, the contractor shall provide the Engineer with a detailed cost breakdown of any rate in the Bill of Quantities.

10.4 Early Warning

The Contractor shall notify the Engineer/Procuring Agency in writing as soon as he is aware of any circumstance which may delay or disrupt the Works, or which may give rise to a claim for additional payment. To the extent of the Contractor‘s failure to notify, which results to the Engineer/Procuring Agency being unable to keep all relevant records or not taking steps to minimize any delay, disruption, or Cost, or the value of any Variation, the Contractor‘s entitlement to extension of the Time for Completion or additional payment shall be reduced/rejected.

10.5 Valuation of Claims

If the Contractor incurs Cost as a result of any of the Procuring Agency‘s Risks, the Contractor shall be entitled to the amount of such Cost. If as a result of any Procuring Agency‘s Risk, it is necessary to change the Works, this shall be dealt with as a Variation subject to Contractor‘s notification for intention of claim to the Engineer/Procuring Agency within fourteen (14) days of the occurrence of cause.

10.6 Variation and Claim Procedure

The Contractor shall submit to the Engineer/Procuring Agency an itemized detailed breakdown of the value of variations and claims within twenty eight (28) days of the instruction or of the event giving rise to the claim. The Engineer/Procuring Agency shall check and if possible agree the value. In the absence of agreement, the Procuring Agency shall determine the value.

11. CONTRACT PRICE AND PAYMENT

11.1 (a) Terms of Payments

The amount due to the Contractor under any Interim Payment Certificate issued by the Engineer pursuant to this Clause, or to any other terms of the Contract, shall , subject to Clause 11.3, be paid by the Procuring Agency to the Contractor within 30 days after such Interim Payment Certificate has been jointly verified by Procuring Agency and Contractor, or, in the case of the Final Certificate referred to in Sub Clause 11.5, within 60days after such Final Payment Certificate has been jointly verified by Procuring Agency and Contractor; Provided that the Interim Payment shall be caused in thirty (30) days and Final Payment in 60 days in case of foreign funded project. In the event of the failure of the Procuring Agency to make payment within 90 days then Procuring Agency shall pay to the Contractor compensation at the 28 days rate of KIBOR+2% per annum in local currency and LIBOR+1% for foreign currency, upon all sums unpaid from the date by which the same should have been paid.

(b) Valuation of the Works

The Works shall be valued as provided for in the Contract Data, subject to Clause 10.

11.2 Monthly Statements

The Contractor shall be entitled to be paid at monthly intervals:

a) The value of the Works executed less to the cumulative amount paid previously; and

b) Value of secured advance on the materials and valuation of variations (if any).

The Contractor shall submit each month to the Engineer/Procuring Agency a statement showing the amounts to which he considers himself entitled.

44

11.3 Interim Payments

Within a period not exceeding seven (07) days from the date of submission of a statement for interim payment by the Contractor, the Engineer shall verify the same and within a period not exceeding thirty (30/60) days from the said date of submission by the Contractor, the Procuring Agency shall pay to the Contractor the sum subject to adjustment for deduction of the advance payments and retention money.

11.4 Retention

Retention money shall be paid by the Procuring Agency to the Contractor within fourteen (14) days after either the expiry of the period stated in the Contract Data, or the remedying of notified defects, or the completion of outstanding work, all as referred to in Sub-Clause 9.1, whichever is the later.

11.5 Final Payment

Within twenty one (21) days from the date of issuance of the Maintenance Certificate the Contractor shall submit a final account to the Engineer to verify and the Engineer shall verify the same within fourteen (14) days from the date of submission and forward the same to the Procuring Agency together with any documentation reasonably required to enable the Procuring Agency to ascertain the final contract value. Within sixty (60) days from the date of receipt of the verified final account from the Engineer, the Procuring Agency shall pay to the Contractor any amount due to the Contractor. While making such payment the Procuring Agency may, for

Reasons to be given to the Contractor in writing, withhold any part or parts of the verified amount.

11.6 Currency

Payment shall be in the currency stated in the Contract Data.

12. DEFAULT

12.1 Defaults by Contractor

If the Contractor abandons the Works, refuses or fails to comply with a valid instruction of the Engineer/Procuring Agency or fails to proceed expeditiously and without delay, or is, despite a written complaint, in breach of the Contract, the Procuring Agency may give notice referring to this Sub-Clause and stating the default.

If the Contractor has not taken all practicable steps to remedy the default within fourteen (14) days after receipt of the Procuring Agency‘s notice, the Procuring Agency may by a second notice given within a further twenty one (21) days, terminate the Contract. The Contractor shall then demobilize from the Site leaving behind any Contractor‘s Equipment which the Procuring Agency instructs, in the second notice, to be used for the completion of the Works at the risk and cost of the Contractor.

12.2 Defaults by Procuring Agency

If the Procuring Agency fails to pay in accordance with the Contract, or is, despite a written complaint, in breach of the Contract, the Contractor may give notice referring to this Sub-Clause and stating the default. If the default is not remedied within fourteen (14) days after the Procuring Agency‘s receipt of this notice, the Contractor may suspend the execution of all or parts of the Works.

If the default is not remedied within twenty eight (28) days after the Procuring Agency‘s receipt of the Contractor‘s notice, the Contractor may by a second notice given within a further twenty one (21) days, terminate the Contract. The Contractor shall then demobilize from the Site.

12.3 Insolvency

If a Party is declared insolvent under any applicable law, the other Party may by notice terminate the Contract immediately. The Contractor shall then demobilize from the site leaving behind, in the case of the Contractor‘s insolvency, any Contractor‘s Equipment which the Procuring Agency instructs in the notice is to be used for the completion of the Works.

12.4 Payment upon Termination

After termination, the Contractor shall be entitled to payment of the unpaid balance of the value of the works executed and of the Materials and Plant reasonably delivered to the site, adjusted by the following:

a) any sums to which the Contractor is entitled under Sub-Clause 10.4,

b) any sums to which the Procuring Agency is entitled,

c) if the Procuring Agency has terminated under Sub-Clause 12.1 or 12.3, the Procuring Agency shall be entitled to a sum equivalent to twenty percent (20%) of the value of parts of the Works not executed at the date of the termination, and

d) if the Contractor has terminated under Sub-Clause 12.2 or 12.3, the Contractor shall be entitled to the cost of his demobilization together with a sum equivalent to ten percent (10%) of the value of parts of the works not executed at the date of termination. The net balance due shall be paid or repaid within twenty eight (28) days of the notice of termination.

13. RISKS AND RESPONSIBILITIES

13.1 Contractor’s Care of the Works

Subject to Sub-Clause 9.1, the Contractor shall take full responsibility for the care of the Works from the Commencement Date until the date of the Procuring Agency‘s/Engineer‘s issuance of Certificate of Completion under Sub-Clause 8.2. Responsibility shall then pass to the Procuring Agency. If any loss or damage happens to the Works during the above period, the Contractor shall rectify such loss or damage so that the Works conform with the Contract. Unless the loss or damage happens as a result of any of the Procuring Agency‘s Risks, the Contractor shall indemnify the Procuring Agency, or his agents against all claims loss, damage and expense arising out of the Works.

13.2 Force Majeure

If Force Majeure occurs, the Contractor shall notify the Engineer/Procuring Agency immediately. If necessary, the Contractor may suspend the execution of the Works and, to the extent agreed with the Procuring Agency demobilize the Contractor‘s Equipment. If the event continues for a period of eighty four (84) days, either Party may then give notice of termination which shall take effect twenty eight (28) days after the giving of the notice. After termination, the Contractor shall be entitled to payment of the unpaid balance of the value of the Works executed and of the Materials and Plant reasonably delivered to the Site, adjusted by the following:

a) any sums to which the Contractor is entitled under Sub-Clause 10.4,

b) the cost of his demobilization, and

c) less any sums to which the Procuring Agency is entitled. The net balance due shall be paid or repaid within thirty five (35) days of the notice of termination.

14. INSURANCE

14.1 Arrangements

The Contractor shall, prior to commencing the Works, effect insurances of the types, in the amounts and naming as insured the persons stipulated in the Contract Data except for items (a) to (e) and (i) of the Procuring Agency‘s Risks under Sub- Clause 6.1. The policies shall be issued by insurers and in terms approved by the Procuring Agency. The Contractor shall provide the Engineer/Procuring Agency with evidence that any required policy is in force and that the premiums have been paid.

14.2 Default

If the Contractor fails to effect or keep in force any of the insurances referred to in the previous Sub-Clause, or fails to provide satisfactory evidence, policies or receipts, the Procuring Agency may, without prejudice to any other right or remedy, effect insurance for the cover relevant to such as a default and pay the premiums due and recover the same plus a sum in percentage given in Contractor Data from any other amounts due to the Contractor.

15. RESOLUTION OF DISPUTES

15.1 Engineer’s Decision

If a dispute of any kind whatsoever arises between the Procuring Agency and the Contractor in connection with the works, the matter in dispute shall, in the first place, be referred in writing to the Engineer, with a copy to the other party. Such reference shall state that it is made pursuant to this Clause. No later than the twenty eight (28) days after the day on which he received such reference, the Engineer shall give notice of his decision to the Procuring Agency (Engineer)and the Contractor. Unless the Contract has already been repudiated or terminated, the Contractor shall, in every case, continue to proceed with the work with all due diligence, and the Contractor and the Procuring Agency ( Engineer) shall give effect forthwith to every such decision of the Engineer unless and until the same shall be revised, as hereinafter provided in an arbitral award.

15.2 Notice of Dissatisfaction

If a Party is dissatisfied with the decision of the Engineer of consultant or if no decision is given within the time set out in Sub-Clause 15.1 here above, the Party may give notice of dissatisfaction referring to this Sub-Clause within fourteen (14) days of receipt of the decision or the expiry of the time for the decision. If no notice of dissatisfaction is given within the specified time, the decision shall be final and binding on the Parties. If notice of dissatisfaction is given within the specified time, the decision shall be binding on the Parties who shall give effect to it without delay unless and until the decision of the Engineer is revised by an arbitrator. If a contractor is dissatisfied with the decision of the Engineer of the department or decision is not given in time then he can approach (Engineer) within 14 days, in case of dissatisfaction with decision of ( Engineer) or not decided within 28 days, then arbitration process would be adopted as per clause 15.3.

15.3 Arbitration

A dispute which has been the subject of a notice of dissatisfaction shall be finally settled as per provisions of Arbitration Act 1940 (Act No. X of 1940) and Rules made there under and any statutory modifications thereto. Any hearing shall be held at the place specified in the Contract Data and in the language referred to in Sub-Clause 1.5.

Contractor

Executive Engineer

PHE Division Dadu

| BOQ / SCHEDULE-B |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Name of work: - (5) |  | CONSTRUCTION OF SHELLOW WELL AT WATER SUPPLY SCHEME GHARI TALUKA K.N.SHAH |  |  |  |  |  |  |
| S.No: | Item | Qty: |  |  | Rate | Unit |  | Amount |
|  | SHELLOW WELL |  |  |  |  |  |  |  |
| 1 | Excavation of well in dry upto 20’ below ground level and disposal of |  |  |  |  |  |  |  |
|  | soil within 1 chain in (ordinary soil) (G.S.I-1 (a) P/ 85). |  |  |  |  |  |  |  |
|  | 0' to 5' depth |  |  |  |  |  |  |  |
|  | 1899.70 | Cft |  | @RS: | 2247.58 | P%0Cft | Rs: | 4270 |
|  | 5' to 10' depth |  |  |  |  |  |  |  |
|  | 1899.70 | Cft |  | @RS: | 2347.4 | P%0Cft | Rs: | 4459 |
|  | 10' to 15' depth |  |  |  |  |  |  |  |
|  | 1899.70 | Cft |  | @RS: | 2641 | P%0Cft | Rs: | 5017 |
| 2 | Pacca brick work in foundation and plinth in cement |  |  |  |  |  |  |  |
|  | sand mortar(1:6)(G.S.I No. 4 P/ 20) |  |  |  |  |  |  |  |
|  | 1473.41 | Cft |  | @Rs: | 11948.36 | P%Cft | Rs: | 176048 |
| 3 | Extra for Pacca brick in staning wells or any other circular massonery |  |  |  |  |  |  |  |
|  | (G.S.I No. 10 P/ 22) |  |  |  |  |  |  |  |
|  | 1473.41 | Cft |  | @Rs: | 1131.63 | P%Cft | Rs: | 16674 |
| 4 | Add: Extra labour for Pacca brick work for every 5 ft additional height |  |  |  |  |  |  |  |
|  | (G.S.I No. 8 P/ 22) |  |  |  |  |  |  |  |
|  | 732.99 | Cft |  | @Rs: | 438.63 | P%Cft | Rs: | 3215 |
| 5 | R.C.C work i/c all labour and material except the cost of steel reinforcement . |  |  |  |  |  |  |  |
|  | and its labour for b/b which will be paid separately. This rate also |  |  |  |  |  |  |  |
|  | i/c all kinds of formsmoulds lifting, hutting, curing, rendering and |  |  |  |  |  |  |  |
|  | finishing the exposed surface (i/c s/w of shingle) (a) R.C work |  |  |  |  |  |  |  |
|  | inroof slab beams columns rafts lintels and other structural |  |  |  |  |  |  |  |
|  | members laid in situ or prrecast laid in position complete in all |  |  |  |  |  |  |  |
|  | respect. (I) Ratio 1:2:4 Lbs cement 2 Cft, sand 4 cft shingle |  |  |  |  |  |  |  |
|  | 1/8” to ¼” gauge. (G.S.I No. 6 P/ 16) |  |  |  |  |  |  |  |
|  | 335.86 | Cft |  | @Rs: | 337 | P/Cft | Rs: | 113185 |
| 6 | Fabrication of mild steel reinforcement for C.C i/c cutting, |  |  |  |  |  |  |  |
|  | bending, laying in position making joints and fastening i/c |  |  |  |  |  |  |  |
|  | cost of binding wire(also i/c removal of rust from bars).(G.S.I No 8 p/ 16) |  |  |  |  |  |  |  |
|  | 12.00 | Cwt |  | @Rs: | 5001.7 | P/Cwt | Rs: | 60020 |
| 7 | wet sinking of wells for depth below spring level by means of |  |  |  |  |  |  |  |
|  | drivers i/c all charges of shoring loading and removing excavated |  |  |  |  |  |  |  |
|  | material with in 1 chain ( in ordinary soil) ( G.S.I No 03 P/ 86 ) |  |  |  |  |  |  |  |
|  | 0' to 5' depth |  |  |  |  |  |  |  |
|  | 1690.00 | Cft |  | @Rs: | 11763.8 | P%0Cft | Rs: | 19881 |
|  | 5' to 10' depth |  |  |  |  |  |  |  |
|  | 1690.00 | Cft |  | @Rs: | 24200.00 | P%0Cft | Rs: | 40898 |
|  | 10' to 15' depth |  |  |  |  |  |  |  |
|  | 1690.00 | Cft |  | @Rs: | 37230.77 | P%0Cft | Rs: | 62920 |
|  | 15' to 20' depth |  |  |  |  |  |  |  |
|  | 1351.96 | Cft |  | @Rs: | 50416.67 | P%0Cft | Rs: | 68161 |
| 8 | Cement, Plaster (1:4) up to 20’ height ½” thick (G.S.I. No.11 P/51) |  |  |  |  |  |  |  |
|  | 202.53 | Sft |  | @Rs: | 2283.93 | P%Sft | Rs: | 4626 |
|  |  |  |  |  |  | Total | Rs: | 579374 |
|  | PUMP HOUSE (FOR SHELLOW WELL) |  |  |  |  |  |  |  |
| 1 | Pacca brick work in ground floor cement, sand, mortar (1:6) |  |  |  |  |  |  |  |
|  | (G.S.I. No 5 P/ 22) |  |  |  |  |  |  |  |
|  | 384.21 | Cft |  | @Rs: | 12674.36 | P%Cft | Rs: | 48696 |
| 2 | R.C.C work i/c all labour and material except the cost of steel |  |  |  |  |  |  |  |
|  | reinforcement and its labour for b/b which will be paid separately. |  |  |  |  |  |  |  |
|  | This rate also i/c all kinds of forms moulds lifting, shutting, curing, |  |  |  |  |  |  |  |
|  | rendering and finishing the exposed surface (i/c s/w of shingle) (a) R.C work in |  |  |  |  |  |  |  |
|  | roof slab beams columns rafts lintels and other structural members laid in |  |  |  |  |  |  |  |
|  | situ or prrecast laid in position complete in all respect. (I) Ratio 2:2:4 Lbs |  |  |  |  |  |  |  |
|  | cement2 Cft, sand 4 cft shingle1/8” to ¼” gauge. (G.S.I No. 6 p/ 49). |  |  |  |  |  |  |  |
|  | 263.44 | Cft |  | @Rs: | 337 | P/Cft | Rs: | 88779 |
| 3 | Fabrication of mild steel reinforcement for C.C i/c cutting, bending, |  |  |  |  |  |  |  |
|  | laying in position making joints and fastening i/c cost of binding wire |  |  |  |  |  |  |  |
|  | (also i/c removal of rust from bars).(G.S.I No 7 p/ 20) |  |  |  |  |  |  |  |
|  | 10.57 | Cwt |  | @Rs: | 5001.7 | P/Cwt | Rs: | 52868 |
| 4 | Cement, Plaster (1:6) up to 20’ height ½” thick (G.S.I. No.11 P/58) |  |  |  |  |  |  |  |
|  | 462 | Sft |  | @Rs: | 2206.6 | P%Sft | Rs: | 10194 |
| 5 | Cement, Plaster (1:4) up to 20’ height 3/8” thick (G.S.I. No.11 P/58) |  |  |  |  |  |  |  |
|  | 462 | Sft |  | @Rs: | 2197.52 | P%Sft | Rs: | 10153 |
| 6 | Cement, Pointing struck joint on walls (1:3) (G.S.I. No.11 P/57) |  |  |  |  |  |  |  |
|  | 500.55 | Sft |  | @Rs: | 1213.58 | P%Sft | Rs: | 6075 |
| 7 | Making and fixing steel grated door with 1/16” thick sheeting angle iron |  |  |  |  |  |  |  |
|  | frame 2”x2”x 3/8” and ¾” sq: bars 4” Center to center with |  |  |  |  |  |  |  |
|  | locking arrangement (G.S.I. No.11 P/97) |  |  |  |  |  |  |  |
|  | 28 | Sft |  | @Rs: | 726.72 | P/Sft | Rs: | 20348 |
| 8 | Fabrication of heavy steel work with angles tees flat iron round iron and |  |  |  |  |  |  |  |
|  | sheet iron for making trusses girders tanks etc: i/c cutting tanks etc: i/c |  |  |  |  |  |  |  |
|  | assembling and fixing but excluding errection in position. (G.S.I-2, P-90). |  |  |  |  |  |  |  |
|  | 2.03 | Cwt |  | @Rs: | 4928.49 | P/Cwt | Rs: | 10005 |
| 9 | PAINTING NEW SURFACE |  |  |  |  |  |  |  |
|  | Preparing surface and painting of door and window any type i/c |  |  |  |  |  |  |  |
|  | Edges 3 coats (G.S.I. No.5 P/6) |  |  |  |  |  |  |  |
|  | 56 | Sft |  | @Rs: | 1489.68 | P%Sft | Rs: | 834 |
| 10 | White washing of three coats (G.S.I. No.26 P/55) |  |  |  |  |  |  |  |
|  | 619.00 | Sft |  | @Rs: | 829.95 | P%Sft | Rs: | 5137 |
| 11 | Color Washing (2 coats) (G.S.I.No:24, P/60). |  |  |  |  |  |  |  |
|  | 962.55 | Sft |  | @Rs: | 859.9 | P%Sft | Rs: | 8191 |
| 12 | Small iron work such as gusset plate knees bends stirrups rings etc: |  |  |  |  |  |  |  |
|  | i/c cutting drilling revertting handling assembling and fixing but excluding |  |  |  |  |  |  |  |
|  | erection in position. (G.S.I-1, P-90). |  |  |  |  |  |  |  |
|  | 5.6 | Cwt. |  | @Rs: | 6420.61 | P/Cwt. | Rs: | 35955 |
|  |  |  |  |  |  |  | Rs: | 297235 |
|  | PUMPING MACHINARY (FOR SHELLOW WELL) |  |  |  |  |  |  |  |
| 1 | Providing Installing and testing in poition i/c tranportation HMA . |  |  |  |  |  |  |  |
|  | stainless steel deep well turbine pump type BP 17-4 + 5.5 BHP siemens motor |  |  |  |  |  |  |  |
|  | (3x400 V, 50 HZ, 2900 RPM) with suction discharge top set 3" dia x 01 No: |  |  |  |  |  |  |  |
|  | pump head 3" outlet with mechanical seal, bowl assembly, suction pipe 1.6m 3" dia,column |  |  |  |  |  |  |  |
|  | pipe assembly 3" dia x 3 Nos: capable given discharge 50 GPM against |  |  |  |  |  |  |  |
|  | the head of 160 ft and pump setting depth 30 ft i/c C.C foundation, earthing Attached) |  |  |  |  |  |  |  |
|  | set with 0.6mx0.6mx3.6mm (2"x2"x1/4") G.I plate burried in the ground at |  |  |  |  |  |  |  |
|  | the depth of 3.7m or 12 ft as per PWD specification and providing f |  |  |  |  |  |  |  |
|  | ixing motor control unit consisting metallic box, circuit breaker, |  |  |  |  |  |  |  |
|  | amper meter, volt meter, magnatic contractor, on/off switch, electronic |  |  |  |  |  |  |  |
|  | over current relay and indications lamps i/c providing internal electric |  |  |  |  |  |  |  |
|  | wiring for main and testing the pumping set against 72 hours etc: complete |  |  |  |  |  |  |  |
|  | (Approvede R.A) |  |  |  |  |  |  |  |
|  |  | 1.00 | Set | @Rs: | 283000 | P/Set. | Rs: | 283000 |
| 2 | Providing Laying G.I Pipe and clamps etc: i/c fixing cutting and fitting |  |  |  |  |  |  |  |
|  | complete i/c the cost of breaking through walls and making good etc: |  |  |  |  |  |  |  |
|  | painting 3 coats after cleaning the pipe with zink paint with pigment to match |  |  |  |  |  |  |  |
|  | the pressure head of 200 ft and handling (Sant: Sch: I-1, P133) |  |  |  |  |  |  |  |
|  | for Suction line 3"dia. |  |  |  |  |  |  |  |
|  |  | 6.00 | Rft. | @Rs: | 304.02 | P/Rft. | Rs: | 1824 |
| 3 | Manufacturing and supplying M.S flanged of different clamps made out of |  |  |  |  |  |  |  |
|  | M.S sheet of various thickness i/c cutting drilling holes and welding clamps |  |  |  |  |  |  |  |
|  | with M.S pipes etc complete (P.H.S.I-1, P-32). |  |  |  |  |  |  |  |
|  |  | 10 | Nos: | @Rs: | 945.00 | Each | Rs: | 9450 |
| 4 | C.I bend with flanged ends with holes i/c turning and facing flanged |  |  |  |  |  |  |  |
|  | for all sizes. (P.H.S (M) I. No 8 P/ 11) |  |  |  |  |  |  |  |
|  |  | 0.57 | Cwt. | @Rs: | 6096 | P/Cwt. | Rs: | 3475 |
| 5 | C.I tapered flat bottomed or central tapered flanged end with holes |  |  |  |  |  |  |  |
|  | i/c turning facing flanged for all sizes (P.H.S. (M) I. No 7 P/ 11) |  |  |  |  |  |  |  |
|  |  | 0.28 | Cwt. | @Rs: | 6096 | P/Cwt. | Rs: | 1707 |
| 6 | C.I sluice valve heavy pattern test pressure 21 kg /sq, cm or 300 lbs /sq inch |  |  |  |  |  |  |  |
|  | (P.H.S (M) I No 16 P/ 11) |  |  |  |  |  |  |  |
|  | 3" dia | 1 | Nos: | @Rs: | 4290 | Each. | Rs: | 4290 |
| 7 | Reflex valve heavy pattern test pressure 21 kg /sq, cm or 300 lbs /sq inch |  |  |  |  |  |  |  |
|  | (P.H.S (M) I No 16 P/ 11) |  |  |  |  |  |  |  |
|  | 3"dia. | 1 | Nos: | @Rs: | 1543.15 | Each. | Rs: | 1543 |
| 8 | Jointing C.I/M.S flanged and specials pipes and inside a trenches i/c |  |  |  |  |  |  |  |
|  | supplying of the rubber packing of the required thickness nuts bolts |  |  |  |  |  |  |  |
|  | and washers etc and other tools required for jointing and testing the |  |  |  |  |  |  |  |
|  | joints in the specifies pressure etc complete (P.H.S I No 1 P/ 35) |  |  |  |  |  |  |  |
|  | 3" dia. | 10 | Nos: | @Rs: | 499 | P/Joint. | Rs: | 4990 |
| 9 | Providing Laying Jointing & testing High Density Polyethylene pipe (HDPE-100) |  |  |  |  |  |  |  |
|  | for W/S conforming to ISO-4427, DIN 8074, 8075 & PS 3580, |  |  |  |  |  |  |  |
|  | 1980 PS 3580 & PSI 3051 i/c earth work in ordinary soil etc: complete. |  |  |  |  |  |  |  |
|  | (P.H.S.I-1, P-26). P.N.- 10 |  |  |  |  |  |  |  |
|  | 3" dia (90mm) | 44 | Rft. | @Rs: | 178 | P/Rft | Rs: | 7832 |
| 10 | BUTT FUSION JOINT |  |  |  |  |  |  |  |
|  | 3" dia | 10 | Nos: | @Rs: | 600 | Each | Rs | 6000 |
| 11 | Supplying flange adaptor ( Non sch: item) |  |  |  |  |  |  |  |
|  | 3" dia | 10 | Nos: | @Rs: | 675 | Each | Rs | 6750 |
|  |  |  |  |  |  |  | Rs: | 330861 |
|  |  |  | 330861 | x | 3 | = | Rs: | 992583 |
|  | RESISITIVITY SURVEY REPORT |  |  |  |  |  |  |  |
| 1 | Conducting of resisitivity survey of Geo electrical |  |  |  |  |  |  |  |
|  | sounding VES evaluation, interpretation and compilation |  |  |  |  |  |  |  |
|  | of resisitivity and hydrogeological survey test i/c mobilization |  |  |  |  |  |  |  |
|  | and de-mobilization of geologist and equipment i/c lodging |  |  |  |  |  |  |  |
|  | and boarding charges. (Approved rate). |  |  |  |  |  |  |  |
|  |  | 1 | Job | @Rs: | 25000 | P/Job | Rs: | 25000 |
|  |  |  |  |  |  |  | Rs: | 25000 |

|  |  |  | ABSTRACT |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Sch: Items | Non S.Item |  | Total |
|  | SHELLOW WELL |  |  |  | 579374 | 0 | Rs: | 579374 |
|  | PUMP HOUSE (FOR SHELLOW WELL) |  |  |  | 297235 | 0 | Rs: | 297235 |
|  | PUMPING MACHINARY (FOR SHELLOW WELL) |  |  |  | 123333 | 869250 | Rs: | 992583 |
|  | RESISITIVITY SURVEY REPORT |  |  |  | 0 | 25000 | Rs: | 25000 |
|  |  |  |  |  | 999942 | 894250 | Rs: | 1894192 |
|  | Total Amount of Composite Schedule _______________% above / below on the rates of CSR Amount to be added / deducted on the basis of premium Total Amount of Non Schedule items TOTAL AMOUNT. Rs: Rs: Rs: Rs: Rs: |  |  |  |  |  |  |  |
|  | CONDITIONS |  |  |  |  |  |  |  |
|  | 1/- | The contractor will have to remove the surplus excavated stuff from the |  |  |  |  |  |  |
|  |  | side of work to out of town at his cost . |  |  |  |  |  |  |
|  | 2/- | The Contractor arrange the materail for construction of work from the approved |  |  |  |  |  |  |
|  |  | quary as shown in the estimate |  |  |  |  |  |  |
|  | 3/- | No premum should be allowed on approved/Market rate. |  |  |  |  |  |  |
|  | 4/- | Any Error or omission in the rats, description, Units shall be refferd to particular |  |  |  |  |  |  |
|  |  | schedule of rates. |  |  |  |  |  |  |
|  | 5/- | No Cartage shall be paid seperately |  |  |  |  |  |  |
|  | CONTRACTOR |  |  |  |  |  |  |  |

|  | SUMMARY OF BILL QUANTITY |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | ABSTRACT |  |  |  |  |  |  |  |
|  | COST OF BID |  |  |  |  |  | Rs: |  |
| ( A ) | Cost based on Composite schedule of rates |  |  |  |  |  | Rs: |  |
| ( B ) | Amount of Item based on Non Schedule Items |  |  |  |  |  | Rs: |  |
|  | TOTAL COST OF BID |  |  |  |  |  | Rs: |  |