## Plan Pinyari Br.0 to 50
ANNEXURE - A1
PROCUREMENT PLAN FOR THE YEAR 2016-17 FOR M&R WOKS (NON-DEVELOPMENT)
Sr. No. | Name of works. | Tentative Qty. |  | Cost of ongoing works (Expenditure already incurred) | Funds earmarked for ongoing works | Cost of New works (Components) | Funds for New works (c - e) | Nature of Procurement | Methodof Procurement | Anticipated / Actual date of Advertisment | Anticipated / Actual date of Start | Anticipated / Actual date of Completion
A | B | C |  | D | E | F | G | H | I | J | K | L
6) Procurement of Goods for the Section of Pinyari Branch RD 0 to 50.
PART-1 (SITE MATERIAL)
1 | Empty Gunny Bags L/S 1st Bharty | 1200 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
2 | Empty Gunny Bags S/S 2nd Bharty | 1500 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
3 | Plastic Bags Katta L/S | 7500 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
4 | Sutli | 60 | P.Kg | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
5 | Pees Wan | 60 | P.Kg | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
6 | Munj Wan | 50 | P.Kg | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
7 | Earthen. | 40 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
8 | Needles For Sewing Bags | 20 | P.Dozen | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
9 | Lai Basket M.S | 60 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
10 | Towas Sur Double Size 6’x7’ | 700 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
11 | Pees Mats Size 6’x4’ | 350 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
12 | Pakkah Reed Kani Size 7’x14’ at site | 150 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
13 | Lai Panjers Size 10 to 12 ft Long | 3000 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
14 | Manjhandari Panjers Size 10’ to 12’ Long | 450 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
15 | Glass Plastic @ Site | 10 | P.Dozen | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
16 | Plastic Sheet @ site | 250 | P.Meter | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
17 | Pakkah Pan Double size 8 x 15 @ site | 350 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
18 | Pan Mate Size 4 .5 x 5.5 @ site | 350 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
19 | Pakha Sur Double size 7 x 14 @ site | 450 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
20 | Waras | 150 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
21 | Thunies | 250 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
22 | Babul Munnas | 450 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
23 | Kerosene Oil. | 150 | P.Liter | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
24 | Providing and fixing mile stone 2’.5”x1’x3” painting lettering etc complete RCC. | 50 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
25 | Lime Un-Slacked | 80 | P.Kg | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
26 | Kodars (Spades) with handle @ site | 40 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
27 | Engaging Casual Labour i/c catering & Lodging | 1000 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
28 | Solar Torch M/S | 250 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
29 | Solar Torch L/S | 15 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
30 | Electric Wire 3/029 copper at site. | 15 | P. Coil | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
31 | Bulb Holdar | 24 | P.Dozen | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2018
32 | Saver Bulb 24 W | 120 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
33 | Solution Tape | 15 | P.Roll | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
34 | Providing Stone Boulder 9” to 12” i/c Carriage | 11000 | % Cft | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
35 | Taint 20x14 with all accessories on hire charges. | 5 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
PART-2 (HIRE OF VEHICLES & MACHINEERY)
1 | Engg: Suzuki pickup on hire charges with POL & Driver at site. | 60 | P.Day | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
2 | Engg: Tractor with Hydraulic Trolly with POL for shifting earth within 3 miles. | 800 | P.Trip | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
3 | Engg: Tractor with Front Blade wheel type on hire charges with POL & Driver at site. | 1000 | P.Hour | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
4 | Engg: Electric Generator on Hire charges with POL at site. | 60 | P.Day | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
5 | Engg: Wheel type Hydraulic Excavator for Earth Work on hire charges with POL & Driver at site. | 3500 | P.Hour | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2018
6 | Engg: chain type Hydraulic Excavator for Earth Work on hire charges with POL & Driver at site. | 2500 | P.Hour | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
7 | Engg: Bulldozer on hire charges with POL | 60 | P.Day | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
8 | Providing Diesel with carriage at site | 1200 | P.Liter | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
9 | Providing Petrol with carraige at site | 2500 | P.Liter | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
10 | Providing Mobil Oil GTX 4 Liters tin at site. | 20 | P.Tin | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
Part – 3 (Closure Materials, Colouring the Gate / Regulators Oiling and Greasing & etc)
1 | Black Bituman Superior @ site | 85 | P.Liter | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
2 | Oil Paint Superior Quality any colour @ site | 60 | P.Liter | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
3 | Colour (distemper any colour) | 5 | P.Tin | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
4 | Red Oxide @ site in liter | 90 | P.Liter | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
5 | Tarpene Oil (Local) in liter @ site | 130 | P.Liter | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
6 | Scraper @ site | 6 | P.Dozen | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
7 | Wire Bursh @ site | 6 | Dozen | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
8 | Grease Superior @ site | 20 | P.Kg | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
9 | Painting Bursh 2” size @ site | 2 | P.Dozen | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
10 | Painting Bursh 4” size @ site | 2 | P.Dozen | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
11 | Cotton Waste @ site | 10 | P.Dozen | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
12 | Mobil Oil (used) in liter @ site | 120 | P.Liter | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
13 | Engaging Painter for painting any type of work at site. | 30 | P.day | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2018
14 | Engaging Helper for Painting at site. | 30 | P.day | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2019
15 | Engaging Helper.(Skilled) for Gate works at site. | 30 | P.day | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2020
16 | Engg: Mistry for Gate works at site. | 30 | P.day | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2021
17 | Providing Electric welding Rod & SWG. Chain at site. | 250 | P.Kg | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2022
18 | Engg: Hire charges of Welding plant at site. | 30 | P.day | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2023
Executive Engineer,
Upper Pinyari Division
Hyderabad

## Plan Ganj Bahar RD 0 to 72
ANNEXURE - A1
PROCUREMENT PLAN FOR THE YEAR 2016-17 FOR M&R WOKS (NON-DEVELOPMENT)
Sr. No. | Name of works. | Tentative Qty. |  | Cost of ongoing works (Expenditure already incurred) | Funds earmarked for ongoing works | Cost of New works (Components) | Funds for New works (c - e) | Nature of Procurement | Methodof Procurement | Anticipated / Actual date of Advertisment | Anticipated / Actual date of Start | Anticipated / Actual date of Completion
A | B | C |  | D | E | F | G | H | I | J | K | L
5) Procurement of Goods for the Section of Ganj Bahar Branch Ex. PFL RD 0 to 72.
PART-1 (SITE MATERIAL)
1 | Empty Gunny Bags L/S 1st Bharty | 1500 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
2 | Empty Gunny Bags S/S 2nd Bharty | 1800 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
3 | Plastic Bags Katta L/S | 7500 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
4 | Sutli | 70 | P.Kg | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
5 | Pees Wan | 75 | P.Kg | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
6 | Munj Wan | 60 | P.Kg | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
7 | Earthen. | 40 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
8 | Needles For Sewing Bags | 24 | P.Dozen | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
9 | Lai Basket M.S | 60 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
10 | Towas Sur Double Size 6’x7’ | 800 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
11 | Pees Mats Size 6’x4’ | 350 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
12 | Pakkah Reed Kani Size 7’x14’ at site | 150 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
13 | Lai Panjers Size 10 to 12 ft Long | 4500 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
14 | Manjhandari Panjers Size 10’ to 12’ Long | 500 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
15 | Glass Plastic @ Site | 10 | P.Dozen | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
16 | Plastic Sheet @ site | 250 | P.Meter | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
17 | Pakkah Pan Double size 8 x 15 @ site | 400 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
18 | Pan Mate Size 4 .5 x 5.5 @ site | 400 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
19 | Pakha Sur Double size 7 x 14 @ site | 500 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
20 | Waras | 200 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
21 | Thunies | 350 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
22 | Babul Munnas | 500 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
23 | Kerosene Oil. | 250 | P.Liter | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
24 | Providing and fixing mile stone 2’.5”x1’x3” painting lettering etc complete RCC. | 50 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
25 | Lime Un-Slacked | 50 | P.Kg | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
26 | Kodars (Spades) with handle @ site | 50 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
27 | Engaging Casual Labour i/c catering & Lodging | 1000 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
28 | Solar Torch M/S | 250 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
29 | Solar Torch L/S | 15 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
30 | Electric Wire 3/029 copper at site. | 20 | P. Coil | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
31 | Bulb Holdar | 24 | P.Dozen | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
32 | Saver Bulb 24 W | 120 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2018
33 | Solution Tape | 15 | P.Roll | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
34 | Providing Stone Boulder 9” to 12” i/c Carriage | 16000 | % Cft | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
35 | Taint 20x14 with all accessories on hire charges. | 5 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
PART-2 (HIRE OF VEHICLES & MACHINEERY)
1 | Engg: Suzuki pickup on hire charges with POL & Driver at site. | 60 | P.Day | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
2 | Engg: Tractor with Hydraulic Trolly with POL for shifting earth within 3 miles. | 1000 | P.Trip | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
3 | Engg: Tractor with Front Blade wheel type on hire charges with POL & Driver at site. | 1200 | P.Hour | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
4 | Engg: Electric Generator on Hire charges with POL at site. | 60 | P.Day | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
5 | Engg: Wheel type Hydraulic Excavator for Earth Work on hire charges with POL & Driver at site. | 3500 | P.Hour | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
6 | Engg: chain type Hydraulic Excavator for Earth Work on hire charges with POL & Driver at site. | 2500 | P.Hour | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2018
7 | Engg: Bulldozer on hire charges with POL | 60 | P.Day | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
8 | Providing Diesel with carriage at site | 2500 | P.Liter | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
9 | Providing Petrol with carraige at site | 3500 | P.Liter | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
10 | Providing Mobil Oil GTX 4 Liters tin at site. | 20 | P.Tin | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
Part – 3 (Closure Materials, Colouring the Gate / Regulators Oiling and Greasing & etc)
1 | Black Bituman Superior @ site | 96 | P.Liter | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
2 | Oil Paint Superior Quality any colour @ site | 80 | P.Liter | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
3 | Colour (distemper any colour) | 5 | P.Tin | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
4 | Red Oxide @ site in liter | 90 | P.Liter | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
5 | Tarpene Oil (Local) in liter @ site | 130 | P.Liter | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
6 | Scraper @ site | 6 | P.Dozen | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
7 | Wire Bursh @ site | 6 | Dozen | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
8 | Grease Superior @ site | 20 | P.Kg | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
9 | Painting Bursh 2” size @ site | 2 | P.Dozen | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
10 | Painting Bursh 4” size @ site | 2 | P.Dozen | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
11 | Cotton Waste @ site | 10 | P.Dozen | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
12 | Mobil Oil (used) in liter @ site | 120 | P.Liter | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
13 | Engaging Painter for painting any type of work at site. | 30 | P.day | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
14 | Engaging Helper for Painting at site. | 30 | P.day | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
15 | Engaging Helper.(Skilled) for Gate works at site. | 30 | P.day | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
16 | Engg: Mistry for Gate works at site. | 30 | P.day | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
17 | Providing Electric welding Rod & SWG. Chain at site. | 450 | P.Kg | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
18 | Engg: Hire charges of Welding plant at site. | 30 | P.day | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
Executive Engineer,
Upper Pinyari Division
Hyderabad

## Plan Miranpur Br. RD 0 to 82
ANNEXURE - A1
PROCUREMENT PLAN FOR THE YEAR 2016-17 FOR M&R WOKS (NON-DEVELOPMENT)
Sr. No. | Name of works. | Tentative Qty. |  | Cost of ongoing works (Expenditure already incurred) | Funds earmarked for ongoing works | Cost of New works (Components) | Funds for New works (c - e) | Nature of Procurement | Methodof Procurement | Anticipated / Actual date of Advertisment | Anticipated / Actual date of Start | Anticipated / Actual date of Completion
A | B | C |  | D | E | F | G | H | I | J | K | L
4) Procurement of Goods for the Section of Miranpur Branch Ex. PFL RD 0 to 82.
PART-1 (SITE MATERIAL)
1 | Empty Gunny Bags L/S 1st Bharty | 1800 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
2 | Empty Gunny Bags S/S 2nd Bharty | 2000 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
3 | Plastic Bags Katta L/S | 8000 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
4 | Sutli | 70 | P.Kg | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
5 | Pees Wan | 75 | P.Kg | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
6 | Munj Wan | 60 | P.Kg | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
7 | Earthen. | 40 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
8 | Needles For Sewing Bags | 24 | P.Dozen | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
9 | Lai Basket M.S | 60 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
10 | Towas Sur Double Size 6’x7’ | 800 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
11 | Pees Mats Size 6’x4’ | 350 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
12 | Pakkah Reed Kani Size 7’x14’ at site | 150 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
13 | Lai Panjers Size 10 to 12 ft Long | 4500 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
14 | Manjhandari Panjers Size 10’ to 12’ Long | 500 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
15 | Glass Plastic @ Site | 10 | P.Dozen | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
16 | Plastic Sheet @ site | 250 | P.Meter | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
17 | Pakkah Pan Double size 8 x 15 @ site | 400 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
18 | Pan Mate Size 4 .5 x 5.5 @ site | 400 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
19 | Pakha Sur Double size 7 x 14 @ site | 500 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
20 | Waras | 200 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
21 | Thunies | 350 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
22 | Babul Munnas | 500 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
23 | Kerosene Oil. | 250 | P.Liter | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
24 | Providing and fixing mile stone 2’.5”x1’x3” painting lettering etc complete RCC. | 50 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
25 | Lime Un-Slacked | 50 | P.Kg | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
26 | Kodars (Spades) with handle @ site | 50 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
27 | Engaging Casual Labour i/c catering & Lodging | 1200 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
28 | Solar Torch M/S | 250 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
29 | Solar Torch L/S | 15 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
30 | Electric Wire 3/029 copper at site. | 20 | P. Coil | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
31 | Bulb Holdar | 24 | P.Dozen | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
32 | Saver Bulb 24 W | 120 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
33 | Solution Tape | 15 | P.Roll | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2018
34 | Providing Stone Boulder 9” to 12” i/c Carriage | 17000 | % Cft | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
35 | Taint 20x14 with all accessories on hire charges. | 5 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
PART-2 (HIRE OF VEHICLES & MACHINEERY)
1 | Engg: Suzuki pickup on hire charges with POL & Driver at site. | 60 | P.Day | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
2 | Engg: Tractor with Hydraulic Trolly with POL for shifting earth within 3 miles. | 1000 | P.Trip | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
3 | Engg: Tractor with Front Blade wheel type on hire charges with POL & Driver at site. | 1200 | P.Hour | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
4 | Engg: Electric Generator on Hire charges with POL at site. | 60 | P.Day | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
5 | Engg: Wheel type Hydraulic Excavator for Earth Work on hire charges with POL & Driver at site. | 3500 | P.Hour | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
6 | Engg: chain type Hydraulic Excavator for Earth Work on hire charges with POL & Driver at site. | 2500 | P.Hour | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
7 | Engg: Bulldozer on hire charges with POL | 60 | P.Day | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2018
8 | Providing Diesel with carriage at site | 2500 | P.Liter | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
9 | Providing Petrol with carraige at site | 3500 | P.Liter | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
10 | Providing Mobil Oil GTX 4 Liters tin at site. | 20 | P.Tin | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
Part – 3 (Closure Materials, Colouring the Gate / Regulators Oiling and Greasing & etc)
1 | Black Bituman Superior @ site | 96 | P.Liter | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
2 | Oil Paint Superior Quality any colour @ site | 80 | P.Liter | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
3 | Colour (distemper any colour) | 5 | P.Tin | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
4 | Red Oxide @ site in liter | 90 | P.Liter | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
5 | Tarpene Oil (Local) in liter @ site | 130 | P.Liter | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
6 | Scraper @ site | 6 | P.Dozen | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
7 | Wire Bursh @ site | 6 | Dozen | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
8 | Grease Superior @ site | 20 | P.Kg | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
9 | Painting Bursh 2” size @ site | 2 | P.Dozen | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
10 | Painting Bursh 4” size @ site | 2 | P.Dozen | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
11 | Cotton Waste @ site | 10 | P.Dozen | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
12 | Mobil Oil (used) in liter @ site | 120 | P.Liter | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
13 | Engaging Painter for painting any type of work at site. | 30 | P.day | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
14 | Engaging Helper for Painting at site. | 30 | P.day | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
15 | Engaging Helper.(Skilled) for Gate works at site. | 30 | P.day | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
16 | Engg: Mistry for Gate works at site. | 30 | P.day | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
17 | Providing Electric welding Rod & SWG. Chain at site. | 450 | P.Kg | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
18 | Engg: Hire charges of Welding plant at site. | 30 | P.day | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
Executive Engineer,
Upper Pinyari Division
Hyderabad

## Plan PFLRD 110 to 168
ANNEXURE - A1
PROCUREMENT PLAN FOR THE YEAR 2016-17 FOR M&R WOKS (NON-DEVELOPMENT)
Sr. No. | Name of works. | Tentative Qty. |  | Cost of ongoing works (Expenditure already incurred) | Funds earmarked for ongoing works | Cost of New works (Components) | Funds for New works (c - e) | Nature of Procurement | Methodof Procurement | Anticipated / Actual date of Advertisment | Anticipated / Actual date of Start | Anticipated / Actual date of Completion
A | B | C |  | D | E | F | G | H | I | J | K | L
3) Procurement of Goods for the Section of P.F.L RD 110 to 168.
PART-1 (SITE MATERIAL)
1 | Empty Gunny Bags L/S 1st Bharty | 1500 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
2 | Empty Gunny Bags S/S 2nd Bharty | 2000 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
3 | Plastic Bags Katta L/S | 8000 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
4 | Sutli | 60 | P.Kg | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
5 | Pees Wan | 60 | P.Kg | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
6 | Munj Wan | 50 | P.Kg | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
7 | Earthen. | 40 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
8 | Needles For Sewing Bags | 20 | P.Dozen | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
9 | Lai Basket M.S | 60 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
10 | Towas Sur Double Size 6’x7’ | 700 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
11 | Pees Mats Size 6’x4’ | 350 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
12 | Pakkah Reed Kani Size 7’x14’ at site | 150 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
13 | Lai Panjers Size 10 to 12 ft Long | 3500 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
14 | Manjhandari Panjers Size 10’ to 12’ Long | 450 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
15 | Glass Plastic @ Site | 10 | P.Dozen | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
16 | Plastic Sheet @ site | 250 | P.Meter | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
17 | Pakkah Pan Double size 8 x 15 @ site | 350 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
18 | Pan Mate Size 4 .5 x 5.5 @ site | 350 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
19 | Pakha Sur Double size 7 x 14 @ site | 450 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
20 | Waras | 150 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
21 | Thunies | 250 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
22 | Babul Munnas | 450 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
23 | Kerosene Oil. | 200 | P.Liter | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
24 | Providing and fixing mile stone 2’.5”x1’x3” painting lettering etc complete RCC. | 50 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
25 | Lime Un-Slacked | 80 | P.Kg | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
26 | Kodars (Spades) with handle @ site | 40 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
27 | Engaging Casual Labour i/c catering & Lodging | 1200 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
28 | Solar Torch M/S | 300 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
29 | Solar Torch L/S | 20 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
30 | Electric Wire 3/029 copper at site. | 15 | P. Coil | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
31 | Bulb Holdar | 24 | P.Dozen | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
32 | Saver Bulb 24 W | 120 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
33 | Solution Tape | 15 | P.Roll | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
34 | Providing Stone Boulder 9” to 12” i/c Carriage | 12000 | % Cft | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2018
35 | Taint 20x14 with all accessories on hire charges. | 5 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
PART-2 (HIRE OF VEHICLES & MACHINEERY)
1 | Engg: Suzuki pickup on hire charges with POL & Driver at site. | 60 | P.Day | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
2 | Engg: Tractor with Hydraulic Trolly with POL for shifting earth within 3 miles. | 800 | P.Trip | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
3 | Engg: Tractor with Front Blade wheel type on hire charges with POL & Driver at site. | 1000 | P.Hour | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
4 | Engg: Electric Generator on Hire charges with POL at site. | 60 | P.Day | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
5 | Engg: Wheel type Hydraulic Excavator for Earth Work on hire charges with POL & Driver at site. | 3500 | P.Hour | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
6 | Engg: chain type Hydraulic Excavator for Earth Work on hire charges with POL & Driver at site. | 2500 | P.Hour | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
7 | Engg: Bulldozer on hire charges with POL | 60 | P.Day | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
8 | Providing Diesel with carriage at site | 1200 | P.Liter | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2018
9 | Providing Petrol with carraige at site | 2500 | P.Liter | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
10 | Providing Mobil Oil GTX 4 Liters tin at site. | 20 | P.Tin | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
Part – 3 (Closure Materials, Colouring the Gate / Regulators Oiling and Greasing & etc)
1 | Black Bituman Superior @ site | 85 | P.Liter | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
2 | Oil Paint Superior Quality any colour @ site | 60 | P.Liter | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
3 | Colour (distemper any colour) | 5 | P.Tin | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
4 | Red Oxide @ site in liter | 90 | P.Liter | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
5 | Tarpene Oil (Local) in liter @ site | 130 | P.Liter | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
6 | Scraper @ site | 6 | P.Dozen | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
7 | Wire Bursh @ site | 6 | Dozen | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
8 | Grease Superior @ site | 20 | P.Kg | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
9 | Painting Bursh 2” size @ site | 2 | P.Dozen | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
10 | Painting Bursh 4” size @ site | 2 | P.Dozen | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
11 | Cotton Waste @ site | 10 | P.Dozen | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
12 | Mobil Oil (used) in liter @ site | 120 | P.Liter | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
13 | Engaging Painter for painting any type of work at site. | 30 | P.day | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
14 | Engaging Helper for Painting at site. | 30 | P.day | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
15 | Engaging Helper.(Skilled) for Gate works at site. | 30 | P.day | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
16 | Engg: Mistry for Gate works at site. | 30 | P.day | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
17 | Providing Electric welding Rod & SWG. Chain at site. | 250 | P.Kg | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
18 | Engg: Hire charges of Welding plant at site. | 30 | P.day | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2018
Executive Engineer,
Upper Pinyari Division
Hyderabad

## Plan PFL RD 0 to 110
ANNEXURE - A1
PROCUREMENT PLAN FOR THE YEAR 2016-17 FOR M&R WOKS (NON-DEVELOPMENT)
Sr. No. | Name of works. | Tentative Qty. |  | Cost of ongoing works (Expenditure already incurred) | Funds earmarked for ongoing works | Cost of New works (Components) | Funds for New works (c - e) | Nature of Procurement | Methodof Procurement | Anticipated / Actual date of Advertisment | Anticipated / Actual date of Start | Anticipated / Actual date of Completion
A | B | C |  | D | E | F | G | H | I | J | K | L
2) Procurement of Goods for the Section of P.F.L RD 0 to 110.
PART-1 (SITE MATERIAL)
1 | Empty Gunny Bags L/S 1st Bharty | 2000 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
2 | Empty Gunny Bags S/S 2nd Bharty | 2500 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
3 | Plastic Bags Katta L/S | 10000 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
4 | Sutli | 80 | P.Kg | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
5 | Pees Wan | 80 | P.Kg | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
6 | Munj Wan | 60 | P.Kg | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
7 | Earthen. | 40 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
8 | Needles For Sewing Bags | 24 | P.Dozen | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
9 | Lai Basket M.S | 60 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
10 | Towas Sur Double Size 6’x7’ | 800 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
11 | Pees Mats Size 6’x4’ | 350 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
12 | Pakkah Reed Kani Size 7’x14’ at site | 150 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
13 | Lai Panjers Size 10 to 12 ft Long | 4500 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
14 | Manjhandari Panjers Size 10’ to 12’ Long | 500 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
15 | Glass Plastic @ Site | 10 | P.Dozen | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
16 | Plastic Sheet @ site | 250 | P.Meter | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
17 | Pakkah Pan Double size 8 x 15 @ site | 400 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
18 | Pan Mate Size 4 .5 x 5.5 @ site | 400 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
19 | Pakha Sur Double size 7 x 14 @ site | 500 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
20 | Waras | 200 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
21 | Thunies | 350 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
22 | Babul Munnas | 500 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
23 | Kerosene Oil. | 250 | P.Liter | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
24 | Providing and fixing mile stone 2’.5”x1’x3” painting lettering etc complete RCC. | 50 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
25 | Lime Un-Slacked | 50 | P.Kg | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
26 | Kodars (Spades) with handle @ site | 50 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
27 | Engaging Casual Labour i/c catering & Lodging | 1500 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
28 | Solar Torch M/S | 500 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
29 | Solar Torch L/S | 50 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
30 | Electric Wire 3/029 copper at site. | 20 | P. Coil | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
31 | Bulb Holdar | 24 | P.Dozen | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
32 | Saver Bulb 24 W | 120 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
33 | Solution Tape | 15 | P.Roll | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
34 | Providing Stone Boulder 9” to 12” i/c Carriage | 18000 | % Cft | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
35 | Taint 20x14 with all accessories on hire charges. | 10 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2018
PART-2 (HIRE OF VEHICLES & MACHINEERY)
1 | Engg: Suzuki pickup on hire charges with POL & Driver at site. | 60 | P.Day | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
2 | Engg: Tractor with Hydraulic Trolly with POL for shifting earth within 3 miles. | 1000 | P.Trip | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
3 | Engg: Tractor with Front Blade wheel type on hire charges with POL & Driver at site. | 1200 | P.Hour | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
4 | Engg: Electric Generator on Hire charges with POL at site. | 60 | P.Day | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
5 | Engg: Wheel type Hydraulic Excavator for Earth Work on hire charges with POL & Driver at site. | 3500 | P.Hour | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
6 | Engg: chain type Hydraulic Excavator for Earth Work on hire charges with POL & Driver at site. | 2500 | P.Hour | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
7 | Engg: Bulldozer on hire charges with POL | 60 | P.Day | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
8 | Providing Diesel with carriage at site | 2500 | P.Liter | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
9 | Providing Petrol with carraige at site | 3500 | P.Liter | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2018
10 | Providing Mobil Oil GTX 4 Liters tin at site. | 20 | P.Tin | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
Part – 3 (Closure Materials, Colouring the Gate / Regulators Oiling and Greasing & etc)
1 | Black Bituman Superior @ site | 96 | P.Liter | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
2 | Oil Paint Superior Quality any colour @ site | 80 | P.Liter | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
3 | Colour (distemper any colour) | 5 | P.Tin | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
4 | Red Oxide @ site in liter | 90 | P.Liter | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
5 | Tarpene Oil (Local) in liter @ site | 130 | P.Liter | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
6 | Scraper @ site | 6 | P.Dozen | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
7 | Wire Bursh @ site | 6 | Dozen | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
8 | Grease Superior @ site | 20 | P.Kg | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
9 | Painting Bursh 2” size @ site | 2 | P.Dozen | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
10 | Painting Bursh 4” size @ site | 2 | P.Dozen | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
11 | Cotton Waste @ site | 10 | P.Dozen | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
12 | Mobil Oil (used) in liter @ site | 120 | P.Liter | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
13 | Engaging Painter for painting any type of work at site. | 30 | P.day | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
14 | Engaging Helper for Painting at site. | 30 | P.day | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
15 | Engaging Helper.(Skilled) for Gate works at site. | 30 | P.day | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
16 | Engg: Mistry for Gate works at site. | 30 | P.day | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
17 | Providing Electric welding Rod & SWG. Chain at site. | 450 | P.Kg | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
18 | Engg: Hire charges of Welding plant at site. | 30 | P.day | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
Executive Engineer,
Upper Pinyari Division
Hyderabad

## Plan Old Fuleli RD 04 to 114
ANNEXURE - A1
PROCUREMENT PLAN FOR THE YEAR 2016-17 FOR M&R WOKS (NON-DEVELOPMENT)
Sr. No. | Name of works. | Tentative Qty. |  | Cost of ongoing works (Expenditure already incurred) | Funds earmarked for ongoing works | Cost of New works (Components) | Funds for New works (c - e) | Nature of Procurement | Methodof Procurement | Anticipated / Actual date of Advertisment | Anticipated / Actual date of Start | Anticipated / Actual date of Completion
A | B | C |  | D | E | F | G | H | I | J | K | L
1) Procurement of Materials & Goods for the Section of Old Fuleli Canal RD 04 to 114.
PART-1 (SITE MATERIAL)
1 | Empty Gunny Bags L/S 1st Bharty | 2000 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
2 | Empty Gunny Bags S/S 2nd Bharty | 2500 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
3 | Plastic Bags Katta L/S | 10000 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
4 | Sutli | 80 | P.Kg | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
5 | Pees Wan | 80 | P.Kg | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
6 | Munj Wan | 60 | P.Kg | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
7 | Earthen. | 40 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
8 | Needles For Sewing Bags | 24 | P.Dozen | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
9 | Lai Basket M.S | 60 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
10 | Towas Sur Double Size 6’x7’ | 800 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
11 | Pees Mats Size 6’x4’ | 350 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
12 | Pakkah Reed Kani Size 7’x14’ at site | 150 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
13 | Lai Panjers Size 10 to 12 ft Long | 4500 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
14 | Manjhandari Panjers Size 10’ to 12’ Long | 500 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
15 | Glass Plastic @ Site | 10 | P.Dozen | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
16 | Plastic Sheet @ site | 250 | P.Meter | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
17 | Pakkah Pan Double size 8 x 15 @ site | 400 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
18 | Pan Mate Size 4 .5 x 5.5 @ site | 400 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
19 | Pakha Sur Double size 7 x 14 @ site | 500 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
20 | Waras | 200 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
21 | Thunies | 350 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
22 | Babul Munnas | 500 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
23 | Kerosene Oil. | 250 | P.Liter | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
24 | Providing and fixing mile stone 2’.5”x1’x3” painting lettering etc complete RCC. | 50 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
25 | Lime Un-Slacked | 50 | P.Kg | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
26 | Kodars (Spades) with handle @ site | 50 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
27 | Engaging Casual Labour i/c catering & Lodging | 1500 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
28 | Solar Torch M/S | 500 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
29 | Solar Torch L/S | 50 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
30 | Electric Wire 3/029 copper at site. | 20 | P. Coil | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
31 | Bulb Holdar | 24 | P.Dozen | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
32 | Saver Bulb 24 W | 120 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
33 | Solution Tape | 15 | P.Roll | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
34 | Providing Stone Boulder 9” to 12” i/c Carriage | 18000 | % Cft | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
35 | Taint 20x14 with all accessories on hire charges. | 10 | Each | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
PART-2 (HIRE OF VEHICLES & MACHINEERY)
1 | Engg: Suzuki pickup on hire charges with POL & Driver at site. | 60 | P.Day | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
2 | Engg: Tractor with Hydraulic Trolly with POL for shifting earth within 3 miles. | 1000 | P.Trip | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
3 | Engg: Tractor with Front Blade wheel type on hire charges with POL & Driver at site. | 1200 | P.Hour | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
4 | Engg: Electric Generator on Hire charges with POL at site. | 60 | P.Day | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
5 | Engg: Wheel type Hydraulic Excavator for Earth Work on hire charges with POL & Driver at site. | 3500 | P.Hour | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
6 | Engg: chain type Hydraulic Excavator for Earth Work on hire charges with POL & Driver at site. | 2500 | P.Hour | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
7 | Engg: Bulldozer on hire charges with POL | 60 | P.Day | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
8 | Providing Diesel with carriage at site | 2500 | P.Liter | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
9 | Providing Petrol with carraige at site | 3500 | P.Liter | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
10 | Providing Mobil Oil GTX 4 Liters tin at site. | 20 | P.Tin | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2018
Part – 3 (Closure Materials, Colouring the Gate / Regulators Oiling and Greasing & etc)
1 | Black Bituman Superior @ site | 96 | P.Liter | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
2 | Oil Paint Superior Quality any colour @ site | 80 | P.Liter | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
3 | Colour (distemper any colour) | 5 | P.Tin | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
4 | Red Oxide @ site in liter | 90 | P.Liter | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
5 | Tarpene Oil (Local) in liter @ site | 130 | P.Liter | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
6 | Scraper @ site | 6 | P.Dozen | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
7 | Wire Bursh @ site | 6 | Dozen | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
8 | Grease Superior @ site | 20 | P.Kg | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
9 | Painting Bursh 2” size @ site | 2 | P.Dozen | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
10 | Painting Bursh 4” size @ site | 2 | P.Dozen | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
11 | Cotton Waste @ site | 10 | P.Dozen | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
12 | Mobil Oil (used) in liter @ site | 120 | P.Liter | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
13 | Engaging Painter for painting any type of work at site. | 30 | P.day | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
14 | Engaging Helper for Painting at site. | 30 | P.day | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
15 | Engaging Helper.(Skilled) for Gate works at site. | 30 | P.day | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
16 | Engg: Mistry for Gate works at site. | 30 | P.day | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
17 | Providing Electric welding Rod & SWG. Chain at site. | 450 | P.Kg | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2017
18 | Engg: Hire charges of Welding plant at site. | 30 | P.day | -- | -- | -- | -- | Single Stage | Single Stage | 24-12-2016 | 16/1/2017 | 30-06-2018
Executive Engineer,
Upper Pinyari Division
Hyderabad