## 20 Works
ANNUAL PROCUREMENT PLAN 2016-2017 EXECUTIVE ENGINEER, HIGHWAYS DIVISION, DADU
SR: NO: | DESCRIPTION OF PROCUREMENT | QUANTITY (Where applicable) | ESTIMATED UNIT COST (Where applicable in Million) | FUNDS ALLOCATED IN MILLION | SOURCE OF FUNDS (ADP & NON-ADP) | PROPOSED PROCURMENT METHOD | TIIMING OF PROCUREMENT |  |  |  | REMARKS
[7 empty] | 1st: Qtr: | 2nd: Qtr: | 3rd: Qtr: | 4th: Qtr:
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
1 | Construction of road from Johi Wahi Pandhi road to Buxo Khan Rustmani Mile 0/0-0/2. |  | 3 | 0.75 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
2 | Construction of road from Chowdagi Phulji Village to Mehrani Jamali Mile 0/0-0/1. |  | 1.5 | 0.375 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
3 | Construction of road from Indus High Way to Mullo Mohammad Jamali Mehrani Mile 0/0-0/1. |  | 1.5 | 0.375 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
4 | Construction of road for Saindad Panhwar mile 0/0-0/1+330'. |  | 3.5 | 0.875 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
5 | Construction of road from Dadu Johi road to village Mubarak Gopang Mile 0/0-0/1+540'. |  | 3.4 | 0.85 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
6 | Construction of road from Paryo Jamali road to Wahid Bux Jamali Mile 0/0-0/1. |  | 2.4 | 0.6 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
7 | Construction of road for Village Shaman khoso Mile 0/0-0/1+220' |  | 2.15 | 0.5375 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
8 | Construction of road from Johi City Haji Khan road to village Sono Khan Khoso Mile 0/0-0/1+110'. |  | 1.9 | 0.475 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
9 | Construction of road from Phulji Chowdagi road to village Hayat khan Jamali Mile 0/0-0/1. |  | 1.5 | 0.375 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
10 | Construction of road from Pir Gunio Hussain Solangi road to Aarab Shaikh Mile 0/0-0/3. |  | 4.1 | 1.025 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
11 | Constt: of C.C Block & Drain at village Khair Muhammad Jamali. |  | 1.45 | 0.3625 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
12 | Construction of road from Khudaabad Shakh to Fareedani Lund Mile 0/0-0/2+330' |  | 3.5 | 0.875 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
13 | Constt: of Culverts & Bridges at various locations of Taluka Johi |  | 2.35 | 0.5875 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
14 | Construction of road from Pir Gunio village Shaman Shaikh Mile 0/0-0/1 |  | 1.5 | 0.375 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
15 | Construction of road from Daro road Eid Gah to Arbab Solangi Mile 0/0-0/2 |  | 3.3 | 0.825 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
16 | Construction of road from Daim Shakh to Pandhi Khan Jamali U/C Chhini 0/0-0/2. |  | 3 | 0.75 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
17 | Construction of road from Jamal Din Janwari road to Hamzo Khan Kolach village mile 0/0-0/6. |  | 10 | 2.5 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
18 | Construction of road from K.N.Shah Burira road to Dil Murad Mangnihar village mile 0/0-0/2. |  | 3.3 | 0.825 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
19 | Construction of road from Burira Sattani Chandio road to Sohrab Gachal village mile 0/0-0/3. |  | 6.6 | 1.65 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
20 | Repair 3' span culvert at village Hurry Taluka K.N.Shah |  | 0.1 | 0.025 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
21 | Construction of Paving Block & Drain at village Hudhio Khoso village Karam Khan Khoso & Haji Ramzan Khan Khoso village Jahan Khan Sodhar village Sainani Lakhair U/C Thalho |  | 10 | 2.5 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
22 | Construction of 5' span culvert at Qomi Charo village Taluka K.N.Shah. |  | 0.235 | 0.05875 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
23 | Construction of 2' Span 10 Rft each Bridge over Kakol Wah at Saeedi Musani stop Sufeed Masjid Mehar. |  | 1.3 | 0.325 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
24 | Construction of 2' span 10 Rft each Bridge over Kudan Minor at Shah Goreo Dargah u/c Thalho. |  | 1.3 | 0.325 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
25 | Construction of 10' Rft each Bridge over Kudan Minor at villag Dosta Muhammad Bhurgari |  | 0.95 | 0.2375 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
26 | Construction of 2' Span 10 Rft each Bridge over Nara Canal at U/C Kandi Chukhi 3 Nos. |  | 3.7 | 0.925 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
27 | Construction of 10' Rft each Bridge over Vicholo Shakh at village Karakm Khan Khoso Mehar |  | 0.93 | 0.2325 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
28 | Construction of 2' span 10 Rft each Bridge over Nara Canal at village Fatulani Gadehi |  | 1.6 | 0.4 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
29 | Constt: of road for Mullo Hassan Panhwar Mile 0/2+330'-0/4. |  | 2 | 0.5 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
30 | Construction of road from Dadu Johi road to Meeram Khan Abro Mile 0/0-0/2. |  | 3 | 0.75 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
31 | Construction of road from Muhammad Hassan Panhwar Ji Landhi to Ghulam Hussain Panhwar Mile 0/2-0/4. |  | 3 | 0.75 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
32 | Construction of road from Changlani road to Ahmed Khan Jatoi, Bakhat Ali Jo Makkan Mile 0/4-0/6. |  | 3 | 0.75 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
33 | Construction of road from Noorja road to Mothrai Mile 0/0-0/2. |  | 3 | 0.75 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
34 | Construction of road from Noorja road to Dargah Sanghar Pir U/C Siyal Mile 0/0-0/2. |  | 3 | 0.75 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
35 | Construction of road from Muhammad Achar Ji Otaq to Middle School Adam Panhwar Mile 0/0-0/1. |  | 1.5 | 0.375 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
36 | Construction of CC Block, Paving Block & Drain at Village Adam Panhwar (Makhan Muhalla & Hafiz Ghulam Qadir Bhand Street). |  | 1.5 | 0.375 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
37 | Construction of Paving Block & Drain from Fateh Khan Zounr Mori to Haji Abdullah Zounr Bhalaro. |  | 1.5 | 0.375 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
38 | Construction of Paving Block & Drain at Village Meenhon Khan Bhand Muhalla Adam Khan Bhand. |  | 1.5 | 0.375 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
39 | Constt: of Paving Block & Drain at Village Kareemdad Lund. |  | 2.5 | 0.625 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
40 | Construction of CC Block & Drain at Village Gul Muhammad Shah Nasrani. |  | 2 | 0.5 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
41 | Construction of Paving Block & Drain at Village Haji Paryal Birahmani (Ali Hyder Birmani Street, Imam Bux Birmani Street, Tagio Birmani Street & Niaz Birmani Street). |  | 1.5 | 0.375 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
42 | Construction of Paving Block & Drain at Village Murad Ali Khushik, Haji Allah Bux House to Qasim Khushik Bahadur Khan House to Taj Muhammad Street & Mukhtiar to Haji Gulsher Khushik. |  | 2 | 0.5 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
43 | Constt: of Paving Block & Drain at Manzoor Kalhoro, Moula Bux, Ali Murad Kalhoro in Village Hafiz Mir Muhammad Kalhoro. |  | 2 | 0.5 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
44 | Construction of CC Block & Drain at Village Meer Hassan Lund (Photo Khan Lund Street & Muhammad Nawaz Street). |  | 1.5 | 0.375 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
45 | Improvement of Road from Jeewan Miyani via Mamtaz Kabooro to village Wadhio Panhwar mile 0/0-0/2. |  | 3 | 0.75 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
46 | Construction of Paving Block & Drain at Village Sardar Dur Muhammad Bozdar Muhalla Near Bus Stand. |  | 0.5 | 0.125 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
47 | Construction of Paving Block & Drain at Village Balach Khan Bozdar & Muhammad Khan Bozdar (Taluka Johi). |  | 1.5 | 0.375 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
48 | Reconditioning of road from Chhinni road to Village Chakar Khan Shahani mile 0/0-0/5 (Taluka Johi). |  | 2.5 | 0.625 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
49 | Construction of Paving Block & Drain at Village Tando Raheem Khan (Taluka Johi). |  | 2 | 0.5 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
50 | Construction of Paving Block & Drain at Village Halry Jungwani Muhalla (Taluka Johi). |  | 2 | 0.5 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
51 | Construction of Road from Chhinni Sawro road to Sijawal Khan Alkhani 0/0-0/1+265' (Taluka Johi). |  | 2 | 0.5 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
52 | Construction of road from Moundar to Village Yakhtiar Shahani U/C Moundar Mile 0/0-0/3+330. |  | 5 | 1.25 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
53 | Improvement of road from Patt to Old Kalri road Mile 0/3-0/7. |  | 5 | 1.25 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
54 | Construction of CC Block & Drain at Village Jumo Abro & Allah Dino Abro. |  | 1 | 0.25 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
55 | Constt: of CC Block & Drain at Village Loung Chahwan U/C Pipri. |  | 1 | 0.25 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
56 | Construction of CC Block & Drain from Muhammad Saleh Khokhar House to Haji Ishaque Mallah, Saleem Qureshi & Hussain Mallah via Thatiar Masjid Dadu. |  | 1.5 | 0.375 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
57 | Construction of CC Block & Drain from Manzoor Khoso House to Akash Panhwar House Marvi Colony Dadu. |  | 1 | 0.25 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
58 | Construction of CC Block & Drain from Dargah Mohsin Shah to Jumo Lund House, Jevan Khan Lund House, Ashrif Lund House, Ali Hassan Abro, Mian Bux Lund House via Nihal Shaikh Street Chhano Shahabad. |  | 1 | 0.25 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
59 | Construction of CC Block i/c Drain & Paving Block U/C-I,II,III,IV at Mubeen Mastoi Street, Zulfiqar Birmhmani Street, Ali Nawaz Mallah, Ali Bux Gurmani, Muhammad Siddique Babar near Bhittai Hotel street approach road 3' Span Culvert in Village Ali Bux Mastoi U/C Siyal & Counciller Ali Hassan Solangi Street Dadu City. |  | 4.5 | 1.125 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
60 | Construction of CC Block & Drain at Ward No: 07 House of Ghulam Hussain Babar, Niaz Sehto and Murtaza Soomro street. |  | 2 | 0.5 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
61 | Construction of CC Block, Paving Block & Drain at Village Meenhon Khan Bhand in Muhalla Shahzad Bhand. |  | 2 | 0.5 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
62 | Construction of road from Mehrab Qambrani to Mirawal Qambrani Mile 0/0-0/2. |  | 3 | 0.75 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
63 | Construction of road from Phulji Chowdagi road to village Adam Panhwar Mile 0/0-0/2. |  | 3 | 0.75 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
64 | Construction of road from 9 Shakh to Sher Mohammad Babar Mile 0/0-0/3. |  | 4.5 | 1.125 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
65 | Construction of C.C Block & Drain @ village Jakhro. |  | 2 | 0.5 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
66 | Redecking / repair of 20' ft Bridge 2 Spans (10' ft Each) at village Kumb. |  | 2 | 0.5 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
67 | Construction of C.C Block & Drain @ Village Khat Lashkar Hingora Muhalla. |  | 1.5 | 0.375 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
68 | Construction of C.C Block & Drain @ Village Saleh Punar. |  | 1 | 0.25 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
69 | Construction of C.C Block & Drain @ Village Ramzan Solangi. |  | 1 | 0.25 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
70 | Construction of C.C Block & Drain @ Village Bachal Rind |  | 2 | 0.5 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
71 | Construction of C.C Block & Drain @ Village Qurban Panhwar Muhalla village Ismail Achra. |  | 1.5 | 0.375 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
72 | Construction of C.C Block @ Village Tajo Panhwar. |  | 1 | 0.25 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
73 | Construction of C.C Block Sayed Hajan Shah Muhalla @ Village Sher Mohammad Solangi. |  | 1.5 | 0.375 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
74 | Construction of road from Sanwal Arwal road to Dara Mari village mile 0/0-0/3. |  | 5 | 1.25 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
75 | Construction of road from K.N.Shah Sindhi Butra road to Jeo Halo, Fazul Muhamamd Bhurgari village, Jurio Halo village mile 0/0-1/0. |  | 15 | 3.75 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
76 | Construction of road from Khanpur Belo Pathan road to Shakh wara Mallah mile 0/0-0/2+330. |  | 4.5 | 1.125 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
77 | Const: of Paving Block at village Gulan Lander Taluka K.N.Shah |  | 5.5 | 1.375 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
78 | Improvement of road from Shah Panjo to Daud Dero village mile 0/0-2/0. |  | 20 | 5 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
79 | Construction of road from Khundi to Ghulam Ali Teewano village mile 0/0-0/2. |  | 4 | 1 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
80 | Improvement of road from Suleman Babar Shoping Center to Al-Azam Builders i/c Service road, Divider, Foot Path & Drain. |  | 19 | 4.75 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
81 | Improvement of road from Al-Rameez State Agency to Bhurghari Plaza i/c Service road, Divider, Foot Path & Drain. |  | 19.5 | 4.875 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
82 | Improvement of road from Mahesar House to Talib Jamali Center i/c Service road, Divider, Foot Path & Drain. |  | 19.5 | 4.875 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
83 | Improvement of road from Hayat Khan Solangi to Excise Office i/c Service road, Divider, Foot Path & Drain. |  | 19.8 | 4.95 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
84 | Improvement of road from Excise Office to Dr. Nazeer Jamali Clinic i/c Service road, Divider, Foot Path & Drain. |  | 19.5 | 4.875 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
85 | Improvement of road from Dr. Nazeer Jamali Clinic to New Bus Stop i/c Service road, Divider, Foot Path & Drain. |  | 19.9 | 4.975 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
86 | Improvement / Extension of road from Wapda Scarp Colony to Jatoi Hotel i/c Paving Block, Divider, Foot Path & Drain. |  | 20 | 5 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
87 | Improvement of road from Girls High School to Post Office i/c Paving Block, Divider, Foot Path & Drain. |  | 19.9 | 4.975 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
88 | Improvement of road from Mounder Naka towards Old District Jail Dadu i/c Paving Block, Divider, Foot Path & Drain. |  | 10 | 2.5 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
89 | Improvement of Dadu Moro road from Jamali PSO Petroluim to Kandi Hotel i/c Foot Path & Drain. |  | 8 | 2 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
90 | Improvement / Extension of road from Agriculture WorkShop road to Shaheed Zulfiqar Gate. |  | 15 | 3.75 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
91 | Improvement of road from Noorani Chowk upto Old Siyal Naka. |  | 19.9 | 4.975 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
92 | Improvement of road from Dadu Moro road to Mehar Chandio house. |  | 9.5 | 2.375 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
93 | Construction of road from Dadu Moro road Mori to Siyal Mori at Non Inspection Path of Dadu Canal Mile 0/0-0/2+440'. |  | 6 | 1.5 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
94 | Improvement of road from Hepatitis Center to Gulf Hotel i/c link to Ghulam Qadir Solangi Senatory Shop. |  | 16 | 4 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
95 | Improvement of road from Emergency Block to Station road via Nadra office. |  | 14 | 3.5 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
96 | W/R of road from Indus Highway to Dargah Shaheed Makhdoom Bilawal i/c Drain, Solar Lights and Monument Main Chowk of Dargah with Paving Block Mile 0/0-0/3. |  | 15 | 3.75 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
97 | Construction of Paving Block from CIA Center to Rahooja House i/c with Plantation. |  | 9 | 2.25 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
98 | Construction of Paving Block & Drain at Azizabad Colony i/c Aftab Soomro House. |  | 5 | 1.25 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
99 | Construction of Paving / Drain from Waseem Hotel to Ghulam Nabi Lund. |  | 1 | 0.25 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
100 | Construction of CC Block & Drain in Ghulam Hyder Jamali Colony Near Daro road Near Masjid. |  | 2.7 | 0.675 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
101 | Widenning & Reconditioning of Sonmiani road from DHO Office to Bhittai Hotel Mile 0/0-0/1+330' |  | 5.5 | 1.375 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
102 | Constructio of (2 Nos) Bridges 30' Rft & 40 Rft over Nai Gaj near Rajo Gandho (i/c Approaches) |  | 11.8 | 2.95 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
103 | Improvement of road from Bye pass Gahi Mahessar chowk to old I.H.Way i/c Drain mile 0/0-0/4. (Taluka Mehar) |  | 7.5 | 1.875 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
104 | Construction of CC Block & Drain at Sita Road Janwari Muhalla K.N.Shah. |  | 4 | 1 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
105 | Construction of CC Block & Drain at Ward.8 Taluka KN Shah. |  | 4 | 1 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
106 | Construction of Road from Gozo Bund to Imam Bargah 0/0-0/2 Taluka KN Shah. |  | 2.8 | 0.7 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
107 | Construction of 20' Rft Bridge over Mashar shakh near Dr. Khudabad Chandio village. Taluka Mehar) |  | 2.2 | 0.55 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
108 | Constt: of 6' Span Culvert at Budho Gopang Over Jagir Shakh. |  | 0.6 | 0.15 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
109 | Const: of road at village Mado to village Allah Bachayo Jesar remote area katcho UC Mado Taluka K.N.Shah District Dadu mile 0/0-1/2 |  | 20 | 5 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
110 | Rehabilitation of Road from Kazi Arif Village to Loung Mahessar village i/c Drain mile 0/0-1/4 Taluka Mehar. |  | 10.7 | 2.675 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
111 | Improvement of Road from Fazul Agro to Gharo Village mile 0/0-1/6 (in portions) Taluka Mehar. |  | 3 | 0.75 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
112 | Construction of Road from K.N.Shah Sindhi Buttara Road to Nazar Muhammad chandio via Kalrai Chandio Sevo Chandio approch Nazar Muhammad Chandio village Taluka K.N.Shah mile 0/0-0/1 |  | 1.8 | 0.45 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
113 | Construction of Road from Talib Palio Poto Road to Jhando Arwal village mile 0/0-0/2+180 Taluka K.N.Shah, |  | 6.2 | 1.55 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
114 | Construction Causeway along Gul Mohammad Jamali to Murad Jamali Road Taluka Johi. |  | 4 | 1 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
115 | Construction of Road from Hussain Solangi to Manjhi Qambrani Taluka Johi. |  | 5 | 1.25 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
116 | Constt: Retaining Wall on MNV Drain at Kheer Mori Taluka Johi. |  | 2.5 | 0.625 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
117 | Constt: of road from Phulji to Ghulam Shabir Abro Mile 0/0-0/3. |  | 4 | 1 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
118 | Construction of Paving Block and Drain Nala from Circuit House to Workshop via Muhamad Mallah Pir Bux Colony. |  | 2.1 | 0.525 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
119 | Construction of Paving Block and Drain Papo Thaheem to Asghar Bhand Street. |  | 2 | 0.5 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
120 | Re-construction of road from Cattle Farm road to Mad Shareef via Abdul Raheem Jo Khooh |  | 2 | 0.5 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
121 | Const: of Paving Block & Drain at village Ameenani Taluka Dadu |  | 2.5 | 0.625 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
122 | Improvement of road from Bahawalpur to Wadhio Panhwar mile 0/4-0/5. |  | 1.5 | 0.375 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
123 | Construction of Paving Block from Wazir Hussain Solangi House to Pir Bux Solangi House Latifabad-C Colony Dadu City. |  | 1 | 0.25 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
124 | Const: of road from Shahjahan Park to Hockey Stadium Ground. |  | 2 | 0.5 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
125 | Construction of Compound Wall / Waranda of Government Primary School Muhammad Panhwar |  | 1.5 | 0.375 | ADP Programme 2016-17 | Single Stage One Envelope Procurement
EXECUTIVE ENGINEER HIGHWAYS DIVISION DADU