## Schemes (edit) (2)
ANNUAL PROCUREMENT PLAN FINANCIAL YEAR 2016-17
EXECUTIVE ENGINEER BUILDINGS DIVISION TANDO ALLAHYAR
Sr. No. | Description of Procurement | Quantity (where applicable) | Estimated Unit cost (where applicable million) | Funds allocated in million | Souree of funds (ADPs / Non-ADPs) | Proposed Procurement Method | Timing of Procurements |  |  |  | Remarks
[7 empty] | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Renovation of RHC Nasarpur District Tando Allahyar (Remaining Work) | Builidng Work | 4.98 | 4.98 | ADP | Single stage one Envolep Procurement | Yes | Yes | Yes | Yes
2 | Up-Gradation of R.H.C Hospital Chamber to the level of T.H.Q Hospital Chamber District Tando Allahyar.
| i) (Compound Wall & C.C Road) | Builidng Work | 4.937 | 4.937 | ADP | Single stage one Envolep Procurement | Yes | Yes | Yes | Yes
| ii) (Waiting Room & Lav. Block) | Builidng Work | 2.149 | 2.149 | ADP | Single stage one Envolep Procurement | Yes | Yes | Yes | Yes
3 | Up Gradation of B.H.U to T.H.Q Hospital Jhando Mari @ Piaro Lund District Tando Allahyar
| i) (Waiting Room & Lav. Block) | Builidng Work | 3.493 | 3.493 | ADP | Single stage one Envolep Procurement | Yes | Yes | Yes | Yes
| ii) (Compound Wall) | Builidng Work | 2.609 | 2.609 | ADP | Single stage one Envolep Procurement | Yes | Yes | Yes | Yes
| iii) (int. W/S , S/F) | Builidng Work | 1.532 | 1.532 | ADP | Single stage one Envolep Procurement | Yes | Yes | Yes | Yes
4 | Renovation / Rehabilitation of Jamia Masjid Ali Ibne Hassan Tando Allahyar (Remaining work) | Builidng Work | 3.127 | 3.127 | ADP | Single stage one Envolep Procurement | Yes | Yes | Yes | Yes
5 | Establishment of 50 beded Children Unit at Civil Hospital Tando Allahyar (int. W/S , S/F & Ext. Drainage) | Builidng Work | 1.911 | 1.911 | ADP | Single stage one Envolep Procurement | Yes | Yes | Yes | Yes
6 | Social Welfare Constt. of Rehabilitation Center for Multiple Handicapped Children at Tando Allahyar (Remaining work F. Floor) | Builidng Work | 1.143 | 1.143 | ADP | Single stage one Envolep Procurement | Yes | Yes | Yes | Yes
7 | Construction of C.C Block in village Haji Jaffer Senhro UC Began Jarwar (Remaining Work) | Builidng Work | 0.964 | 0.964 | ADP | Single stage one Envolep Procurement | Yes | Yes | Yes | Yes
8 | Construction of CC Block from Sajjad Khaim khani House to Ramzan Abbasi House UC-III Tando Allahyar (Remaining Work) | Builidng Work | 0.399 | 0.399 | ADP | Single stage one Envolep Procurement | Yes | Yes | Yes | Yes
Total |  |  | 27.244 | 27.244