## Est
ESTIMATE
Name of Work: |  | RENOVATION OF RHC NASARPUR DISTRICT TANDO ALLAHYAR (REMAINING WORK)
S. No. | Description | [10 empty] | QTY | Rate | Unit | AMOUNT
1 | Dismantling Cement concrete Plain 1:2:4 (S.I.No. 19 (c ) P-10)
| W Roof |  |  | 1 | x | 91 | x | 21.25 | x | 0.17 | = | 329
|  |  |  | 1 | x | 91 | x | 8.63 | x | 0.17 | = | 134
| Ward |  |  | 3 | x | 18 | x | 16 | x | 0.17 | = | 147
|  |  |  | 1 | x | 10 | x | 16 | x | 0.17 | = | 27
|  |  |  | 2 | x | 8 | x | 16 | x | 0.17 | = | 44
|  |  |  | 1 | x | 85.75 | x | 6 | x | 0.17 | = | 87
[12 empty] | 768 | 3327.5 | %Cft | 25555
2 | Dismantling Cement concrete reinforced separating reinfor cement from concrete cleaning and straightening the same (S.I.No. 20 P-10)
| B/S |  |  | 1 | x | 91 | x | 21.25 | x | 0.5 | = | 967
| ________Ver |  |  | 1 | x | 91 | x | 9.75 | x | 0.5 | = | 444
| Wall Top Beam |  |  | 3 | x | 88 | x | 1.13 | x | 1.5 | = | 447
| ___ |  |  | 2 | x | 23.13 | x | 1.13 | x | 1.5 | = | 78
| ___ |  |  | 5 | x | 16 | x | 1.13 | x | 1.5 | = | 136
| O.H Beam |  |  | 2 | x | 12 | x | 1 | x | 1 | = | 24
| _____ |  |  | 2 | x | 5 | x | 1 | x | 1 | = | 10
| Wall |  |  | 2 | x | 12 | x | 0.75 | x | 4 | = | 72
| ___ |  |  | 2 | x | 5 | x | 0.75 | x | 4 | = | 30
| Slab |  |  | 2 | x | 12 | x | 6.5 | x | 0.5 | = | 78
[12 empty] | 2286 | 5445 | %Cft | 124473
3 | Dismantling Pack brick work in lime or cement mortar (S.I.No. 13 P-10)
| R Wall |  |  | 2 | x | 88 | x | 1.13 | x | 1.75 | = | 348
| _____O/o |  |  | 1 | x | 88 | x | 1.13 | x | 4 | = | 398
| ______i/i |  |  | 7 | x | 16 | x | 1.13 | x | 1.75 | = | 221
| Ver i/i |  |  | 2 | x | 6 | x | 1.13 | x | 1.75 | = | 24
[12 empty] | 991 | 1285.63 | %Cft | 12741
4 | Scraping ordinary distemper iol bound distemper or paint on walls (S.I.No. 54 (b) P-13)
| P-A Wall | 3 | x | 2 | ( | 18 | + | 16 | ) |  | = | 204
| Lav | 2 | x | 2 | ( | 16 | + | 18 | ) |  | = | 136
| D Room | 1 | x | 2 | ( | 10 | + | 16 | ) |  | = | 52
| Store | 1 | x | 2 | ( | 14 | + | 10 | ) |  | = | 48
| Disp | 1 | x | 2 | ( | 14 | + | 16 | ) |  | = | 60
| Store | 1 | x | 2 | ( | 10 | + | 15 | ) |  | = | 50
| H.V/MO | 3 | x | 2 | ( | 12 | + | 15 | ) |  | = | 162
|  | 2 | x | 2 | ( | 10 | + | 10.57 | ) |  | = | 82
| AH Lav | 2 | x | 2 | ( | 9.92 | + | 3.92 | ) |  | = | 55
| Enter Hall | 1 | x | 2 | ( | 12 | + | 15 | ) |  | = | 54
| O/S |  |  | 1 | x | 417.25 |  |  |  |  | = | 417
1320
|  | 1320 |  |  | x | 9.5 |  |  |  |  | = | 12540
| P-B Ver | 1 | x | 2 | ( | 85.75 | + | 6 | ) |  | = | 184
|  | 1 | x | 2 | ( | 109 | + | 6 | ) |  | = | 230
|  | 1 | x | 2 | ( | 27 | + | 6 | ) |  | = | 66
480
|  | 480 |  |  | x | 7.5 |  |  |  |  | = | 3600
| Total A+B | 12540 |  |  | + | 3600 |  |  |  |  | = | 16140
Ded
| Door |  |  | 1 | x | 5 | x | 7 |  |  | = | 35
|  |  |  | 3 | x | 4.5 | x | 7 |  |  | = | 95
|  |  |  | 7 | x | 3.5 | x | 7 |  |  | = | 172
|  |  |  | 3 | x | 3 | x | 7 |  |  | = | 63
|  |  |  | 2 | x | 2.5 | x | 7 |  |  | = | 35
| W |  |  | 9 | x | 4.5 | x | 4 |  |  | = | 162
|  |  |  | 15 | x | 3 | x | 4 |  |  | = | 180
| H.W |  |  | 6 | x | 2.5 | x | 1.5 |  |  | = | 23
| Opp |  |  | 1 | x | 12 | x | 12 |  |  | = | 144
| __ |  |  | 2 | x | 6 | x | 9.5 |  |  | = | 114
| __ |  |  | 1 | x | 4.5 | x | 7 |  |  | = | 32
1055
| Net Qty | 16140 |  |  | - | 1055 |  |  |  |  | = | 15085 | 226.88 | %Sft | 34225
5 | Pacca bricks work in Gorund floor in cement sand mortar 1:6 (S.I.No. 5- I (e) P-20)
| Qty Same as Item No. 03 | [10 empty] | 991
[12 empty] | 991 | 12674.36 | %Cft | 125603
6 | RCC work I/c all labor and material except the cost of steel reinforcement and its labor for bending and binding which will be paid separately this rate also include all kinds of forms moulds lifting shuttering curing rendering and finishing the exposed surface (i/c screening and washing of shingle R.C work in roof slab, beams columns rafts, lintels and other structural members laid in situ or precast laid in position complete in all respects ratio 1:2:4 ) 90 lbs. cement 2cft Sand 4 cft shingle 1/8" to 1/4" gauge. (S.I.No.6 (a) (i) P-16)
| B/S |  |  | 1 | x | 91 | x | 21.25 | x | 0.5 | = | 967
| ________Ver |  |  | 1 | x | 91 | x | 9.75 | x | 0.5 | = | 444
| Wall Top Beam |  |  | 3 | x | 88 | x | 1.13 | x | 1.5 | = | 447
| ___ |  |  | 2 | x | 23.13 | x | 1.13 | x | 1.5 | = | 78
| ___ |  |  | 5 | x | 16 | x | 1.13 | x | 1.5 | = | 136
| O.H Beam |  |  | 2 | x | 12 | x | 1 | x | 1.5 | = | 36
| _____ |  |  | 2 | x | 10 | x | 1 | x | 1.5 | = | 30
| Wall |  |  | 2 | x | 12 | x | 0.75 | x | 4 | = | 72
| ___ |  |  | 2 | x | 10 | x | 0.75 | x | 4 | = | 60
| Slab |  |  | 1 | x | 12 | x | 11.5 | x | 0.5 | = | 69
| Top |  |  | 1 | x | 12 | x | 11.5 | x | 0.33 | = | 46
[12 empty] | 2385 | 337 | P-Cft | 803745
7 | Fabrication of mild steel reinforcement for cement concrete I/c cutting bending laying in position making joints and fastenings I/c cost of binding wire (also includes removal of rust from bars) using Tor bars (S.I. No: 8 (a) (b)/P-16/17)
| Qty same as item No 06 |  |  |  | 2385 |  | x | 6 | / | 112 |  | 127.7679 | 5001.7 | P-Cwt | 639056
8 | Cement plaster 1:6 upto 12' height 1/2" thick (S.I. No.13(b)/p-52).
| Wall |  |  | 2 | x | 2 | x | 87.5 | x | 4 | = | 1400
| __ |  |  | 1 | x | 2 | x | 88 | x | 5 | = | 880
| _____ |  |  | 7 | x | 2 | x | 16 | x | 4 | = | 896
| __ |  |  | 2 | x | 2 | x | 6 | x | 4 | = | 96
| Plinth |  |  | 1 | x | 417 | x | 3.5 |  |  | = | 1460
| O.H | 1 | x | 2 | ( | 10.5 | + | 10 | ) | 4 | = | 164
| __ | 1 | x | 2 | ( | 12 | + | 11.5 | ) | 6 | = | 282
[12 empty] | 5178 | 2206.6 | %Sft | 114258
9 | Cement plaster 1:4 upto 12' height 3/8" thick (S.I. No. 11/a/p-51).
| Qty same as item No 08 | [10 empty] | 5178
[12 empty] | 5178 | 2197.52 | %Sft | 113788
10 | P/L 1-1/2" thick topping i/c surface finishing & dividing into panels C.C 1:2:4 (S.I. No. 16/p-46).
| Over roof |  |  | 1 | x | 91 | x | 21.25 |  |  | = | 1934
|  |  |  | 1 | x | 91 | x | 8.63 |  |  | = | 785
|  |  |  | 1 | x | 10 | x | 10.5 |  |  | = | 105
|  |  |  | 1 | x | 12 | x | 11.5 |  |  | = | 138
[12 empty] | 2962 | 2548.29 | %Sft | 75480.3498
11 | Two coat of bitumen laid hot using 34 Ibs for % Sft over roof and blinded with sand at 1 Cft per % Sft. (S. I. No. 13 , P-35)
| Qty same as item No 10 | [10 empty] | 2962
[12 empty] | 2962 | 1887.4 | %Sft | 55905
12 | Cement concrete plain i/c placing compacting finishing and curring complete (i/c Screening and Washing at stone aggregate without shuttering 1:2:4 (S.I.No-5 f/P-16)
| P-A Ward |  |  | 3 | x | 18 | x | 16 |  |  | = | 864
| D Room |  |  | 1 | x | 10 | x | 16 |  |  | = | 160
| Lav |  |  | 2 | x | 8 | x | 16 |  |  | = | 256
| Ver |  |  | 1 | x | 85.75 | x | 6 |  |  | = | 515
1795
|  | 1795 |  |  | x | 0.13 |  |  |  |  | = | 233.35
| P-B |  |  | 1 | x | 27 | x | 45 | x | 0.25 | = | 304
|  |  |  | 1 | x | 80 | x | 20 | x | 0.25 | = | 400
704
| Total A+B | 233.35 |  |  | + | 704 |  |  |  |  | = | 937.35 | 14429.25 | %Cft | 135253
13 | Laying white marble flooring fine dressed on the surface without winding set' in lime mortar 1:2 including rubbing and polishing of the joints. (a) 3/4" thick flooring (S.I.No.28. (a) P.No.43)
| Ward |  |  | 3 | x | 18 | x | 16 |  |  | = | 864
|  |  |  | 1 | x | 10 | x | 16 |  |  | = | 160
|  |  |  | 1 | x | 85.75 | x | 6 |  |  | = | 515
[12 empty] | 1539 | 567.48 | P-Sft | 873352
14 | P/F 3/8” thick marble tiles of approved quality and colour and shade size 8”x4/6” x4” in dado skirting and facing removal /tucking of existing plaster surface etc. Over ½” thick base of cement mortar 1:3 setting of tiles in slurry of white cement over mortar base i/c filling the joints and washing the tiles with white cement slurry , currint finishing cleaning and ploishing etc complete (i) for new work (S.I No. 68 (i) /P-49).
| Ward | 3 | x | 2 | ( | 18 | + | 16 | ) | 3 | = | 612
| D Room | 1 | x | 2 | ( | 10 | + | 16 | ) | 0.5 | = | 26
| Ver | 1 | x | 2 | ( | 85.75 | + | 6 | ) | 3 | = | 550.5
1188.5
Ded:
| Door |  |  | 3 | x | 4 | x | 5 |  |  | = | 60
60
| Net Qty | 1188.5 |  |  | - | 60 |  |  |  |  | = | 1128.5 | 186.04 | P-Sft | 209946
15 | Lying floor of approved colored glazed tile 1/4" thick laid in white cement and pigment on a bed of 3/4" thick cement mortar 1:2 complete (S. I. No. 25, P-42)
|  |  |  | 2 | x | 8 | x | 16 |  |  | = | 256
|  |  |  | 1 | x | 18 | x | 16 |  |  | = | 288
[12 empty] | 544 | 27747.06 | %Sft | 150944
16 | glazed tile dado 1/4" thick laid in pigment over 1:2 cement sand mortar 3/4" thick I/c finishing.(S.I.No.38 P-45)
|  | 2 | x | 2 | ( | 8 | + | 16 | ) | 5.5 | = | 528
|  |  |  | 3 | x | 16 | x | 5.5 |  |  | = | 264
|  | 1 | x | 2 | ( | 18 | + | 16 | ) | 7 | = | 476
1268
Ded:
|  |  |  | 1 | x | 4 | x | 7 |  |  | = | 28
|  |  |  | 2 | x | 3 | x | 5.5 |  |  | = | 33
61
| Net Qty | 1268 |  |  | - | 61 |  |  |  |  | = | 1207 | 28299.3 | %Sft | 341573
17 | First Class deodar wood with wrought joinery in doors & wind: i/c with chowkhats hold fasts hinges cords cheats with handle etc. paneled or paneled & glazed or fully glazed 1 3/4" thick (S.I. No. 7/p-64).
| D |  |  | 1 | x | 4.68 | x | 8 |  |  | = | 37
|  |  |  | 3 | x | 4.17 | x | 6.82 |  |  | = | 85
|  |  |  | 6 | x | 2.17 | x | 6.82 |  |  | = | 89
|  |  |  | 6 | x | 2.17 | x | 1.13 |  |  | = | 15
[12 empty] | 226 | 902.93 | P-Rft | 204062
18 | P/F G.I frames /Chowkets of size 7"x2" or 4-1/2"x3" foor door using 20 gauge G.I sheet i/c welded hinges & fixing at site with necessary hold asts filling with cement sand slurry of ratio 1:6(S.Ino.29/P-98)
| Door |  |  | 1 | x | 25.33 |  |  |  |  | = | 25
|  |  |  | 4 | x | 18.17 |  |  |  |  | = | 73
|  |  |  | 6 | x | 16.17 |  |  |  |  | = | 97
[12 empty] | 195 | 228.9 | P-Rft | 44636
19 | P/F G.I frames /Chowkets of size 7"x2" or 4-1/2"x3" for windows using 20 gauge G.I sheet i/c welded hinges & fixing at site with necessary hold asts filling with cement sand slurry of ratio 1:6(S.Ino.29/P-98)
| W |  |  | 6 | x | 23.68 |  |  |  |  | = | 142
[12 empty] | 142 | 240.5 | P-Rft | 34151
20 | White washing ( C) three coats (S.I.No. 26 (c ) P-60)
| Qty same as item No 14 | [10 empty] | 1128.5
| Qty same as item No 15 | [10 empty] | 544
[12 empty] | 1672.5 | 829.95 | %Sft | 13881
21 | Preparing the surface and painting with matt finish i/c rubbing the surface with bathy ( silicon carbide rubbing brick) filling the voids with zink / chalk / plaster of paris mixture, applying first coat premix making the surface smooth and then painting 3 coats with matt finish of approved make etc complete (new surface) (S.I.No36/ (A) P-55)
| P-A Wall | 3 | x | 2 | ( | 18 | + | 16 | ) |  | = | 204
| Lav | 2 | x | 2 | ( | 16 | + | 18 | ) |  | = | 136
| D Room | 1 | x | 2 | ( | 10 | + | 16 | ) |  | = | 52
| Sin | 1 | x | 2 | ( | 14 | + | 10 | ) |  | = | 48
| Disp | 1 | x | 2 | ( | 14 | + | 16 | ) |  | = | 60
| Sin | 1 | x | 2 | ( | 10 | + | 15 | ) |  | = | 50
| H.V/MO | 3 | x | 2 | ( | 12 | + | 15 | ) |  | = | 162
|  | 2 | x | 2 | ( | 10 | + | 10.57 | ) |  | = | 82
| AH Lav | 2 | x | 2 | ( | 9.92 | + | 3.92 | ) |  | = | 55
| Enter Hall | 1 | x | 2 | ( | 12 | + | 15 | ) |  | = | 54
903
|  | 903 |  |  | x | 11.5 |  |  |  |  | = | 10385
| P-B Ver | 1 | x | 2 | ( | 85.75 | + | 6 | ) |  | = | 184
| Fornt | 1 | x | 2 | ( | 109 | + | 6 | ) |  | = | 230
| F. Disp | 1 | x | 2 | ( | 27 | + | 6 | ) |  | = | 66
480
|  | 480 |  |  | x | 9.5 |  |  |  |  | = | 4560
| Total A+B | 10385 |  |  | + | 4560 |  |  |  |  | = | 14945
Ded
| Door |  |  | 1 | x | 5 | x | 8 |  |  | = | 40
|  |  |  | 3 | x | 4.5 | x | 7 |  |  | = | 95
|  |  |  | 7 | x | 3.5 | x | 7 |  |  | = | 172
|  |  |  | 3 | x | 3 | x | 7 |  |  | = | 63
|  |  |  | 2 | x | 2.5 | x | 7 |  |  | = | 35
| W |  |  | 2 | x | 4.5 | x | 4 |  |  | = | 36
|  |  |  | 11 | x | 3 | x | 4 |  |  | = | 132
573
| Net Qty | 14945 |  |  | - | 573 |  |  |  |  | = | 14372 | 1989.62 | %Sft | 285948
22 | Preparing the surface and applying rock wall / shield (Natural wall texture ) coating to provide durable crust to wall, thickness b/w 2mm to 32mm (1/8" ) with acrylic co-polymer emulsion, selected marble chips, adhesive and bactericdes, water resistance (SINo-43/P-55)
|  |  |  | 1 | x | 417.25 | x | 13.5 |  |  | = | 5633
5633
Ded
|  |  |  | 1 | x | 5 | x | 8 |  |  | = | 40
| Opp |  |  | 19 | x | 5 | x | 4 |  |  | = | 380
| W |  |  | 4 | x | 3 | x | 4 |  |  | = | 48
| H.W |  |  | 6 | x | 2.5 | x | 1.5 |  |  | = | 23
491
| Net Qty | 5633 |  |  | - | 491 |  |  |  |  | = | 5142 | 4504.5 | %Sft | 231621
23 | First class deodar wood wrought joimery wortk in wire gauze D/W with 22 S.W.G galvanized wire gauge 144 mesh per sq: iron fitting complete (d) galvanized wire guaze fixed to chowkhats with 3/4" thick deodar steps with screw (S.I.NO:14 d /P-60).
|  |  |  | 10 | x | 4 | x | 5 |  |  | = | 200
[12 empty] | 200 | 190.72 | P-Sft | 38144
24 | First class deodar wood wrought joimery wortk in wire gauze D/W with 22 S.W.G galvanized wire gauge 144 mesh per sq: iron fitting complete (C) 1/2" strip on seprate 2" x 2" deoadar fram(S.I.NO:14 c /P-60).
|  |  |  | 15 | x | 4 | x | 5 |  |  | = | 300
[12 empty] | 300 | 575.61 | P-Sft | 172683
25 | S/F in position iron / steel grill of 3/4" x 1/4" size flat iron of pproved design i/c painting three coats. etc complete (weight not to be less than 3.7 Lbs/ Sq. Foot of finished grill). (S.I. No. 26/p-92).
|  |  |  | 4 | x | 4 | x | 5 |  |  | = | 80
[12 empty] | 80 | 180.5 | P-Sft | 14440
26 | Providing nd fixing iron steel grill door with angle frame of 1-1/2" x 1-1/2" x 1/4" and flat iron of 3/4" x 1/4" with approved deisgn and locking arrangments an messonary as per instruction of Engineer Incharge (S. I. No. 31 P-94)
|  |  |  | 1 | x | 4.5 | x | 8.5 |  |  | = | 38
|  |  |  | 1 | x | 5 | x | 8.5 |  |  | = | 43
[12 empty] | 81 | 231.6 | P-Sft | 18760
27 | Painted sashes fan lights glazed or gauzed doors and windows (S.I.No. 4 (b) P-68)
| Qty same as item No 23 | [10 empty] | 200
[12 empty] | 200 | 1270.83 | %Sft | 2542
28 | Preparing surface and painting of doors and windows any type (i/c edges) three coats (S. I. No. 5 (c ) (i,ii) P-70)
| D |  |  | 1 | x | 2 | x | 5 | x | 7 | = | 70
|  |  |  | 3 | x | 2 | x | 4.5 | x | 7 | = | 189
|  |  |  | 6 | x | 2 | x | 2.5 | x | 7 | = | 210
|  |  |  | 6 | x | 2 | x | 2.5 | x | 1.5 | = | 45
[12 empty] | 514 | 2116.41 | %Sft | 10878
29 | Supplying and Filling sand under floor and plugging into walls (P. No. 29, S. No. 25)
|  |  |  | 1 | x | 27 | x | 45 | x | 1 | = | 1215
|  |  |  | 1 | x | 80 | x | 20 | x | 1 | = | 1600
[12 empty] | 2815 | 1141.25 | %Cft | 32126
30 | Cement Concrete brick or stone ballast 1-1/2" to 2" gauage Ratio 1:4:8 (S.I. No: 4 (b)/P-15)
|  |  |  | 1 | x | 27 | x | 45 | x | 0.5 | = | 608
|  |  |  | 1 | x | 80 | x | 20 | x | 0.5 | = | 800
[12 empty] | 1408 | 9416.28 | %Cft | 132581
[12 empty] | Total |  | 5072350.3498
| Sub-Engineer | [10 empty] | Assistant Engineer
Buildings Sub-Division
Tando Allahyar

## Schdl B
SCHEDULE-B
Name of Work: |  | RENOVATION OF RHC NASARPUR DISTRICT TANDO ALLAHYAR (REMAINING WORK)
S. No. | Description |  |  | QTY | Rate | Unit | AMOUNT
1 | Dismantling Cement concrete Plain 1:2:4 (S.I.No. 19 (c ) P-10)
|  |  |  | 768 | 3327.5 | %Cft | 25555
(Rupees Three Thousands Three Hundred Twenty Seven Point Five Zero Only)
2 | Dismantling Cement concrete reinforced separating reinfor cement from concrete cleaning and straightening the same (S.I.No. 20 P-10)
|  |  |  | 2286 | 5445 | %Cft | 124473
(Rupees Five Thousands Four Hundred Forty Five Only)
3 | Dismantling Pack brick work in lime or cement mortar (S.I.No. 13 P-10)
|  |  |  | 991 | 1285.63 | %Cft | 12741
(Rupees One Thousands Two Hundred Eighty Five Point Six Three Only)
4 | Scraping ordinary distemper iol bound distemper or paint on walls (S.I.No. 54 (b) P-13)
|  |  |  | 15085 | 226.88 | %Sft | 34225
(Rupees Two Hundred Twenty Six Point Eight Eight Only)
5 | Pacca bricks work in Gorund floor in cement sand mortar 1:6 (S.I.No. 5- I (e) P-20)
|  |  |  | 991 | 12674.36 | %Cft | 125603
(Rupees Twelve Thousands Six Hundred Seventy Four Point Three Six Only)
6 | RCC work I/c all labor and material except the cost of steel reinforcement and its labor for bending and binding which will be paid separately this rate also include all kinds of forms moulds lifting shuttering curing rendering and finishing the exposed surface (i/c screening and washing of shingle R.C work in roof slab, beams columns rafts, lintels and other structural members laid in situ or precast laid in position complete in all respects ratio 1:2:4 ) 90 lbs. cement 2cft Sand 4 cft shingle 1/8" to 1/4" gauge. (S.I.No.6 (a) (i) P-16)
|  |  |  | 2385 | 337 | P-Cft | 803745
(Rupees Three Hundred Thirty Seven Only)
7 | Fabrication of mild steel reinforcement for cement concrete I/c cutting bending laying in position making joints and fastenings I/c cost of binding wire (also includes removal of rust from bars) using Tor bars (S.I. No: 8 (a) (b)/P-16/17)
|  |  |  | 127.7679 | 5001.7 | P-Cwt | 639056
(Rupees Five Thousand One Point Seven Zero Only)
8 | Cement plaster 1:6 upto 12' height 1/2" thick (S.I. No.13(b)/p-52).
|  |  |  | 5178 | 2206.6 | %Sft | 114258
(Rupees Two Thousand Two Hundred Six Point Six Zero Only)
9 | Cement plaster 1:4 upto 12' height 3/8" thick (S.I. No. 11/a/p-51).
|  |  |  | 5178 | 2197.52 | %Sft | 113788
(Rupees Two Thousand One Hundred Ninety Seven Point Five Two Only)
10 | P/L 1-1/2" thick topping i/c surface finishing & dividing into panels C.C 1:2:4 (S.I. No. 16/p-46).
|  |  |  | 2962 | 2548.29 | %Sft | 75480.3498
(Rupees Two Thousands Five Hundred Forty Eight Point Two Nine Only)
11 | Two coat of bitumen laid hot using 34 Ibs for % Sft over roof and blinded with sand at 1 Cft per % Sft. (S. I. No. 13 , P-35)
|  |  |  | 2962 | 1887.4 | %Sft | 55905
(Rupees One Thousands Eight Hundred Eighty Seven Point Four Zero Only)
12 | Cement concrete plain i/c placing compacting finishing and curring complete (i/c Screening and Washing at stone aggregate without shuttering 1:2:4 (S.I.No-5 f/P-16)
|  |  |  | 937 | 14429.25 | %Cft | 135253
(Rupees Forteen Thousands Four Hundred Twenty Nine Point Two Five Only)
13 | Laying white marble flooring fine dressed on the surface without winding set' in lime mortar 1:2 including rubbing and polishing of the joints. (a) 3/4" thick flooring (S.I.No.28. (a) P.No.43)
|  |  |  | 1539 | 567.48 | P-Sft | 873352
(Rupees Five Hundred Sixty Seven Point Four Eight Only)
14 | P/F 3/8” thick marble tiles of approved quality and colour and shade size 8”x4/6” x4” in dado skirting and facing removal /tucking of existing plaster surface etc. Over ½” thick base of cement mortar 1:3 setting of tiles in slurry of white cement over mortar base i/c filling the joints and washing the tiles with white cement slurry , currint finishing cleaning and ploishing etc complete (i) for new work (S.I No. 68 (i) /P-49).
|  |  |  | 1128.5 | 186.04 | P-Sft | 209946
(Rupees One Hundred Eighty Six Point Four Zero Only)
15 | Lying floor of approved colored glazed tile 1/4" thick laid in white cement and pigment on a bed of 3/4" thick cement mortar 1:2 complete (S. I. No. 25, P-42)
|  |  |  | 544 | 27747.06 | %Sft | 150944
(Rupees Twenty Seven Thousands Seven Hundred Forty Seven Point Zero Six Only)
16 | glazed tile dado 1/4" thick laid in pigment over 1:2 cement sand mortar 3/4" thick I/c finishing.(S.I.No.38 P-45)
|  |  |  | 1207 | 28299.3 | %Sft | 341573
(Rupees Twenty Eight Thousands Two Hundred Ninety Nine Point Three Zero Only)
17 | First Class deodar wood with wrought joinery in doors & wind: i/c with chowkhats hold fasts hinges cords cheats with handle etc. paneled or paneled & glazed or fully glazed 1 3/4" thick (S.I. No. 7/p-64).
|  |  |  | 226 | 902.93 | P-Rft | 204062
(Rupees Nine Hundred Two Point Nine Three Only)
18 | P/F G.I frames /Chowkets of size 7"x2" or 4-1/2"x3" foor door using 20 gauge G.I sheet i/c welded hinges & fixing at site with necessary hold asts filling with cement sand slurry of ratio 1:6(S.Ino.29/P-98)
|  |  |  | 195 | 228.9 | P-Rft | 44636
(Rupees Two Hundred Twenty Eight Point Nine Zero Only)
19 | P/F G.I frames /Chowkets of size 7"x2" or 4-1/2"x3" for windows using 20 gauge G.I sheet i/c welded hinges & fixing at site with necessary hold asts filling with cement sand slurry of ratio 1:6(S.Ino.29/P-98)
|  |  |  | 142 | 240.5 | P-Rft | 34151
(Rupees Two Hundred Forty Point Five Zero Only)
20 | White washing ( C) three coats (S.I.No. 26 (c ) P-60)
|  |  |  | 1672.5 | 829.95 | %Sft | 13881
(Rupees Eight Hundred Twenty Nine Point Nine Five Only)
21 | Preparing the surface and painting with matt finish i/c rubbing the surface with bathy ( silicon carbide rubbing brick) filling the voids with zink / chalk / plaster of paris mixture, applying first coat premix making the surface smooth and then painting 3 coats with matt finish of approved make etc complete (new surface) (S.I.No36/ (A) P-55)
|  |  |  | 14372 | 1989.62 | %Sft | 285948
(Rupees One Thousands Nine Hundred Eighty Nine Point Six Two Only)
22 | Preparing the surface and applying rock wall / shield (Natural wall texture ) coating to provide durable crust to wall, thickness b/w 2mm to 32mm (1/8" ) with acrylic co-polymer emulsion, selected marble chips, adhesive and bactericdes, water resistance (SINo-43/P-55)
|  |  |  | 5142 | 4504.5 | %Sft | 231621
(Rupees Four Thousands Five Hundred Four Point Five Zero Only)
23 | First class deodar wood wrought joimery wortk in wire gauze D/W with 22 S.W.G galvanized wire gauge 144 mesh per sq: iron fitting complete (d) galvanized wire guaze fixed to chowkhats with 3/4" thick deodar steps with screw (S.I.NO:14 d /P-60).
|  |  |  | 200 | 190.72 | P-Sft | 38144
(Rupees One Hundred Ninety Point Seven Two Only)
24 | First class deodar wood wrought joimery wortk in wire gauze D/W with 22 S.W.G galvanized wire gauge 144 mesh per sq: iron fitting complete (C) 1/2" strip on seprate 2" x 2" deoadar fram(S.I.NO:14 c /P-60).
|  |  |  | 300 | 575.61 | P-Sft | 172683
(Rupees Five Hundred Seventy Five Point Six One Only)
25 | S/F in position iron / steel grill of 3/4" x 1/4" size flat iron of pproved design i/c painting three coats. etc complete (weight not to be less than 3.7 Lbs/ Sq. Foot of finished grill). (S.I. No. 26/p-92).
|  |  |  | 80 | 180.5 | P-Sft | 14440
(Rupees One Hundred Eighty Point Five Zero Only)
26 | Providing nd fixing iron steel grill door with angle frame of 1-1/2" x 1-1/2" x 1/4" and flat iron of 3/4" x 1/4" with approved deisgn and locking arrangments an messonary as per instruction of Engineer Incharge (S. I. No. 31 P-94)
|  |  |  | 81 | 231.6 | P-Sft | 18760
(Rupees Two Hundred Thirty One Point Six Zero Only)
27 | Painted sashes fan lights glazed or gauzed doors and windows (S.I.No. 4 (b) P-68)
|  |  |  | 200 | 1270.83 | %Sft | 2542
(Rupees One Thousands Two Hundred Seventy Point Eight Three Only)
28 | Preparing surface and painting of doors and windows any type (i/c edges) three coats (S. I. No. 5 (c ) (i,ii) P-70)
|  |  |  | 514 | 2116.41 | %Sft | 10878
(Rupees Two Thousands One Hundred Sixteen Point Four One Only)
29 | Supplying and Filling sand under floor and plugging into walls (P. No. 29, S. No. 25)
|  |  |  | 2815 | 1141.25 | %Cft | 32126
(Rupees One Thousands One Hundred Forty One Point Two Five Only)
30 | Cement Concrete brick or stone ballast 1-1/2" to 2" gauage Ratio 1:4:8 (S.I. No: 4 (b)/P-15)
|  |  |  | 1408 | 9416.28 | %Cft | 132581
(Rupees Nine Thousands Four Hundred Sixteen Point Two Eight Only)
|  |  |  | Total |  | 5072350.3498
TERMS & CONDITIONS:
1 | No Premium Shall be allowed on items based on market rates or sanctined by competent
authority the Schedule of rates.
2 | Nothing shall be paid for cartage of any material what so ever brought at the site of work
material cartage form Government stores
3 | The material for use in the work or his finished product can be got tested an approved lab, at the
direction of incharge Engineer or his representative and all expencess in connection with such
testing shall be borne by the Government on his account.
| Contractor |  | Executive Engineer
Buildings Division
Tando Allahyar