## Annual Proc Plan 2016-17
ANNUAL PROCUREMENT PLAN FOR THE YEAR 2016-17 IN RESPECT OF EXECUTIVE ENGINEER BUILDINGS DIVISION THARPARKAR @ MITHI WORKS & SERVICES DEPARTMENT GOVERNMENT OF SINDH.
S.No | Description of Procurement | Quantity (where applicable) | Estimated Unit cost (where applicable) | Estimated total cost (In Million Rs.) | Funds allocated (In Million Rs.) | Source of Funds (ADP/Non-ADP) | Project procurement method | Timing of Procurement
[8 empty] | 1ST QTR | 2ND QTR | 3RD QTR | 4TH QTR
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
PSDP 2016-17
1 | Construction of Kitchen Block, Dhobi Block & Vehicle Shade at District Headquarter Hospital Mithi |  | 7.258 | 7.258 |  | District Government (PSDP) | Single Stage one Envelope
2 | Construction of Medical Dispensaries in Taluka Chachro & Dahli District Tharparkar (03-units) @ Village Paderal & Others |  |  |  |  | District Government (PSDP) | Single Stage one Envelope
| (i)At Village Paderal U/C Dharendharo Taluka Chachro |  | 3.12 | 3.12
| (ii) At Village Allah Rakhio Jo Par U/C Gul Muhammad Rind Taluka Dahli |  | 3.12 | 3.12
| (iii) At Village Murad Paro Peerani Jo Par Taluka Dahli |  | 3.12 | 3.12
|  | Total 3-Units | 9.36 | 9.36
3 | Construction of Medical Dispensaries in Taluka Diplo District Tharparkar (05-Units) @ Village Abdul Hakeem Jamot Amrno & Others |  |  |  |  | District Government (PSDP) | Single Stage one Envelope
| (i) At Village Abdul Hakeem Jamot Amrno U/C Talo Jam Taluka Diplo |  | 3.12 | 3.12
| (ii) At Village Bando Lund U/C Bolhari Taluka Diplo |  | 3.12 | 3.12
| (iii)At Village Banhwar U/C Sarhore Taluka Diplo |  | 3.12 | 3.12
| (iv)At Village Bhadhor U/C Bhadhor Taluka Diplo |  | 3.12 | 3.12
| (v) At Village Kharak U/C Kaloi Taluka Diplo |  | 3.12 | 3.12
|  | Total 5-Units | 15.6 | 15.6
4 | Construction of Medical Dispensaries in Taluka Islamkot District Tharparkar (05-Units) @ Village Ade Jo Tar & Others |  |  |  |  | District Government (PSDP) | Single Stage one Envelope
| (i) At Village Ade Jo Tar U/C Khario Ghulam Shah Taluka Islamkot |  | 3.12 | 3.12
| (ii) At Village Ahsan Shah Jo Tar U/C Khario Ghulam Shah Taluka Islamkot |  | 3.12 | 3.12
| (iii) At Village Batangari U/C Boharari Taluka Islamkot |  | 3.12 | 3.12
| (iv) At Village Jhangaro U/C Giryancho Taluka Islamkot |  | 3.12 | 3.12
| (v) At Village Kikari U/C Kehari Taluka Islamkot |  | 3.12 | 3.12
|  | Total 5-Units | 15.6 | 15.6
5 | Construction of Medical Dispensaries in Taluka Islamkot District Tharparkar (05-Units) @ Village Morano Muhammad Khan Paro & Others |  |  |  |  | District Government (PSDP) | Single Stage one Envelope
| (i) At Village Morano Muhd Khan Paro Kehari Taluka Islamkot |  | 3.12 | 3.12
| (ii) At Village Muto Jo Tar Dodo Paro U/C Khario Ghulam Shah Taluka Islamkot |  | 3.12 | 3.12
| (iii) At Village Nabisar Lanja U/C Manjthi Taluka Islamkot |  | 3.12 | 3.12
| (iv) At Village Nathro U/C Bapuhar Taluka Islamkot |  | 3.12 | 3.12
| (v) At Village Ranjho Noon U/C Sonal Bah Taluka Islamkot |  | 3.12 | 3.12
|  | Total 5-Units | 15.6 | 15.6
6 | Construction of Medical Dispensaries in Taluka Islamkot District Tharparkar (05-Units) @ Village Sajwani & Others |  |  |  |  | District Government (PSDP) | Single Stage one Envelope
| (i) At Village Sajwani U/C Sonal Bah Taluka Islamkot |  | 3.12 | 3.12
| (ii) At Village Siranghu U/C Kehari Taluka Islamkot |  | 3.12 | 3.12
| (iii) At Village Tarai Borli Hussain Abad Paro U/C Khario Ghulam Shah Taluka Islamkot |  | 3.12 | 3.12
| (iv) At Village Tepari U/C Buhariri Taluka Islamkot |  | 3.12 | 3.12
| (v) At Village Tooh U/C Bapuhar Taluka Islamkot |  | 3.12 | 3.12
|  | Total 5-Units | 15.6 | 15.6
7 | Construction of Medical Dispensaries in Taluka Mithi District Tharparkar (05-Units) @ Village Bitra & Others |  |  |  |  | District Government (PSDP) | Single Stage one Envelope
| (i) At Village Bitra U/C Chelhar Taluka Mithi |  | 3.12 | 3.12
| (ii) At Village Hothiar U/C Malanhore Veena Taluka Mithi |  | 3.12 | 3.12
| (iii) At Village Joruo Meghwar U/C Joruo Taluka Mithi |  | 3.12 | 3.12
| (iv) At Village Kerti U/C Bhakuo Taluka Mithi |  | 3.12 | 3.12
| (v) At Village Mehyari Shahani U/C Chelhar Taluka Mithi |  | 3.12 | 3.12
|  | Total 5-Units | 15.6 | 15.6
8 | Construction of Medical Dispensaries in Taluka Mithi & Nagarparkar District Tharparkar (05-Units) @ Village Mukhi Ladharam Jo Tar & Others |  |  |  |  | District Government (PSDP) | Single Stage one Envelope
| (i) At Village Mukhi Ladharam Jo Tar Mahraj Paro U/C Mithrio Bhati Taluka Mithi |  | 3.12 | 3.12
| (ii) At Village Bantari U/C Pithapur Taluka Nagarparkar |  | 3.12 | 3.12
| (iii) At Village Chooncha Obhayo Junejo Paro U/C Harho Taluka Nagarparkar |  | 3.12 | 3.12
| (iv) At Village Gadhro Charan Kirshan Charan Paro U/C Pithapur Taluka Nagarparkar |  | 3.12 | 3.12
| (v) At Village Jojharo U/C Pithapur Taluka Nagarparkar |  | 3.12 | 3.12
|  | Total 5-Units | 15.6 | 15.6
9 | Construction of Medical Dispensaries in Taluka Nagarparkar District Tharparkar (05-Units) @ Village Nasarullah Sand Arbab Sand & Others |  |  |  |  | District Government (PSDP) | Single Stage one Envelope
| (i) At Village Nasarullah Sand Arbab Sand Paro Taluka Nagarparkar |  | 3.12 | 3.12
| (ii) At Village Sahu Sand Yar Mohammad Paro Taluka Nagarparkar |  | 3.12 | 3.12
| (iii) At Village Sakar Vero U/C Virawah Taluka Nagarparkar |  | 3.12 | 3.12
| (iv) At Village Umar Unar Mohd Ali Unar Paro Taluka Nagarparkar |  | 3.12 | 3.12
| (v) At Village Unehar U/C Nagarparkar Taluka Nagarparkar |  | 3.12 | 3.12
|  | Total 5-Units | 15.6 | 15.6
10 | Construction of Medical Dispensaries In Taluka Diplo District Tharparkar (05-Units) @ Village Jaghari Bajeer & Others |  |  |  |  | District Government (PSDP) | Single Stage one Envelope
| (i)At Village Jaghari Bajeer U/C Jhirmirio Taluka Diplo |  | 3.12 | 3.12
| (ii)At Village Chaho Meghwar U/C Bhador Taluka Diplo |  | 3.12 | 3.12
| (iii)At Village Bhoongar Lund U/C Phant Taluka Diplo |  | 3.12 | 3.12
| (iv) At Village Sonal Boh (Thakur Paro) U/C Sonal Bah Taluka Nagarparkar |  | 3.12 | 3.12 |  | District Government (PSDP) | Single Stage one Envelope
| (v) At Village Hemari U/C Satidera Taluka Nagarparkar |  | 3.12 | 3.12
|  | Total 5-Units | 15.6 | 15.6
11 | Construction of Medical Dispensaries In District Tharparkar (1) At Village Dabhri Meghwar U/C Bhadoor Taluka Diplo (2) At Village Soorachand Taluka Nagarparkar |  |  |  |  | District Government (PSDP) | Single Stage one Envelope
| (i) At Village Dabhri Meghwar U/C Bhador Taluka Diplo |  | 3.12 | 3.12
| (ii) At Village Soorachand U/C Nagarparkar Taluka Nagarparkar |  | 3.12 | 3.12
|  | Total 2-Units | 6.24 | 6.24
Executive Engineer
Buildings Division
Tharparkar