## AC
DETAILED WORKING ESTIMATE FOR RENOVATION OF PUBLIC PARK CHOONDIKO TOWN, TALUKA NARA, DISTRICT KHAIRPUR
ABSTRACT OF COST
| Part-I: | Canteen & Lavatory Block: |  | = | Rs: | 917136.3981
| Part-II: | C.C. Pavers Block: |  | = | Rs: | 82813.5263
|  |  | Total = |  | Rs: | 999949.9244
|  |  | Say = |  | Rs: | 1000000
Assistant Executive Engineer
Town Committee, Nara
Town Officer
Town Committee, Nara
Chairman
Town Committee, Nara

## Sheet1
BILL OF QUANTITY (B.O.Q)
195
DETAILED WORKING ESTIMATE FOR RENOVATION OF PUBLIC PARK CHOONDIKO TOWN, TALUKA NARA, DISTRICT KHAIRPUR
S. NO. | DESCRIPTION | QUANTITY |  | RATE |  |  | UNIT | AMOUNT
PART-I: Canteen & Lavatory Block:
1 | Excavation in foundation of building bridges and other structure i/c dag belling, dressing refilling around structure with excavated earth lead upto one chain and lift up to 5 feet (In or soil) (CSI No:18-b, P-4)
|  | 550.33 | Cft. | Rs. | 3176.25 |  | %0Cft | 1748 | /-
2 | C.C brick or stone ballast 1-½” to gauge ratio 1:4:8 (CSI No:4-b, P-15)
C.C brick or stone ballast 1-½” to gauge ratio 1:4:8 (CSI No:4-b, P-15)
|  | 291.76 | Cft. | Rs. | 9416.28 |  | %Cft | 27473 | /-
3 | Pacca brick work in foundation and plinth in cement sand mortar 1:6. (CSI No:4-I/e, P-20/21)
|  | 284.97 | Cft. | Rs. | 11948.36 |  | %Cft | 34049 | /-
4 | Coursed Ruble masonry including hammer dressing in cement sand mortar Ratio 1:4. (CSI No:2-I/ii, P-27)
|  | 118.06 | Cft. | Rs. | 26475 |  | %Cft | 31256 | /-
5 | R.C.C work i/c all labour and material except the cost of steel rein for cement and its labour for bending which will be paid separately. This rate also i/c all kinds forms moulds lifting shuttering curing rendering finishing the exposed surface (a) Rc work in roof slab beams Columns rafts lintels & other structural members laid in situ or per cost laid in position complete in all respects ration 1:2:4 (CSI No:6-a, P-16/17).
|  | 387.07 | Cft. | Rs. | 337 |  | P.Cft | 130443 | /-
6 | Fabrication of mild steel reinforcement for cement concrete work i/c cutting fitting and laying position making joints and fastenings i/c. cost of binding wire also i/c removal of rust from bars, (ii). Using tor bars. (CSI No:8-b, P-17)
|  | 19.008 | Cwt. | Rs. | 5001.7 |  | P.Cwt | 95072 | /-
7 | Filling watering and ramming earth under floor with new earth (excavated from outside) lead up to one chain and lift up to 5 feet.[CSI No:22, P-4].
|  | 430.22 | Cft. | Rs. | 3630 |  | %0Cft | 1562 | /-
8 | Extra for every 50 ft. additional lead or part thereof. for Earth work (soft, ordinary or hard soil). (CSI-No:8-a, P-No:2) Lead = 1/2 Mile 5280/2=2640-100=2540/50=50.80 Leads x Rs:100.78=5119.62 %ocft.
430.22
|  | 430.22 | Cft. | Rs. | 5119.62 |  | %0Cft | 2203 | /-
9 | Pacca brick work in ground floor i/c sticking or joints in cement sand mortar 1:6 Ratio (CSI No:5-I/e, P-21)
|  | 1048.04 | Cft. | Rs. | 12674.36 |  | %Cft | 132832 | /-
10 | Providing and fixing G.I. frames/ chowkhats of size 7"x2" or 4-1/2"x3" for door using 20 gauge G.I. sheet i/c. welded hinges and fixing at site with necessary hold fasts, filling with cement sand slurry of ratio 1:6 and repairing the jambs. The cost also i/c. all carriage, tools and plants used in making and fixing. (CSI-29, P-93)
|  | 650.5 | Rft. | Rs. | 228.9 |  | P.Sft | 14993 | /-
|  | 80.06 | Rft | Rs. | 240.5 |  | P.Sft | 19254 | /-
12 | First class deodar wood wrought, joinery in doors and windows etc. fixed in position including chowkats hold fasts hinges, iron tower bolts, chocks cleats, handles and cords with hooks. etc. Deodar panelled or panelled and glazed, or fully glazed. (b). 1-3/4" thick. (CSI-7-b, P-58)
|  | 137.79 | Sft. | Rs. | 621.05 |  | P.Sft | 85574 | /-
13 | Supplying & fixing in position iron/ steel grill of 3/4"x1/4" size flat iron of approved design i/c. painting 3 coats etc. complete (weight not to be less than 3.7 Lbs. per Sq.ft. of finished grill. (CSI No:26, P-93)
|  | 53.43 | Sft | Rs. | 180.5 |  | P.Sft | 9644 | /-
14 | Wiring for light or fan point with 3/0.29 PVC insulated wire in 20mm (3/4") PVC conduit recessed in the wall or column as required. (ESI No:124, P-15)
|  |  |  | x | 1 | x
|  | 16 | Point | Rs. | 1130 |  | P.Point | 18080 | /-
15 | Cement plaster 1:6 up to 20’ height ½” thick. (CSI No:13-b, P-52)
|  | 1520.13 | Sft. | Rs. | 2206.6 |  | %Sft | 33543 | /-
16 | Cement Plaster 1:4 up to 20’ height 3/8” thick. (CSI No:11-a, P-52)
|  | 1520.13 | Cwt. | Rs. | 2197.52 |  | %Sft | 33405 | /-
17 | Providing & Laying 1" thick topping cement concrete (1:2:4) i/c. surface finishing and dividing into panels. 3" thick (CSI No:16-d, P-42)
x
|  | 434 | Sft. | Rs. | 4411.82 |  | %Sft | 19147 | /-
18 | Cement pointing on walls 1:2 ratio (CSI No:19-a, P-53)
|  | 1324.12 | Sft. | Rs. | 1287.44 |  | %Sft | 17047 | /-
19 | Pointing flush on stone work in cement sand mortar 1:3 ratio (CSI No:20-3, P-53)
|  | 117.8 | Sft. | Rs. | 1062.33 |  | %Sft | 1251 | /-
20 | White washing three coasts.
(CSI No:26-c, P-54)
|  | 479.57 | Sft. | Rs. | 829.95 |  | %Sft | 3980 | /-
21 | Prime Coat of Chalk Distemper.
(CSI No:23, P-54)
|  | 1520.13 | Sft. | Rs. | 442.75 |  | %Sft | 6730 | /-
22 | Distempering 2 Coats.
(CSI No:24-b, P-54)
|  | 1520.13 | Sft. | Rs. | 1043.9 |  | %Sft | 15869 | /-
23 | Colour washing two coats.
(CSI No:25-b, P-54)
|  | 1324.12 | Sft. | Rs. | 103.79 |  | %Sft | 1374 | /-
24 | Painting new surface:
(d) Preparing surface and painting of doors and windows any type, (including edges). 3 coats. (CSI No:5-c, P-69/70)
|  | 487.5 | Sft. | Rs. | 2116.41 |  | %Sft | 10317 | /-
25 | Providing & fixing brass ceiling fan 56" size. (ESI No:234, P-34)
| Steps |  |  | x | 1 | x
|  | 3 | Nos. | Rs. | 3185 |  | Each | 9555 | /-
26 | Providing & fixing squating type white glazed earthen were W.C. Pan with i/c. the cost of flushing cistern with internal fitting and flush pipe with bend & making requisite number of holes in walls plinth & floor for pipe connections & making good in cement concrete 1:2:4. (A) W.C. pan of not less than 23" clean opening between flushing rims and 3 gallons flushing tank with 4" dia C.I. trape. (WSSI No:1-A, P-1)
[5 empty] | 1 | x
|  | 2 | Nos. | Rs. | 5044.6 |  | P.Each | 10089 | /-
27 | Providing & fixing 4"x4"x4" dia. Plain C.I. branch of the required degree i/c. extra painting to match the colour of the building. (WSSI No:7, P-9)
|  | 2 | Nos. | Rs. | 704.2 |  | P.Each | 1408 | /-
28 | Providing & fixing 4" dia. C.I. soil and went pipe i/c. cutting and fitting and extra painting to match the colour of the building. (WSSI No:1, P-9)
[5 empty] | 1 | x
|  | 14 | ft. | Rs. | 333.29 |  | P.ft. | 4666 | /-
29 | Providing and fixing 4" dia. C.I. terminal guard i/c. extra painting to match the colour of the building. (WSSI-11, P10)
|  | 2 | Nos. | Rs. | 389.7 |  | P.Each | 779 | /-
30 | Providing & fixing M.S. Clamps of the approved design to 4" dia C.I. Pipe sockets i/c. the cost of cutting and making good to wall or M.S. bolts and nuts 4" into wall i/c. Pipe distance Pieces extra painting to match the colour of the building. (WSSI No:2, P-9)
|  | 2 | Nos. | Rs. | 72.16 |  | P.Each | 144 | /-
31 | Providing & fixing 24"x18" lavatory basin white glazed earthen ware complete with and i/c. the cost of WI or CI cantileve brackets 6" built into wall painted white in two coats after a primary coat of red lead paint, a pair of 1/2" dia. rubber plug and chrome plate brass chain 1-1/4" dia. malloable iron or CP brass traps malloable iron or brass unions and making required number holes in walls plinth and floor for pipe connection and making good in cement concrete 1:2:4, (Standard pattern) . (WSSI No:8, P-9)
|  | 2 | Nos. | @Rs: | 4253.7 |  | P.Each | 8507 | /-
32 | C.P. Brass Bib cock & stop cocks (a). 3/4" dia. Bass bib cock, Light pattern. (WSSI No:1-a, P-16)
|  | 6 | Nos. | Rs. | 348.92 |  | P.Each | 2094 | /-
33 | Providing & fixing handle valves (China) 3/4" dia. (WSSI No:5-I, P-17)
3/4" dia.
|  | 3 | Nos. | Rs. | 271.92 |  | P.Each | 816 | /-
35 | Providing G.I Pipes, specials, and clamps etc, i/c. fixing cutting & fitting complete with and i/c. the cost of breaking through walls and roof, making good etc. painting two coats after cleaning the pipe etc. with white zink paint with pigment to match the colour of the building and testing with water to a pressure head of 200 feet and handling. (WSSI No:1-I/II/III, P-12)
i. | 1-1/4" dia.
|  | 4 | Rft. | Rs. | 153.19 |  | P.Rft. | 613 | /-
ii. | 1" dia. |  |  | x | 1 | x
|  | 30 | Rft. | Rs. | 128.55 |  | P.Rft. | 3857 | /-
iii. | 3/4" dia. |  |  | x | 1 | x
|  |  |  | x | 1 | x
|  | 190 | Rft. | Rs. | 95.79 |  | P.Rft. | 18200 | /-
[7 empty] | Total | 807574 | /-
[5 empty] | Added 13.57% Above |  |  | 109588 | /-
| Contractor | [6 empty] | 917162 | /-
Chairman
Town Committee, Nara
Town Officer
Town Committee, Nara
Assistant Executive Engineer
Town Committee, Nara

## Sheet2
MATERIAL STATEMENT
S. No. | Item | Qty | Cement | Bholari | Stone Crash | Steel | Brick | Barrow Pit
1 | C.C. b/s (1:4:8) | 291.76 | 22.76 | 142.96 | 285.92 | --- | --- | ---
2 | Pacca Brick Work (1:6) | 284.97 | 9.8 | 73.24 | --- | --- | 3847 | ---
3 | Course Rubble 1:4 | 118.06 | 7.56 | 37.78 | 159.38 | --- |  | ---
4 | Pacca Brick Ground | 1048.04 | 36.05 | 269.35 | --- | --- | 14149 | ---
5 | RCC work | 387.07 | 68.12 | 170.31 | 340.62 |  | --- | ---
6 | Fabrication | 19.008 | --- | --- | --- | 0.95 | --- | ---
7 | Filling Sand | 430.22 | --- | --- | --- | --- | --- | 430.22
11 | Cement Plaster (1:6) 1/2 | 1520.13 | 8.06 | 60.81 | --- | --- | --- | ---
12 | Cement Plaster (1:4) 3/8" | 1520.13 | 8.66 | 45.6 | --- | --- | --- | ---
12 | Cement Topping 3" thick | 434 | 19.1 | 47.74 | 95.48 | --- | --- | ---
13 | Cement Pointing 1:2 | 1324.12 | 9.53 | 23.83 | --- | --- | --- | ---
14 | Pointing flush 1:3 | 117.8 | 0.64 | 2.36 | --- | --- | --- | ---
|  | Total | 190.28 | 873.98 | 881.4 | 0.95 | 17996 | 430.22
|  | Say | 190 | 874 | 881 | 0.95 | 17996 | 430
| Lead to site of work in miles |  | 162 | 166 | 15 | 39 | 10 | 2
| Rates in Rupess |  | 103.53 | 5981.56 | 1065 | 18.46 | 721.74 | 502.52
|  |  | 19699.6884 | 52277.6381 | 9386.91 | 17.537 | 12988.433 | 2161.9415
|  | Total | 96532.1481
Sub-Engineer
Town committee, Nara
Assistant Executive Engineer
Town committee, Nara

## Internal & External
BILL OF QUANTITY (B.O.Q)
195
PART-II: C.C. PAVER BLOCK: | [10 empty] | MATERIAL STATEMENT
S.# | Description | Quantity |  | Rate |  | Unit |  | Amount
1 | Excavation in foundation of building bridges & other structure i/c dug belling dressing refilling around the structure with excavator earth watering ramming load, up to one chain & lift upto 5”ft (CSI-No:18-a, P-No:4) In sand, ashes or lose soil. | [9 empty] | Item | Qty | Cement (Bags) | Bholari (Cft.) | Crush (Cft.) | Brick (Nos.) | Brick sand (Nos.) | Paver Blocks (Nos.)
[11 empty] | CC Plain (1:4:8) | 98.1978 | 9.427 | 47.1349 | 94.2699 | --- | --- | ---
|  | 40.25 | Cft. | Rs. | 2722.5 |  | %oCft. | Rs: | 109.567 | /= | Cement plaster (1:4) 1/2" | 80.49 | 0.58758 | 2.8976 | --- | --- | --- | ---
Rs.
2 | Cement concrete plain i/c placing compacting finishing and curring complete i/c Screening &washing of stone aggregates W/O shuttering. (CSI-No:5-i, P-No:16) Ratio 1:4:8 | [9 empty] | Crushed fire bricks sand | 27.9032 | --- | --- | --- | --- | 27.9032 | ---
[11 empty] | C.C. Pavers | 214.64 | --- | --- | --- | --- | --- | 965.88
|  | 98.2 | Cft. | Rs. | 11288.75 |  | %Cft. | Rs: | 11085.3041 | /= | Rates in Rupess |  | 40.53 | 7283.96 | 837.08 | 2204.6 | 2204.6 | 8536.74
3 | Pacca brick work in foundation plinth in cement | [11 empty] | 4.62 | 4397.7308 | 789.1144 | 3078.2836 | 615.1539 | 8245.4664
sand mortar (1:6)(CSI-No:4/I-e, P-No:20/21)
[12 empty] | Total | 17130.3692
|  | 40.25 | Cft. | Rs. | 14429.25 |  | %Cft. | Rs: | 5807.0517 | /=
4 | Cement plaster 1:4 upto 20” height 1/2" (CSI-No:11-b, P-No:52)
|  | 80.49 | sft | Rs. | 2283.93 |  | %sft | Rs: | 1838 | /=
5 | Borrow pit excavation unddressed lead upto 100 ft
a) ordinary soil (CSI-No:3-a, P-No:1)
|  | 107.32 | cft | Rs. | 2117.5 |  | %ocft | Rs: | 227.2501 | /=
6 | Extra for every 50 ft. additional lead or part thereof. for Earth work (soft, ordinary or hard soil). (CSI-No:8-a, P-No:2) Lead = 1/2 Mile 5280/2=2640-100=2540/50=50.80 Leads x Rs:100.78=5119.62 %ocft.
|  | 107.32 | cft | Rs. | 5119.62 |  | %ocft | Rs: | 549.4376 | /=
7 | Earth work compation (soft, ordinary or hard soil) Laying earth in 6” layer leveling & dressing & watering for compaction (a) etc. complete (CSI-No:13-b, P-No:3)
|  | 107.32 | cft | Rs. | 354 |  | %ocft | Rs: | 37.9913 | /=
8 | Providing & laying crushed fire bricks graded as sand
(CSI-No:51, P-No:4)
|  | 27.9 | Cft. | Rs. | 11288.75 |  | %Cft. | Rs: | 3149.9225 | /=
9 | Providing & fixing cement paving blocks flooring having size of 197x97x60 (mm) of city/ quddra/ cobble shape with natural colours having strength between 5000-8000 psi i/c. filling the joints with hill sand and laying in specified manner / pattern and design etc. complete.(CSI-No:71, P-No:49)
|  | 214.64 | Sft. | Rs. | 199.77 |  | P.Sft. | Rs: | 42878.6328 | /=
[8 empty] | Rs: | 65683.1571 | /=
|  |  |  | Added 26.08% Above |  |  |  | Rs: | 17130 | /=
[8 empty] | Rs: | 82813.1571 | /=
Sub-Engineer
Town committee, Nara
Assistant Executive Engineer
Town committee, Nara
CHAIRMAN
Town Committee, Nara